## JUNE
Legend
Completed on time
Completed late
S/N | ACTION/TASK | Store | Reason for Breakdown | Maintenance Category | Responsible | Specific Equipment | Category | Request Date | Days Since Request | Date Shared by Helpdesk | Days Delayed by Helpdesk | Date Attended/Checked by Vendor/Technician | Days Delayed by Vendor/Technician | Date Sent for Negotiation | Date Negotiated | Days Since Negotiation Request | Date Approval Requested | Days Since Approval Request | Approved Date | Days Since Approval | Expected Delivery Date | Cost | Status | Actual delivery date | Compliance check | Insert Comment
1 | BROKEN PIPE IN SEPTIC CHAMBER | LAG, ALIMOSHO | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-06-24 | 15 | 2024-06-24 | 0 | 2024-07-08 | 14 | 2024-07-08 | 2024-07-08 | 255 | 2024-07-08 | 0 | 2024-07-08 | 1 | 2024-07-09 | 96750 | Completed | 2024-07-09 | 1
2 | FALLING ROOF CR ALAPERE | LAG, NNPC ALAPERE | Others | Breakdown | ACORN | ROOF | BUILDING | 2024-06-29 | 9 | 2024-06-29 | 0 | 2024-06-30 | 1 | 2024-07-07 | 2024-07-07 | 0 | 2024-07-07 | 3 | 2024-07-10 | -2 | 2024-07-10 | 100125 | Completed | 2024-07-08 | 1
3 | REQUEST FOR NEW ROLLER SHUTTER REMOTE | LAG, ABULE EGBA | Corrective Action | Corrective | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-06-22 | 18 | 2024-07-07 | 15 | 2024-07-08 | 1 | 2024-07-08 | 2024-07-08 | 0 | 2024-07-09 | 0 | 2024-07-09 | 1 | 2024-07-10 | 73000 | Completed | 2024-07-10 | 1
4 | REPAINTING MAINTENANCE | ABIA, AZIKIWE RD, UMUAHIA | Others | Breakdown | JOWYN | PAINTING | BUILDING | 2024-06-11 | 282 | 2024-06-13 | 2 | 2024-07-03 | 20 | 2024-07-03 | 2024-07-04 | 1 | 2024-07-04 | 259 |  |  |  |  | Overdue
5 | PROFUSE LEAKING OF WATER IN STORE LOBBY | LAG, HEYDEN IPAJA | Others | Breakdown | PROPEARJEFF | ROOF | BUILDING | 2024-06-03 | 57 | 2024-06-03 | 0 | 2024-07-14 | 41 | 2024-07-17 | 2024-07-17 | 0 | 2024-07-17 | 0 | 2024-07-17 | 13 | 2024-07-19 |  | Completed | 2024-07-30 | 0
6 | Faulty water heater | LAG, OMOLE | Wear & Tear | Breakdown | TIMILEYIN | WATER HEATER | PLUMBING | 2024-06-01 | 8 | 2024-06-01 | 0 | 2024-06-07 | 6 | 2024-06-07 | 2024-06-07 | 0 | 2024-06-07 | 0 | 2024-06-07 | 2 | 2024-06-09 |  | Completed | 2024-06-09 | 1
7 | Freezer room not attaining temperature | ANAMBRA, ZIK AVENUE, AWKA | Routine Servicing | Preventive | Moffen | COLD ROOM UNIT | HVAC | 2024-06-01 | 5 | 2024-06-01 | 0 | 2024-06-03 | 2 | 2024-06-03 | 2024-06-04 | 1 | 2024-06-04 | 0 | 2024-06-04 | 2 | 2024-06-05 |  | Completed | 2024-06-06 | 0
8 | Freezer room break down | LAG, AGUNGI | Routine Servicing | Preventive | Visafonkintegrated | COLD ROOM UNIT | HVAC | 2024-06-01 | 9 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-08 | 2024-06-08 | 0 | 2024-06-08 | 0 | 2024-06-08 | 2 |  | 300000 | Completed | 2024-06-10 | 0
9 | Faulty ice cream machine | IBADAN, IDI-APE (IWO RD) | Electrical Surge | Breakdown | Just food | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-06-01 | 7 | 2024-06-01 | 0 | 2024-06-03 | 2 | 2024-06-03 | 2024-06-03 | 0 | 2024-06-03 | 1 | 2024-06-04 | 4 |  |  | Completed | 2024-06-08 | 0
10 | Broken glass in the lobby | LAG, MOBIL OGBA | Others | Breakdown | Taidav | WINDOW | BUILDING | 2024-06-01 | 11 | 2024-06-01 | 0 | 2024-07-08 | 37 | 2024-06-09 | 2024-06-10 | 1 | 2024-06-10 | 0 | 2024-06-10 | 2 |  |  | Completed | 2024-06-12 | 0
12 | Damaged Ceiling | LAG, MOBIL OGBA | Others | Breakdown | Full turn | CEILING BOARD | BUILDING | 2024-06-01 | 21 | 2024-06-01 | 0 | 2024-06-05 | 4 | 2024-06-06 | 2024-06-06 | 0 | 2024-06-06 | 1 | 2024-06-07 | 15 | 2024-06-09 | 340000 | Completed | 2024-06-22 | 0
13 | Generator servicing | IBADAN, OJOO | Routine Servicing | Preventive | Gen Warehouse | 135KVA GENERATOR |  | 2024-06-01 | 2 | 2024-06-01 | 0 | 2024-06-03 | 2 | 2024-06-03 | 2024-06-03 | 0 | 2024-06-03 | 0 | 2024-06-03 | 0 |  |  | Completed | 2024-06-03 | 0
14 | Generator over heating | LAG, AGUNGI | Routine Servicing | Preventive | Gen Warehouse | 135KVA GENERATOR |  | 2024-06-01 | 1 | 2024-06-01 | 0 | 2024-06-02 | 1 | 2024-06-02 | 2024-06-02 | 0 | 2024-06-02 | 0 | 2024-06-02 | 0 | 2024-06-02 |  | Completed | 2024-06-02 | 1
15 | Faulty Entrance Door | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | Taidav | OTHERS | OTHERS | 2024-06-01 | 4 | 2024-06-01 | 0 | 2024-06-04 | 3 | 2024-06-04 | 2024-06-04 | 0 | 2024-06-04 | 0 | 2024-06-04 | 1 |  |  | Completed | 2024-06-05 | 0
16 | Generator breakdown | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | Gamma | 135KVA GENERATOR |  | 2024-06-01 | 1 | 2024-06-01 | 0 | 2024-06-02 | 1 | 2024-06-02 | 2024-06-02 | 0 | 2024-06-02 | 0 | 2024-06-02 | 0 |  | 90000 | Completed | 2024-06-02 | 0
17 | Generator due for servicing | LAG, OSOLOWAY | Routine Servicing | Preventive | Gamma | 135KVA GENERATOR |  | 2024-06-01 | 1 | 2024-06-01 | 0 | 2024-06-02 | 1 | 2024-06-02 | 2024-06-02 | 0 | 2024-06-02 | 0 | 2024-06-02 | 0 |  |  | Completed | 2024-06-02 | 0
18 | Faulty kitchen hot water Tap | LAG, MAGODO | Others | Breakdown | Pro Equip | TAP | PLUMBING | 2024-06-01 | 1 | 2024-06-01 | 0 | 2024-06-02 | 1 | 2024-06-02 | 2024-06-02 | 0 | 2024-06-02 | 0 | 2024-06-02 | 0 | 2024-06-03 |  | Completed | 2024-06-02 | 1
19 | Faulty freezer room | LAG, OGUNLANA DRIVE | Wear & Tear | Breakdown | BB Commercial | FREEZER ROOM | HVAC | 2024-06-01 | 14 | 2024-06-01 | 0 | 2024-06-15 | 14 | 2024-06-15 | 2024-06-15 | 0 | 2024-06-15 | 0 | 2024-06-15 | 0 |  |  | Completed | 2024-06-15 | 0
20 | Request for generator turbo charger, lift pump and module | ENUGU, NSUKKA | Wear & Tear | Breakdown | Gamma | 135KVA GENERATOR |  | 2024-06-02 | 33 | 2024-06-02 | 0 | 2024-06-11 | 9 | 2024-06-13 | 2024-06-20 | 7 | 2024-06-24 | 3 | 2024-06-27 | 8 |  |  | Completed | 2024-07-05 | 0
21 | Cold Room and lobby AC not attaining temperature | PH, WOJI | Routine Servicing | Preventive | Moffen | COLD ROOM UNIT | HVAC | 2024-06-02 | 2 | 2024-06-02 | 0 | 2024-06-04 | 2 | 2024-06-04 | 2024-06-04 | 0 | 2024-06-04 | 0 | 2024-06-04 | 0 |  |  | Completed | 2024-06-04 | 0
22 | Lobby AC Frozen | LAG, AGUNGI | Routine Servicing | Preventive | Tona oguns | 5HP STANDING AC UNIT 1 | HVAC | 2024-06-02 | 8 | 2024-06-02 | 0 | 2024-06-10 | 8 | 2024-06-10 | 2024-06-10 | 0 | 2024-06-10 | 0 | 2024-06-10 | 0 |  |  | Completed | 2024-06-10 | 0
23 | Septic Tank Evacuation | LAG, OSOLOWAY | Others | Breakdown | Berrade | SEPTIC TANK | EVACUATION | 2024-06-02 | 1 | 2024-06-02 | 0 | 2024-06-03 | 1 | 2024-06-03 | 2024-06-03 | 0 | 2024-06-03 | 0 | 2024-06-03 | 0 |  |  | Completed | 2024-06-03 | 0
24 | Leaking Generator Pipe | LAG, HEYDEN IPAJA | Wear & Tear | Breakdown | Mid tech | 135KVA GENERATOR |  | 2024-06-02 | 291 | 2024-06-02 | 0 |  | 291 | [9 empty] | Overdue
25 | Generator breakdown | ANAMBRA, ZIK AVENUE, AWKA | Wear & Tear | Breakdown | Gamma | 135KVA GENERATOR |  | 2024-06-02 | 1 | 2024-06-02 | 0 | 2024-06-03 | 1 | 2024-06-03 | 2024-06-03 | 0 | 2024-06-03 | 0 | 2024-06-03 | 0 |  |  | Completed | 2024-06-03 | 0
26 | Leaking water at customers Restroom | LAG, HEYDEN IPAJA | Others | Breakdown | Propearjeff | OTHERS | OTHERS | 2024-06-02 | 3 | 2024-06-03 | 1 | 2024-06-03 | 0 | 2024-06-03 | 2024-06-03 | 0 | 2024-06-03 | 0 | 2024-06-03 | 2 |  |  | Completed | 2024-06-05 | 0
28 | Hanging or not Aligning entrance door | LAG, HEYDEN IPAJA | Others | Breakdown | Taidav | OTHERS | OTHERS | 2024-06-03 | 1 | 2024-06-03 | 0 | 2024-06-04 | 1 | 2024-06-04 | 2024-06-04 | 0 | 2024-06-04 | 0 | 2024-06-04 | 0 |  |  | Completed | 2024-06-04 | 0
29 | Extractor not working | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | Abbey electrical | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2024-06-02 | 5 | 2024-06-03 | 1 | 2024-06-06 | 3 | 2024-06-06 | 2024-06-06 | 0 | 2024-06-06 | 0 | 2024-06-06 | 1 |  |  | Completed | 2024-06-07 | 0
30 | Car park painting and demarcation | LAG, AJOSE ADEOGUN | Others | Breakdown | Western Design | OTHERS | OTHERS | 2024-06-02 | 291 | 2024-06-03 | 1 |  | 290 | [9 empty] | Overdue
31 | Faulty cabinet bulb | LAG, FREEDOMWAY | Wear & Tear | Breakdown | Kitchtech | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-06-03 | 290 | 2024-06-03 | 0 |  | 290 | [9 empty] | Overdue
32 | Office AC Dripping waters | LAG, BODE THOMAS | Wear & Tear | Breakdown | G.Boyejo | 5HP STANDING AC UNIT 1 | HVAC | 2024-06-03 | 5 | 2024-06-03 | 0 | 2024-06-06 | 3 | 2024-06-07 | 2024-06-08 | 1 | 2024-06-08 | 0 | 2024-06-08 | 0 | 2024-06-08 |  | Completed | 2024-06-08 | 1
33 | Generator due for servicing | LAG, DIYA STREET | Routine Servicing | Preventive | Delightsome | 135KVA GENERATOR |  | 2024-06-03 | 2 | 2024-06-03 | 0 | 2024-06-04 | 1 | 2024-06-04 | 2024-06-04 | 0 | 2024-06-04 | 0 | 2024-06-04 | 1 | 2024-06-05 |  | Completed | 2024-06-05 | 1
34 | Request for replace of faded lobby tiles | ABIA, FACTORY RD, ABA | Others | Breakdown | Deaconess | OTHERS | OTHERS | 2024-06-03 | 5 | 2024-06-03 | 0 | 2024-06-08 | 5 | 2024-06-08 | 2024-06-08 | 0 | 2024-06-08 | 0 | 2024-06-08 | 0 | 2024-06-08 |  | Completed | 2024-06-08 | 1
35 | Generator steaming and radiator flushing | LAG, AGUNGI | Wear & Tear | Breakdown | Gen Warehouse | 135KVA GENERATOR |  | 2024-06-01 | 292 | 2024-06-03 | 2 |  | 290 | [9 empty] | Overdue
36 | Request for under bar fridge gasket | PH, ONNE RD, GRA | Others | Breakdown | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-06-03 | 290 | 2024-06-03 | 0 | 2024-06-06 | 3 | 2024-06-06 | 2024-06-06 | 0 | 2024-06-06 | 2 | 2024-06-08 | 285 |  |  | Overdue
37 | Refloring of BOH floor and tap area | LAG, JOEL OGUNNAIKE | Others | Breakdown | Cradleview | OTHERS | OTHERS | 2024-06-03 | 290 | 2024-06-03 | 0 | 2024-06-04 | 1 | 2024-06-05 | 2024-06-05 | 0 | [6 empty] | Overdue
38 | Faulty cabinet bulb | LAG, FREEDOMWAY | Wear & Tear | Breakdown |  | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-06-03 | 290 | 2024-06-03 | 0 |  | 290 | [9 empty] | Overdue
39 | Detached ROT Machine cover | LAG, BADORE | Wear & Tear | Breakdown | Service center | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-06-03 | 290 | 2024-06-03 | 0 | 2024-06-03 | 0 | [9 empty] | Overdue
40 | No water in the store | LAG, NNPC ALAPERE | Wear & Tear | Breakdown | Pro equipment | OTHERS | OTHERS | 2024-06-03 | 3 | 2024-06-03 | 0 | 2024-06-06 | 3 | 2024-06-06 | 2024-06-06 | 0 | 2024-06-06 | 0 | 2024-06-06 | 0 | 2024-06-07 |  | Completed | 2024-06-06 | 1
41 | Cabinet not attainaing temperature | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | Kitchtech | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-06-03 | 290 | 2024-06-03 | 0 |  | 290 | [9 empty] | Overdue
42 | Faulty dry store AC | LAG, LATEEF JAKANDE | Others | Breakdown |  |  |  | 2024-06-03 | 290 | 2024-06-03 | 0 |  | 290 | [9 empty] | Overdue
43 | Vegetable shreeder not working | LAG, OSOLOWAY | Others | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-06-03 | 290 | 2024-06-03 | 0 |  | 290 | [9 empty] | Overdue
44 | Broken handwash sink | LAG, MARINA | Others | Breakdown | Propearjeff | KITCHEN WASH HAND SINK | PLUMBING | 2024-06-03 | 290 | 2024-06-03 | 0 |  | 290 | [9 empty] | Overdue
45 | Faulty Roller shutter | LAG, AGUNGI | Others | Breakdown | Basscomm | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-06-16 | 277 | 2024-06-16 | 0 | 2024-06-19 | 3 | [9 empty] | Overdue
46 | Inverter Isuue | LAG, ILUPEJU | Electrical Surge | Breakdown | Damant tech | INVERTER SYSTEM | INVERTER
47 | Lobby door self close | LAG, SKYMALL | Others | Breakdown | Full turn | OTHERS | OTHERS
48 | Faulty Dumpster door handle | LAG, OMOLE | Others | Breakdown | Matolad | CHICKEN DUMP TROLLEY | FURNITURE
49 | Claddng of rear wall | LAG, OPEBI | Others | Breakdown | Acorn | WALL | BUILDING
50 | Supply of white flower bed stone | LAG, IKOTUN | Others | Breakdown | Venys | OTHERS | OTHERS
51 | Detached entrance pole stand | LAG, IDIMU | Others | Breakdown | Pentecostal | OTHERS | OTHERS
52 | Blocked fat trap pipe | LAG, ALIMOSHO | Others | Breakdown | Pentecostal | SEPTIC TANK | EVACUATION
53 | Broken slab at car park | LAG, IRE-AKARI | Others | Breakdown | Acorn | SLAB | BUILDING
54 | Gs burner hosepipe recheck | LAG, OPEBI | Wear & Tear | Breakdown | Berrade | GAS HOSE & SUNDRIES | GAS
55 | Servicing of Generator | IMO, OKIGWE | Routine Servicing | Preventive | Gamma | 135KVA GENERATOR
56 | Supply of dumpster | LAG, MAGODO | Others | Breakdown | Acorn | CHICKEN DUMP TROLLEY | FURNITURE
57 | Pressure fryers not coming up | LAG, MARINA | Wear & Tear | Breakdown | Lebiz | PRESURE FRYER 1 | KITCHEN_EQUIPMENT
58 | Broken letter C on Signage bulb | OGUN, HEYDEN IBAFO | Others | Breakdown | Accentrex | OTHERS | OTHERS
59 | Generator due for servicing | LAG, MAGODO | Routine Servicing | Preventive | Mid tech | 135KVA GENERATOR
60 | Request for park line | LAG, OMOLE | Others | Breakdown | Western Design | OTHERS | OTHERS | 2024-06-10 | 20 | 2024-06-10 | 0 | 2024-06-12 | 2 | 2024-06-13 | 2024-06-13 | 0 | 2024-06-14 | 14 | 2024-06-28 | 2 | 2024-06-29 | 250000 | Completed | 2024-06-30 | 0
61 | Ice cream needs servicing | PH, OYIGBO | Routine Servicing | Preventive | Just food | ICE CREAM MACHINE | KITCHEN_EQUIPMENT
62 | Faulty air curtain | BAYELSA, TOMBIA | Others | Breakdown
63 | AIR CONDITIONERS IN DRY STORE AND CUSTOMERS CONVINIENTS NOT WORKING | PH, TRANS AMADI | Routine Servicing | Preventive | Moffen | 5HP STANDING AC UNIT 1 | HVAC | 2024-06-28 | 265 | 2024-06-28 | 0 |  | 265 | [9 empty] | Overdue
64 | RUSTED TOWER TANK STAND | LAG, OGUNLANA DRIVE | Others | Breakdown | Acorn | OTHERS | OTHERS | 2024-06-12 | 68 | 2024-06-12 | 0 | 2024-08-02 | 51 | 2024-08-05 | 2024-08-09 | 4 | 2024-08-09 | 0 | 2024-08-09 | 10 |  | 2197350 | Completed | 2024-08-19 | 0
65 | CABINET SHELF | LAG, ILUPEJU | Others | Breakdown | Matolad | DISPLAY CABINET | KITCHEN_EQUIPMENT
66 | FAULTY WASH HAND TAP | LAG, AKOWONJO | Others | Breakdown | Propearjeff | TAP | PLUMBING | 2024-06-07 | 286 | 2024-06-24 | 17 |  | 269 | [9 empty] | Overdue
67 | GENERATOR DUE FOR SERVICING | LAG, IKORODU | Routine Servicing | Preventive | Mid tech | GENERATOR | GENERATOR | 2024-06-27 | -11 | 2024-06-27 | 0 |  | 266 | [8 empty] | 45489 | Completed | 2024-06-16 | 0
68 | STORE VEGETABLE SHREDDING MACHINE STOPPER | OGUN, OKE-ILEWO | Others | Breakdown | BCE | DICING MACHINE | KITCHEN_EQUIPMENT | 2024-06-30 | 263 |  | 263 | [11 empty] | Overdue
69 | Faulty Cold room and freezer room temperature check | EBONYI, WATERWORKS, ABAKALIKI | Wear & Tear | Breakdown | Moffen | FREEZER ROOM | HVAC | 2024-06-14 | 279 | 2024-06-14 | 0 |  | 279 | [9 empty] | Overdue
70 | GENERATOR NOT STARTING | LAG, OKOTA | Routine Servicing | Preventive | Mid tech | GENERATOR | GENERATOR | 2024-06-30 | 263 | 2024-06-30 | 0 | 2024-06-30 | 0 | [9 empty] | Overdue
71 | DISPLACED WATER TREATMENT PLANT NET COVER | LAG, AWOLOWO 2 | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-06-02 | 26 | 2024-06-04 | 2 | 2024-06-28 | 24 | [9 empty] | Completed | 2024-06-28 | 0
72 | FAULTY LOOBY ENTRANCE DOOR | LAG, AJOSE ADEOGUN | Others | Breakdown | Taidav | OTHERS | OTHERS | 2024-06-27 | 266 | 2024-06-27 | 0 | 2024-06-28 | 1 | [9 empty] | Overdue
73 | FAULTY FREEZER ROOM | LAG, FREEDOMWAY | Others | Breakdown | Tona oguns | FREEZER ROOM | HVAC | 2024-06-30 | 263 | 2024-06-30 | 0 | 2024-07-01 | 1 | [9 empty] | Overdue
74 | TAYLOR MACHINE NOT WORKING EFFECTIVELY | LAG, OBA AKRAN | Corrective Action | Corrective | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-06-30 | 263 | 2024-06-30 | 0 |  | 263 | [9 empty] | Overdue
75 | FAULTY SOUND SYSTEM | LAG, ETERNA LEKKI | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-06-27 | 266 | 2024-06-27 | 0 | 2024-06-28 | 1 | 2024-07-02 | 2024-07-02 | 0 | 2024-07-04 | 6 | 2024-07-10 | 253 | 2024-07-12 | 201250 | Overdue
76 | FAULTY LAMP HOLDER IN THE CABINET | LAG, OBA AKRAN | Electrical Surge | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-06-30 | 263 | 2024-06-30 | 0 |  | 263 | [9 empty] | Overdue
77 | FAULTY CHIPS DUMP MACHINE. | LAG, ALIMOSHO | Others | Breakdown | BCE | CHIPS DUMP | KITCHEN_EQUIPMENT | 2024-06-30 | 263 | 2024-06-30 | 0 |  | 263 | [9 empty] | Overdue
78 | FAULTY WATER HEATER. | LAG, ALIMOSHO | Others | Breakdown | Propearjeff | WATER HEATER | PLUMBING | 2024-06-30 | 263 | 2024-06-30 | 0 |  | 263 | [9 empty] | Overdue
79 | SEPTIC TANK EVACUATION | LAG, FREEDOMWAY | Others | Breakdown | Berrade | SEPTIC TANK | EVACUATION | 2024-06-30 | 263 | 2024-06-30 | 0 |  | 263 | [9 empty] | Overdue
80 | COLDROOM NOT ATTAINING TEMPERATURE | LAG, LATEEF JAKANDE | Corrective Action | Corrective | TRIPPLE O | COLD ROOM UNIT | HVAC | 2024-06-30 | 263 | 2024-06-30 | 0 |  | 263 | [9 empty] | Overdue
81 | FAULTY ROLLER SHUTTER | EDO, SILUKO | Others | Breakdown | Basscomm | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-06-30 | 263 | 2024-06-30 | 0 |  | 263 | [9 empty] | Overdue
82 | FREEZER ROOM BREAKDOWN | ABIA, OGBOR HILLS | Corrective Action | Corrective | JERRY ENWENYEOKU | FREEZER ROOM | HVAC | 2024-06-24 | 269 | 2024-06-24 | 0 | 2024-06-28 | 4 | [9 empty] | Overdue
83 | FAULTY/BURNT INVERTER | ENUGU, NSUKKA | Electrical Surge | Breakdown | PETOJO4STAR | INVERTER SYSTEM | INVERTER | 2024-06-09 | 284 | 2024-06-09 | 0 |  | 284 | [9 empty] | Overdue
84 | GENERATOR DUE FOR SERVICING | LAG, AJAH | Routine Servicing | Preventive | Gamma | GENERATOR | GENERATOR | 2024-06-29 | 2 | 2024-06-30 | 1 | 2024-06-30 | 0 | [9 empty] | Completed | 2024-07-01 | 0
85 | GENERATOR DUE FOR SERVICING | LAG, MAGODO | Others | Breakdown | ACORN | CHIPS DUMP | KITCHEN_EQUIPMENT | 2024-06-17 | 19 | 2024-06-17 | 0 | 2024-06-17 | 0 | 2024-06-17 | 2024-06-19 | 2 | 2024-06-20 | 1 | 2024-06-21 | 15 | 2024-07-06 | 100000 | Completed | 2024-07-06 | 1
86 | BLOCKED CAR PARK DRAINAGE | LAG, IDIMU | Others | Breakdown | Pentecostal | OTHERS | OTHERS | 2024-06-10 | 20 | 2024-06-10 | 0 | 2024-06-11 | 1 | 2024-06-11 | 2024-06-13 | 2 | 2024-06-13 | 4 | 2024-06-17 | 13 | 2024-06-18 | 180000 | Completed | 2024-06-30 | 0
87 | REPAINTING OF CASHIERS COUNTER | LAG, HEYDEN ALAPERE | Others | Breakdown | Matolad | PAINTING | BUILDING | 2024-06-29 | 264 | 2024-06-29 | 0 | 2024-06-30 | 1 | [9 empty] | Overdue
88 | CUSTOMERS REST ROOM AC DRIPPING OUT WATER | LAG, AJAH | Others | Breakdown | Tona oguns | 5HP STANDING AC UNIT 1 | HVAC | 2024-06-28 | 265 | 2024-06-30 | 2 | 2024-07-01 | 1 | [9 empty] | Overdue
89 | INVERT NOT WORKING, SMELL BURNT | LAG, MAGODO | Electrical Surge | Breakdown | Damant tech | INVERTER SYSTEM | INVERTER | 2024-06-30 | 263 | 2024-06-30 | 0 |  | 263 | [9 empty] | Overdue
90 | TILTING PAN NOT HEATING | PPU PH | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-06-30 | 263 | 2024-06-30 | 0 |  | 263 | [9 empty] | Overdue
91 | CABINET NOT WORKING | LAG, FESTAC | Electrical Surge | Breakdown | Kitchtech | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-06-24 | 269 | 2024-06-30 | 6 |  | 263 | [9 empty] | Overdue
92 | FAULTY AC | LAG, JOEL OGUNNAIKE | Others | Breakdown | THIO AND PARTNERS | 5HP STANDING AC UNIT 1 | HVAC | 2024-06-28 | 265 | 2024-06-30 | 2 |  | 263 | [9 empty] | Overdue
93 | FAULTY FOOD WARMER HANDLE | LAG, MMA2 | Electrical Surge | Breakdown | BCE | OTHERS | OTHERS | 2024-06-29 | 264 | 2024-06-30 | 1 | 2024-07-02 | 2 | [9 empty] | Overdue
94 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | LAG, MOBIL OGBA | Electrical Surge | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-06-29 | 264 | 2024-06-30 | 1 |  | 263 | [9 empty] | Overdue
95 | GENERATOR DUE FOR SERVICING | LAG, AJAH | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-06-29 | 2 | 2024-06-30 | 1 |  | 263 | [9 empty] | Completed | 2024-07-01 | 0
96 | Freezer room handle | EBONYI, WATERWORKS, ABAKALIKI | Others | Breakdown | Moffen | FREEZER ROOM | HVAC | 2024-06-29 | 264 | 2024-06-30 | 1 |  | 263 | [9 empty] | Overdue
97 | Replacement of BOH wash hand basin and 4 soap dispenser | IBADAN, CHALLENGE | Others | Breakdown | PRO EQUIP | LOBBY WASH HAND BASIN | PLUMBING | 2024-06-29 | 264 | 2024-06-30 | 1 | 2024-07-01 | 1 | 2024-07-01 | 2024-07-01 | 0 | 2024-07-01 | 9 | 2024-07-10 | 253 | 2024-07-11 | 120000 | Overdue
98 | CABINET NOT ATTAINING TEMPERATURE | LAG, IKEJA MALL | Electrical Surge | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-06-22 | 271 | 2024-06-23 | 1 |  | 270 | [9 empty] | Overdue
99 | BOH LEAKING ROOF | LAG, MARINA | Others | Breakdown | ACORN | ROOF | BUILDING | 2024-06-25 | 268 | 2024-06-25 | 0 | 2024-06-25 | 0 | [9 empty] | Overdue
100 | REPLACEMENT OF BOH HAND STAND | LAG, TOTAL LEKKI | Others | Breakdown | PRO EQUIP | OTHERS | OTHERS | 2024-06-30 | 263 | 2024-06-30 | 0 |  | 263 | [7 empty] | 2024-07-02 |  | Overdue
101 | FAULTY OFFICE AC | LAG, FREEDOMWAY | Others | Breakdown | Tona oguns | 5HP STANDING AC UNIT 1 | HVAC | 2024-06-27 | 266 | 2024-06-29 | 2 | 2024-07-01 | 2 | [9 empty] | Overdue
102 | BROKEN DIESEL MAIN TANK PLATFORM | IMO, WETHERAL RD, OWERRI | Wear & Tear | Breakdown | Deaconess | GENERATOR | GENERATOR | 2024-06-25 | 268 | 2024-06-26 | 1 | 2024-06-27 | 1 | [9 empty] | Overdue
103 | REQUEST FOR NEW ROLLER SHUTTER REMOTE | LAG, ABULE EGBA | Others | Breakdown | Basscomm | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-06-22 | 271 | 2024-06-22 | 0 | 2024-07-08 | 16 | 2024-07-08 | 2024-07-08 | 0 | [6 empty] | Overdue
104 | FAULTY OFFICE AC | LAG, FREEDOMWAY | Routine Servicing | Preventive | Tona oguns | 5HP STANDING AC UNIT 1 | HVAC | 2024-06-27 | 266 |  | 266 | [11 empty] | Overdue
105 | Faulty rotisserie machine | IBADAN, CHALLENGE | Wear & Tear | Breakdown | SIWA | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-06-29 | 264 | 2024-06-29 | 0 | 2024-06-19 | -10 | 2024-06-20 | 2024-06-21 | 1 | 2024-06-21 | 3 | 2024-06-24 | 269 | 2024-06-25 |  | Overdue
106 | FAULTY CUSTOMER TOILET | LAG, OKE-AFA | Others | Breakdown | Propearjeff | OTHERS | OTHERS | 2024-06-29 | 264 | 2024-06-29 | 0 |  | 264 | [9 empty] | Overdue
107 | BROKEN DIESEL MAIN TANK PLATFORM | IMO, WETHERAL RD, OWERRI | Wear & Tear | Breakdown | Deaconess | GENERATOR | GENERATOR | 2024-06-25 | 268 | 2024-06-26 | 1 | 2024-06-27 | 1 | 2024-07-01 |  | 262 | [5 empty] | 1801921.88 | Overdue
108 | ROOF LEAKAGE | LAG, AJOSE ADEOGUN | Others | Breakdown | BAMOCON | ROOF | BUILDING | 2024-06-11 | 18 | 2024-06-11 | 0 | 2024-06-15 | 4 | 2024-06-28 | 2024-06-28 | 0 | 2024-06-28 | 0 | 2024-06-28 | 1 | 2024-06-30 | 320000 | Completed | 2024-06-29 | 1
109 | Engine Block & crankshaft Replacement and Overhaul at Taiwo, Ilorin | ILORIN, TAIWO RD | Wear & Tear | Breakdown | Mid tech | GENERATOR | GENERATOR | 2024-06-25 | 268 | 2024-06-25 | 0 | 2024-06-29 | 4 |  |  |  | 2024-01-07 | 177 | 2024-07-02 | 261 | 2024-07-03 | 3938000 | Overdue
110 | FAULTY GENERATOR | PH AGGREY | Wear & Tear | Breakdown | PAGISEL | GEAR SWITCH | ELECTRICAL | 2024-06-27 | 1 | 2024-06-28 | 1 | 2024-06-28 | 0 | [9 empty] | Completed | 2024-06-28 | 0
111 | FAULTY FLOAT SWITCH | LAG, IRE-AKARI | Wear & Tear | Breakdown | PRO EQUIP | WATER TREATMENT PLANT BLD | BUILDING | 2024-06-29 | 264 | 2024-06-29 | 0 |  | 264 | [9 empty] | Overdue
112 | REQUEST FOR FLOOD LIGHT | IBADAN, BODIJA | Others | Breakdown | RANEX4WARD | FLOODLIGHT | ELECTRICAL | 2024-06-29 | 264 | 2024-06-29 | 0 |  | 264 | [9 empty] | Overdue
113 | FAULTY ROTISSEIRE MACHINE | BAYELSA, YENAGOA | Wear & Tear | Breakdown | SIWA | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-06-29 | 264 | 2024-06-29 | 0 | 2024-07-10 | 11 | [9 empty] | Overdue
114 | Painting of Cr Ikot Ekpene Building | AKWA IBOM, IKOT EKPENE RD | Others | Breakdown | JOWYN | PAINTING | BUILDING | 2024-06-12 | 281 | 2024-06-12 | 0 |  | 281 | 2024-06-20 |  | 273 | 2024-07-01 | 0 | 2024-07-01 | 262 | 2024-07-03 | 750000 | Overdue
115 | FAULTY INVERTER | PH, RUMUOLA | Others | Breakdown | DE SAM GLOBAL | INVERTER SYSTEM | INVERTER | 2024-06-23 | 270 | 2024-06-23 | 0 |  | 270 | 2024-07-09 | 2024-07-09 | 0 | 2024-07-10 | 253 |  |  |  |  | Overdue
116 | FAULTY CABINET LAMP HOLDER | LAG, AWOLOWO 2 | Others | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-06-04 | 25 | 2024-04-06 | -59 | 2024-06-29 | 84 | [9 empty] | Completed | 2024-06-29 | 0
117 | COLD ROOM FREEZING | LAG, AGUNGI | Others | Breakdown | Tona oguns | COLD ROOM UNIT | HVAC | 2024-06-28 | 265 | 2024-06-28 | 0 |  | 265 | [9 empty] | Overdue
118 | BAD KITCHEN TAPS | LAG, MAGODO | Others | Breakdown | PRO EQUIP | TAP | PLUMBING | 2024-06-24 | 5 | 2025-06-24 | 365 |  | -96 | [9 empty] | Completed | 2024-06-29 | 0
119 | FAULTY DOOR LOCK IN THE MANAGERS OFFICE. | LAG, LEKKI PHASE 1 | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-06-19 | 274 | 2024-06-25 | 6 |  | 268 | [9 empty] | Overdue
120 | FAULTY DRY STORE LOCK | LAG, LEKKI PHASE 1 | Others | Breakdown | Full turn | OTHERS | OTHERS | 2024-06-24 | -45461 | 2024-06-24 | 0 |  | 269 |  |  |  | 2024-06-28 | 265 |  |  | 2024-06-29 |  | Completed | 1900-01-05 | 1
121 | BOH LEAKING ROOF | LAG, MARINA | Others | Breakdown | Matolad | ROOF | BUILDING | 2024-06-25 | #VALUE! |  | 268 | [11 empty] | Completed | 6/ | 0
122 | DRY STORE'S AC NOT WORKING EFFECTIVELY. | LAG, MARINA | Others | Breakdown | G.Boyejo | 5HP STANDING AC UNIT 1 | HVAC | 2024-06-13 | #VALUE! | 2024-06-13 | 0 |  | 280 | [9 empty] | Completed | 26/1900 | 0
123 | RUNING TAP WATER | LAG, MOBIL OGBA | Others | Breakdown | PRO EQUIP | TAP | PLUMBING | 2024-06-27 | 0 | 2024-06-27 | 0 |  | 266 | [9 empty] | Completed | 2024-06-27 | 0
124 | FAULTY PPU OVEN AND WARMER | OSUN, GBONGAN | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-06-27 | 266 | 2024-06-27 | 0 | 2024-06-28 | 1 | 2024-06-28 |  | 265 | 2024-06-28 | 0 | 2024-06-28 | 265 | 2024-06-29 | 297775 | Overdue
125 | SINK LEAKAGE IN BACK OF HOUSE (COOK SECTION) | LAG, MOBIL OGBA | Others | Breakdown | PRO EQUIP | KITCHEN WASH HAND SINK | PLUMBING | 2024-06-26 | 3 | 2024-06-24 | -2 | 2024-06-29 | 5 | [9 empty] | Completed | 2024-06-29 | 0
126 | BROKEN WATER TREATMENT PIPES | LAG, ENTOURAGE MALL | Others | Breakdown | PRO EQUIP | WATER TREATMENT PLANT BLD | BUILDING | 2024-06-18 | 275 | 2024-06-18 | 0 | 2024-06-29 | 11 | [9 empty] | Overdue
127 | LEAKING UNDER SINK | LAG, DIYA STREET | Others | Breakdown | PRO EQUIP | KITCHEN WASH HAND SINK | PLUMBING | 2024-06-21 | 8 | 2024-06-21 | 0 |  | 272 | [9 empty] | Completed | 2024-06-29 | 0
128 | TURNED WARMER GASKET | OSUN, AYETORO | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-06-12 | 281 | 2024-06-12 | 0 | 2024-06-26 | 14 | 2024-06-26 |  | 267 | 2024-06-29 | 264 |  |  |  |  | Overdue
129 | TURNED WARMER GASKET | LAG, VGC | Others | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2024-06-06 | 287 | 2024-06-06 | 0 |  | 287 | [9 empty] | Overdue
130 | Rotisserie Machine Installation | LAG, VGC | Others | Breakdown | SIWA | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-06-21 | 7 | 2024-06-27 | 6 | 2024-06-28 | 1 | [9 empty] | Completed | 2024-06-28 | 0
131 | AIR CONDITIONERS IN DRY STORE AND CUSTOMERS CONVINIENTS NOT WORKING | PH, TRANS AMADI | Routine Servicing | Preventive | Moffen | 5HP STANDING AC UNIT 1 | HVAC | 2024-06-28 | 265 | 2024-06-28 | 0 |  | 265 | [9 empty] | Overdue
132 | ROOF LEAKAGE | LAG, AJOSE ADEOGUN | Others | Breakdown | BAMOCON | ROOF | BUILDING | 2024-06-11 | 19 | 2024-06-11 | 0 |  | 282 | 2024-06-28 |  | 265 | [5 empty] | 347585.13 | Completed | 2024-06-30 | 0
133 | BAD LIDGASKET | PH, WOJI | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-06-28 | 2 | 2024-06-28 | 0 | 2024-06-28 | 0 |  |  |  | 2024-06-28 | 0 | 2024-06-28 | 2 | 2024-06-19 | 86000 | Completed | 2024-06-30 | 0
134 | BAD LIDGASKET | LAG, LEKKI PHASE 1 | Others | Breakdown | FULL TURN | OTHERS | OTHERS | 2024-06-24 | 269 | 2024-06-24 | 0 |  | 269 | [9 empty] | Overdue
135 | Request for Car Park Line | LAG, IKORODU | Others | Breakdown | Western Design | OTHERS | OTHERS | 2024-06-10 | 20 | 2024-06-10 | 0 | 2024-06-12 | 2 | 2024-06-13 | 2024-06-14 | 1 | 2024-06-28 | 0 | 2024-06-28 | 2 | 2024-06-29 | 200000 | Completed | 2024-06-30 | 0
136 | Request for Car Park Line | LAG, LATEEF JAKANDE | Others | Breakdown | Western Design | OTHERS | OTHERS | 2024-06-10 | 20 | 2024-06-10 | 0 | 2024-06-12 | 2 | 2024-06-13 | 2024-06-14 | 1 | 2024-06-28 | 0 | 2024-06-28 | 2 | 2024-06-29 | 340000 | Completed | 2024-06-30 | 0
137 | REQUEST FOR NEW WATER CISTERN FOR CUSTOMER RESTROOM | AKWA IBOM, ORON RD | Others | Breakdown | SUNDAY UDOU | OTHERS | OTHERS | 2024-06-03 | 19 | 2024-06-03 | 0 | 2024-06-20 | 17 | 2024-06-20 | 2024-06-20 | 0 | 2024-06-20 | 0 | 2024-06-20 | 2 | 2024-06-21 | 60700 | Completed | 2024-06-22 | 0
138 | Gbagada Project level up 2024 -update | LAG, GBAGADA | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-07-07 | 256 | 2024-06-09 | -28 | 2024-06-26 | 17 | 2024-06-26 | 2024-06-26 | 0 | 2024-06-28 | 265 |  |  | 2024-06-27 | 1550000 | Overdue
139 | ROTISSERIE MACHINE CONTROL PANEL NOT DISPLAYING | LAG, OBA AKRAN | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-06-22 | 271 | 2024-06-22 | 0 | 2024-06-28 | 6 |  |  |  | 2024-06-28 | 0 | 2024-06-28 | 265 | 2024-06-29 |  | Overdue
140 | FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, OGUDU | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-06-28 | 1 | 2024-06-28 | 0 | 2024-06-28 | 0 | [9 empty] | Completed | 2024-06-29 | 0
141 | OPENED CEILING NEEDS REPLACEMENT | LAG, IKORODU | Others | Breakdown | MATOLAD | ROOF | BUILDING | 2024-06-27 | 266 | 2024-06-28 | 1 |  | 265 | [9 empty] | Overdue
142 | ROTISSERIE MACHINE CONTROL PANEL NOT DISPLAYING | LAG, OBA AKRAN | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-06-22 | 8 | 2024-06-28 | 6 |  | 265 | [8 empty] | 461175 | Completed | 2024-06-30 | 0
143 | REPLACEMENT OF LOBBY TABLE STAND | LAG, IRE-AKARI | Others | Breakdown | TAIDAV | CUSTOMER TABLE | FURNITURE | 2024-06-27 | 266 | 2024-06-28 | 1 |  | 265 | [9 empty] | Overdue
144 | CHIPS DUMP BULB FUSED OUT | LAG, MAGODO | Others | Breakdown | BCE | CHIPS DUMP | KITCHEN_EQUIPMENT | 2024-06-18 | 275 | 2024-06-19 | 1 |  | 274 | [9 empty] | Overdue
145 | WORN OUT WARMER GASKET | BAYELSA, TOMBIA | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-06-27 | 266 | 2024-06-27 | 0 | 2024-06-28 | 1 | [8 empty] | 110725 | Overdue
146 | DETACHED ROOF FOR DUST BIN | LAG, AWOLOWO | Others | Breakdown | FULL TURN | ROOF | BUILDING | 2024-06-22 | 271 | 2024-06-23 | 1 | 2024-06-26 | 3 | 2024-06-26 | 2024-06-27 | 1 | 2024-06-27 | 1 | 2024-06-28 | 265 | 2024-06-29 | 45000 | Overdue
147 | AIR CONDITIONERS IN DRY STORE AND CUSTOMERS CONVINIENTS NOT WORKING | PH, TRANS AMADI | Others | Breakdown | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-06-28 | 265 | 2024-06-28 | 0 |  | 265 | [9 empty] | Overdue
148 | LEAKING AERATION TANK | LAG, ALIMOSHO | Others | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-06-23 | 6 | 2024-06-23 | 0 | 2024-06-28 | 5 | 2024-06-28 | 2024-06-28 | 0 | 2024-06-28 | 265 |  |  |  | 1760000 | Completed | 2024-06-29 | 0
149 | DETACHED LOBBY POP CEILING | LAG, IDIMU | Others | Breakdown | PENTECOSTAL | CEILING BOARD | BUILDING | 2024-06-18 | 275 | 2024-06-18 | 0 | 2024-06-18 | 0 | 2024-06-25 | 2024-06-25 | 0 | 2024-06-25 | 268 |  |  |  | 140000 | Overdue
150 | CONNECTION OF DIESEL TANK TO GENERATOR BASE TANK | LAG, IKORODU | Others | Breakdown | MID TECH | GENERATOR | GENERATOR | 2024-06-21 | 272 | 2024-06-21 | 0 |  | 272 |  |  |  | 2024-06-27 | 266 |  |  |  | 277635 | Overdue
151 | FAULTY ICE CREAM MACHINE | LAG, AJAH | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-06-25 | 7 | 2024-06-25 | 0 |  | 268 |  |  |  | 27/06/2024 | 0 | 2024-06-27 | 5 | 2024-06-29 | 277635 | Completed | 2024-07-02 | 0
152 | GENERATOR SERVICING | ABIA, ADAZI RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-06-23 | 4 | 2024-06-23 | 0 | 2024-06-24 | 1 | [8 empty] | 45475 | Completed | 2024-06-27 | 0
153 | GENERATOR SERVICING | CALABAR, NDIDEM | Routine Servicing | Preventive | GEN WAREHOUSE | GENERATOR | GENERATOR | 2024-06-27 | 0 | 2024-06-27 | 0 | 2024-06-27 | 0 |  |  |  | 2024-06-27 | 0 | 2024-06-27 | 0 |  | 478375 | Completed | 2024-06-27 | 0
154 | FAULTY MALE CHAGING ROOM DOOR AND CASHIER SWING DOOR | LAG, FESTAC | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-06-15 | 278 | 2024-06-15 | 0 |  | 278 | [9 empty] | Overdue
155 | DAMAGE OFFICE DOOR | LAG, AJOSE ADEOGUN | Others | Breakdown | FULL TURN | OTHERS | OTHERS | 2024-06-11 | 17 | 2024-06-11 | 0 |  | 282 |  |  |  | 2024-06-13 | 1 | 2024-06-14 | 14 |  | 109886.5 | Completed | 2024-06-28 | 0
156 | LEAKING WATER FROM UNDER BAR | LAG, HEYDEN IPAJA | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-06-17 | 13 | 2024-06-17 | 0 |  | 276 | [9 empty] | Completed | 2024-06-30 | 0
157 | GENERATOR DUE FOR SERVICING | LAG, IKORODU | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-06-27 | 1 | 2024-06-27 | 0 |  | 266 | [9 empty] | Completed | 2024-06-28 | 0
158 | FREEZER / COLD ROOM NOT ATTAINING TEMPERATURE | DELTA, EFFURUN | Others | Breakdown | MOFFEN | FREEZER ROOM | HVAC | 2024-06-27 | 266 | 2024-06-27 | 0 |  | 266 | [9 empty] | Overdue
159 | FAULTY ICE CREAM MACHINE | LAG, OGUDU | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-06-08 | 285 | 2024-06-08 | 0 |  | 285 |  |  |  | 2024-07-12 | 251 |  |  |  |  | Overdue
160 | RUSTED DIESEL TANK | LAG, IRE-AKARI | Wear & Tear | Breakdown | DAMI FOTE | GENERATOR | GENERATOR | 2024-06-27 | 266 | 2024-06-27 | 0 | 2024-07-01 | 4 |  |  |  | 2024-07-05 | 258 |  |  |  |  | Overdue
161 | FAULTY FEED TUBE | IMO, WETHERAL RD, OWERRI | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-06-09 | 284 | 2024-06-09 | 0 | 2024-06-13 | 4 | 2024-06-13 |  | 280 | 2024-06-13 | 5 | 2024-06-18 | 275 |  |  | Overdue
162 | DETACHED STAIRCASE HANDRAIL IN THE STORE | LAG, LATEEF JAKANDE | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-06-25 | 268 | 2024-06-25 | 0 |  | 268 | [9 empty] | Overdue
163 | NEW GENERATOR BATTERY | PPU Ajah | Wear & Tear | Breakdown | MID TECH | GENERATOR | GENERATOR | 2024-06-25 | 268 | 2024-06-25 | 0 |  | 268 | [9 empty] | Overdue
164 | FAULTY UNDER BAR CHILLER | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | G.B BOYEJO | NBC CHILLER | HVAC | 2024-06-15 | 278 | 2024-06-15 | 0 |  | 278 | [9 empty] | Overdue
165 | GENERATOR IS DUE FOR SERVICE | OGUN, SOKENU | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-06-25 | 1 | 2024-06-25 | 0 | 2024-06-26 | 1 | [9 empty] | Completed | 2024-06-26 | 0
166 | FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, ILUPEJU | Routine Servicing | Preventive | TONA OGUNS | FREEZER ROOM | HVAC | 2024-06-25 | 268 | 2024-06-25 | 0 | 2024-06-24 | -1 | [9 empty] | Overdue
167 | IN STORE MINOR REPAIRS | DELTA, ISOKO RD | Others | Breakdown | LOCAL VENDOR | LOBBY WALL MIRROR | OTHERS | 2024-06-27 | 266 | 2024-06-27 | 0 | 2024-06-27 | 0 |  |  |  | 2024-06-27 | 0 | 2024-06-27 | 266 | 2024-06-28 | 65000 | Overdue
168 | LEAKING CHIPS MACHINE | ENUGU, CHIME AVENUE | Others | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-06-17 | 276 | 2024-06-17 | 0 | 2024-06-18 | 1 | [7 empty] | 2024-06-30 |  | Overdue
169 | FAULTY UV LIGHT AND PUMPING MACHINE | LAG, VGC | Electrical Surge | Breakdown | JOEL OMOTOSHO | UV LIGHT | WTP | 2024-06-26 | 1 | 2024-06-26 | 0 | 2024-06-27 | 1 | [9 empty] | Completed | 2024-06-27 | 0
170 | GENERATOR BREAK DOWN | LAG, ETERNA LEKKI | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-06-25 | 2 | 2024-06-25 | 0 | 2024-06-26 | 1 | [9 empty] | Completed | 2024-06-27 | 0
171 | RUNING TAP WATER | LAG, MOBIL OGBA | Others | Breakdown | PRO EQUIP | TAP | PLUMBING | 2024-06-27 | 0 | 2024-06-27 | 0 | 2024-06-27 | 0 | [9 empty] | Completed | 2024-06-27 | 0
172 | FAULTY MALE CUSTOMER RESTROOM FLUSHER | LAG, IDIMU | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-06-25 | 268 | 2024-06-25 | 0 |  | 268 | [9 empty] | Overdue
173 | GENERATOR IS DUE FOR SERVICE | OGUN, SOKENU | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-06-25 | 268 | 2024-06-25 | 0 |  | 268 | [9 empty] | Overdue
174 | FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, ILUPEJU | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-06-25 | 268 | 2024-06-25 | 0 |  | 268 | [9 empty] | Overdue
175 | FAULTY EQUIPMENT(FAULTY TILTING PAN) | IMO, OKIGWE | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-06-25 | 268 | 2024-06-25 | 0 | 2024-06-25 | 0 | [9 empty] | Overdue
176 | FAULTY WATER BOILER | LAG, JOEL OGUNNAIKE | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-06-25 | 268 | 2024-06-25 | 0 |  | 268 | [9 empty] | Overdue
177 | FAULTY OFFICE AIR CONDITIONER | DELTA, ISOKO RD | Routine Servicing | Preventive | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-06-25 | 268 | 2024-06-25 | 0 |  | 268 | [9 empty] | Overdue
178 | BAD LOBBY ENTRANCE DOOR | LAG, OKOTA | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-06-25 | 268 | 2024-06-25 | 0 |  | 268 | [9 empty] | Overdue
179 | PARTICULES FOUND IN WATER | LAG, BADORE | Others | Breakdown | PRO EQUIP | TAP | PLUMBING | 2024-06-23 | 270 | 2024-06-24 | 1 | 2024-06-25 | 1 | [9 empty] | Overdue
180 | FAULTY WARMER | LAG, FESTAC | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-06-25 | 268 | 2024-06-25 | 0 | 2024-06-25 | 0 | [7 empty] | 2024-06-26 |  | Overdue
181 | FAULTY INVERTER; LIMCA ROAD ONITSHA | ANAMBRA, LIMCA RD, ONITSHA | Others | Breakdown | PETOJO4STAR | INVERTER SYSTEM | INVERTER | 2024-06-10 | 283 | 2024-06-10 | 0 |  | 283 | [9 empty] | Overdue
182 | GENERATOR ISSUE | LAG, JIBOWU | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-06-10 | 283 | 2024-06-10 | 0 |  | 283 | [9 empty] | Overdue
183 | Removal of Signage (Signage Repair) | LAG, OBA AKRAN | Others | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-06-03 | 7 | 2024-06-04 | 1 | 2024-06-07 | 3 | 2024-06-07 | 2024-06-07 | 0 | 2024-06-07 | 0 | 2024-06-07 | 3 | 2024-06-09 | 250000 | Completed | 2024-06-10 | 0
184 | FAULTY LOBBY ENTRANCE DOOR HINGES | LAG, LEKKI PHASE 1 | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-06-05 | 288 | 2024-06-06 | 1 | 2024-06-07 | 1 | [9 empty] | Overdue
185 | FAULTY AIR CURTAIN | LAG, EJIGBO | Others | Breakdown | EKNOR | OTHERS | OTHERS | 2024-06-08 | 285 | 2024-06-10 | 2 |  | 283 | [9 empty] | Overdue
186 | BROKEN TOILET BASE | LAG, OGUDU | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-06-10 | 283 | 2024-06-10 | 0 |  | 283 | [9 empty] | Overdue
187 | GENERATOR DUE FOR SERVICE | PPU Oniru | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-06-10 | 29 | 2024-06-10 | 0 | 2024-06-10 | 0 | [9 empty] | Completed | 2024-07-09 | 0
188 | GENERATOR DUE FOR SERVICE | LAG, GBAGADA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-06-10 | 283 | 2024-06-10 | 0 | 2024-06-10 | 0 | [9 empty] | Overdue
189 | FAULTY ROLLER SHUTTER | LAG, OBA AKRAN | Others | Breakdown | Basscomm | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-06-10 | 283 | 2024-06-10 | 0 |  | 283 | [9 empty] | Overdue
190 | CONNECTION OF PIPE FROM GEN TO DIESEL TANK | LAG, ETERNA LEKKI | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-06-10 | 283 | 2024-06-10 | 0 | 2024-06-10 | 0 | [7 empty] | 2024-06-11 |  | Overdue
191 | DOOR HANDLE FAULTY | LAG, OBA AKRAN | Wear & Tear | Breakdown | FULL TURN | OTHERS | OTHERS | 2024-06-05 | 288 | 2024-06-05 | 0 | 2024-06-05 | 0 |  |  |  |  | 45452 | 2024-06-09 | 284 | 2024-06-12 |  | Overdue
192 | CR OLOFAWAY GENERATOR SERVICE | ILORIN, OLOFAWAY | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-06-05 | 288 | 2024-06-05 | 0 |  | 288 | [9 empty] | Overdue
193 | GENERTOR DUE FOR SERVICING | LAG, TEJUOSHO | Routine Servicing | Preventive | GEN WAREHOUSE | GENERATOR | GENERATOR | 2024-06-05 | 288 | 2024-06-05 | 0 | 2024-06-06 | 1 |  |  |  | 2024-06-06 | 287 |  |  |  |  | Overdue
194 | EVACUATION AND EXCAVATION OF SEWAGE | LAG, FESTAC | Others | Breakdown | PENTECOASTAL | SEPTIC TANK | EVACUATION | 2024-06-10 | 283 | 2024-06-10 | 0 | 2024-06-10 | 0 | [8 empty] | 336260 | Overdue
195 | GENERATOR DUE FOR SERVICING | LAG, IPAJA RD | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-06-08 | 285 | 2024-06-10 | 2 |  | 283 | [9 empty] | Overdue
196 | FAULTY ICE CREAM MACHINE | LAG, OGUDU | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-06-08 | 285 | 2024-06-08 | 0 | 2024-06-10 | 2 | [9 empty] | Overdue
197 | GENERATOR DUE FOR SERVICING | ILORIN, TAIWO RD | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-06-08 | 285 | 2024-06-10 | 2 |  | 283 | [9 empty] | Overdue
198 | REQUEST FOR HAND WASH DISPENSER | IBADAN, IDI-APE (IWO RD) | Others | Breakdown | PRO EQUIP | OTHERS | OTHERS | 2024-06-10 | 283 | 2024-06-10 | 0 |  | 283 | [9 empty] | Overdue
199 | FREEZER ROOM FAULTY | LAG, OGUNLANA DRIVE | Others | Breakdown | BB Commercial | FREEZER ROOM | HVAC | 2024-06-01 | 292 | 2024-06-10 | 9 | 2024-06-10 | 0 | [7 empty] | 2024-06-11 |  | Overdue
200 | PX ILUPEJU DISCONNECTED INTERNET CABLE AND RODENT HOLE | LAG, ILUPEJU | Others | Breakdown | FULL TURN | OTHERS | OTHERS | 2024-06-04 | 289 | 2024-06-04 | 0 | 2024-06-05 | 1 | 2024-06-05 | 2024-05-06 | -30 | 2024-05-06 | 30 | 2024-06-05 | 288 | 2024-06-10 |  | Overdue
201 | FIXING OF FAULTY ROTISSERIE MACHINE | LAG, MARINA | Others | Breakdown | SIWA | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-06-05 | 288 | 2024-06-05 | 0 | 2024-06-06 | 1 | [8 empty] | 475520.31 | Overdue
202 | REPAIR OF WARMER GASKET | LAG, ETERNA LEKKI | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-06-08 | 285 | 2024-06-08 | 0 |  | 285 | [9 empty] | Overdue
203 | Servicing of Generator | AKWA IBOM, EKET-ORON RD | Routine Servicing | Preventive | GEN WAREHOUSE | GENERATOR | GENERATOR | 2024-06-08 | 285 | 2024-06-08 | 0 | 2024-06-10 | 2 |  |  |  | 2024-06-10 | 0 | 2024-06-10 | 283 | 2024-06-11 | 188125 | Overdue
204 | DETACHED GAS COOKER KNOB | LAG, IPAJA RD | Others | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-06-06 | 287 | 2024-06-07 | 1 | 2024-06-08 | 1 | [8 empty] | 50000 | Overdue
205 | LOBBY SPEAKER NOT WORKING | LAG, MAGODO | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-06-08 | 285 | 2024-06-08 | 0 |  | 285 | [9 empty] | Overdue
206 | Requesting for lobby dumpster | IBADAN, IDI-APE (IWO RD) | Others | Breakdown | MATOLAD | CHICKEN DUMP TROLLEY | FURNITURE | 2024-06-05 | 288 | 2024-06-05 | 0 | 2024-06-09 | 4 | [9 empty] | Overdue
207 | URGENT GENERATOR MAINTENANCE | ENUGU, ABAKPA | Routine Servicing | Preventive | GEN WAREHOUSE | GENERATOR | GENERATOR | 2024-06-03 | 290 | 2024-06-03 | 0 | 2024-06-04 | 1 |  |  |  | 2024-06-04 | 289 |  |  |  | 344000 | Overdue
208 | REQUEST FOR REPAIR OF BROKEN GLASS CABINET | LAG, OKOTA | Others | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-06-07 | 1 | 2024-06-07 | 0 | 2024-06-08 | 1 | [9 empty] | Completed | 2024-06-08 | 0
209 | ROTISSERIE MACHINE NOT HEATING | ANAMBRA, ZIK AVENUE, AWKA | Electrical Surge | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-06-30 | 263 | 2024-06-30 | 0 | 2024-07-11 | 11 | [9 empty] | Overdue
210 | FAULTY ICE CREAM MACHINE | PH, ABACHA RD | Electrical Surge | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-06-07 | 286 | 2024-06-08 | 1 | 2024-06-20 | 12 | 2024-06-20 |  | 273 | [5 empty] | 482951 | Overdue
211 | REQUEST FOR GABLE END FOR THE UPPER PART OF THE BUILDING | OSUN, GBONGAN | Others | Breakdown | DEFAVOUR | OTHERS | OTHERS | 2024-06-19 | 274 | 2024-06-20 | 1 | 2024-07-03 | 13 | 2024-07-05 | 2024-07-05 | 0 | 2024-07-05 | 4 | 2024-07-09 | 254 | 2024-07-10 | 384000 | Overdue
212 | REQUEST FOR EVACUATION IN ORDER TO FIX BROKEN PIPE IN THE SEPTIC CHAMBER | LAG, ALIMOSHO | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-06-24 | 269 | 2024-06-24 | 0 | 2024-07-08 | 14 |  |  |  |  | 45481 | 2024-07-08 | 255 | 2024-07-11 | 225750 | Overdue
213 | ROLLER SHUTTER IN CHOP BOX OPEBI FAULTY | LAG, OPEBI | Others | Breakdown | Basscomm | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-06-27 | 266 | 2024-06-27 | 0 | 2024-07-09 | 12 | [9 empty] | Overdue
214 | FAULTY UNDER BAR CHILLER | BAYELSA, TOMBIA | Others | Breakdown | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-06-20 | 273 | 2024-06-20 | 0 | 2024-06-25 | 5 | [9 empty] | Overdue
215 | AIR CONDITIONING SERVICING | OYO, OWODE | Routine Servicing | Preventive | THIO AND PARTNERS | 5HP STANDING AC UNIT 1 | HVAC | 2024-06-26 | 267 | 2024-06-26 | 0 | 2024-07-11 | 15 | [9 empty] | Overdue
216 | FAULTY HENNY ROT MACHINE | BAYELSA, YENAGOA | Others | Breakdown | ECS | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-06-29 | 264 | 2024-06-29 | 0 | 2024-07-11 | 12 | [8 empty] | 268750 | Overdue
217 | GENERATOR DUE FOR SERVICE | LAG, IRE-AKARI | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-06-30 | 263 | 2024-06-30 | 0 |  | 263 | [9 empty] | Overdue
218 | FAULTY FLAME GRILLED OVEN | LAG, LATEEF JAKANDE | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-06-15 | 278 | 2024-06-17 | 2 | 2024-06-20 | 3 | [9 empty] | Overdue
219 | FAULTY UNDER BAR CHILLER | BAYELSA, TOMBIA | Others | Breakdown | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-06-20 | 273 | 2024-06-20 | 0 | 2024-06-25 | 5 | [9 empty] | Overdue
220 | RE-PAINTING MAINTENANC CR AZIKWE | ABIA, AZIKIWE RD, UMUAHIA | Others | Breakdown | JOWYN | PAINTING | BUILDING | 2024-06-11 | 282 | 2024-06-13 | 2 | 2024-07-03 | 20 | 2024-07-03 | 2024-07-03 | 0 | 2024-07-04 | 7 | 2024-07-11 | 252 |  | 640000 | Overdue
221 | COLLAPSED ENTRANCE COLD ROOM AND FREEZER ROOM DOOR | PH, DOX RD | Others | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-06-26 | 267 | 2024-06-26 | 0 |  | 267 | [9 empty] | Overdue
222 | PAINTING BOBBY CHAIRS AND TABLES | EBONYI, AFIKPO, ABAKALIKI | Others | Breakdown | PRO EQUIP | CUSTOMER TABLE | FURNITURE | 2024-06-13 | 280 | 2024-06-13 | 0 |  | 280 | [9 empty] | Overdue
223 | REPACEMENT OF CHILLER RACK | IBADAN, CHALLENGE | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-06-27 | 266 | 2024-06-27 | 0 |  | 266 | [9 empty] | Overdue
224 | ROT MACHINE NOT HEATING | ANAMBRA, ZIK AVENUE, AWKA | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-06-30 | 0 | 2024-06-30 | 0 | 2024-06-30 | 0 | [9 empty] | Completed | 2024-06-30 | 0
225 | BROKEN COUNTER TOP AND CHIPPED OFF TABLES EDGES | LAG, AWOLOWO | Others | Breakdown | FULL TURN | CUSTOMER TABLE | FURNITURE | 2024-06-21 | 272 | 2024-07-15 | 24 |  | 248 | [9 empty] | Overdue
226 | FAULTY FREEZER ROOM SELF LOCK AND GREASE TRAP | BAYELSA, YENAGOA | Others | Breakdown | MOFFEN | FREEZER ROOM | HVAC | 2024-06-27 | 266 | 2024-06-27 | 0 |  | 266 | [9 empty] | Overdue
227 | FAULTY LOBBY RAILINGS | LAG, DOMINO E-CENTRE | Others | Breakdown | FULL TURN | OTHERS | OTHERS | 2024-06-03 | 290 | 2024-06-04 | 1 | 2024-07-17 | 43 | 2024-07-29 | 2024-08-02 | 4 | 2024-08-02 | 230 |  |  |  | 730000 | Overdue
228 | BROKEN COUNTER TOP AND CHIPPED OFF TABLES EDGE | LAG, AWOLOWO | Others | Breakdown | FULL TURN | CUSTOMER TABLE | FURNITURE | 2024-06-21 | 272 | 2024-06-21 | 0 | 2024-06-22 | 1 | 2024-08-06 |  | 226 | [6 empty] | Overdue
229 | PAINTING OF COLDROOM AND FREEZER ROOM WALL | IBADAN, CHALLENGE | Others | Breakdown | Western Design | COLD ROOM UNIT | HVAC | 2024-06-09 | 284 | 2024-06-15 | 6 | 2024-07-16 | 31 | 2024-07-16 | 2024-07-17 | 1 | 2024-07-17 | 0 | 2024-07-17 | 246 |  |  | Overdue
230 | FAULTY UNDER BAR CHILLER HANDLE | ENUGU, POLO MALL | Others | Breakdown | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-06-25 | 268 | 2024-07-15 | 20 | 2024-08-09 | 25 | [9 empty] | Overdue
231 | REPAINTING OF UPRIGHT CHILLER | LAG, JOEL OGUNNAIKE | Others | Breakdown | Western Design | OTHERS | OTHERS | 2024-06-02 | 291 | 2024-06-03 | 1 | 2024-06-27 | 24 | 2024-06-27 | 2024-06-27 | 0 | 2024-06-24 | 35 | 2024-07-29 | 234 |  |  | Overdue
232 | BROKEN COUNTER TOP CHIPPED OFF TABLES EDGES | LAG, AWOLOWO | Others | Breakdown | FULL TURN | CASHIER COUNTER | BUILDING | 2024-06-21 | 272 | 2024-07-15 | 24 | 2024-08-06 | 22 | 2024-08-06 | 2024-08-20 | 14 | 2024-08-20 | 212 |  |  |  |  | Overdue
233 | FAULTY ROLLER SHUTTER | LAG, IPAJA RD | Others | Breakdown | Basscomm | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-06-06 | 287 | 2024-06-06 | 0 |  | 287 | [9 empty] | Overdue
234 | STIFNESS OF ENTRANCE DOOR | LAG, ALIMOSHO | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-06-21 | 17 | 2024-07-02 | 11 | 2024-07-06 | 4 | 2024-07-06 | 2024-07-06 | 0 | 2024-07-06 | 0 | 2024-07-06 | 2 |  |  | Completed | 2024-07-08 | 0
235 | DISPLAY CABINET OVER HEATING WITHOUT CONTROL | OGUN, OKE-ILEWO | Others | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-06-05 | 288 | 2024-06-06 | 1 |  | 287 | [9 empty] | Overdue
236 | FAULTY GENERATOR PPU RHAMAT |  | Routine Servicing | Preventive | PETOJO4STAR | INVERTER BATTERIES | INVERTER | 2024-06-11 | 282 | 2024-06-11 | 0 | 2024-06-11 | 0 | 2024-06-13 | 2024-06-20 | 7 | 2024-06-20 | 0 | 2024-06-20 | 273 |  | 180000 | Overdue
237 | FAULTY COLDROOM LOCK | LAG, LEKKI PHASE 1 | Others | Breakdown | TONA OGUNS | OTHERS | OTHERS | 2024-06-27 | 42 | 2024-06-27 | 0 | 2024-08-08 | 42 | 2024-08-08 | 2024-08-08 | 0 | 2024-08-08 | 0 | 2024-08-08 | 0 |  |  | Completed | 2024-08-08 | 0
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
Formulas:
Days Since Request = IF([Request Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Request Date],TODAY()-[Request Date]))
Days Delayed by Helpdesk = IF([Date Shared by Helpdesk]<>"",[Date Shared by Helpdesk]-[Request Date],IF([Request Date]="","",TODAY()-[Request Date]))
Days Delayed by Vendor/Technician = IF(M6<>"",M6-[Date Shared by Helpdesk],IF([Date Shared by Helpdesk]="","",TODAY()-[Date Shared by Helpdesk]))
Days Since Negotiation Request = TODAY() - [Date Negotiated]
Days Since Negotiation Request = IF([Date Negotiated]<>"",[Date Negotiated]-[Date Sent for Negotiation],IF([Date Sent for Negotiation]="","",TODAY()-[Date Sent for Negotiation]))
Days Since Approval Request = IF([Approved Date]<>"",[Approved Date]-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval = IF([Approved Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Approved Date],TODAY()-[Approved Date]))
Status = IF([Request Date]="","",IF([Actual delivery date]<>"","Completed",IF(TODAY()<[Expected Delivery Date],"Planned",IF(TODAY()=[Expected Delivery Date],"Due","Overdue"))))
Note on AA6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vendor gave feedback thaat part is not available on 18 of Jan

## JULY
Legend
Completed on time
Completed late
S/N | ACTION/TASK | Store | Reason for Breakdown | Maintenance Category | Responsible | Specific Equipment | Category | Request Date | Days Since Request | Date Shared by Helpdesk | Days Delayed by Helpdesk | Date Attended/Checked by Vendor/Technician | Days Delayed by Vendor/Technician | Date Sent for Negotiation | Date Negotiated | Days Since Negotiation Request | Date Approval Requested | Days Since Approval Request | Approved Date | Days Since Approval | Expected Delivery Date | Cost | Status | Actual delivery date | Compliance check | Insert Comment
1 | WATER HEATER LEAKING | LAG, OPEBI | Others | Breakdown | PROPERJEFF | WATER HEATER | PLUMBING | 2024-07-01 | 14 | 2024-07-01 | 0 |  | 262 |  |  | 45736 | [6 empty] | Completed | 2024-07-15 | 0
2 | EXTRACTOR NOT EFFECTIVE | LAG, MARINA | Routine Servicing | Preventive | ABBEY ELECTRICAL | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2024-07-01 | 262 | 2024-07-02 | 1 |  | 261 | [9 empty] | Overdue
3 | BLOCKD DRAINAGE | LAG, MARINA | Others | Breakdown | JOEL OMTOSHO | OTHERS | OTHERS | 2024-07-01 | 0 | 2024-07-03 | 2 |  | 260 | [9 empty] | Completed | 2024-07-01 | 0
4 | GENERATOR DUE FOR SERVICING | IBADAN, AKOBO | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-01 | 262 | 2024-07-04 | 3 |  | 259 | [9 empty] | Overdue
5 | CHANGE OVER SWITCH | LAG, IKOTUN | Corrective Action | Corrective | FRIDAY | OTHERS | OTHERS | 2024-07-01 | 262 | 2024-07-05 | 4 |  | 258 | [9 empty] | Overdue
6 | FAULTY FREEZER ROOM | EBONYI, WATERWORKS, ABAKALIKI | Others | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-07-01 | 262 | 2024-07-06 | 5 |  | 257 | [9 empty] | Overdue
7 | BROKEN SWING DOOR | LAG, OMOLE | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-01 | 262 | 2024-07-07 | 6 |  | 256 | [9 empty] | Overdue
8 | LEAKING PIPE IN LAB | LAG, ILUPEJU | Others | Breakdown | PROPERJEFF | OTHERS | OTHERS | 2024-07-01 | 9 | 2024-07-08 | 7 |  | 255 | [9 empty] | Completed | 2024-07-10 | 0
9 | SIGNAGE LIGHT | LAG, TOTAL LEKKI | Others | Breakdown | ACCENTRIX | OTHERS | OTHERS | 2024-07-01 | 262 | 2024-07-09 | 8 |  | 254 | [9 empty] | Overdue
10 | FAULTY ITEMS AT PPU ILUPEJU | LAG, ILUPEJU | Others | Breakdown | SEASON BENDAN,TONA OGUNS MATOLAD,PROPEARJEFF | OTHERS | OTHERS | 2024-07-01 | 262 | 2024-07-10 | 9 |  | 253 | [9 empty] | Overdue
12 | OPENED UP AC COMPRESSOR | LAG, LATEEF JAKANDE | Wear & Tear | Breakdown | TRIPPLE O | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-01 | 262 | 2024-07-11 | 10 |  | 252 | [7 empty] | 2024-07-16 |  | Overdue
13 | FAULTY DICING MACHINE | LAG, LATEEF JAKANDE | Others | Breakdown | BCE | DICING MACHINE | KITCHEN_EQUIPMENT | 2024-07-01 | 262 | 2024-07-12 | 11 |  | 251 | [9 empty] | Overdue
14 | BROKEN EXTRANCE GLASS | LAG, JIBOWU | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-07-01 | 262 | 2024-07-13 | 12 |  | 250 | [9 empty] | Overdue
15 | REQUEST FOR INSECTOCUTOR BULB | IBADAN, BODIJA | Others | Breakdown | RANEX4WARD | INSECT KILLER LOBBY 1 | ELECTRICAL | 2024-07-01 | 262 | 2024-07-14 | 13 |  | 249 | [9 empty] | Overdue
16 | REQUEST TO PAINT PX OGUDU | LAG, OGUDU | Others | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-07-05 | 258 | 2024-07-15 | 10 |  | 248 | [8 empty] | 90000 | Overdue
17 | SPOILT SOAP DISPENSER | LAG, OPEBI | Users Misuse | Breakdown | PROPERJEFF | OTHERS | OTHERS | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
18 | FAULTY COLD ROOM | LAG, OPEBI | Routine Servicing | Preventive | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-07-07 | 256 | 2024-07-07 | 0 |  | 256 |  |  |  |  | 45480 | 2024-07-07 | 256 | 2024-07-08 |  | Overdue
19 | FAULTY FRYER AND OTHER EQUIPMENT | ILORIN, MM WAY | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-07-07 | 256 | 2024-07-07 | 0 |  | 256 | [9 empty] | Overdue
20 | SIGNAGE FOR IBAFO | OGUN, HEYDEN IBAFO | Others | Breakdown | ARISMAYA | OTHERS | OTHERS | 2024-07-08 | 255 | 2024-07-08 | 0 |  | 255 | [9 empty] | Overdue
21 | CHOP BOX SIGNAGE | LAG, AGUNGI | Others | Breakdown | ARISMAYA | OTHERS | OTHERS | 2024-07-08 | 255 | 2024-07-08 | 0 | 2024-07-08 | 0 | 2024-07-09 | 2024-07-11 | 2 | 2024-07-11 | 0 | 2024-07-11 | 252 |  |  | Overdue
22 | FAULTY MC ADAMS 4 HEAD PRESSURE FRYER LID GASKET | IBADAN, OJOO | Corrective Action | Corrective | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-08 | 255 | 2024-07-08 | 0 |  | 255 | [9 empty] | Overdue
23 | FAULTY CUSTOMERS RESTROOM | LAG, MARINA | Others | Breakdown | PROPERJEFF | OTHERS | OTHERS | 2024-07-09 | 254 | 2024-07-09 | 0 |  | 254 | [9 empty] | Overdue
24 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | LAG, OMOLE | Others | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-01 | 262 | 2024-07-01 | 0 |  | 262 | [9 empty] | Overdue
25 | REQUEST FOR AC SERVICING | AKWA IBOM, ABAK RD | Routine Servicing | Preventive | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
26 | AJOSE INVERTER NOT CHARGING | LAG, AJOSE ADEOGUN | Others | Breakdown | DALMATRIX | INVERTER SYSTEM | INVERTER | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
28 | DAILY EQUIPMENT STATUS | PPU Ajah | Others | Breakdown | TONA OGUNS | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
29 | GENERATOR SERVICING REQUEST | ABIA, ABA-OWERRI RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
30 | FAULTY FREEZER ROOM | LAG, MARINA | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
31 | OPEN CEILING IN MANAGER OFFICE | LAG, VGC | Others | Breakdown | FULLTURN | ROOF | BUILDING | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
32 | WATER HEATER NOT WORKING | LAG, JOEL OGUNNAIKE | Others | Breakdown | PROPEARJEFF | WATER HEATER | PLUMBING | 2024-07-07 | 256 | 2024-07-02 | -5 |  | 261 | [9 empty] | Overdue
33 | FAULTY TOASTING MACHINE | LAG, AGUNGI | Others | Breakdown | KITCHTECH | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
34 | GENERATOR SERVICING | EDO, SILUKO | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
35 | FAULTY INVERTER | PH, WOJI | Others | Breakdown | DESAMTECH | INVERTER SYSTEM | INVERTER | 2024-07-01 | 262 | 2024-07-02 | 1 |  | 261 | [9 empty] | Overdue
36 | FREEZER ROOM DOOR HANDLE | IBADAN, OJOO | Others | Breakdown | BCE | FREEZER ROOM | HVAC | 2024-07-01 | 262 | 2024-07-02 | 1 |  | 261 | [9 empty] | Overdue
37 | EXTRACTOR BULB | LAG, OMOLE | Others | Breakdown | TIMILEYIN | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2024-07-01 | 1 | 2024-07-02 | 1 |  | 261 | [9 empty] | Completed | 2024-07-02 | 0
38 | WATER TREATMENT BY PASS | PH, RUKPOKWU | Others | Breakdown | PRO EQUIP | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-01 | 262 | 2024-07-02 | 1 |  | 261 |  | 2024-07-05 | 45478 | [5 empty] | 1620000 | Overdue
39 | WATER NOT RUNNING IN STORE | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | TOISN OLATUNDE | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-02 | 2 | 2024-07-02 | 0 |  | 261 | [9 empty] | Completed | 2024-07-04 | 0
40 | COLD ROOM SELF LOCK | DELTA, OKPE RD | Others | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
41 | HOLE IN DRY STORE | LAG, ENTOURAGE MALL | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
42 | SUPLY OF CABINET BULBS | LAG, AWOLOWO 2 | Others | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
43 | FAULTY INSECT KILLER | LAG, MOBIL OGBA | Others | Breakdown | MOSES OLABIWONU | OTHERS | OTHERS | 2024-07-02 | 1 | 2024-07-02 | 0 |  | 261 | [9 empty] | Completed | 2024-07-03 | 0
44 | SIGNAGE LIGHT | LAG, TOTAL LEKKI | Others | Breakdown | ACCENTRIX | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-02 | 0 | 2024-07-06 | 4 | [9 empty] | Overdue
45 | BEND BOLLARD POLE/ REPAINTING | LAG, JOEL OGUNNAIKE | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-07-02 | 41 | 2024-07-02 | 0 | 2024-07-05 | 3 | 2024-07-10 | 2024-07-10 | 0 | 2024-07-10 | 0 | 2024-07-10 | 33 |  |  | Completed | 2024-08-12 | 0
46 | COLD ROOM NOT ATTAINNG TEMPERATURE | LAG, OKOTA | Others | Breakdown | THIO AND PARTNER | COLD ROOM UNIT | HVAC | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
47 | COLD ROOM NOT ATTAINNG TEMPERATURE | LAG, AJAH | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
48 | FAULTY FRONT GLASS | LAG, FESTAC | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-07-02 | 2 | 2024-07-02 | 0 |  | 261 | [9 empty] | Completed | 2024-07-04 | 0
49 | WATER HEATER NOT WORKING | LAG, OKOTA | Others | Breakdown | PRO EQUIP | WATER HEATER | PLUMBING | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
50 | FEMALE CHANGE ROOM DRAINAGE | LAG, OGUNLANA DRIVE | Others | Breakdown | 2024-07-02 | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
51 | MAINTENANCE ISSUES TO BE CLOSED | IBADAN, IDI-APE (IWO RD) | Others | Breakdown | OPEYEMI ABIDOYE | OTHERS | OTHERS | 2024-07-02 | 0 | 2024-07-02 | 0 |  | 261 | [9 empty] | Completed | 2024-07-02 | 0
52 | FEMALE CHANGE ROOM LOCKER | LAG, OGUNLANA DRIVE | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
53 | BOH CHEST CHILLER NOT ATTAINING TEMP | LAG, AJAH | Others | Breakdown | BCE | CHEST FREEZER | HVAC | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
54 | GENERATOR DUE FOR SERVICING | LAG, LATEEF JAKANDE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
55 | INSTALLATION OF FREEZER ROOM CURTAIN | EDO, UGBOWO, BENIN | Others | Breakdown | MOFEEN | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-02 | 0 | 2024-08-14 | 43 | 2024-08-14 | 2024-08-14 | 0 | [5 empty] | 190000 | Overdue
56 | INSTALLATION OF FREEZER ROOM CURTAIN | EDO, AIRPORT RD, BENIN | Others | Breakdown | MOFEEN | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
57 | INSTALLATION OF FREEZER ROOM CURTAIN | EDO, SILUKO | Others | Breakdown | MOFEEN | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
58 | INSTALLATION OF FREEZER ROOM CURTAIN | DELTA, OKPE RD | Others | Breakdown | MOFEEN | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
59 | INSTALLATION OF FREEZER ROOM CURTAIN | DELTA, EFFURUN | Others | Breakdown | MOFEEN | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
60 | INSTALLATION OF FREEZER ROOM CURTAIN | EDO, SAPELE RD, BENIN | Others | Breakdown | MOFEEN | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
61 | INSTALLATION OF FREEZER ROOM CURTAIN | EDO, RAHMAT PARK, BENIN | Others | Breakdown | MOFEEN | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
62 | GENERATOR NOT STARTING | ABIA, ABA-OWERRI RD | Routine Servicing | Preventive | INNOCENT | GENERATOR | GENERATOR | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
63 | BLOCKED STAFF ROOM DRAINAGE | LAG, OPEBI | Others | Breakdown | ADEREMI | OTHERS | OTHERS | 2024-07-02 | -117 | 2024-07-02 | 0 |  | 261 | [9 empty] | Completed | 2024-03-07 | 0
64 | WATER DRIPPING FROM THE ROOF | LAG, ALIMOSHO | Others | Breakdown | PENTECOSTAL | ROOF | BUILDING | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
65 | GENERATOR DUE FOR SERVICING | LAG, LEKKI PHASE 1 | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
66 | FAULTY COLD ROOM DOOR | LAG, AWOLOWO 2 | Others | Breakdown | OTHER | COLD ROOM UNIT | HVAC | 2024-07-02 | 261 | 2024-07-03 | 1 |  | 260 | [9 empty] | Overdue
67 | FAULTY INSECTOCUTOR | LAG, JOEL OGUNNAIKE | Others | Breakdown | TIMILEYIN | INSECT KILLER BOH | ELECTRICAL | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
68 | LEAKING WATER TANK | LAG, OGUDU | Others | Breakdown | MATOLAD | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
69 | OPEN ROOF IN DRY STORE | LAG, OGUDU | Others | Breakdown | PROPEARJEFF | ROOF | BUILDING | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
70 | MALE STAFF ROOM AIR VENT | LAG, IDIMU | Others | Breakdown | ABBEY ELECTRICAL | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
71 | GENERATOR SERVICING | LAG, BADORE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
72 | REQUEST FOR COLLETROMACTIC GASKET | ENUGU, CHIME AVENUE | Others | Breakdown | BCE | COLLECTRAMATIC OIL PUMP MACHINE | KITCHEN_EQUIPMENT | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
73 | FAULTY SEWAGE | PH, IWOFE | Others | Breakdown | JOWYN | SEPTIC TANK | EVACUATION | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
74 | HEAVY RAIN DROPPING IN STORE | LAG, DIYA STREET | Others | Breakdown | VENYS | ROOF | BUILDING | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 |  | 2024-07-05 | 45478 | [5 empty] | 195000 | Overdue
75 | STORE CEILING DROPPING WATER | LAG, MAGODO | Others | Breakdown | ACORN | ROOF | BUILDING | 2024-07-03 | 260 | 2024-07-03 | 0 | 2024-07-08 | 5 | 2024-07-09 |  | 254 | [6 empty] | Overdue
76 | FILLED SEPTIC TANK | LAG, IDI-IROKO RD | Others | Breakdown | MOOLIGHT | SEPTIC TANK | EVACUATION | 2024-07-02 | 261 | 2024-07-03 | 1 |  | 260 | [9 empty] | Overdue
77 | REQUEST FOR REPLACE OF BAD MOBILE WARMER | ANAMBRA, LIMCA RD, ONITSHA | Electrical Surge | Breakdown | BCE | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-03 | 1 |  | 260 | [9 empty] | Overdue
78 | GENERATOR DUE FOR SERVICING | PPU Tombia | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-07-02 | 2 | 2024-07-03 | 1 |  | 260 | [9 empty] | Completed | 2024-07-04 | 0
79 | WORN OUT CHILLER GASKET | LAG, FREEDOMWAY | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-03 | 1 |  | 260 | [9 empty] | Overdue
80 | LOBBY TV NOT DISPLAYING | LAG, AJAH | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-03 | 1 | 2024-07-06 | 3 |  | 2024-07-06 | 45479 | 2024-07-06 | 257 |  |  |  |  | Overdue
81 | ISSUES IN PX UGBOWO | EDO, UGBOWO, BENIN | Others | Breakdown |  |  |  | 2024-07-02 | 261 | 2024-07-03 | 1 |  | 260 | [9 empty] | Overdue
82 | OPEN CEILING IN DRY STORE | LAG, OPEBI | Others | Breakdown | MATOLAD | ROOF | BUILDING | 2024-07-02 | 261 | 2024-07-03 | 1 |  | 260 | [9 empty] | Overdue
83 | CHIPS FRYER LEAKING | LAG, FATGBEMS | Others | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
84 | LEAKAGE UNDER SINK AND FAULTY MALE TOILET | LAG, FESTAC | Others | Breakdown | OLATUNDE TOSIN | KITCHEN WASH HAND SINK | PLUMBING | 2024-07-02 | 2 | 2024-07-03 | 1 |  | 260 | [9 empty] | Completed | 2024-07-04 | 0
85 | FAULTY GAS VALVE | LAG, JIBOWU | Others | Breakdown | OLATUNDE TOSIN | GAS HOSE & SUNDRIES | GAS | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
86 | FAULTY TOASTER MACHINE | LAG, AKOWONJO | Others | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
87 | GENERATOR SERVICING | OYO, OWODE | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-07-03 | 260 | 2024-07-03 | 0 | 2024-07-05 | 2 | 2024-07-05 | 2024-07-05 | 0 | 2024-07-06 | 0 | 2024-07-06 | 257 | 2024-07-07 | 293851.25 | Overdue
88 | LEAKING ROOF IN STORE | LAG, OGUDU | Others | Breakdown |  | ROOF | BUILDING | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
89 | COLD ROOM FREEZING | LAG, AGUNGI | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-07-03 | 260 | 2024-07-03 | 0 | 2024-07-04 | 1 | [9 empty] | Overdue
90 | FAULTY TOILET FLUSHER | LAG, OGUDU | Others | Breakdown | ADEREMI WAHAB | OTHERS | OTHERS | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
91 | FAULTY LOW CABINET | PH, IWOFE | Electrical Surge | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
92 | FAULTY STORE AC | LAG, GBAGADA | Routine Servicing | Preventive | THIO AND PARTNER | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
93 | COLD ROOM NOT ATTAINNG TEMPERATURE | LAG, GBAGADA | Others | Breakdown | THIO AND PARTNER | COLD ROOM UNIT | HVAC | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
94 | DRY STORE AC NOT ATTAINING TEMP | PH, RUKPOKWU | Others | Breakdown | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
95 | FALLING WOODEN STRUCTURE | LAG, AJAH | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-03 | 260 | 2024-07-03 | 0 | 2024-07-05 | 2 | 2024-07-05 | 2024-07-05 | 0 | [5 empty] | 240000 | Overdue
96 | EVACUATION OF DISEL FROM BASE TANK | LAG, ILUPEJU | Others | Breakdown | DAMI FOTE | GENERATOR | GENERATOR | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
97 | CHIPS FRYER MACHINE NOT COMING UP | ENUGU, CHIME AVENUE | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
98 | FAULTY FRONT GLASS DOOR | LAG, FESTAC | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-07-02 | 2 | 2024-07-02 | 0 |  | 261 | [9 empty] | Completed | 2024-07-04 | 0
99 | AC LEAKAGE | LAG, OBA AKRAN | Others | Breakdown | G.B BOYEJO | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
100 | FREEZER ROOM NOT ATTAINING TEMP | DELTA, SAPELE-WARRI RD | Others | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
101 | OPEN WINDOW NET | LAG, OPEBI | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-03 | 1 |  | 260 | [9 empty] | Overdue
102 | ISAWO MAINTENACE TRACKER | LAG, ISAWO-IKORODU | Others | Breakdown | BAMOCOON | OTHERS | OTHERS | 2024-07-03 | 260 | 2024-07-03 | 0 |  | 260 | [9 empty] | Overdue
103 | NEED FOR STANDBY PUMPING MACHINE | LAG, GBAGADA | Others | Breakdown | PRO EQUIP | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-03 | 260 | 2024-07-04 | 1 |  | 259 | [9 empty] | Overdue
104 | FAULTY FRYER MACHINE | LAG, ETERNA LEKKI | Others | Breakdown | KITCHTECH | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
105 | CABINET NOT HEATING UP | PH, IWOFE | Electrical Surge | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
106 | FAULTY LOBBY TV | LAG, LEKKI PHASE 1 | Electrical Surge | Breakdown | ACORN | OTHERS | OTHERS | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [8 empty] | 396825 | Overdue
107 | GENERATOR DUE FOR SERVICING | LAG, TOTAL LEKKI | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-04 | 259 | 2024-07-04 | 0 | 2024-07-04 | 0 | [9 empty] | Overdue
108 | STORE ROLLER SHUTTER KEY FAULTY | LAG, JOEL OGUNNAIKE | Others | Breakdown | VENYS | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
109 | DEAD BULB IN THE LOBBY | LAG, JOEL OGUNNAIKE | Electrical Surge | Breakdown | MOSES OLABIWONU | OTHERS | OTHERS | 2024-07-04 | 0 | 2024-07-04 | 0 |  | 259 | [9 empty] | Completed | 2024-07-04 | 0
110 | FAULTY SOUND SYSTEM | LAG, DIYA STREET | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
111 | REPAINTING OF TABLES | LAG, FESTAC | Others | Breakdown | MATOLAD | PAINTING | BUILDING | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
112 | BOREHOLE WITHOUT WATER | LAG, AWOLOWO | Others | Breakdown | JOEL OMTOSHO | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
113 | BROKEN SWING DOOR | LAG, OMOLE | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-01 | 262 | 2024-07-01 | 0 |  | 262 | [9 empty] | Overdue
114 | GENERATOR ENGINE OIL | LAG, OGUNLANA DRIVE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-03 | 260 | 2024-07-04 | 1 |  | 259 | [9 empty] | Overdue
115 | GENERATOR DUE FOR SERVICING | LAG, TOTAL LEKKI | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
116 | CHIPS FRYER NOT WORKING | LAG, OGUNLANA DRIVE | Others | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
117 | SEPTIC TANK EVACUATION | LAG, ETERNA LEKKI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
118 | ELECTRIC SHOCK FROM BOHEQUIPMENT AND TABLE | LAG, IPAJA RD | Electrical Surge | Breakdown | DYNAMITE | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
119 | BROKEN BRICKS AT CAR PARK | LAG, BADORE | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
120 | BROKEN DOOR HANDLE | LAG, BADORE | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-03 | 260 | 2024-07-04 | 1 |  | 259 |  | 2024-07-05 | 45478 |  | 45480 | 2024-07-07 | 256 | 2024-07-08 | 67403.5 | Overdue
121 | GENERATOR SERVICING | IBADAN, BODIJA | Routine Servicing | Preventive | SYMINERTIAS | GENERATOR | GENERATOR | 2024-07-03 | 260 | 2024-07-04 | 1 |  | 259 | [9 empty] | Overdue
122 | BROKEN SLAP AT CAR PARK | LAG, EKORO | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-07-03 | 260 | 2024-07-04 | 1 |  | 259 | [9 empty] | Overdue
123 | GENERATOR SERVICING REQUEST | ANAMBRA, AWKA RD, ONITSHA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
124 | EXTRACTOR NOT WORKING PERFECTLY | LAG, TOTAL LEKKI | Others | Breakdown | SEASON BENDAN | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2024-07-03 | 260 | 2024-07-04 | 1 |  | 259 | [9 empty] | Overdue
125 | LOBBY CEILING LEAK | LAG, ABULE EGBA | Others | Breakdown | PENTECOSTAL | ROOF | BUILDING | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
126 | GENERATOR DUE FOR SERVICING | LAG, VGC | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 |  | 2024-07-05 | 45478 | 2024-07-06 | 257 |  |  |  | 213763.75 | Overdue
127 | TILTING PAN BREAK DOWN PPU ORON | AKWA IBOM, ORON RD | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
128 | REQUEST FOR AC SERVICING | AKWA IBOM, ABAK RD | Routine Servicing | Preventive | MOFFEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-02 | 261 | 2024-07-02 | 0 |  | 261 | [9 empty] | Overdue
129 | SPOILT SOAP DISPENSER | PPU Opebi | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
130 | HOS REPLCEMENT AND DISEL EVACUATION | LAG, VGC | Others | Breakdown | DAMI FOTE | GAS HOSE & SUNDRIES | GAS | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
131 | LOW VOLTAGE LECTRICAL SUPPLY | LAG, LATEEF JAKANDE | Electrical Surge | Breakdown | GBATMO | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-07-04 | 0 | 2024-07-04 | 0 |  | 259 | [9 empty] | Completed | 2024-07-04 | 0
132 | WATER NOT FLOWING INSIDE THE STORE | LAG, JOEL OGUNNAIKE | Others | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-04 | 0 | 2024-07-04 | 0 |  | 259 | [9 empty] | Completed | 2024-07-04 | 0
133 | FAULTY GENERATOR | PH, RUMUBIAKANI | Wear & Tear | Breakdown | PAGISEL | GENERATOR | GENERATOR | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
134 | BROKEN CABINET | LAG, AJAH | Electrical Surge | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
135 | DISPLAY CABINET SHOCKING | BAYELSA, OPOLO | Electrical Surge | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-04 | 0 | 2024-07-04 | 0 |  | 259 | [9 empty] | Completed | 2024-07-04 | 0
136 | DISPLAY CABINET DOOR FAULTY AND NOT WORKING PROPERLY | LAG, AJAH | Others | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
137 | STORE ROLLER SHUTTER | LAG, JOEL OGUNNAIKE | Others | Breakdown | VENYS | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
138 | CK CANTEEN AC | LAG, ILUPEJU | Routine Servicing | Preventive | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-04 | 259 | 2024-07-04 | 0 | 2024-07-05 | 1 | 2024-07-05 | 2024-07-05 | 0 | 2024-07-06 | 0 | 2024-07-06 | 257 | 2024-07-07 | 215000 | Overdue
139 | UNDERBAR CHILLER NOT WORKING | ANAMBRA, AWKA RD, ONITSHA | Others | Breakdown | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
140 | SEPTIC TANK EVACUATION | LAG, BODE THOMAS | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
141 | GENERATOR SERVICING | ABUJA, UTAKO | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 |  | 2024-07-05 | 45478 |  | 45478 | 2024-07-05 | 258 | 2024-07-06 | 198875 | Overdue
142 | PX AKOWONJO FAULTY CABINET | LAG, AKOWONJO | Electrical Surge | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-05 | 1 | 2024-07-05 | 0 |  | 258 | [9 empty] | Completed | 2024-07-06 | 0
143 | GENERATOR BELT | LAG, BADORE | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 |  |  |  |  | 45478 | 2024-07-05 | 258 |  |  | Overdue
144 | INVERTER NOT BACKING UP | LAG, LEKKI PHASE 1 | Electrical Surge | Breakdown | DALAMATRIX | INVERTER SYSTEM | INVERTER | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
145 | STORE AC REPAIRS | IBADAN, CHALLENGE | Routine Servicing | Preventive | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
146 | OGBOR HILL GEN SERVICING | ABIA, OGBOR HILLS | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-07-05 | 258 | 2024-07-05 | 0 | 2024-07-05 | 0 | 2024-07-05 | 2024-07-05 | 0 | 2024-07-05 | 0 | 2024-07-05 | 258 | 2025-07-06 | 204250 | Planned
147 | FREEZER ROOM AND COLD ROOM RUBBER CURTAIN | IBADAN, OJOO | Others | Breakdown | BCE | FREEZER ROOM | HVAC | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
148 | GENERATOR NOT POWERING EQUIPMENT | LAG, IDIMU | Others | Breakdown | MID TECH | GENERATOR | GENERATOR | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
149 | GENERATOR DUE FOR SERVICING | LAG, OMOLE | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
150 | OFFICE AC DRIPPING WATER | LAG, IDI-IROKO RD | Others | Breakdown | G.B BOYEJO | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
151 | FAULTY WARMER | LAG, OGUDU | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
152 | CAR PARK | EDO, UGBOWO, BENIN | Others | Breakdown | DEACONESS | OTHERS | OTHERS | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
153 | GENERATOR SERVICING | LAG, OSOLOWAY | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
154 | FAULTY INVERTER | PH, WOJI | Others | Breakdown | DE SAM | INVERTER SYSTEM | INVERTER | 2024-07-01 | 262 | 2024-07-01 | 0 | 2024-07-05 | 4 | 2024-07-05 | 2024-07-05 | 0 | 2024-07-05 | 0 | 2024-07-05 | 258 | 2024-07-06 | 75000 | Overdue
155 | LEAKING IN THE LAB | LAG, ILUPEJU | Others | Breakdown | PROPERJEFF | KITCHEN WASH HAND SINK | PLUMBING | 2024-07-01 | 262 | 2024-07-01 | 0 |  | 262 | [9 empty] | Overdue
156 | BROKEN PIPES AND TILES | LAG, IKORODU | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
157 | REQUEST FOR GENERATOR SERVICING | ENUGU, NSUKKA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
158 | GENERATOR SERVICING | LAG, OBA AKRAN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
159 | REQUEST FOR SECURITY LIGHT | EDO, UGBOWO, BENIN | Others | Breakdown | FRANK OGHOGO | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
160 | FAULTY STREET LIGHT | LAG, IPAJA RD | Others | Breakdown |  | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
161 | FREEZER ROOM NOT ATTAINING TEMP | LAG, AGUNGI | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
162 | DAMAGED TAP | LAG, ABULE EGBA | Others | Breakdown | PROPEARJEFF | TAP | PLUMBING | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
163 | FAULTY FEMALE STAFF RESTROOM DOOR | LAG, ONIRU | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
164 | DAMAGED ROLLER SHUTTER | LAG, HEYDEN ALAPERE | Others | Breakdown | BASSCOOM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-07-08 | 255 | 2024-07-08 | 0 | 2024-07-12 | 4 | 2024-07-23 | 2024-07-23 | 0 | 2024-07-23 | 240 |  |  |  | 4107341.05 | Overdue
165 | INVERTER NOT WORKING | LAG, OGUNLANA DRIVE | Others | Breakdown | DALAMATRIX | INVERTER SYSTEM | INVERTER | 2024-07-19 | 244 | 2024-07-19 | 0 | 2024-07-20 | 1 | [7 empty] | 2024-07-29 |  | Overdue
166 | SOAK AWAY PIT | LAG, BODE THOMAS | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-07-18 | 245 | 2024-07-19 | 1 |  | 244 | [9 empty] | Overdue
167 | LEAKING CUSTOMRS RESTROOM AC | LAG, BODE THOMAS | Others | Breakdown | G.B BOYEJO | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
168 | LOBBY AC NOT ATTAINING TEMPEARTURE | LAG, OMOLE | Others | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
169 | BROKEN PPR PIPE AT THE FRYER SECTION | LAG, IKEJA MALL | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
170 | SEPTIC TANK EVACUATION | LAG, AWOLOWO 2 | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-07-05 | 2 | 2024-07-05 | 0 |  | 258 | [9 empty] | Completed | 2024-07-07 | 0
171 | GENERATOR SERVICING | LAG, OSOLOWAY | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
172 | FAULTY CHIPS DUMP | ABIA, AZIKIWE RD, UMUAHIA | Others | Breakdown | BCE | CHIPS DUMP | KITCHEN_EQUIPMENT | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
173 | FAULTY BAKING OVEN | OYO, OWODE | Others | Breakdown | ECS | OTHERS | OTHERS | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
174 | FAULTY ROT MACHINE | LAG, OKOTA | Others | Breakdown | HEFHEM | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
175 | BREAD TOSTER CALIBRATION | LAG, OGUNLANA DRIVE | Others | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
176 | FAULTY HEAD DRYER | LAG, OMOLE | Others | Breakdown | PROPEARJEFF | HAND DRYER LOBBY | ELECTRICAL | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
177 | FAULTY SOAP DISPENSER | LAG, OMOLE | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
178 | GENERATOR DUE FOR SERVICING | LAG, OGUDU | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
179 | REINSTALLATION OF 1.5 HP AC | LAG, TEJUOSHO | Others | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 2 | HVAC | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
180 | FAULTY TOASTER MACHINE | LAG, JIBOWU | Others | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2024-07-05 | 258 | 2024-07-05 | 0 |  | 258 | [9 empty] | Overdue
181 | COLD ROOM NOT WORKING | LAG, ABULE EGBA | Others | Breakdown | DYNAMITE | COLD ROOM UNIT | HVAC | 2024-07-06 | 257 | 2024-07-06 | 0 |  | 257 | [9 empty] | Overdue
182 | FAULTY GENERATOR | PH AGGREY | Others | Breakdown | PAGISEL | GENERATOR | GENERATOR | 2024-07-06 | 257 | 2024-07-06 | 0 |  | 257 |  |  |  |  | 45479 | 2024-07-06 | 257 |  |  | Overdue
183 | GENERATOR DUE FOR SERVICING | ILORIN, MM WAY | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-06 | 257 | 2024-07-06 | 0 |  | 257 | [9 empty] | Overdue
184 | COLDROOM NOT WORKING AT PPU ILORIN | ILORIN, MM WAY | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-07-06 | 257 | 2024-07-06 | 0 | 2024-07-07 | 1 | 2024-07-07 | 2024-07-07 | 0 | 2024-07-07 | 0 | 2024-07-07 | 256 |  | 155000 | Overdue
185 | BLOCKD DRAINAGE CHAMBER | LAG, MOBIL OGBA | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-07-06 | 257 | 2024-07-06 | 0 | 2024-07-07 | 1 | 2024-07-07 | 2024-07-08 | 1 | 2024-07-08 | 255 |  |  |  |  | Overdue
186 | FAULTY PUMP SWITCH | LAG, IRE-AKARI | Others | Breakdown | PRO EQUIP | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-06 | 257 | 2024-07-07 | 1 |  | 256 | [9 empty] | Overdue
187 | FAULTY COLD ROOM DOOR AND SELF LOCK | LAG, JOEL OGUNNAIKE | Others | Breakdown | THIO AND PARTNER | COLD ROOM UNIT | HVAC | 2024-07-06 | 257 | 2024-07-07 | 1 |  | 256 | [9 empty] | Overdue
188 | FAULTY CHIPS FRYER | PH, RUKPOKWU | Others | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-06 | 257 | 2024-07-07 | 1 |  | 256 | [9 empty] | Overdue
189 | FAULTY RESTROOM | LAG, ISAWO-IKORODU | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-06 | 257 | 2024-07-07 | 1 |  | 256 | [9 empty] | Overdue
190 | COLD ROOM NOT ATTAINING STANDARD TEMP | LAG, IKORODU | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-07-06 | 257 | 2024-07-07 | 1 |  | 256 | [9 empty] | Overdue
191 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | EDO, SAKPOMBA | Others | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-06 | 257 | 2024-07-07 | 1 |  | 256 | [9 empty] | Overdue
192 | GENERATOR DUE FOR SERVICING | IBADAN, IDI-APE (IWO RD) | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-06 | 257 | 2024-07-06 | 0 |  | 257 | [9 empty] | Overdue
193 | GENERATOR START UP DELAY | IMO, IKENEGBU, OWERRI | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-06 | 257 | 2024-07-07 | 1 |  | 256 | [9 empty] | Overdue
194 | BURNT TOASTER | LAG, JIBOWU | Electrical Surge | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2024-07-06 | 1 | 2024-07-07 | 1 |  | 256 | [9 empty] | Completed | 2024-07-07 | 0
195 | DEPRESSED CAR PARK | DELTA, ISOKO RD | Others | Breakdown | DT CONSULT | OTHERS | OTHERS | 2024-07-06 | 257 | 2024-07-07 | 1 |  | 256 | [9 empty] | Overdue
196 | SERVICING OF GENERATOR | LAG, OKE-AFA | Routine Servicing | Preventive | MID TECH | OTHERS | OTHERS | 2024-07-06 | 257 | 2024-07-07 | 1 |  | 256 | [9 empty] | Overdue
197 | FAULTY BOH CHEST FREEZER | LAG, MARINA | Others | Breakdown | G.B BOYEJO | CHEST FREEZER | HVAC | 2024-07-06 | 257 | 2024-07-07 | 1 |  | 256 | [9 empty] | Overdue
198 | PX ILUPEJU | LAG, ILUPEJU | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-06 | 257 | 2024-07-07 | 1 | 2024-07-22 | 15 | 2024-07-24 |  | 239 | [6 empty] | Overdue
199 | PX EJIGBO INSECTOCUTOR | LAG, EJIGBO | Electrical Surge | Breakdown | PROPEARJEFF | INSECT KILLER LOBBY 1 | ELECTRICAL | 2024-07-06 | 257 | 2024-07-07 | 1 |  | 256 | [9 empty] | Overdue
200 | PRESSURE FRYER NOT ATTAINING TEMP | ENUGU, POLO MALL | Others | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-06 | 257 | 2024-07-07 | 1 |  | 256 | [9 empty] | Overdue
201 | SEWAGE EVACUATION | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-07-06 | 257 | 2024-07-07 | 1 |  | 256 | [9 empty] | Overdue
202 | STAFF ROOM LOCKERS | LAG, JOEL OGUNNAIKE | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-07 | 256 | 2024-07-07 | 0 |  | 256 | [9 empty] | Overdue
203 | APAPA FAULTY CABINET PX APAPA | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-07 | 256 | 2024-07-07 | 0 |  | 256 | [9 empty] | Overdue
204 | GENERATOR DUE FOR SERVICING | LAG, AWOLOWO 2 | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-07 | 256 | 2024-07-07 | 0 |  | 256 | [9 empty] | Overdue
205 | REQUEST FOR GENERATOR SERVICING | ENUGU, CHIME AVENUE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-07 | 256 | 2024-07-07 | 0 |  | 256 | [9 empty] | Overdue
206 | GENERATOR BREAKDOWN | PH, IWOFE | Others | Breakdown | PAGISEL | GENERATOR | GENERATOR | 2024-07-07 | 256 | 2024-07-07 | 0 |  | 256 | [9 empty] | Overdue
207 | FAULTY COLDROOM | PPU Opebi | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-07-07 | 256 | 2024-07-07 | 0 |  | 256 | [9 empty] | Overdue
208 | FAULTY FREEZER ROOM | PPU Ilupeju | Others | Breakdown | BCE | FREEZER ROOM | HVAC | 2024-07-07 | 256 | 2024-07-07 | 0 |  | 256 | [9 empty] | Overdue
209 | GENERATOR DUE FOR SERVICING | IBADAN, MOKOLA | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-07 | 256 | 2024-07-07 | 0 |  | 256 | [9 empty] | Overdue
210 | FAULTY HENNY PENNY PRESSURE FRYER | LAG, AKOWONJO | Others | Breakdown | HEFHEM | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-07 | 1 | 2024-07-07 | 0 |  | 256 | [9 empty] | Completed | 2024-07-08 | 0
211 | DAMAGED FREEZER ROOM ENTRANCE | LAG, FREEDOMWAY | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-07-08 | 255 | 2024-07-08 | 0 |  | 255 | [9 empty] | Overdue
212 | GENERATOR ISSUES | PH, RUMUOLA | Others | Breakdown | PAGISEL | GENERATOR | GENERATOR | 2024-07-08 | 1 | 2024-07-08 | 0 |  | 255 | [9 empty] | Completed | 2024-07-09 | 0
213 | FREEZER ROOM NOT WORKING | LAG, FREEDOMWAY | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-07-09 | 1 | 2024-07-09 | 0 | 2024-07-10 | 1 | [7 empty] | 2024-07-10 |  | Completed | 2024-07-10 | 1
214 | FAULTY FREEZER ROOM | LAG, SKYMALL | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-07-09 | 254 | 2024-07-09 | 0 |  | 254 | [9 empty] | Overdue
215 | PEELING SHELF PX VGC | LAG, VGC | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-09 | 254 | 2024-07-09 | 0 | 2024-07-09 | 0 | 2024-07-09 | 2024-07-09 | 0 | [5 empty] | 240000 | Overdue
216 | INVERTER NOT COMING UP | LAG, MOBIL OGBA | Others | Breakdown | DALAMATRIX | INVERTER SYSTEM | INVERTER | 2024-07-09 | 254 | 2024-07-09 | 0 | 2024-07-09 | 0 | 2024-07-09 | 2024-07-09 | 0 | 2024-07-09 | 254 |  |  |  |  | Overdue
217 | PENDING ISSUES AT PPU OPEBI | PPU Opebi | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-05 | 258 | 2024-07-05 | 0 | 2024-07-29 | 24 | 2024-07-29 | 2024-07-30 | 1 | [5 empty] | 600000 | Overdue
218 | LEAKING PIPE IN THE LABORATORY | LAG, ILUPEJU | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-01 | 262 | 2024-07-01 | 0 |  | 262 | [9 empty] | Overdue
219 | WATER NOT ENTERING THE STORE | LAG, HEYDEN ALAPERE | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-09 | 254 | 2024-07-09 | 0 |  | 254 | [9 empty] | Overdue
220 | LOW VOLTAGE FROM NEPA SUPPLY | LAG, IRE-AKARI | Others | Breakdown | GBATMO | OTHERS | OTHERS | 2024-07-09 | 254 | 2024-07-09 | 0 |  | 254 | [9 empty] | Overdue
221 | REQUEST FOR REPAIR OF BROKEN GLASS CABINET | LAG, OKOTA | Others | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-07 | 256 | 2024-07-07 | 0 | 2024-07-08 | 1 | [9 empty] | Overdue
222 | INVOICE FOR GENERATOR SERVICE | LAG, ISAWO-IKORODU | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-07-08 | 255 | 2024-07-08 | 0 |  | 255 | [9 empty] | Overdue
223 | FAULTY CUSTOMERS RESTROOM | LAG, MARINA | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-09 | 254 | 2024-07-09 | 0 |  | 254 | [9 empty] | Overdue
224 | OIL LEAKAGE FROM 6HEAD MACHINE | LAG, ILUPEJU | Others | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-08 | 3 | 2024-07-09 | 1 | 2024-07-11 | 2 | 2024-07-11 | 2024-07-11 | 0 | 2024-07-11 | 0 | 2024-07-11 | 0 |  |  | Completed | 2024-07-11 | 0
225 | FREEZER ROOM NOT ATTAINING TEMPERATURE | EDO, UGBOWO, BENIN | Others | Breakdown | MOFFEN | FREEZER ROOM | HVAC | 2024-07-08 | 255 | 2024-07-09 | 1 |  | 254 | [9 empty] | Overdue
226 | REQUEST FOR NEW BATTERY | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | MID TECH | GENERATOR | GENERATOR | 2024-07-08 | 255 | 2024-07-09 | 1 |  | 254 | [9 empty] | Overdue
227 | GENERATOR SERVICING | PPU Oniru | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-09 | 254 | 2024-07-09 | 0 |  | 254 | [9 empty] | Overdue
228 | FAULTY COLLECTRAMATIC | LAG, TOTAL LEKKI | Others | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-09 | 2 | 2024-07-09 | 0 |  | 254 | [9 empty] | Completed | 2024-07-11 | 0
229 | EQUIPMENT SHOCKING | LAG, ONIRU | Electrical Surge | Breakdown | TIMILEYIN | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-07-08 | 1 | 2024-07-08 | 0 | 2024-07-09 | 1 | [9 empty] | Completed | 2024-07-09 | 0
230 | HOLE IN THE DRY STORE AT ENTOURAGE MALL | LAG, ENTOURAGE MALL | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-02 | 261 | 2024-07-02 | 0 | 2024-07-09 | 7 |  |  |  | 2024-07-09 | 254 |  |  |  | 78636.25 | Overdue
231 | FAULTY ROTESERIE MACHINE WHEEL / EXPOSED WIRE IN CHIPS FRYER | DELTA, EFFURUN | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-07-09 | 1 | 2024-07-09 | 0 |  | 254 | [9 empty] | Completed | 2024-07-10 | 0
232 | BLOW OUT BULBS | DELTA, EFFURUN | Electrical Surge | Breakdown | FRANK OGHOGO | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-07-09 | 254 | 2024-07-09 | 0 |  | 254 | [9 empty] | Overdue
233 | FREEZER ROOM CONTACTOR | IBADAN, CHALLENGE | Others | Breakdown | RANEX4WARD | FREEZER ROOM | HVAC | 2024-07-09 | 254 | 2024-07-09 | 0 | 2024-07-09 | 0 |  |  |  | 2024-07-09 | 254 |  |  |  | 48375 | Overdue
234 | FAULTY SWTICH CONTROL OF DISPLAY CABINET | LAG, CONOIL IKEJA | Electrical Surge | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-09 | 254 | 2024-07-09 | 0 |  | 254 | [9 empty] | Overdue
235 | GENERATOR SERVICING | BAYELSA, TOMBIA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-09 | 2 | 2024-07-09 | 0 |  | 254 | [9 empty] | Completed | 2024-07-11 | 0
236 | EMERGENCY NEED TO FIX PUNCTURED PIPE | LAG, HEYDEN IPAJA | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-09 | 254 | 2024-07-09 | 0 |  | 254 | [9 empty] | Overdue
237 | DAMAGED FREEZER ROOM ENTRANCE | LAG, FREEDOMWAY | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-07-08 | 255 | 2024-07-08 | 0 |  | 255 | [9 empty] | Overdue
238 | REPLACEMENT OF FEMALE STAFF CHANGING ROOM DOOR HANDLE | LAG, IDIMU | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-09 | 254 | 2024-07-09 | 0 |  | 254 | [9 empty] | Overdue
239 | REPAINTING OF KIOSK | LAG, BODE THOMAS | Others | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-07-08 | 255 | 2024-07-08 | 0 | 2024-07-08 | 0 |  |  |  | 2024-07-08 | 1 | 2024-07-09 | 254 |  |  | Overdue
240 | REQUEST FOR GENERATOR SERVICING | ABIA, AZIKIWE RD, UMUAHIA | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-07-08 | 255 | 2024-07-08 | 0 | 2024-07-09 | 1 |  |  |  |  | 45482 | 2024-07-09 | 254 | 2024-07-10 | 247250 | Overdue
241 | REQUEST FOR CABBAGE SHREDDER BLADE | PH, IWOFE | Others | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-07-08 | 255 | 2024-07-08 | 0 | 2024-07-09 | 1 | [8 empty] | 680475 | Overdue
242 | REQUEST FOR NEW GENEREATOR BATTERY | EDO, SILUKO | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-07-08 | 255 | 2024-07-08 | 0 |  | 255 | [9 empty] | Overdue
243 | LIMCA ROAD GENERATOR SERVICE REQUEST | ANAMBRA, LIMCA RD, ONITSHA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-08 | 255 | 2024-07-08 | 0 |  | 255 | [9 empty] | Overdue
244 | GENERATOR SERVICING BIRABI | PH, GRA BIRABI | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-08 | 255 | 2024-07-08 | 0 |  | 255 | [9 empty] | Overdue
245 | BURNT AC CABLES | LAG, ONIRU | Electrical Surge | Breakdown | FOLLTEC | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-08 | 255 | 2024-07-08 | 0 |  | 255 | [9 empty] | Overdue
246 | COLD ROOM & FREEZER ROOM CURTAIN REQUEST | OGUN, HEYDEN IBAFO | Others | Breakdown | TRIPPLE O | COLD ROOM UNIT | HVAC | 2024-07-08 | 255 | 2024-07-08 | 0 | 2024-07-09 | 1 | [9 empty] | Overdue
247 | FAULTY CUSTOMERS RESTROOM | LAG, IDIMU | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-08 | 255 | 2024-07-08 | 0 |  | 255 | [9 empty] | Overdue
248 | DEAD CABINET BULBS PX | IMO, IKENEGBU, OWERRI | Electrical Surge | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-07 | 256 | 2024-07-08 | 1 |  | 255 | [9 empty] | Overdue
249 | URGENT REPAIR OF COLLAPSE WALL TILES | DELTA, ISOKO RD | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-07 | 256 | 2024-07-08 | 1 | 2024-07-24 | 16 | 2024-08-05 | 2024-08-14 | 9 | [6 empty] | Overdue
250 | ISSUES SIGHTED BY OSC NOT YET FIXED | LAG, TEJUOSHO | Others | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2024-07-03 | 260 | 2024-07-08 | 5 |  | 255 | [9 empty] | Overdue
251 | CR OLOFAWAY GENERATOR SERVICE | ILORIN, OLOFAWAY | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-08 | 255 | 2024-07-08 | 0 |  | 255 | [9 empty] | Overdue
252 | EVACUATION OF SEPTIC TANK | LAG, IKORODU | Others | Breakdown | MOOLIGHT | SEPTIC TANK | EVACUATION | 2024-07-10 | 1 | 2024-07-10 | 0 | 2024-07-11 | 1 | [7 empty] | 2024-07-11 |  | Completed | 2024-07-11 | 1
253 | SERVICING OF GENERATOR | LAG, ALIMOSHO | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-08 | 4 | 2024-07-08 | 0 | 2024-07-08 | 0 | [7 empty] | 2024-07-12 |  | Completed | 2024-07-12 | 1
254 | PIE EXPRESS OKE AFA BROKEN CABINET GLASS | LAG, OKE-AFA | Others | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-08 | 255 | 2024-07-08 | 0 | 2024-07-12 | 4 | [9 empty] | Overdue
255 | Ice cream machine cover need replacement | DELTA, SAPELE-WARRI RD | Others | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
256 | FAULTY ROLLER SHUTTER | LAG, FREEDOMWAY | Others | Breakdown | BASSCOOM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-07-10 | 253 | 2024-07-10 | 0 | 2024-07-11 | 1 |  |  |  | 2024-07-11 | 0 | 2024-07-11 | 252 | 2024-07-12 |  | Overdue
257 | DRY STORE KEY LOCK GOT SPOILT | LAG, OGUDU | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-11 | 252 | 2024-07-11 | 0 | 2024-07-11 | 0 | [8 empty] | 51630 | Overdue
258 | ENGINE OIL NOT NEEDED | ILORIN, GRA | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
259 | Generator not working-Abakpa | AKWA IBOM, ABAK RD | Others | Breakdown | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-07-11 | 252 | 2024-07-11 | 0 | 2024-07-12 | 1 | [9 empty] | Overdue
260 | DAMAGED LOBBY CUPBOARD | LAG, MARINA | Others | Breakdown | FULLTURN | FLOOR CUPBOARD | FURNITURE | 2024-07-08 | 255 | 2024-07-11 | 3 | 2024-07-12 | 1 | 2024-07-12 | 2024-07-12 | 0 | 2024-07-12 | 251 |  |  |  |  | Overdue
261 | GENERATOR DUE FOR SERVICING | LAG, OGUNLANA DRIVE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
262 | CHANGE OF WATER FILTER | LAG, ONIRU | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-07-10 | 253 | 2024-07-11 | 1 |  | 252 | [9 empty] | Overdue
263 | BROKEN CEILING | LAG, FREEDOMWAY | Others | Breakdown | VENYS | ROOF | BUILDING | 2024-07-11 | 252 | 2024-07-11 | 0 | 2024-07-11 | 0 | [8 empty] | 66395 | Overdue
264 | FAULTY CUSTOMER RESTROOM | LAG, MARINA | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-09 | 254 | 2024-07-09 | 0 | 2024-07-10 | 1 | [9 empty] | Overdue
265 | REQUEST FOR EXTRACTOR BLADE | LAG, OKOTA | Others | Breakdown | Abbey electrical | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
266 | GENERATOR DUE FOR SERVICING | ILORIN, OFFA GARAGE | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
267 | GENERATOR SERVICE AT CR ASADAM | ILORIN, ASA DAM | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
268 | FAULTY CABINET BULB PX | LAG, MARINA | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
269 | LOBBY SOUND SYSTEM NOT WORKING | LAG, OKOTA | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
270 | AUTOMATIC HAND WASH NOT WORKING | PPU Oniru | Electrical Surge | Breakdown | PRO EQUIP | HAND DRYER LOBBY | ELECTRICAL | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
271 | BAD SOAP DISPENSER | LAG, MARINA | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
272 | FAULTY WATER HEATER | LAG, MARINA | Electrical Surge | Breakdown | PROPEARJEFF | WATER HEATER | PLUMBING | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
273 | FAULTY UNDER BAR CHILLER | LAG, ILUPEJU | Others | Breakdown | G.B BOYEJO | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
274 | REQUEST FOR REPAIR(DESK) | LAG, ILUPEJU | Others | Breakdown | FULLTURN | OFFICE DESK | FURNITURE | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
275 | FAULTY ICECREAM MACHINE | EDO, UGBOWO, BENIN | Electrical Surge | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
276 | TILTING PAN BREAK DOWN PPU ORON | AKWA IBOM, ORON RD | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-07-04 | 259 | 2024-07-04 | 0 | 2024-07-04 | 0 | [9 empty] | Overdue
277 | Critical items needs for challenge | IBADAN, CHALLENGE | Others | Breakdown | RANEX4WARD | OTHERS | OTHERS | 2024-07-11 | 252 | 2024-07-11 | 0 | 2024-07-11 | 0 |  |  |  | 2024-07-11 | 0 | 2024-07-11 | 252 |  |  | Overdue
278 | ICE CREAM MACHIN GIVING FUNNY SOUND | LAG, OSOLOWAY | Others | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-07-10 | 253 | 2024-07-10 | 0 |  | 253 | [9 empty] | Overdue
279 | BLOCKD DRAINAGE CHAMBER | LAG, MOBIL OGBA | Others | Breakdown | PENTECOSTAL | DRAIN COVER | BUILDING | 2024-07-06 | 257 | 2024-07-07 | 1 | 2024-07-07 | 0 | 2024-07-07 | 2024-07-08 | 1 | 2024-07-08 | 3 | 2024-07-11 | 252 |  | 170000 | Overdue
280 | GENERATOR SERVICING | BAYELSA, YENAGOA | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
281 | FAULTY FREEZER ROOM DOOR FAN | PH, OMOKU | Others | Breakdown | MOFFEN | FREEZER ROOM | HVAC | 2024-07-09 | 254 | 2024-07-11 | 2 |  | 252 | [9 empty] | Overdue
282 | REPLACEMENT OF EXTRACTOR HOODS | LAG, MARINA | Others | Breakdown | Abbey electrical | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2024-07-11 | 252 |  | 252 | [11 empty] | Overdue
283 | LEAKING CHIPS FRYER MACHINE | ANAMBRA, LIMCA RD, ONITSHA | Others | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-10 | 253 | 2024-07-11 | 1 |  | 252 | [9 empty] | Overdue
284 | RUSTY BOH UPRIGHT CHILLERS | DELTA, ISOKO RD | Others | Breakdown | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-07-10 | 253 | 2024-07-10 | 0 |  | 253 | [9 empty] | Overdue
285 | FAULTY ENTRANCE ROLLER SHUTTER | LAG, AJOSE ADEOGUN | Others | Breakdown | BASSCOOM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
286 | FAULTY TOASTING MACHINES BULBS FOR DISPLAY CABINET | LAG, AGUNGI | Electrical Surge | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
287 | BAD FREEZER ROOM LOCK | EDO, SAKPOMBA | Others | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-07-10 | 253 | 2024-07-11 | 1 |  | 252 | [9 empty] | Overdue
288 | FREEZER ROOM STOPPED WORKING | LAG, OGUDU | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-07-10 | 253 | 2024-07-11 | 1 |  | 252 | [9 empty] | Overdue
289 | CHANGE WATER FILTER | PPU Oniru | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-07-10 | 253 | 2024-07-11 | 1 |  | 252 | [9 empty] | Overdue
290 | FAULTY BOREHOLE MACHINE | LAG, CONOIL IKEJA | Others | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-10 | 253 | 2024-07-11 | 1 |  | 252 | [9 empty] | Overdue
291 | REQUEST FOR TWO SOAP DISPENSER | LAG, AJOSE ADEOGUN | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
292 | INVERTER BATTERY NOT BACKING UP | LAG, LATEEF JAKANDE | Others | Breakdown | DALAMATRIX | INVERTER BATTERIES | INVERTER | 2024-07-11 | 252 | 2024-07-11 | 0 |  | 252 | [9 empty] | Overdue
293 | FAULTY FREEZER ROOM DOOR | LAG, IPAJA RD | Others | Breakdown | DYNAMITE | FREEZER ROOM | HVAC | 2024-07-11 | 252 | 2024-07-11 | 0 | 2024-07-11 | 0 | [9 empty] | Overdue
294 | SEPTIC TANK EVACUATION | LAG, FREEDOMWAY | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-07-10 | 253 | 2024-07-11 | 1 |  | 252 | [9 empty] | Overdue
295 | COLD ROOM LID GASKET BAD | LAG, IKEJA MALL | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-07-10 | 253 | 2024-07-10 | 0 |  | 253 | [9 empty] | Overdue
296 | BROKEN SLAB AT CAR PARK AND PITTED HOLE AT CAR PARK | LAG, EKORO | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-07-03 | 260 | 2024-07-04 | 1 | 2024-07-14 | 10 | [8 empty] | 281650 | Overdue
297 | SERVICING OF GENERATOR | LAG, IPAJA RD | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
298 | ICE CREAM MACHINE NOT FROZEN | LAG, MARINA | Others | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-07-12 | 251 | 2024-07-14 | 2 |  | 249 | [9 empty] | Overdue
299 | SPOILTCABINET BULB | LAG, IKORODU | Electrical Surge | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-12 | 251 | 2024-07-14 | 2 |  | 249 | [9 empty] | Overdue
300 | FREEZER ROOM BREAK DOWN | LAG, AJOSE ADEOGUN | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-07-12 | 251 | 2024-07-14 | 2 |  | 249 | [9 empty] | Overdue
301 | PX IKOTUN BROKEN DOOR HANDLE | LAG, IKOTUN | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-12 | 251 | 2024-07-14 | 2 |  | 249 | [9 empty] | Overdue
302 | FREEZER ROOM NOT WORKING | LAG, IKOTUN | Others | Breakdown | DYNAMITE | FREEZER ROOM | HVAC | 2024-07-12 | 251 | 2024-07-14 | 2 |  | 249 | [9 empty] | Overdue
303 | OFFICE AC NOT COOLING | LAG, LEKKI PHASE 1 | Others | Breakdown | G.B BOYEJO | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-12 | 251 | 2024-07-14 | 2 |  | 249 | [9 empty] | Overdue
304 | FAULTY WINDOW ROLLER SHUTTER | LAG, TOTAL LEKKI | Others | Breakdown | EKNOR | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-07-12 | 251 | 2024-07-14 | 2 |  | 249 | [9 empty] | Overdue
305 | FAULTY ROLLER SHUTTER | LAG, GBAGADA | Others | Breakdown | BASSCOOM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-07-12 | 251 | 2024-07-14 | 2 |  | 249 | [9 empty] | Overdue
306 | SAGGED CEILING | LAG, ABULE EGBA | Others | Breakdown | CRADLEVIEW | ROOF | BUILDING | 2024-07-13 | 250 | 2024-07-13 | 0 | 2024-07-14 | 1 | 2024-07-22 | 2024-07-31 | 9 | 2024-07-31 | 0 | 2024-07-31 | 232 | 2024-08-02 | 1000000 | Overdue
307 | ABA-OWERRI ROAD FREEZER ROOM NOT WORKING | ABIA, ABA-OWERRI RD | Others | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-07-13 | 1 | 2024-07-14 | 1 |  | 249 | [9 empty] | Completed | 2024-07-14 | 0
308 | BUILDING OF CAGE FOR PACKAGING MATERIALS | LAG, ENTOURAGE MALL | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
309 | FAULTY FEMALE REST ROOM DOOR | LAG, ONIRU | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-05 | 258 | 2024-07-05 | 0 | 2024-07-12 | 7 | [8 empty] | 31175 | Overdue
310 | ROTISSERIE MACHINE NOT ROTATING | LAG, BADORE | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-07-13 | 15 | 2024-07-14 | 1 | 2024-07-28 | 14 | 2024-07-28 | 2024-07-28 | 0 | 2024-07-28 | 0 | 2024-07-28 | 0 |  |  | Completed | 2024-07-28 | 0
311 | FAULTY FOOD WARMER | LAG, GBAGADA | Electrical Surge | Breakdown | BCE | OTHERS | OTHERS | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
312 | OFFICE AC NOT WORKING | LAG, ENTOURAGE MALL | Others | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
313 | FAULTY CHIPS FRYER | LAG, JOEL OGUNNAIKE | Electrical Surge | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
314 | WATER TREATMENT FLOAT SWITCH NOT WORKING | OYO, OGBOMOSHO | Others | Breakdown | PRO EQUIP | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
315 | EVACUATION OF SEPTIC TANK | LAG, MARINA | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-07-13 | 1 | 2024-07-14 | 1 |  | 249 | [7 empty] | 2024-07-14 |  | Completed | 2024-07-14 | 1
316 | CR Ajah signage not coming up | LAG, AJAH | Electrical Surge | Breakdown | ACCENTRIX | OTHERS | OTHERS | 2024-07-12 | 251 | 2024-07-14 | 2 |  | 249 | [9 empty] | Overdue
317 | ABA-OWERRI ROAD FREEZER ROOM NOT WORKING | ABIA, ABA-OWERRI RD | Others | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
318 | FAULTY FREEZER ROOM | LAG, ISAWO-IKORODU | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-07-12 | 251 | 2024-07-14 | 2 |  | 249 | [9 empty] | Overdue
319 | REQUEST FOR DOOR CURTAIN | IBADAN, BODIJA | Others | Breakdown | OPEYEMI ABIDOYE | OTHERS | OTHERS | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
320 | SEPTIC TANK EVACUATION | LAG, IPAJA RD | Others | Breakdown | MOOLIGHT | SEPTIC TANK | EVACUATION | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
321 | REQUEST FOR NOTICE BOARD | LAG, EKORO | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
322 | OKIGWE RD. STORE TANK CALIBRATION | IMO, OKIGWE | Others | Breakdown | DAMI FOTE | GENERATOR | GENERATOR | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
323 | FAULTY GAS BURNER | LAG, CONOIL IKEJA | Others | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
324 | FAULTY CABINET HANDLE | LAG, IRE-AKARI | Others | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-12 | 251 |  | 251 | [11 empty] | Overdue
325 | COLD ROOM NOT ATTAINING TEMPERATURE | CALABAR, NDIDEM | Others | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
326 | ELECTRIC SPARK FROM WARMER | LAG, IDI-IROKO RD | Electrical Surge | Breakdown | BCE | OTHERS | OTHERS | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
327 | FLOODED STORE ENTRANCE | LAG, FREEDOMWAY | Others | Breakdown | BAMOCOON | OTHERS | OTHERS | 2024-07-10 | 4 | 2024-07-10 | 0 | 2024-07-13 | 3 | [9 empty] | Completed | 2024-07-14 | 0
328 | WATER LEAKAGE FROM LOBBY FLOOR TILES | LAG, IKORODU | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
329 | STANDING CHILLER AT THE BACK OF HOUSE IS FAULTY | LAG, IKEJA MALL | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-07-12 | 251 | 2024-07-14 | 2 |  | 249 | [9 empty] | Overdue
330 | GENERATOR SERVICING | PH AGGREY | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
331 | REPLACEMENT OF SHOE RACK AND STAFF EATING AREA BENCH | LAG, OKOTA | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
332 | CABINET NOT ATTAINING TEMPERATURE | LAG, AJOSE ADEOGUN | Others | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-14 | 249 | 2013-07-14 | -4018 |  | 4267 | [9 empty] | Overdue
333 | ICE CREAM MACHINE SERVINCING AND PARTS REPLACMENT | LAG, DOMINO E-CENTRE | Others | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
334 | Request for soap dispenser | LAG, DOMINO E-CENTRE | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
335 | FAULTY FEMALE CUSTOMER RESTROOM FLUSHER | LAG, IDIMU | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
336 | LEAKING ROOFTOP/CEILING | IBADAN, RING-ROAD | Others | Breakdown | DE FAVOUR | ROOF | BUILDING | 2024-07-02 | 48 | 2024-07-14 | 12 | 2024-07-14 | 0 | 2024-07-14 | 2024-07-17 | 3 | 2024-07-17 | 1 | 2024-07-18 | 32 | 2024-07-20 | 300000 | Completed | 2024-08-19 | 0
337 | FREEZER NOT ATTENDING TEMPERATURES | BAYELSA, TOMBIA | Others | Breakdown | MOFFEN | FREEZER ROOM | HVAC | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
338 | FAULTY ROT MACHINE | LAG, AKOWONJO | Others | Breakdown | HEFHEM | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
339 | BOH EXTRACTOR NOT WORKING | LAG, EKORO | Others | Breakdown | Abbey electrical | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
340 | GENERATOR SERVICING | EDO, UGBOWO, BENIN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
341 | REQUESTING FOR KIOSK REPAINT | ILORIN, OFFA GARAGE | Others | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-07-14 | 249 | 2024-07-14 | 0 | 2024-07-14 | 0 | [9 empty] | Overdue
342 | REQUEST FOR ICE CREAM MACHINE SERVICING | IMO, WETHERAL RD, OWERRI | Routine Servicing | Preventive | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
343 | GENERATOR DUE FOR SERVICING | LAG, GBAGADA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
344 | HOT WATER DISPERSER STOPPED WORKING | OGUN, OKE-ILEWO | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
345 | LOW PRODUCT QUALITY OF ROT MACHINE | LAG, AGUNGI | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
346 | BAD DRY STORE DOOR | LAG, ENTOURAGE MALL | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
347 | REPAIR OF ROLLER SHUTTER DOOR CR OLOFA | ILORIN, OLOFAWAY | Others | Breakdown | BASSCOOM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-07-12 | 17 | 2024-07-14 | 2 |  | 249 | [8 empty] | 254636.81 | Completed | 2024-07-29 | 0
348 | FAULTY EXTRACTOR | LAG, ONIRU | Others | Breakdown | SEASON BENDE | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2024-07-13 | 250 | 2024-07-13 | 0 |  | 250 | [9 empty] | Overdue
349 | GENERATOR DUE FOR SERVICING | LAG, ABULE EGBA | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
350 | CR Rumubiakani A.C not building ice and not chilling. | PH, RUMUBIAKANI | Others | Breakdown | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
351 | FAULTY CABINET SWITH AND BULBS PX | LAG, EJIGBO | Electrical Surge | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-29 | 234 | 2024-07-29 | 0 | 2024-07-29 | 0 | [9 empty] | Overdue
352 | FREEZER ROOM NOT ATTAINING TEMP | IBADAN, CHALLENGE | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-07-24 | 239 | 2024-07-24 | 0 | 2024-08-15 | 22 | [9 empty] | Overdue
353 | REPLACEMENT OF DOOR LOCKS | IBADAN, CHALLENGE | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-09 | 254 | 2024-07-09 | 0 |  | 254 | [9 empty] | Overdue
354 | CR ASA DAM LEAKING ICE CREAM MACHINE | ILORIN, ASA DAM | Others | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
355 | PX APAPA FAULTY CABINET | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-15 | 248 | 2024-07-15 | 0 |  | 248 | [9 empty] | Overdue
356 | FAULTY CUSTOMERS RESTROOM HANDLE | LAG, IKOTUN | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-26 | 237 | 2024-07-26 | 0 |  | 237 | [9 empty] | Overdue
357 | GENERATOR DUE FOR SERVICING | LAG, TOTAL LEKKI | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-26 | 237 | 2024-07-26 | 0 |  | 237 | [9 empty] | Overdue
358 | DEAD BULBS IN CABINET | LAG, OKOTA | Others | Breakdown | FRIDAY | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-22 | 241 | 2024-07-22 | 0 |  | 241 | [9 empty] | Overdue
359 | BROKEN GLASS | LAG, MOBIL OGBA | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-07-22 | 241 | 2024-07-22 | 0 | 2024-07-22 | 0 | 2024-07-29 | 2024-07-29 | 0 | [6 empty] | Overdue
360 | UNDERBAR NOT ATTAINING TEMRERATURE | LAG, OKOTA | Others | Breakdown | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
361 | FAULTY CHIPS FRYER DOOR LOCK | LAG, OKE-AFA | Others | Breakdown | HEFHEM | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-22 | 241 | 2024-07-22 | 0 |  | 241 | [9 empty] | Overdue
362 | FAULTY FOOD WARMER HANDLE | LAG, IKORODU | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-07-21 | 242 | 2024-07-25 | 4 | 2024-07-30 | 5 | [9 empty] | Overdue
363 | BLOCKED DRAINAGE IN FRYER SECTION | LAG, MOBIL OGBA | Others | Breakdown | ADEREMI KAZEEM | OTHERS | OTHERS | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
364 | SEWAGE EVACUATION | LAG, EJIGBO | Others | Breakdown | MOOLIGHT | SEPTIC TANK | EVACUATION | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
365 | HOT WATER NOT ATTAINING TEMPERATURE | LAG, IKORODU | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-28 | 235 | 2024-07-29 | 1 |  | 234 | [9 empty] | Overdue
366 | COLDROOM AND FREEZER ROOM NOT ATTAINING TEMP | LAG, OKOTA | Others | Breakdown | THIO AND PARTNER | COLD ROOM UNIT | HVAC | 2024-07-29 | 234 | 2024-07-29 | 0 | 2024-07-30 | 1 | [9 empty] | Overdue
367 | BAD SHREDDING MACHINE BLADE | LAG, IKEJA MALL | Others | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-07-23 | 240 | 2024-07-24 | 1 |  | 239 | [9 empty] | Overdue
368 | EXTRACTOR NOT WORKING | LAG, ETERNA LEKKI | Others | Breakdown | SEASON BENDE | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2024-07-21 | 242 | 2024-07-21 | 0 |  | 242 | [9 empty] | Overdue
369 | FAULTY UNDERBAR FRIDGE GASKET | LAG, ETERNA LEKKI | Others | Breakdown | G.B BOYEJO | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-07-19 | 244 | 2024-07-19 | 0 |  | 244 | [9 empty] | Overdue
370 | WOBLING LOBBY TABLE | LAG, ETERNA LEKKI | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-19 | 14 | 2024-07-19 | 0 |  | 244 | [9 empty] | Completed | 2024-08-02 | 0
371 | FAULTY PASTRY CABINT BULB PX | IBADAN, CHALLENGE | Electrical Surge | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-25 | 238 | 2024-07-25 | 0 |  | 238 | [9 empty] | Overdue
372 | GENERATOR DUE FOR SERVICING | LAG, OKOTA | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
373 | LEAKAGE FROM THE COLD ROOM AND FREEZER ROOM TO THE PACKAGING DRYSTORE | LAG, ONIRU | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-07-23 | 240 | 2024-07-25 | 2 |  | 238 | [9 empty] | Overdue
374 | SHORTAGE FROM WRONG TANK CALIBRATION | DELTA, ISOKO RD | Others | Breakdown | DAMI FOTE | GENERATOR | GENERATOR | 2024-07-29 | 234 | 2024-07-29 | 0 | 2024-07-30 | 1 | 2024-07-31 | 2024-08-02 | 2 | 2024-08-05 | 0 | 2024-08-05 | 227 |  |  | Overdue
375 | GENERATOR SERVICING | BAYELSA, TOMBIA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-29 | 234 | 2024-07-29 | 0 | 2024-07-29 | 0 | [9 empty] | Overdue
376 | OVERFLOWING BIO DEGRADABLE | LAG, OPEBI | Others | Breakdown | ZEBRA | OTHERS | OTHERS | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
377 | FRONT OF HOUSE ENTRANCE DOOR | LAG, OGUNLANA DRIVE | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
378 | BROKEN PIPE AT BACK OF HOUSE WASH AREA | LAG, IDI-IROKO RD | Others | Breakdown | PRO EQUIP | OTHERS | OTHERS | 2024-07-18 | 245 | 2024-07-19 | 1 |  | 244 | [9 empty] | Overdue
379 | HENNY PENNY PRESSURE FRYER NOT WORKING | LAG, ENTOURAGE MALL | Others | Breakdown | SIWA | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-25 | 238 | 2024-07-25 | 0 |  | 238 | [9 empty] | Overdue
380 | UPRIGHT CHILLER NOT ATTAINING TEMPERATURE | LAG, JOEL OGUNNAIKE | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
381 | CHIPS DUMP NOT WORKING | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | BCE | CHIPS DUMP | KITCHEN_EQUIPMENT | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
382 | WIRING OF LED LIGHTS AND SOCKET OUTLET TO INVERTER | LAG, DOMINO E-CENTRE | Electrical Surge | Breakdown | TIMILEYIN | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-07-28 | 1 | 2024-07-28 | 0 |  | 235 |  |  |  | 2024-07-28 | 0 | 2024-07-28 | 1 |  |  | Completed | 2024-07-29 | 0
383 | FAULTY DRAINAGE PUMPING MACHINE | LAG, ILUPEJU | Others | Breakdown | PRO EQUIP | FILTRATION PUMP 1 | WTP | 2024-07-20 | 243 | 2024-07-20 | 0 | 2024-07-20 | 0 | [9 empty] | Overdue
384 | FAULTY PANEL BREAKER | LAG, OKE-AFA | Electrical Surge | Breakdown | GBATMO | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-07-28 | 235 | 2024-07-28 | 0 |  | 235 | [9 empty] | Overdue
385 | GENERATOR SERVICING | BAYELSA, TOMBIA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
386 | FAULTY COLD ROOM FAN | LAG, TOTAL LEKKI | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
387 | BOH DOOR NET TORN | LAG, TEJUOSHO | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
388 | WEAK TANK PLACEMENT LEADS TO HOLE, TANK FALL, AND SPILLAGE PPU | IMO, OKIGWE | Others | Breakdown | DAMI FOTE | OTHERS | OTHERS | 2024-07-24 | 239 | 2024-07-24 | 0 |  | 239 | [9 empty] | Overdue
389 | WATER NOT RUNNING IN STORE | LAG, AWOLOWO 2 | Others | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-28 | 1 | 2024-07-28 | 0 |  | 235 | [9 empty] | Completed | 2024-07-29 | 0
390 | BROKEN HAND WASH SINK STAND | LAG, IKORODU | Others | Breakdown | PROPEARJEFF | LOBBY WASH HAND BASIN | PLUMBING | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
391 | FAULTY DOZING PUMP | ABIA, FACTORY RD, ABA | Others | Breakdown | PRO EQUIP | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-22 | 241 | 2024-07-29 | 7 |  | 234 | [9 empty] | Overdue
392 | GENERATOR DUE FOR SERVICING | LAG, EKORO | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-07-26 | 3 | 2024-07-26 | 0 |  | 237 | [9 empty] | Completed | 2024-07-29 | 0
393 | Freezer Room not Attaining temperature PPU IBADAN | IBADAN, MOKOLA | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
394 | GENERATOR DUE FOR SERVICE | LAG, OKOTA | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
395 | CHEST FREEZER NOT ATTAINING | LAG, IDI-IROKO RD | Others | Breakdown | G.B BOYEJO | CHEST FREEZER | HVAC | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
396 | GAS LEAKAGE IN THE STORE | IBADAN, CHALLENGE | Others | Breakdown | BERRADE | GAS CYLINDER | GAS | 2024-07-27 | 236 | 2024-07-27 | 0 | 2024-07-29 | 2 | 2024-07-29 |  | 234 | [5 empty] | 445075 | Overdue
397 | STORE PAINTING REQUEST | LAG, VGC | Others | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-07-20 | 243 | 2024-07-20 | 0 | 2024-07-29 | 9 | 2024-07-29 |  | 234 | [6 empty] | Overdue
398 | Fuel Line Piping installation for CR AND PPU Stores | IBADAN, CHALLENGE | Others | Breakdown | MID TECH | OTHERS | OTHERS | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
399 | CRACKED FOH HAND SINK TAP | IBADAN, VENTURA MALL | Others | Breakdown | PRO EQUIP | KITCHEN WASH HAND SINK | PLUMBING | 2024-07-27 | 6 | 2024-07-28 | 1 |  | 235 | [9 empty] | Completed | 2024-08-02 | 0
400 | FAULTY WATER HEATER | IBADAN, IDI-APE (IWO RD) | Others | Breakdown | PRO EQUIP | WATER HEATER | PLUMBING | 2024-07-29 | 234 | 2024-07-29 | 0 | 2024-07-29 | 0 | [9 empty] | Overdue
401 | RE-PAINTING OF THE LOBBY, CLOAK ROOM AND DRINK CAGE | LAG, IRE-AKARI | Others | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-07-19 | 244 | 2024-07-19 | 0 | 2024-07-29 | 10 | 2024-07-29 |  | 234 | [5 empty] | 578875 | Overdue
402 | QUOTATION SUBMITTED FOR LOBBY BROKEN GLASS | LAG, MOBIL OGBA | Others | Breakdown | TAIDAV | LOBBY WALL MIRROR | OTHERS | 2024-07-22 | 241 | 2024-07-22 | 0 |  | 241 | [9 empty] | Overdue
403 | URGENT CONNECTION OF THE DIESEL MAIN TANK DIRECTLY TO THE BASE TANK | LAG, FESTAC | Others | Breakdown | MID TECH | GENERATOR | GENERATOR | 2024-07-19 | 244 | 2024-07-19 | 0 |  | 244 | 2024-07-29 | 2024-07-29 | 0 | 2024-07-29 | 234 |  |  |  | 850000 | Overdue
404 | BROKEN FLOWER POT | LAG, AJAH | Others | Breakdown | VENYS | OTHERS | OTHERS | 2024-07-26 | 237 | 2024-07-27 | 1 | 2024-07-30 | 3 | 2024-07-30 |  | 233 | [6 empty] | Overdue
405 | FOH facade tiles and roller shutter washing | LAG, OSOLOWAY | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-07-20 | 243 | 2024-07-21 | 1 | 2024-07-21 | 0 |  |  |  | 2024-07-21 | 0 | 2024-07-21 | 242 |  | 182750 | Overdue
406 | Shortage from wrong tank calibration | DELTA, ISOKO RD | Others | Breakdown | DAMI FOTE | GENERATOR | GENERATOR | 2024-07-29 | 234 | 2024-07-29 | 0 |  | 234 | [9 empty] | Overdue
407 | FAULTY LOBBY AC | LAG, OPEBI | Others | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-29 | 234 | 2024-07-29 | 0 | 2024-07-30 | 1 | [7 empty] | 2024-07-30 |  | Overdue
408 | SCOTCH EGG FRYER DOWN | PPU Ilupeju | Others | Breakdown | BCE | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-07-15 | 248 | 2024-07-15 | 0 |  | 248 | [9 empty] | Overdue
409 | COLD ROOM NOT ATTAINING TEMPERATURE | CALABAR, NDIDEM | Others | Breakdown | BCE | COLD ROOM UNIT | HVAC | 2024-07-13 | 250 | 2024-07-13 | 0 |  | 250 | [9 empty] | Overdue
410 | FAULTY FOOD WARMER | LAG, GBAGADA | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-07-13 | 250 | 2024-07-14 | 1 | 2024-07-15 | 1 |  |  |  | 2024-07-15 | 0 | 2024-07-15 | 248 |  |  | Overdue
411 | FAULTY FEMALE CUSTOMER RESTROOM FLUSHER | LAG, IDIMU | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
412 | BROKEN CABINET GLASSS PX | LAG, AGUNGI | Others | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-15 | 248 | 2024-07-15 | 0 |  | 248 | [9 empty] | Overdue
413 | REQUEST FOR CABINET SWITCH NOB PX | LAG, AGUNGI | Others | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-15 | 248 | 2024-07-15 | 0 |  | 248 | [9 empty] | Overdue
414 | SPOILT ENTRANCE DOOR HANDLE | LAG, ABULE EGBA | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
415 | DRIPPING WATER AT ELECTRICAL CABLE | PPU Oniru | Others | Breakdown | ADEREMI KAZEEM | OTHERS | OTHERS | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
416 | FAUKTY FREEZER ROOM HINGES | LAG, OSOLOWAY | Others | Breakdown | THIO AND PARTNER | OTHERS | OTHERS | 2024-07-15 | 248 | 2024-07-15 | 0 |  | 248 | [9 empty] | Overdue
417 | FAULTY ROTISSERIE MACHINE | LAG, AKOWONJO | Others | Breakdown | HEFHEM | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-07-14 | 249 | 2024-07-14 | 0 | 2024-07-14 | 0 | [9 empty] | Overdue
418 | FREZZER ROOM NOT ATTANNING TEMPERATURE | OSUN, AYETORO | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-07-15 | 248 | 2024-07-15 | 0 |  | 248 | [9 empty] | Overdue
419 | SERVICING OF GENERATOR | OSUN, AYETORO | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-15 | 248 | 2024-07-15 | 0 |  | 248 | [9 empty] | Overdue
420 | GENERATOR DUE FOR SERVICING | LAG, GBAGADA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-14 | 249 | 2024-07-14 | 0 |  | 249 | [9 empty] | Overdue
421 | GENERATOR SERVICING | EDO, UGBOWO, BENIN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-07-15 | 248 |  | 248 | [11 empty] | Overdue
422 | COLDROOM NOT ATTAINING TEMPERATURE | IBADAN, AKOBO | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-07-15 | 248 | 2024-07-15 | 0 |  | 248 | [9 empty] | Overdue
423 | GENERATOR NOT POWERING ON | LAG, BODE THOMAS | Others | Breakdown | MID TECH | GENERATOR | GENERATOR | 2024-07-15 | 0 | 2024-07-15 | 0 |  | 248 | [9 empty] | Completed | 2024-07-15 | 0
424 | GENERATOR BREAKDOWN | PH, DOX RD | Others | Breakdown | PAGISEL | GENERATOR | GENERATOR | 2024-07-15 | 248 | 2024-07-15 | 0 |  | 248 | [9 empty] | Overdue
425 | REQUEST FOR PAINTING | LAG, IKORODU | Others | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2014-07-15 | 3901 | 2024-07-15 | 3653 |  | 248 | [9 empty] | Overdue
426 | EVACUATION OF SEPTIC TANK | LAG, AWOLOWO 2 | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-07-15 | 0 | 2024-07-15 | 0 |  | 248 | [9 empty] | Completed | 2024-07-15 | 0
427 | BROKEN OUTER KIOSK WALLS PX | LAG, ABULE EGBA | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-07-06 | 257 | 2024-07-15 | 9 | 2024-07-15 | 0 | [9 empty] | Overdue
428 | FAULTY GAS BURNER | LAG, CONOIL IKEJA | Others | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-07-13 | 250 | 2024-07-14 | 1 | 2024-07-15 | 1 | [8 empty] | 72875 | Overdue
429 | FAULTY 4 HEAD MACHINE FRYER | LAG, OPEBI | Others | Breakdown | HEFHEM | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-15 | 248 | 2024-07-15 | 0 |  | 248 | [9 empty] | Overdue
430 | ROTMACHINE NOT ROTATING | LAG, BADORE | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-07-13 | 250 | 2024-07-14 | 1 |  | 249 | [9 empty] | Overdue
431 | BROKEN PIPE AND TILES | LAG, IKORODU | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-07-05 | 258 | 2024-07-05 | 0 | 2024-07-06 | 1 | 2024-07-06 | 2024-07-08 | 2 | 2024-07-08 | 255 |  |  |  | 130000 | Overdue
432 | SERVICING OF OUTLET ENTRANCE DOOR | LAG, MARINA | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-07-15 | 248 | 2024-07-15 | 0 |  | 248 | [9 empty] | Overdue
433 | FAULTY FRYER AND OTHER EQUIPMENT PPU | ILORIN, MM WAY | Others | Breakdown | BCE | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-07-07 | 256 | 2024-07-08 | 1 |  | 255 | [9 empty] | Overdue
434 | FAULTY MC ADAMS 4 HEAD PRESSURE FRYER LID GASKET | IBADAN, OJOO | Others | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-08 | 255 | 2024-07-08 | 0 | 2024-07-15 | 7 | [9 empty] | Overdue
435 | BROKEN FLAMEGRILL MACHINE GLASS. | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-07-15 | 248 | 2024-07-15 | 0 | 2024-08-13 | 29 | 2024-08-13 | 2024-08-13 | 0 | 2024-08-13 | 0 | 2024-08-13 | 219 |  |  | Overdue
436 | ESCAPE OF AIR FROM THE FOUR HEAD MACHINE | LAG, FESTAC | Others | Breakdown | HEFHEM | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-07-22 | 1 | 2024-07-22 | 0 | 2024-07-23 | 1 | [9 empty] | Completed | 2024-07-23 | 0
437 | PASTRY CABINET NOT ATTAINING TEMPERATURE | IBADAN, CHALLENGE | Others | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-19 | 244 | 2024-07-20 | 1 |  | 243 | [9 empty] | Overdue
438 | ROT MACHINE NOT HEATING | ANAMBRA, ZIK AVENUE, AWKA | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-07-08 | 255 | 2024-07-08 | 0 | 2024-07-13 | 5 |  |  |  | 2024-08-05 | 227 |  |  |  |  | Overdue
439 | CRACK COCK HEAD | LAG, ETERNA LEKKI | Others | Breakdown | ACCENTRIX | OTHERS | OTHERS | 2024-07-19 | 244 | 2024-07-24 | 5 | 2024-07-29 | 5 | 2024-07-29 |  | 234 | [6 empty] | Overdue
440 | FAULTY ROLLER SHUTTER AT FESTAC | LAG, FESTAC | Others | Breakdown | BASSCOM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-07-25 | 238 | 2024-07-25 | 0 | 2024-07-26 | 1 |  |  |  | 2024-07-26 | 1 | 2024-07-27 | 236 |  |  | Overdue
441 | REQUEST FOR NEW EXTRACTOR BLADES | LAG, AJAH | Others | Breakdown | Abbey electrical | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2024-07-26 | 237 | 2024-07-26 | 0 |  | 237 | [9 empty] | Overdue
442 | CRACKED CABINET GLASS PX | LAG, OMOLE | Others | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-23 | 240 | 2024-07-23 | 0 |  | 240 | [9 empty] | Overdue
443 | BAD WINDOW NET/ ENTRANCE DOOR | LAG, JOEL OGUNNAIKE | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-07-31 | 20 | 2024-07-31 | 0 | 2024-08-20 | 20 | 2024-08-20 | 2024-08-20 | 0 | 2024-08-20 | 0 | 2024-08-20 | 0 |  |  | Completed | 2024-08-20 | 0
444 | SIGNAGE NOT WORKING |  | Electrical Surge | Breakdown | ACCENTRIX | OTHERS | OTHERS | 2024-07-25 | 238 | 2024-07-26 | 1 | 2024-07-31 | 5 | 2024-07-31 | 2024-08-01 | 1 | 2024-08-01 | 0 | 2024-08-01 | 231 | 2024-08-07 |  | Overdue
445 | REPAIR OF STAFF LOCKER | LAG, NNPC ALAPERE | Others | Breakdown | VENYS | OTHERS | OTHERS | 2024-07-27 | 236 | 2024-07-30 | 3 |  | 233 | [9 empty] | Overdue
446 | EVACUATION AND EXCAVATION OF THE STORE SEPTIC TANK | LAG, EKORO | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-07-17 | 246 | 2024-07-17 | 0 | 2024-07-19 | 2 | 2024-07-19 | 2024-07-20 | 1 | 2024-07-21 | 1 | 2024-07-22 | 241 | 2024-07-24 |  | Overdue
447 | BROKEN TILE AT KITCHEN AND LOBBY | LAG, IDI-IROKO RD | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-07-25 | 238 | 2024-07-25 | 0 | 2024-08-05 | 11 | [9 empty] | Overdue
448 | SERVICING OF COLD ROOM | OSUN, GBONGAN | Routine Servicing | Preventive | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-07-27 | 9 | 2024-07-28 | 1 | 2024-08-05 | 8 | [8 empty] | 277250 | Completed | 2024-08-05 | 0
449 | FAULTY GREASE TRAP | BAYELSA, YENAGOA | Others | Breakdown | STANQUANT | OTHERS | OTHERS | 2024-07-23 | 240 | 2024-07-23 | 0 | 2024-07-31 | 8 | [9 empty] | Overdue
450 | COLD ROOM FAULTY | LAG, ENTOURAGE MALL | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-07-29 | 234 | 2024-07-30 | 1 |  | 233 | [9 empty] | Overdue
451 | EXPOSED CABLES AT THE WATER TREATMENT PLANT | LAG, IDI-IROKO RD | Others | Breakdown | PRO EQUIP | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-30 | 233 | 2024-07-30 | 0 |  | 233 | [9 empty] | Overdue
452 | STAFF WALL HANGER | LAG, TOTAL LEKKI | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-23 | 240 | 2024-07-23 | 0 |  | 240 | [9 empty] | Overdue
453 | WOODEN FURNITURE DAMAGE PX OSOLO | LAG, OSOLOWAY | Others | Breakdown | MATOLAD | PRODUCTION TABLE | FURNITURE | 2024-07-17 | 246 | 2024-07-17 | 0 | 2024-07-18 | 1 | 2024-07-18 | 2024-07-18 | 0 | 2024-07-18 | 245 |  |  |  | 85000 | Overdue
454 | OPEN CEILING AROUND THE EXTRACTOR AREA | LAG, SKYMALL | Others | Breakdown | ACORN | ROOF | BUILDING | 2024-07-26 | 237 | 2024-07-26 | 0 |  | 237 | [9 empty] | Overdue
455 | FALLING CEILING IN THE DRY STORE | LAG, OGUDU | Others | Breakdown | FULLTURN | ROOF | BUILDING | 2024-07-16 | 247 | 2024-07-16 | 0 | 2024-07-18 | 2 | 2024-08-01 | 2024-08-02 | 1 | 2024-08-02 | 0 | 2024-08-02 | 230 | 2024-08-05 | 300000 | Overdue
456 | IDENTIFIED ISSUES CAPTURED DURING FUMIGATION EXCERCISE | LAG, AJOSE ADEOGUN | Others | Breakdown | BAMCOON | OTHERS | OTHERS | 2024-07-08 | 255 | 2024-07-08 | 0 | 2024-07-13 | 5 | 2024-07-24 | 2024-07-30 | 6 | 2024-07-30 | 233 |  |  |  | 310000 | Overdue
457 | DAMAGED FREEZER ROOM FLOOR | LAG, OKE-AFA | Others | Breakdown | DYNAMITE | FREEZER ROOM | HVAC | 2024-07-23 | 240 | 2024-07-24 | 1 |  | 239 | [9 empty] | Overdue
458 | Quotation for changing 7,5hp compressor as follows | LAG, OKE-AFA | Others | Breakdown |  | OTHERS | OTHERS | 2024-07-26 | 237 | 2024-07-31 | 5 | 2024-07-31 | 0 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 220 |  | 550000 | Overdue
459 | LEAKING AIR CONDITIONER | PH, ABACHA RD | Others | Breakdown | MOFFEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-07-31 | 232 | 2024-07-31 | 0 |  | 232 | [9 empty] | Overdue
460 | FAULTY BACK OF HOUSE UPRIGHT CHILLER AND ITS RACKS | LAG, AJAH | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-07-24 | 239 | 2024-07-24 | 0 |  | 239 | [9 empty] | Overdue
461 | Unusual noise from generator fan belt/ radiator, service,water, water pump - CR OGBOR HILL, ABA, ABIA - STATE | ABIA, OGBOR HILLS | Others | Breakdown | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-07-30 | 233 | 2024-07-30 | 0 | 2024-07-30 | 0 |  |  |  | 2024-08-02 | 230 |  |  |  | 655750 | Overdue
462 | BROKEN TILES AT PX EBUTE METTA |  | Others | Breakdown | VENYS | OTHERS | OTHERS | 2024-07-04 | 259 | 2024-07-04 | 0 |  | 259 | [9 empty] | Overdue
463 | REQUEST FOR HAND WASH AND SANITIZER DISPENSER | IBADAN, VENTURA MALL | Others | Breakdown | PRO EQUIP | OTHERS | OTHERS | 2024-07-29 | 4 | 2024-07-30 | 1 |  | 233 | [9 empty] | Completed | 2024-08-02 | 0
464 | FAULTY WATER HEATER | IBADAN, IDI-APE (IWO RD) | Others | Breakdown | PRO EQUIP | WATER HEATER | PLUMBING | 2024-07-29 | 4 | 2024-07-29 | 0 | 2024-07-29 | 0 |  |  |  | 2024-07-30 | 0 | 2024-07-30 | 3 | 2024-07-31 | 241875 | Completed | 2024-08-02 | 0
465 | BAD CASHIER COUNTER | LAG, OKE-AFA | Others | Breakdown | MATOLAD | CASHIER COUNTER | BUILDING | 2024-07-29 | 234 | 2024-07-29 | 0 | 2024-07-31 | 2 | 2024-07-31 | 2024-08-02 | 2 | [5 empty] | 700000 | Overdue
466 | REPAIR OF ROLLER SHUTTER | ILORIN, GRA | Others | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-07-30 | 233 | 2024-07-30 | 0 | 2024-07-31 | 1 |  |  |  | 2024-07-31 | 1 | 2024-08-01 | 231 |  |  | Overdue
467 | BROKEN TILES IN THE STORE(BOH &FOH) | LAG, AJAH | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-07-26 | 237 | 2024-07-26 | 0 |  | 237 | [9 empty] | Overdue
468 | GNERATOR NEEDS SERVICING | PPU Opebi | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-07-31 | 232 | 2024-07-31 | 0 |  | 232 | [7 empty] | 2024-08-03 |  | Overdue
469 | TOASTING MACHINE | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2024-07-30 | 233 | 2024-07-30 | 0 |  | 233 | [9 empty] | Overdue
470 | CABINET NOT ATTAINING TEMPERATURE | IBADAN, CHALLENGE | Others | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-24 | 239 | 2024-07-24 | 0 | 2024-08-09 | 16 | [9 empty] | Overdue
471 | CRACKD AND STAIND LOBBY CEILING | LAG, MMA2 | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-24 | 239 | 2024-07-24 | 0 |  | 239 | [9 empty] | Overdue
472 | FOOD SAFETY ISSUE = RAT HOLES/ LIVE ROACHES IN THE STORE | LAG, OMOLE | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-07-29 | 234 | 2024-07-29 | 0 | 2024-07-31 | 2 |  |  |  | 2024-07-31 | 2 | 2024-08-02 | 230 |  | 79657.5 | Overdue
473 | MACCADAM PRESSURE FRYER NOT RELEASING PRESSURE | LAG, MAGODO | Others | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-07-30 | 233 | 2024-07-30 | 0 |  | 233 | [9 empty] | Overdue
474 | GAS BURNER DUE FOR SERVICE | LAG, IDI-IROKO RD | Routine Servicing | Preventive | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-07-30 | 233 | 2024-07-30 | 0 | 2024-07-31 | 1 | 2024-08-04 |  | 228 | [6 empty] | Overdue
475 | FAULTY FOH AIR CURTAIN | LAG, BADORE | Others | Breakdown | EKNOR | OTHERS | OTHERS | 2024-07-25 | 238 | 2024-07-25 | 0 |  | 238 | [9 empty] | Overdue
476 | COLD ROOM AND FREEZER ROOM CONDERSER | IBADAN, CHALLENGE | Others | Breakdown | BCE | COLD ROOM UNIT | HVAC | 2024-07-31 | 232 | 2024-07-31 | 0 | 2024-08-06 | 6 | [9 empty] | Overdue
477 | FAULTY FOOD WARMER DOOR GASKET | IBADAN, OJOO | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-07-28 | 235 | 2024-07-28 | 0 | 2024-08-06 | 9 |  |  |  | 2024-08-06 | 0 | 2024-08-06 | 226 |  |  | Overdue
478 | FLAMMED GRILLED MACHINE MALFUCTIONING | LAG, JOEL OGUNNAIKE | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-07-19 | 244 | 2024-07-19 | 0 | 2024-08-06 | 18 |  |  |  | 2024-08-06 | 226 |  |  |  |  | Overdue
479 | FAULTY PUMPING MACHINE | LAG, TOTAL LEKKI | Others | Breakdown | PRO EQUIP | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-30 | 233 | 2024-07-30 | 0 | 2024-07-30 | 0 | [9 empty] | Overdue
480 | FAULTY ENERGY SAVER PANEL | LAG, TOTAL ONIGBAGBO | Electrical Surge | Breakdown | SEASON BENDE | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-07-29 | 234 | 2024-07-30 | 1 | 2024-08-03 | 4 | [9 empty] | Overdue
481 | FAULTY HAND WASH SINK | LAG, ISAWO-IKORODU | Others | Breakdown | PROPEARJEFF | LOBBY WASH HAND BASIN | PLUMBING | 2024-07-26 | -18 | 2024-07-27 | 1 |  | 236 | [9 empty] | Completed | 2024-07-08 | 0
482 | PEELED WALL IN CHANGING ROOM | LAG, CONOIL IKEJA | Others | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-07-31 | 15 | 2024-07-31 | 0 | 2024-08-12 | 12 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 3 | 2024-08-14 |  | Completed | 2024-08-15 | 0
483 | WATER TREATMENT PLANT BYPASSED INTO RUNNING THE WATER IN THE STORE | ENUGU, CHIME AVENUE | Others | Breakdown | PRO EQUIP | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-22 | 241 | 2024-07-24 | 2 | 2024-08-06 | 13 | 2024-08-07 |  | 225 | [6 empty] | Overdue
484 | PX IDIMU CABINET ISSUES | LAG, IDIMU | Others | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-27 | 236 | 2024-07-27 | 0 | 2024-08-08 | 12 | [9 empty] | Overdue
485 | COLD ROOM ENTRANC DOOR FLOOR IRON SLAB DETACHED | LAG, EKORO | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-08-06 | 226 | 2024-08-06 | 0 | 2024-08-06 | 0 | 2024-08-06 | 2024-08-06 | 0 | 2024-08-07 | 1 | 2024-08-08 | 224 |  | 43000 | Overdue
486 | COLD ROOM NOT WORKING | DELTA, ISOKO RD | Others | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2024-07-30 | 233 | 2024-07-30 | 0 |  | 233 | [9 empty] | Overdue
487 | RE ROOFING AND WELDING OF CHANGE OVER AREA | IMO, IKENEGBU, OWERRI | Others | Breakdown | FULLTURN | ROOF | BUILDING | 2024-07-19 | 244 | 2024-07-19 | 0 | 2024-08-05 | 17 | 2024-08-05 |  | 227 | [6 empty] | Overdue
488 | REPAINTING OF STORE | DELTA, ISOKO RD | Others | Breakdown | FULLTURN | PAINTING | BUILDING | 2024-07-18 | 245 | 2024-07-19 | 1 | 2024-08-05 | 17 | 2024-08-05 |  | 227 | [6 empty] | Overdue
489 | BROKEN ENTRANCE DOOR | IBADAN, VENTURA MALL | Others | Breakdown | DE FAVOUR | OTHERS | OTHERS | 2024-07-27 | 236 | 2024-07-28 | 1 | 2024-08-08 | 11 | [9 empty] | Overdue
490 | REQUEST FOR LED CABINET BULBS | LAG, MARINA | Others | Breakdown | ISMAIL | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-19 | 21 | 2024-07-20 | 1 | 2024-07-22 | 2 | 2024-07-22 | 2024-07-22 | 0 | 2024-07-22 | 0 | 2024-07-22 | 18 |  |  | Completed | 2024-08-09 | 0
491 | FAULTY SOUND SYSTEM | LAG, FREEDOMWAY | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-07-29 | 234 | 2024-07-29 | 0 | 2024-07-31 | 2 | 2024-07-31 | 2024-08-09 | 9 | 2024-08-09 | 223 |  |  |  | 179625 | Overdue
492 | DAILY EQUIPMENT STATUS | PPU Ajah | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-07-26 | 237 | 2024-07-26 | 0 | 2024-08-02 | 7 | 2024-08-05 | 2024-08-09 | 4 | [6 empty] | Overdue
493 | INSTALLATION OF DISPLAY CABINET | LAG, ETERNA LEKKI | Others | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-07-30 | 233 | 2024-07-30 | 0 | 2024-08-12 | 13 | [9 empty] | Overdue
494 | INSTALLATION OF ICE CREAM MACHINE | LAG, ETERNA LEKKI | Others | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-07-30 | 2 | 2024-07-30 | 0 | 2024-08-01 | 2 | 2024-08-01 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-02 |  | Completed | 2024-08-01 | 1
495 | PEELING OFFICE & STAFF AREA WALL | LAG, ETERNA LEKKI | Others | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-08-02 | 230 | 2024-08-02 | 0 | 2024-08-12 | 10 | 2024-08-12 |  | 220 | [6 empty] | Overdue
496 | LOBBY BOOTH CHAIR AND TABLE WITH DISCOLOURED PAINT AND CHIPPED EDGE | LAG, JOEL OGUNNAIKE | Others | Breakdown | MATOLAD | CUSTOMER CHAIR | FURNITURE | 2024-07-28 | 235 | 2024-07-29 | 1 |  | 234 | [9 empty] | Overdue
497 | DEAD BULB IN THE STORE | LAG, MMA2 | Electrical Surge | Breakdown | TIMILEYIN | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-07-24 | 239 | 2024-07-24 | 0 | 2024-08-12 | 19 | [9 empty] | Overdue
498 | FAULTY ENTRANCE AND DRY STORE DOOR HANDLE | LAG, AWOLOWO 2 | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-30 | 233 | 2024-07-30 | 0 | 2024-08-08 | 9 | 2024-08-08 | 2024-08-08 | 0 | 2024-08-08 | 224 |  |  |  | 43403.13 | Overdue
499 | CRACKED AND STAINED LOBBY CEILING | LAG, MMA2 | Others | Breakdown |  | ROOF | BUILDING | 2024-07-24 | 239 | 2024-07-24 | 0 |  | 239 | [9 empty] | Overdue
500 | REPLACEMENT OF ALL ASECTIONAL TAP AND STAFF REST ROOM | LAG, ETERNA LEKKI | Others | Breakdown | PRO EQUIP | TAP | PLUMBING | 2024-07-24 | 19 | 2024-07-24 | 0 | 2024-08-08 | 15 | 2024-08-08 | 2024-08-08 | 0 | 2024-08-08 | 0 | 2024-08-08 | 4 |  |  | Completed | 2024-08-12 | 0
501 | FAULTY FEMALE STAFF RESTROOM DOOR HANDLE | LAG, AJOSE ADEOGUN | Others | Breakdown | FULLTURN | OTHERS | OTHERS | 2024-07-26 | 237 | 2024-08-07 | 12 | 2024-08-08 | 1 | [9 empty] | Overdue
502 | OPEN DRINKAGE | LAG, ILUPEJU | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-07-25 | 238 | 2024-07-25 | 0 | 2024-08-11 | 17 | [9 empty] | Overdue
503 | BAD WC FLUSHER IN CUSTOMER/STAFF RESTROOM | DELTA, EFFURUN | Others | Breakdown | FRANK | OTHERS | OTHERS | 2024-07-09 | 254 | 2024-07-09 | 0 |  | 254 | [9 empty] | Overdue
504 | BROKEN GLASS | LAG, MOBIL OGBA | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-07-22 | 21 | 2024-07-22 | 0 | 2024-07-22 | 0 | 2024-07-22 | 2024-07-29 | 7 | 2024-07-29 | 0 | 2024-07-29 | 14 |  | 850000 | Completed | 2024-08-12 | 0
505 | FAULTY A.C AT DRY STORE | LAG, AWOLOWO 2 | Others | Breakdown | G.B BOYEJO | OTHERS | OTHERS | 2024-07-30 | 14 | 2024-07-30 | 0 | 2024-08-05 | 6 | 2024-08-05 | 2024-08-05 | 0 | 2024-08-05 | 0 | 2024-08-05 | 8 |  |  | Completed | 2024-08-13 | 0
506 | OPENED CEILING | LAG, LEKKI PHASE 1 | Others | Breakdown | FULLTURN | ROOF | BUILDING | 2024-07-15 | 248 | 2024-07-16 | 1 | 2024-07-17 | 1 | 2024-07-17 | 2024-07-17 | 0 | 2024-07-17 | 1 | 2024-07-18 | 245 |  |  | Overdue
507 | FAULTY FOH COUNTER | LAG, LEKKI PHASE 1 | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-31 | 232 | 2024-07-31 | 0 |  | 232 | [9 empty] | Overdue
508 | LOBBY SOUND SYSTEM NOT WORKING | LAG, CONOIL IKEJA | Electrical Surge | Breakdown | ACORN | OTHERS | OTHERS | 2024-07-30 | 233 | 2024-07-30 | 0 | 2024-08-10 | 11 | 2024-08-10 |  | 222 | [6 empty] | Overdue
509 | REPAINTING OF STAFF RESTROOM | LAG, FESTAC | Others | Breakdown | WESTERN DESIGN | OTHERS | OTHERS | 2024-07-11 | 252 | 2024-07-12 | 1 | 2024-07-16 | 4 | 2024-07-16 | 2024-07-17 | 1 | 2024-07-17 | 0 | 2024-07-17 | 246 |  |  | Overdue
510 | BROKEN LOBBY BACK OF HOUSE TILES | LAG, SKYMALL | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-07-12 | 251 | 2024-07-16 | 4 | 2024-08-12 | 27 | [9 empty] | Overdue
511 | PAINTING OF STORES EXTERIOR WALLS | ANAMBRA, ZIK AVENUE, AWKA | Others | Breakdown | JOWYN | PAINTING | BUILDING | 2024-07-08 | 255 | 2024-07-08 | 0 | 2024-08-12 | 35 | [9 empty] | Overdue
512 |  | LAG, LEKKI PHASE 1 | Others | Breakdown | MODEL | OTHERS | OTHERS | 2024-07-26 | 237 | 2024-07-26 | 0 | 2024-08-18 | 23 | 2024-08-18 |  | 214 | [6 empty] | Overdue
513 | LOBBY AIR CURTAIN | LAG, IDIMU | Others | Breakdown | EKNOR | OTHERS | OTHERS | 2024-07-31 | 24 | 2024-07-31 | 0 | 2024-08-05 | 5 | 2024-08-09 | 2024-08-14 | 5 | 2024-08-15 | 8 | 2024-08-23 | 1 | 2024-08-24 | 829840 | Completed | 2024-08-24 | 1
514 | LEAKING EROSION TANK | LAG, TEJUOSHO | Others | Breakdown | PROPEARJEFF | AERATION TANK | WTP | 2024-07-15 | 248 | 2024-07-30 | 15 | 2024-08-17 | 18 | 2024-08-20 |  | 212 | [6 empty] | Overdue
515 | REPAIR OF LOBBY COUPLE | LAG, IRE-AKARI | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-07-19 | 244 | 2024-07-19 | 0 | 2024-08-20 | 32 | 2024-08-20 |  | 212 | [6 empty] | Overdue
516 | BROKEN WASTE BIN COVERAGE | LAG, OBA AKRAN | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-07-24 | 27 | 2024-07-24 | 0 | 2024-08-20 | 27 | 2024-08-20 | 2024-08-20 | 0 | 2024-08-20 | 0 | 2024-08-20 | 0 |  |  | Completed | 2024-08-20 | 0
517 | LOBBY HAND DRYER MALFUTIONING | LAG, AJAH | Others | Breakdown | JOEL OMOTOSHO | OTHERS | OTHERS | 2024-07-15 | 0 | 2024-07-15 | 0 | 2024-07-15 | 0 | 2024-07-15 | 2024-07-15 | 0 | 2024-07-15 | 0 | 2024-07-15 | 0 |  |  | Completed | 2024-07-15 | 0
518 | REQUEST FOR NEW HAND DRYER | LAG, AJAH | Others | Breakdown | PRO EQUIP | HAND DRYER LOBBY | ELECTRICAL | 2024-07-25 | 26 | 2024-07-25 | 0 | 2024-08-20 | 26 | 2024-08-20 | 2024-08-20 | 0 | 2024-08-20 | 0 | 2024-08-20 | 0 |  |  | Completed | 2024-08-20 | 0
519 | COLD ROOM NOT WORKING | LAG, ENTOURAGE MALL | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-07-21 | 1 | 2024-07-22 | 1 | 2024-07-22 | 0 | 2024-07-22 | 2024-07-22 | 0 | 2024-07-22 | 0 | 2024-07-22 | 0 | 2024-07-23 |  | Completed | 2024-07-22 | 1
520 | COLLECTRAMATIC MACHINE LEAKAGE | LAG, AJOSE ADEOGUN | Others | Breakdown | BCE | COLLECTRAMATIC OIL PUMP MACHINE | KITCHEN_EQUIPMENT | 2024-07-25 | 36 | 2024-07-25 | 0 | 2024-08-26 | 32 | 2024-08-26 | 2024-08-26 | 0 | 2024-08-26 | 0 | 2024-08-26 | 4 |  |  | Completed | 2024-08-30 | 0
521 | CRACKED LOBBY CEILING | LAG, MMA2 | Others | Breakdown | VENYS | ROOF | BUILDING | 2024-07-24 | 239 | 2024-07-26 | 2 | 2024-08-27 | 32 | 2024-08-28 | 2024-08-29 | 1 | 2024-08-29 | 0 | 2024-08-29 | 203 |  | 330000 | Overdue
522 | CONSTRUCTION OF DRAINAGE COVER | LAG, OSOLOWAY | Others | Breakdown | ACORN | DRAIN COVER | BUILDING | 2024-07-01 | 262 | 2024-07-01 | 0 | 2024-08-29 | 59 | 2024-08-30 |  | 202 | [6 empty] | Overdue
523 | DEAD CABINET BULB AND DEAD SECURITY LIGHT . | LAG, ALIMOSHO | Others | Breakdown | FRIDAY | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-08-29 | 1 | 2024-08-30 | 1 | 2024-08-30 | 0 | 2024-08-30 | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-31 |  | Completed | 2024-08-30 | 1
524 | DEAD BULB IN THE DRY STORE | LAG, FREEDOMWAY | Corrective Action | Corrective | ISMAIL | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-08-27 | 205 | 2024-08-28 | 1 |  | 204 | [9 empty] | Overdue
525 | CONSTRUCTION OF NEW SEPTIC TANK | AKWA IBOM, IKOT EKPENE RD | Others | Breakdown | DEACONESS | SEPTIC TANK | EVACUATION | 2024-07-29 | 234 | 2024-07-29 | 0 | 2024-09-19 | 52 | 2024-09-19 | 2024-09-20 | 1 | 2024-09-20 | 0 | 2024-09-20 | 181 |  |  | Overdue
526 | GAS LEAKAGE | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | BERRADE | GAS CYLINDER | GAS | 2024-07-16 | 3 | 2024-07-19 | 3 | 2024-07-19 | 0 | 2024-07-19 | 2024-07-19 | 0 | 2024-07-19 | 0 | 2024-07-19 | 0 |  |  | Completed | 2024-07-19 | 0
527 | FAULTY BOH CHILLER DOOR HANDLE | LAG, ONIRU | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-07-30 | 72 | 2024-07-30 | 0 | 2024-10-10 | 72 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 |  | Completed | 2024-10-10 | 1
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
Formulas:
Days Since Request = IF([Request Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Request Date],TODAY()-[Request Date]))
Days Delayed by Helpdesk = IF([Date Shared by Helpdesk]<>"",[Date Shared by Helpdesk]-[Request Date],IF([Request Date]="","",TODAY()-[Request Date]))
Days Delayed by Vendor/Technician = IF(M6<>"",M6-[Date Shared by Helpdesk],IF([Date Shared by Helpdesk]="","",TODAY()-[Date Shared by Helpdesk]))
Days Since Negotiation Request = TODAY() - [Date Negotiated]
Days Since Negotiation Request = IF([Date Negotiated]<>"",[Date Negotiated]-[Date Sent for Negotiation],IF([Date Sent for Negotiation]="","",TODAY()-[Date Sent for Negotiation]))
Days Since Approval Request = IF([Approved Date]<>"",[Approved Date]-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval = IF([Approved Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Approved Date],TODAY()-[Approved Date]))
Status = IF([Request Date]="","",IF([Actual delivery date]<>"","Completed",IF(TODAY()<[Expected Delivery Date],"Planned",IF(TODAY()=[Expected Delivery Date],"Due","Overdue"))))
Note on AA6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vendor gave feedback thaat part is not available on 18 of Jan

## AUGUST
Legend
Completed on time
Completed late
S/N | ACTION/TASK | Store | Reason for Breakdown | Maintenance Category | Responsible | Specific Equipment | Category | Request Date | Days Since Request | Date Shared by Helpdesk | Days Delayed by Helpdesk | Date Attended/Checked by Vendor/Technician | Days Delayed by Vendor/Technician | Date Sent for Negotiation | Date Negotiated | Days Since Negotiation Request | Date Approval Requested | Days Since Approval Request | Approved Date | Days Since Approval | Expected Delivery Date | Cost | Status | Actual delivery date | Compliance check | Insert Comment
1 | FAULTY GAS BURNER | LAG, ABULE EGBA | Others | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-08-04 | 2 | 2024-08-04 | 0 | 2024-08-05 | 1 | 2024-08-05 | 2024-08-05 | 227 | 2024-08-05 | 227 |  |  | 2024-08-06 | 65000 | Completed | 2024-08-06 | 1
2 | FAULTY CHIPS FRYER MACHINE | CALABAR, NDIDEM | Others | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-08-02 | 2 | 2024-08-05 | 3 | 2024-08-05 | 0 | 2024-08-04 | 2024-08-04 | 0 | 2024-08-04 | 0 | 2024-08-04 | 0 |  |  | Completed | 2024-08-04 | 0
3 | ESCAPE OF AIR FROM THE FOUR HEAD MACHINE | LAG, FESTAC | Others | Breakdown | HEFHEM | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-08-01 | 4 | 2024-08-01 | 0 | 2024-08-05 | 4 | 2024-08-05 | 2024-08-05 | 0 | 2024-08-05 | 0 | 2024-08-05 | 0 | 2024-08-06 |  | Completed | 2024-08-05 | 1
4 | POLARITY ISSUE | LAG, ENTOURAGE MALL | Others | Breakdown | ISMAIL ODEDELE | OTHERS | OTHERS | 2024-08-04 | 15 | 2024-08-04 | 0 | 2024-08-19 | 15 | 2024-08-19 | 2024-08-19 | 0 | 2024-08-19 | 0 | 2024-08-19 | 0 | 2024-08-19 |  | Completed | 2024-08-19 | 1
5 | REQUEST FOR SERVICING OF GAS BURNER | LAG, OKE-AFA | Routine Servicing | Preventive | BERRADE | GAS CYLINDER | GAS | 2024-08-02 | 4 | 2024-08-02 | 0 | 2024-08-02 | 0 | 2024-08-02 | 2024-08-02 | 0 | 2024-08-05 | 0 | 2024-08-05 | 1 | 2024-08-06 | 56875 | Completed | 2024-08-06 | 1
6 | EQUIPMENTS NOT WORKING UNDER PHCN SUPPLY | LAG, ILUPEJU | Electrical Surge | Breakdown | GBATMO | OTHERS | OTHERS | 2024-08-01 | 7 | 2024-08-01 | 0 | 2024-08-05 | 4 | 2024-08-08 | 2024-08-08 | 0 | 2024-08-08 | 0 | 2024-08-08 | 0 | 2024-08-08 |  | Completed | 2024-08-08 | 1
7 | FAULTY GAS BURNER | LAG, IRE-AKARI | Others | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-08-02 | 4 | 2024-08-05 | 3 | 2024-08-05 | 0 | 2024-08-05 | 2024-08-05 | 0 | 2024-08-05 | 0 | 2024-08-05 | 1 | 2024-08-06 | 76625 | Completed | 2024-08-06 | 1
8 | PEELING OFFICE AND STAFF AREA WALL | LAG, ETERNA LEKKI | Others | Breakdown | WESTERN DESIGN | WALL | BUILDING | 2024-08-02 | 230 | 2024-08-02 | 0 | 2024-08-12 | 10 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-13 | 0 | 2024-08-13 | 219 |  |  | Overdue
9 | CHIP MACHINE SHOWING TOO HOT | LAG, ETERNA LEKKI | Others | Breakdown | KITCHTECH | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-08-05 | 2 | 2024-08-05 | 0 | 2024-08-07 | 2 | 2024-08-07 | 2024-08-07 | 0 | 2024-08-07 | 0 | 2024-08-07 | 0 | 2024-08-08 |  | Completed | 2024-08-07 | 1
10 | COLD ROOM NOT WORKING | LAG, CONOIL IKEJA | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-08-05 | 4 | 2024-08-05 | 0 | 2024-08-07 | 2 | 2024-08-07 | 2024-08-07 | 0 | 2024-08-07 | 0 | 2024-08-07 | 2 | 2024-08-08 |  | Completed | 2024-08-09 | 0
12 | DISLOCATED FREEZER ROOM DOOR | LAG, IDIMU | Others | Breakdown | DYNAMITE | FREEZER ROOM | HVAC | 2024-08-05 | 17 | 2024-08-05 | 0 | 2024-08-05 | 0 | 2024-08-05 | 2024-08-05 | 0 | 2024-08-05 | 0 | 2024-08-05 | 17 | 2024-08-06 |  | Completed | 2024-08-22 | 0
13 | MANAGER OFFICE NOT COOLING | LAG, LEKKI PHASE 1 | Others | Breakdown | G.B BOYEJO | 5HP STANDING AC UNIT 1 | HVAC | 2024-08-05 | 227 | 2024-08-05 | 0 |  | 227 | [9 empty] | Overdue
14 | COLECTROMATIC MACHINE NOT ATTAINING TEMPERATURE | LAG, IPAJA RD | Others | Breakdown | BCE | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-08-05 | 227 | 2024-08-05 | 0 |  | 227 | [9 empty] | Overdue
15 | COLD ROOM NOT WORKING | ILORIN, MM WAY | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-08-02 | 24 | 2024-08-03 | 1 | 2024-08-11 | 8 | 2024-08-11 | 2024-08-11 | 0 | 2024-08-11 | 221 |  |  |  | 299000 | Completed | 2024-08-26 | 0
16 | UNEFFECTIVE COLD ROOM AND FREEZER ROOM | LAG, AWOLOWO | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-08-05 | 23 | 2024-08-05 | 0 | 2024-08-28 | 23 | 2024-08-28 | 2024-08-28 | 0 | 2024-08-28 | 0 | 2024-08-28 | 0 | 2024-08-28 |  | Completed | 2024-08-28 | 1
17 | FAULTY BOH CHILLER AND FIXING OF CHILLER RACK | LAG, AGUNGI | Others | Breakdown |  | OTHERS | OTHERS | 2024-08-05 | 227 |  | 227 | [11 empty] | Overdue
18 | LEAKING OFFICE AC | LAG, IDIMU | Others | Breakdown | G.B BOYEJO | 5HP STANDING AC UNIT 1 | HVAC | 2024-08-05 | 3 | 2024-08-05 | 0 | 2024-08-05 | 0 | 2024-08-05 | 2024-08-05 | 0 | 2024-08-05 | 0 | 2024-08-05 | 3 | 2024-08-06 |  | Completed | 2024-08-08 | 0
19 | DISPLAY HOLDING CABINET NOT CLOSING PROPERLY | LAG, JIBOWU | Others | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-08-05 | 3 | 2024-08-05 | 0 | 2024-08-05 | 0 | 2024-08-05 | 2024-08-05 | 0 | 2024-08-05 | 0 | 2024-08-05 | 3 | 2024-08-07 |  | Completed | 2024-08-08 | 0
20 | SERVICING OF FAT TRAP | LAG, OKE-AFA | Routine Servicing | Preventive | ZEBRA | OTHERS | OTHERS | 2024-08-01 | 231 | 2024-08-01 | 0 | 2024-08-05 | 4 | 2024-08-05 |  | 227 | [6 empty] | Overdue
21 | CHIPS DUMP NOT HEATING UP | LAG, JIBOWU | Others | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-08-05 | 8 | 2024-08-05 | 0 | 2024-08-13 | 8 | 2024-08-13 | 2024-08-13 | 0 | 2024-08-13 | 0 | 2024-08-13 | 0 | 2024-08-13 |  | Completed | 2024-08-13 | 1
22 | WARMER NOT CLOSING PROPERLY | LAG, JIBOWU | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-08-05 | 5 | 2024-08-05 | 0 | 2024-08-10 | 5 | 2024-08-10 | 2024-08-10 | 0 | 2024-08-10 | 0 | 2024-08-10 | 0 |  |  | Completed | 2024-08-10 | 0
23 | GENERATOR SERVICING | PH, RUMUOLA | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-08-02 | 4 | 2024-08-05 | 3 | 2024-08-06 | 1 | 2024-08-06 | 2024-08-06 | 0 | 2024-08-06 | 0 | 2024-08-06 | 0 | 2024-08-06 |  | Completed | 2024-08-06 | 1
24 | DRY STORE AC DRIPPING WATER | LAG, ENTOURAGE MALL | Others | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-08-05 | 227 | 2024-08-05 | 0 |  | 227 | [9 empty] | Overdue
25 | GENERATOR SERVICING | BAYELSA, YENAGOA | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-08-02 | 1 | 2024-08-02 | 0 | 2024-08-03 | 1 | 2024-08-03 | 2024-08-03 | 0 | 2024-08-03 | 0 | 2024-08-03 | 0 | 2024-08-03 |  | Completed | 2024-08-03 | 1
26 | FAULTY CABINET | KANO, AIRPORT RD | Others | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-08-04 | 228 | 2024-08-04 | 0 |  | 228 | [9 empty] | Overdue
28 | FAULTY ROT MACHINE | IMO, WETHERAL RD, OWERRI | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-08-03 | 229 | 2024-08-04 | 1 |  | 228 | [9 empty] | Overdue
29 | UNABLE TO GET ACCESS TO STORE ENTRANCE DUE TO FAULTY ROLLER SHUTTLE | EDO, SAPELE RD, BENIN | Others | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-08-03 | 229 | 2024-08-03 | 0 | 2024-08-22 | 19 | [9 empty] | Overdue
30 | BROKEN WALL TILES | LAG, AWOLOWO |  |  | ACORN | OTHERS | OTHERS | 2024-08-04 | 27 | 2024-08-05 | 1 | 2024-08-10 | 5 | 2024-08-10 | 2024-08-22 | 12 | 2024-08-23 | 5 | 2024-08-28 | 3 | 2024-08-30 | 440875 | Completed | 2024-08-31 | 0
31 | COLD ROOM AND FREZZER ROOM NOT ATTAINING TEMPERATURE | LAG, FESTAC | Others | Breakdown | THIO AND PARTNERS | COLD ROOM UNIT | HVAC | 2024-08-01 | 231 | 2024-08-05 | 4 |  | 227 | [9 empty] | Overdue
32 | FREEZER ROOM NOT ATTAINING TEMPERATURE | PH, ONNE | Others | Breakdown | MOFFEN | FREEZER ROOM | HVAC | 2024-08-02 | 6 | 2024-08-02 | 0 | 2024-08-05 | 3 | 2024-08-05 | 2024-08-05 | 0 | 2024-08-05 | 0 | 2024-08-05 | 3 | 2024-08-07 |  | Completed | 2024-08-08 | 0
33 | BURNT SURGE SUPPLY | LAG, ILUPEJU | Electrical Surge | Breakdown | DAMANT | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-08-02 | 230 | 2024-08-02 | 0 | 2024-08-03 | 1 | 2024-08-03 |  | 229 | [6 empty] | Overdue
34 | SEWAGE EVACUATION | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-08-02 | 1 | 2024-08-02 | 0 | 2024-08-02 | 0 | 2024-08-03 | 2024-08-03 | 0 | 2024-08-03 | 0 | 2024-08-03 | 0 | 2024-08-03 |  | Completed | 2024-08-03 | 1
35 | ROACHES ACTIVITIES | LAG, IKEJA MALL | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-08-02 | 230 | 2024-08-02 | 0 |  | 230 | [9 empty] | Overdue
36 | NEPA LIGHT NOT ENTERING STORE | LAG, MARINA | Electrical Surge | Breakdown | ISMAIL ODEDELE | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-08-02 | 1 | 2024-08-02 | 0 | 2024-08-03 | 1 | 2024-08-03 | 2024-08-03 | 0 | 2024-08-03 | 0 | 2024-08-03 | 0 | 2024-08-03 |  | Completed | 2024-08-03 | 1
37 | FAULTY FREEZER ROOM | ILORIN, OFFA GARAGE | Others | Breakdown | BCE | FREEZER ROOM | HVAC | 2024-08-02 | 230 | 2024-08-02 | 0 |  | 230 | [9 empty] | Overdue
38 | CRACK BROKEN COLDROOM FLOOR TILES | LAG, OKE-AFA | Others | Breakdown | VENYS | COLD ROOM UNIT | HVAC | 2024-08-02 | 230 | 2024-08-02 | 0 |  | 230 | [9 empty] | Overdue
39 | GENERATOR DUE FOR SERVICING | PPU Tombia | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-08-01 | 2 | 2024-08-02 | 1 | 2024-08-03 | 1 | 2024-08-03 | 2024-08-03 | 0 | 2024-08-03 | 0 | 2024-08-03 | 0 |  |  | Completed | 2024-08-03 | 0
40 | LEAKING WINDOW ROLLER SHUTTER | ABIA, AZIKIWE RD, UMUAHIA | Others | Breakdown | BASSCOMM | WINDOW ROLLER SHUTTER | SECURITY | 2024-08-01 | 231 | 2024-08-01 | 0 |  | 231 | [9 empty] | Overdue
41 | FREEZER ROOM NOT ATTAINING TEMPERATURE | PPU Oniru | Others | Breakdown |  | FREEZER ROOM | HVAC | 2024-08-02 | 230 |  | 230 | [11 empty] | Overdue
42 | FAULTY ROLLER SHUTTER | LAG, MAGODO | Others | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-08-06 | 79 | 2024-08-06 | 0 | 2024-08-09 | 3 | 2024-08-09 | 2024-08-09 | 0 | 2024-10-07 | 8 | 2024-10-15 | 9 | 2024-10-24 | 268981.86 | Completed | 2024-10-24 | 1
43 | FILLED SEPTIC TANK | LAG, IDI-IROKO RD | Others | Breakdown | MOOLIGHT | SEPTIC TANK | EVACUATION | 2024-08-06 | 43 | 2024-08-06 | 0 | 2024-09-18 | 43 | 2024-09-18 | 2024-09-18 | 0 | 2024-09-18 | 0 | 2024-09-18 | 0 |  |  | Completed | 2024-09-18 | 0
44 | WATER DAMAGED PANEL REPLACEMENT FOR COLD ROOM AND FREEZER ROOM | LAG, OBA AKRAN | Others | Breakdown | BCE | FREEZER ROOM | HVAC | 2024-08-06 | 226 | 2024-08-06 | 0 | 2024-08-06 | 0 | 2024-08-06 | 2024-08-06 | 0 | 2024-08-06 | 226 |  |  |  |  | Overdue
45 | PRESSURE FRYER NOT ATTAINING TEMPERATURE | LAG, DIYA STREET | Others | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-08-06 | 7 | 2024-08-06 | 0 | 2024-08-12 | 6 | 2024-12-08 | 2024-08-12 | #REF! | 2024-08-12 | 0 | 2024-08-12 | 1 |  |  | Completed | 2024-08-13 | 0
46 | BLOWN CABINET BULB | LAG, MARINA | Electrical Surge | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-08-06 | 4 | 2024-08-06 | 0 | 2024-08-08 | 2 | 2024-08-08 | 2024-08-08 | 0 | 2024-08-08 | 0 | 2024-08-08 |  | 2024-08-09 |  | Completed | 2024-08-10 | 0
47 | CLEANING OF CHICKEN REPUBLIC SIGNAGE AT CR-BADORE | LAG, BADORE | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-08-05 | 227 | 2024-08-05 | 0 | 2024-08-08 | 3 | 2024-08-08 | 2024-08-08 | 0 | 2024-08-08 | 224 |  |  |  | 182750 | Overdue
48 | HOT WATER NOT ATTAINING TEMERATURE | LAG, LEKKI PHASE 1 | Others | Breakdown | PRO EQUIP | OTHERS | OTHERS | 2024-08-05 | 227 | 2024-08-05 | 0 | 2024-08-09 | 4 | [9 empty] | Overdue
49 | OPENED WALL TILE | LAG, LEKKI PHASE 1 | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-08-05 | 227 | 2024-08-06 | 1 | 2024-08-06 | 0 | [9 empty] | Overdue
50 | FAULTY SOAP DISPENSER IN THE CUSTOMERS REST ROOM. | LAG, LEKKI PHASE 1 | Others | Breakdown | PRO EQUIP | OTHERS | OTHERS | 2024-08-06 | 226 | 2024-08-06 | 0 |  | 226 | [9 empty] | Overdue
51 | FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, ETERNA LEKKI | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-08-05 | 227 | 2024-08-05 | 0 | 2024-08-08 | 3 | [9 empty] | Overdue
52 | FAULTY ROT MACHINE | LAG, TOTAL LEKKI | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-08-01 | 15 | 2024-08-01 | 0 | 2024-08-05 | 4 | 2024-08-05 | 2024-08-05 | 0 | 2024-08-08 | 5 | 2024-08-13 | 3 |  |  | Completed | 2024-08-16 | 0
53 | BROKEN PIPE( GREASE TRAP LEAKING) | LAG, MAGODO | Others | Breakdown | ADEREMI | OTHERS | OTHERS | 2024-08-03 | 6 | 2024-08-04 | 1 | 2024-08-07 | 3 | 2024-08-07 | 2024-08-07 | 0 | 2024-08-07 | 0 | 2024-08-07 | 2 |  |  | Completed | 2024-08-09 | 0
54 | FAULTY HAND DRYER | LAG, OBA AKRAN | Others | Breakdown | PROPEARJEFF | HAND DRYER LOBBY | ELECTRICAL | 2024-08-07 | 225 | 2024-08-07 | 0 |  | 225 | [9 empty] | Overdue
55 | LEAKING PIPE | LAG, OSOLOWAY | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-08-07 | 225 | 2024-08-07 | 0 |  | 225 | [9 empty] | Overdue
56 | BAD TOILET SIT COVER | LAG, MARINA | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-08-06 | 226 | 2024-08-06 | 0 |  | 226 | [9 empty] | Overdue
57 | BURNT CABINET LAMP HOLDER AND DEAD CABINET BULB | LAG, MMA2 | Electrical Surge | Breakdown | KITCHTECH | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-08-05 | 8 | 2024-08-05 | 0 | 2024-08-13 | 8 | 2024-08-13 | 2024-08-13 | 0 | 2024-08-13 | 0 | 2024-08-13 | 0 |  |  | Completed | 2024-08-13 | 0
58 | NO RUNNING WATER IN THE STORE | LAG, AJOSE ADEOGUN | Others | Breakdown | JOEL OMOTOSHO | WATER TREATMENT PLANT BLD | BUILDING | 2024-08-07 | 1 | 2024-08-07 | 0 | 2024-08-07 | 0 | 2024-08-07 | 2024-08-07 | 0 | 2024-08-07 | 0 | 2024-08-07 | 1 | 2024-08-08 |  | Completed | 2024-08-08 | 1
59 | REPLACEMENT OF DOOR HANDLE | LAG, AWOLOWO 2 | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-08-07 | 3 | 2024-08-07 | 0 | 2024-08-09 | 2 | 2024-08-09 | 2024-08-09 | 0 | 2024-08-09 | 0 | 2024-08-09 | 1 |  |  | Completed | 2024-08-10 | 0
60 | STORE FAN NOT WORKING |  | Electrical Surge | Breakdown | ADEREMI KAZEEM | OTHERS | OTHERS | 2024-08-07 | 225 | 2024-08-07 | 0 | 2024-08-07 | 0 | [9 empty] | Overdue
61 | ALL LOBBY AC NOT WORKING | IBADAN, MOKOLA | Others | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-08-05 | 11 | 2024-08-05 | 0 | 2024-08-07 | 2 | 2024-08-07 | 2024-08-07 | 0 | 2024-08-07 | 0 | 2024-08-07 | 9 |  | 330000 | Completed | 2024-08-16 | 0
62 | BURNT PHCN CABLE | LAG, FREEDOMWAY | Electrical Surge | Breakdown | GBATMO | OTHERS | OTHERS | 2024-08-06 | 8 | 2024-08-06 | 0 | 2024-08-07 | 1 | 2024-08-07 | 2024-08-07 | 0 | 2024-08-07 | 6 | 2024-08-13 | 1 | 2024-08-14 | 580000 | Completed | 2024-08-14 | 1
63 | FAULTY FAT TRAP SEIVE | LAG, AWOLOWO 2 | Others | Breakdown | ZEBRA | OTHERS | OTHERS | 2024-08-07 | 225 | 2024-08-07 | 0 | 2024-08-08 | 1 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 220 |  |  |  | 81700 | Overdue
64 | GREASE TRAP NOT WORKING | LAG, AGUNGI | Others | Breakdown | ZEBRA | OTHERS | OTHERS | 2024-08-06 | 226 | 2024-08-07 | 1 | 2024-08-08 | 1 | [9 empty] | Overdue
65 | BROKEN WALLS AND FLOORS | LAG, ETERNA LEKKI | Others | Breakdown | VENYS | OTHERS | OTHERS | 2024-08-05 | 227 | 2024-08-05 | 0 | 2024-08-08 | 3 | 2024-08-08 | 2024-08-08 | 0 | 2024-08-08 | 0 | 2024-08-08 | 224 |  |  | Overdue
66 | FAULTY INVERTER BATTRIES | PH, RUKPOKWU | Others | Breakdown | PETOJO4STAR | INVERTER BATTERIES | INVERTER | 2024-08-04 | 228 | 2024-08-04 | 0 | 2024-08-08 | 4 | 2024-08-13 |  | 219 | [6 empty] | Overdue
67 | BROKEN TILES PX FAGBA |  | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-08-07 | 225 | 2024-08-07 | 0 | 2024-08-07 | 0 | 2024-08-08 |  | 224 | [5 empty] | 64500 | Overdue
68 | FAULTY CHIPS FRYER | ABIA, FACTORY RD, ABA | Others | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-08-07 | 5 | 2024-08-07 | 0 | 2024-08-08 | 1 | 2024-08-08 | 2024-08-08 | 0 | 2024-08-08 | 1 | 2024-08-09 | 3 |  |  | Completed | 2024-08-12 | 0
69 | FAULTY DISPLAY CABINET | LAG, IDIMU | Others | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-08-09 | 223 | 2024-08-09 | 0 |  | 223 | [9 empty] | Overdue
70 | PX IGANDO DETACHED KIOSKS |  | Others | Breakdown | VENYS | OTHERS | OTHERS | 2024-08-05 | 7 | 2024-08-06 | 1 | 2024-08-06 | 0 | 2024-08-07 | 2024-08-07 | 0 | 2024-08-07 | 2 | 2024-08-09 |  |  | 95000 | Completed | 2024-08-12 | 0
71 | FAULTY GREASE TRAP | LAG, OBA AKRAN | Others | Breakdown | PENTECOSTAL | GREASE TRAP | GREASE_TRAP | 2024-08-09 | 223 | 2024-08-09 | 0 | 2024-08-13 | 4 | 2024-08-13 | 2024-08-15 | 2 | 2024-08-15 | 217 |  |  |  | 500000 | Overdue
72 | BULBS AND INSECTOCUTORS NOT TURNING ON PX | LAG, OKOTA | Electrical Surge | Breakdown | FRIDAY | INSECT KILLER BOH | ELECTRICAL | 2024-08-09 | 223 | 2024-08-09 | 0 |  | 223 | [9 empty] | Overdue
73 | FLUNTUATING BULB AT CASH POINT | LAG, OBA AKRAN | Electrical Surge | Breakdown | TIMILEYIN | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-08-09 | 1 | 2024-08-09 | 0 | 2024-08-10 | 1 | 2024-08-10 | 2024-08-10 | 0 | 2024-08-10 | 0 | 2024-08-10 | 0 |  |  | Completed | 2024-08-10 | 0
74 | LEAKING COLD ROOM FLOOR | ILORIN, OFFA GARAGE | Others | Breakdown | BCE | COLD ROOM UNIT | HVAC | 2024-08-08 | 224 | 2024-08-08 | 0 | 2024-08-28 | 20 | [9 empty] | Overdue
75 | UPDATE ON ELETRICAL SHOCK IN THE STORE | LAG, MAGODO | Electrical Surge | Breakdown | KOLA | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-08-06 | 2 | 2024-08-08 | 2 | 2024-08-08 | 0 | 2024-08-08 | 2024-08-08 | 0 | 2024-08-08 | 0 | 2024-08-08 | 0 |  |  | Completed | 2024-08-08 | 0
76 | REQUEST FOR TWO INDUSTRIAL SOCKET | LAG, MARINA | Electrical Surge | Breakdown | ISMAIL ODEDELE | OTHERS | OTHERS | 2024-08-07 | 5 | 2024-08-08 | 1 | 2024-08-09 | 1 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 0 |  |  | Completed | 2024-08-12 | 0
77 | POWER SURGE IN THE STORE | LAG, WAREHOUSE RD, APAPA | Electrical Surge | Breakdown |  | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-08-06 | 226 | 2024-08-08 | 2 |  | 224 | [9 empty] | Overdue
78 | FAULTY ROLLER SHUTTER | PH, WOJI | Others | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-08-07 | 225 | 2024-08-08 | 1 | 2024-08-09 | 1 | [9 empty] | Overdue
79 | REPLACEMENT OF DRAINAGE COVER | LAG, AWOLOWO 2 | Others | Breakdown | MODEL | DRAIN COVER | BUILDING | 2024-08-07 | 225 | 2024-08-08 | 1 | 2024-08-19 | 11 | 2024-08-19 | 2024-08-22 | 3 | 2024-08-23 | 33 | 2024-09-25 | 176 |  | 650000 | Overdue
80 | CABINET NOT ATTAINING | LAG, AJOSE ADEOGUN | Electrical Surge | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-08-06 | 226 | 2024-08-06 | 0 |  | 226 | [9 empty] | Overdue
81 | DROP LIGHT NOT WORKING PX FAGBA |  | Electrical Surge | Breakdown | TIMILEYIN | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-08-08 | 2 | 2024-08-08 | 0 | 2024-08-10 | 2 | 2024-08-10 | 2024-08-10 | 0 | 2024-08-10 | 0 | 2024-08-10 | 0 |  |  | Completed | 2024-08-10 | 0
82 | FAULTY ICE CREAM MACHINE | NIGER, SULEJA | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-08-06 | 226 | 2024-08-06 | 0 | 2024-08-07 | 1 | 2024-08-07 | 2024-08-07 | 0 | 2024-08-08 | 0 | 2024-08-08 | 224 |  |  | Overdue
83 | PITTED INTERLOCK AT CAR PARK | LAG, JOEL OGUNNAIKE | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-08-05 | 227 | 2024-08-06 | 1 | 2024-08-07 | 1 | 2024-08-07 | 2024-08-09 | 2 | 2024-08-09 | 223 |  |  |  | 602000 | Overdue
84 | BROKEN BOH CHILLER BASED COVER | LAG, SKYMALL | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-08-09 | 223 | 2024-08-09 | 0 |  | 223 | [9 empty] | Overdue
85 | ELECTRICAL MATERIALS FOR OK ILEWO | OGUN, OKE-ILEWO | Electrical Surge | Breakdown | RANEX4WARD | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-08-09 | 223 | 2024-08-09 | 0 | 2024-08-09 | 0 | 2024-08-09 | 2024-08-09 | 0 | 2024-08-09 | 0 | 2024-08-09 | 223 |  | 177375 | Overdue
86 | ROLLER SHUTTER NOT WORKING | LAG, OGUNLANA DRIVE | Others | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-08-08 | 1 | 2024-08-08 | 0 | 2024-08-08 | 0 | 2024-08-08 | 2024-08-08 | 0 | 2024-08-08 | 0 | 2024-08-08 | 1 |  |  | Completed | 2024-08-09 | 0
87 | FAULTY CUSTOMERS RESTROOM | LAG, ONIRU | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-08-09 | 223 | 2024-08-09 | 0 |  | 223 | [9 empty] | Overdue
88 | OPENING AT THE BASE OF BOH NETTED DOOR | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | BAMOCOON | OTHERS | OTHERS | 2024-08-07 | 225 | 2024-08-09 | 2 |  | 223 | [9 empty] | Overdue
89 | FAULTY ROT MACHINE | LAG, TOTAL LEKKI | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-08-01 | 231 | 2024-08-01 | 0 | 2024-08-05 | 4 | 2024-08-07 | 2024-08-07 | 0 | 2024-08-08 | 5 | 2024-08-13 | 219 |  |  | Overdue
90 | BOH CHILLER HANDLE | LAG, AWOLOWO | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-08-06 | 226 | 2024-08-06 | 0 |  | 226 | [9 empty] | Overdue
91 | FAULTY SECURITY LIGHT | LAG, VGC | Electrical Surge | Breakdown | ADEREMI KAZEEM | DROPPING LIGHT | ELECTRICAL | 2024-08-10 | 222 | 2024-08-10 | 0 |  | 222 | [9 empty] | Overdue
92 | FAULTY KITCHEN WARMER | LAG, VGC | Others | Breakdown | ADEREMI KAZEEM | OTHERS | OTHERS | 2024-08-09 | 6 | 2024-08-09 | 0 | 2024-08-14 | 5 | 2024-08-14 | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 | 1 |  |  | Completed | 2024-08-15 | 0
93 | STUCKER ROLLER SHUTTER PX | LAG, VGC | Others | Breakdown | VENYS | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-08-11 | 5 | 2024-08-11 | 0 | 2024-08-14 | 3 | 2024-08-15 | 2024-08-15 | 0 | 2024-08-15 | 0 | 2024-08-15 | 1 | 2024-08-16 | 66500 | Completed | 2024-08-16 | 1
94 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | LAG, MOBIL OGBA | Others | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-08-08 | 224 | 2024-08-08 | 0 | 2024-08-12 | 4 | [9 empty] | Overdue
95 | DRAINAGE BLOCKED | LAG, EKORO | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-08-09 | 4 | 2024-08-10 | 1 | 2024-08-10 | 0 | 2024-08-10 | 2024-08-10 | 0 | 2024-08-10 | 0 | 2024-08-10 | 3 | 2024-08-12 |  | Completed | 2024-08-13 | 0
96 | FAULTY ROLLER SHUTTER | LAG, IPAJA RD | Others | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-08-06 | 9 | 2024-08-06 | 0 | 2024-08-12 | 6 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 3 |  |  | Completed | 2024-08-15 | 0
97 | FAULTY MALE URINAL | LAG, AWOLOWO | Others | Breakdown | JOEL OMOTOSHO | OTHERS | OTHERS | 2024-08-10 | 2 | 2024-08-10 | 0 | 2024-08-12 | 2 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 0 |  |  | Completed | 2024-08-12 | 0
98 | FAULTY 4 HEAD MACHINE START BUTTON | LAG, OPEBI | Others | Breakdown | BCE | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-08-10 | 2 | 2024-08-10 | 0 | 2024-08-12 | 2 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 |  | Completed | 2024-08-12 | 1
99 | MAINTENANACE ISSUE IN STORE | OYO, OGBOMOSHO | Others | Breakdown | IFEONU ECHEZONA | OTHERS | OTHERS | 2024-08-09 | 4 | 2024-08-09 | 0 | 2024-08-12 | 3 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 1 |  |  | Completed | 2024-08-13 | 0
100 | STIFNESS OF ENTRANCE DOOR | LAG, ALIMOSHO | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-08-12 | 1 | 2024-08-12 | 0 | 2024-08-13 | 1 | 2024-08-13 | 2024-08-13 | 0 | 2024-08-13 | 0 | 2024-08-13 | 0 | 2024-08-13 |  | Completed | 2024-08-13 | 1
101 | GENERATOR ISSUE | ABIA, OGBOR HILLS | Others | Breakdown | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-08-10 | 2 | 2024-08-10 | 0 | 2024-08-10 | 0 | 2024-08-10 | 2024-08-10 | 0 | 2024-08-10 | 0 | 2024-08-10 | 2 |  |  | Completed | 2024-08-12 | 0
102 | DETACHED SUSPENDED LOBBY LAMP | LAG, MMA2 | Others | Breakdown | TAYO ALBERT | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-08-08 | 4 | 2024-08-08 | 0 | 2024-08-12 | 4 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 0 |  |  | Completed | 2024-08-12 | 0
103 | FAULTY ROLLER SHUTTER REMOTE | LAG, IRE-AKARI | Others | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-08-11 | 221 | 2024-08-11 | 0 | 2024-08-12 | 1 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-14 | 218 |  |  |  |  | Overdue
104 | BROKEN DRAIN COVER | LAG, AJOSE ADEOGUN | Others | Breakdown | TONA OGUNS | DRAIN COVER | BUILDING | 2024-08-09 | 223 | 2024-08-09 | 0 |  | 223 | 2024-08-12 |  | 220 | [6 empty] | Overdue
105 | FAULTY ROLLER SHUTTER | LAG, ENTOURAGE MALL | Others | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-08-09 | 223 | 2024-08-10 | 1 | 2024-08-12 | 2 | [9 empty] | Overdue
106 | FAULTY ROLLER SHUTTER AT THE FRONT OF HOUSE | LAG, LATEEF JAKANDE | Others | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-08-09 | 223 | 2024-08-10 | 1 | 2024-08-12 | 2 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-14 | 8 | 2024-08-22 | 210 |  |  | Overdue
107 | STAFF RESTROOM DOORS DETACHED | EKORO | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-08-07 | 225 | 2024-08-07 | 0 |  | 225 | [9 empty] | Overdue
108 | UNDERGROUND LINKAGE IN THE DRY STORE | LAG, AJOSE ADEOGUN | Others | Breakdown | BASSCOMM | OTHERS | OTHERS | 2024-08-07 | 5 | 2024-08-07 | 0 | 2024-08-12 | 5 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 0 |  |  | Completed | 2024-08-12 | 0
109 | GENERATOR SERVICING | LAG, AJOSE ADEOGUN | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-08-07 | 1 | 2024-08-07 | 0 | 2024-08-08 | 1 | 2024-08-08 | 2024-08-08 | 0 | 2024-08-08 | 0 | 2024-08-08 | 0 |  |  | Completed | 2024-08-08 | 0
110 | MALE AND FEMALE RESTROOM WC NOT FLUSHING | LAG, AJOSE ADEOGUN | Others | Breakdown | JOEL OMOTOSHO | OTHERS | OTHERS | 2024-08-07 | 1 | 2024-08-07 | 0 | 2024-08-08 | 1 | 2024-08-08 | 2024-08-08 | 0 | 2024-08-08 | 0 | 2024-08-08 | 0 |  |  | Completed | 2024-08-08 | 0
111 | PEELED LOBBY CHAIR | LAG, AJOSE ADEOGUN | Others | Breakdown | MATOLAD | CUSTOMER CHAIR | FURNITURE | 2024-08-09 | 1 | 2024-08-09 | 0 | 2024-08-10 | 1 | 2024-08-10 | 2024-08-10 | 0 | 2024-08-10 | 0 | 2024-08-10 | 0 |  |  | Completed | 2024-08-10 | 0
112 | RUSTY COLD & FREEZER ROOM DOOR | LAG, AJOSE ADEOGUN | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-08-09 | 223 | 2024-08-09 | 0 | 2024-08-14 | 5 | 2024-08-14 | 2024-08-15 | 1 | 2024-08-22 | 210 |  |  |  | 85000 | Overdue
113 | STORE WITH CRITICAL FILTRATION MEDIA REPLACEMENT | LAG, AWOLOWO | Others | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-08-06 | 226 | 2024-08-06 | 0 | 2024-08-06 | 0 | 2024-08-06 | 2024-08-11 | 5 | 2024-08-12 | 220 |  |  |  | 710000 | Overdue
114 | STORE WITH CRITICAL FILTRATION MEDIA REPLACEMENT | LAG, OBA AKRAN | Others | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-08-06 | 226 | 2024-08-06 | 0 | 2024-08-06 | 0 | 2024-08-06 | 2024-08-11 | 5 | [5 empty] | 1000000 | Overdue
115 | STORE WITH CRITICAL FILTRATION MEDIA REPLACEMENT | LAG, EJIGBO | Others | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-08-06 | 226 | 2024-08-06 | 0 | 2024-08-06 | 0 | 2024-08-06 | 2024-08-11 | 5 | [5 empty] | 950000 | Overdue
116 | STORE WITH CRITICAL FILTRATION MEDIA REPLACEMENT | LAG, HEYDEN ALAPERE | Others | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-08-06 | 226 | 2024-08-06 | 0 | 2024-08-06 | 0 | 2024-08-06 | 2024-08-11 | 5 | [5 empty] | 950000 | Overdue
117 | STORE WITH CRITICAL FILTRATION MEDIA REPLACEMENT | LAG, MARINA | Others | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-08-06 | 226 | 2024-08-06 | 0 | 2024-08-06 | 0 | 2024-08-06 | 2024-08-11 | 5 | [5 empty] | 900000 | Overdue
118 | PEST WALK THROUGH REPORT | LAG, EJIGBO | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-08-11 | 221 | 2024-08-11 | 0 |  | 221 | [9 empty] | Overdue
119 | GENRATOR DUE FOR SERVICE | LAG, VGC | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-08-11 | 221 | 2024-08-11 | 0 | 2024-08-12 | 1 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 220 |  |  | Overdue
120 | FAULTY SIX HEAD MACHIN LID GASKET | EDO, UGBOWO, BENIN | Others | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-08-11 | 221 | 2024-08-11 | 0 |  | 221 | [9 empty] | Overdue
121 | BROKEN CABINET GLASS | LAG, JIBOWU | Others | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-08-06 | 226 | 2024-08-06 | 0 |  | 226 | [9 empty] | Overdue
122 | BAD SELF DOOR | LAG, ETERNA LEKKI | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-08-04 | 228 | 2024-08-05 | 1 | 2024-08-11 | 6 | [9 empty] | Overdue
123 | BROKEN DOUGHNUT DISPLAY CABINET GLASS | LAG, BODE THOMAS | Others | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-08-11 | 221 | 2024-08-11 | 0 |  | 221 | [9 empty] | Overdue
124 | AC DRIPPING WATER | LAG, AWOLOWO | Others | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-08-02 | 230 | 2024-08-04 | 2 |  | 228 | [9 empty] | Overdue
125 | STORE INTERIOR PAINTING | LAG, AWOLOWO 2 | Others | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-08-12 | 220 | 2024-08-12 | 0 | 2024-08-20 | 8 | [9 empty] | Overdue
126 | CABINET WITH LOSE/SPARKLING ELETRICAL WIRE | LAG, FESTAC | Electrical Surge | Breakdown | HEFHEM | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-08-10 | 222 | 2024-08-10 | 0 | 2024-08-15 | 5 | [9 empty] | Overdue
127 | BAD WARMER GASKET | LAG, FESTAC | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-08-09 | 4 | 2024-08-10 | 1 | 2024-08-10 | 0 | 2024-08-10 | 2024-08-10 | 0 | 2024-08-10 | 0 | 2024-08-10 | 3 |  |  | Completed | 2024-08-13 | 0
128 | CHEST FREEZER NOT ATTAINING TEMPERATURE | LAG, AJAH | Others | Breakdown | THIO AND PARTNERS | CHEST FREEZER | HVAC | 2024-08-09 | 223 | 2024-08-10 | 1 |  | 222 | [9 empty] | Overdue
129 | BROKEN SANITIZER DISPENSER | LAG, AWOLOWO | Others | Breakdown | JOEL OMOTOSHO | OTHERS | OTHERS | 2024-08-06 | 226 | 2024-08-06 | 0 |  | 226 | [9 empty] | Overdue
130 | FAULTY ICE CREAM MACHINE | LAG, DOMINO E-CENTRE | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-08-01 | 231 | 2024-08-01 | 0 |  | 231 | [9 empty] | Overdue
131 | FAULTY FAT TRAP SEIVE | LAG, AWOLOWO 2 | Others | Breakdown | ZEBRA | OTHERS | OTHERS | 2024-08-07 | 225 | 2024-08-07 | 0 | 2024-08-11 | 4 | 2024-08-11 | 2024-08-11 | 0 | 2024-08-12 | 220 |  |  |  | 81700 | Overdue
132 | FAULTY GAS BURNER | LAG, OGUNLANA DRIVE | Others | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-08-12 | 1 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 1 |  | 46500 | Completed | 2024-08-13 | 0
133 | FAULTY HAND WASH TAP | LAG, ILUPEJU | Others | Breakdown | ADEREMI WAHAB | LOBBY WASH HAND BASIN | PLUMBING | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 0 |  |  | Completed | 2024-08-12 | 0
134 | GENERATOR SERVICING | OYO, OWODE | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-08-03 | 5 | 2024-08-03 | 0 | 2024-08-08 | 5 | 2024-08-08 | 2024-08-08 | 0 | 2024-08-08 | 0 | 2024-08-08 | 0 |  | 219138.75 | Completed | 2024-08-08 | 0
135 | COLD ROOM NOT ATTAINING TMPERATURE | LAG, AGUNGI | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-08-07 | 225 | 2024-08-07 | 0 |  | 225 | [9 empty] | Overdue
136 | BAD BOH UPRIGHT FRIDGE BULB | LAG, IDI-IROKO RD | Others | Breakdown | TAYO ALBERT | OTHERS | OTHERS | 2024-08-12 | 220 | 2024-08-12 | 0 | 2024-08-12 | 0 | [9 empty] | Overdue
137 | FAULTY GAS BURNER | LAG, FESTAC | Others | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-08-12 | 220 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 220 |  | 56500 | Overdue
138 | RAT DROPPINGS AND DEAD COCK ROACHES IN STORE | LAG, FREEDOMWAY | Others | Breakdown | BAMOCOON | OTHERS | OTHERS | 2024-08-12 | 220 | 2024-08-12 | 0 | 2024-08-12 | 0 | [9 empty] | Overdue
139 | REQUEST FOR PAINTING | LAG, MARINA | Others | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-08-06 | 226 | 2024-08-06 | 0 | 2024-08-12 | 6 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-13 | 219 |  |  |  | 400000 | Overdue
140 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | LAG, BADORE | Others | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-08-12 | 220 | 2024-08-12 | 0 |  | 220 | [9 empty] | Overdue
141 | BAD BULB ON PRODUCTION FLOOR | LAG, IKEJA MALL | Electrical Surge | Breakdown | TAYO ALBERT | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-08-12 | 2 | 2024-08-13 | 1 | 2024-08-14 | 1 | 2024-08-14 | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 |  | Completed | 2024-08-14 | 1
142 | FREEZER ROOM NOT ATTAINING TEMPERATURE | IBADAN, BODIJA | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-08-13 | 219 | 2024-08-13 | 0 |  | 219 | [9 empty] | Overdue
143 | FAULTY MOBILE WARMER DOOR HANDLE. LIMCA ROAD ONITSHA | ANAMBRA, LIMCA RD, ONITSHA | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-08-13 | 4 | 2024-08-13 | 0 | 2024-08-15 | 2 | 2024-08-15 | 2024-08-15 | 0 | 2024-08-15 | 0 | 2024-08-15 | 2 |  |  | Completed | 2024-08-17 | 0
144 | GENERATOR DUE FOR SERVICE | LAG, VGC | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-08-11 | 3 | 2024-08-11 | 0 | 2024-08-12 | 1 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 2 |  |  | Completed | 2024-08-14 | 0
145 | ICE CREAM MACHINE NOT WORKING | LAG, IKEJA MALL | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-08-13 | 219 | 2024-08-13 | 0 |  | 219 | [9 empty] | Overdue
146 | GENERATOR DUE FOR SERVICING | LAG, HEYDEN IPAJA | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-08-13 | 2 | 2024-08-13 | 0 | 2024-08-15 | 2 | 2024-08-15 | 2024-08-15 | 0 | 2024-08-15 | 0 | 2024-08-15 | 0 |  |  | Completed | 2024-08-15 | 0
147 | OPEN WALL AT THE MALE RESTROOM | LAG, JOEL OGUNNAIKE | Others | Breakdown | ACORN | WALL | BUILDING | 2024-08-12 | 2 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-13 | 2024-08-13 | 0 | 2024-08-13 | 1 | 2024-08-14 | 0 |  |  | Completed | 2024-08-14 | 0
148 | PAINTING | LAG, IKEJA MALL | Others | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-08-12 | 220 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 220 |  |  |  |  | Overdue
149 | BROKEN FREEZER ROOM FLOOR TILES | LAG, BODE THOMAS | Others | Breakdown | TRIPPLE O | FREEZER ROOM | HVAC | 2024-08-13 | 219 | 2024-08-13 | 0 |  | 219 | [9 empty] | Overdue
150 | FREEZING COLDROOM | LAG, AGUNGI | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-08-13 | 3 | 2024-08-14 | 1 | 2024-08-15 | 1 | 2024-08-15 | 2024-08-15 | 0 | 2024-08-15 | 0 | 2024-08-15 | 1 | 2024-08-16 |  | Completed | 2024-08-16 | 1
151 | FAULTY DISPLAY CABINET DETACHED FLAP | LAG, AGUNGI | Others | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-08-09 | 223 | 2024-08-10 | 1 |  | 222 | [9 empty] | Overdue
152 | ICE CREAM MACHINE SERVICING | CALABAR, NDIDEM | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-08-14 | 1 | 2024-08-14 | 0 | 2024-08-15 | 1 | 2024-08-15 | 2024-08-15 | 0 | 2024-08-15 | 0 | 2024-08-15 | 0 |  |  | Completed | 2024-08-15 | 0
153 | FAULTY MOBILE WARMR DOOR HANDLE | ANAMBRA, LIMCA RD, ONITSHA | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-08-13 | 4 | 2024-08-13 | 0 | 2024-08-15 | 2 | 2024-08-15 | 2024-08-15 | 0 | 2024-08-15 | 0 | 2024-08-15 | 2 |  |  | Completed | 2024-08-17 | 0
154 | ROTISSERIE MACHINE WORKING IN FAHRENHEIT INSTEAD OF CELSIUS | LAG, ABULE EGBA | Others | Breakdown | HEFHEM | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-08-03 | 14 | 2024-08-03 | 0 | 2024-08-15 | 12 | 2024-08-15 | 2024-08-15 | 0 | 2024-08-15 | 0 | 2024-08-15 | 2 |  |  | Completed | 2024-08-17 | 0
155 | ELECTRIC HARZARD IN THE STORE | LAG, ENTOURAGE MALL | Others | Breakdown | ISMAIL ODEDELE | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-08-07 | 8 | 2024-08-07 | 0 | 2024-08-15 | 8 | 2024-08-15 | 2024-08-15 | 0 | 2024-08-15 | 0 | 2024-08-15 | 0 |  |  | Completed | 2024-08-15 | 0
156 | PEEL OFF WALL PAINT AT DRY STORE | LAG, JOEL OGUNNAIKE | Others | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-08-05 | 227 | 2024-08-05 | 0 | 2024-08-26 | 21 | [9 empty] | Overdue
157 | FAULTY ROT MACHINE | LAG, MARINA | Others | Breakdown | KITCHTECH | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-08-14 | 1 | 2024-08-14 | 0 | 2024-08-15 | 1 | 2024-08-15 | 2024-08-15 | 0 | 2024-08-15 | 0 | 2024-08-15 | 0 | 2024-08-15 |  | Completed | 2024-08-15 | 1
158 | FAULTY LOBBY AC | LAG, MAGODO | Others | Breakdown | TRIPPLE O | 5HP STANDING AC UNIT 1 | HVAC | 2024-08-08 | 24 | 2024-08-08 | 0 | 2024-08-12 | 4 | 2024-08-12 | 2024-08-15 | 3 | 2024-08-15 | 14 | 2024-08-29 | 3 | 2024-08-30 | 450000 | Completed | 2024-09-01 | 0
159 | CHIPS OPEN FRYER NOT HEATING UP | LAG, VGC | Others | Breakdown | KITCHTECH | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-08-14 | 1 | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 | 1 |  |  | Completed | 2024-08-15 | 0
160 | CHEST FREEZER NOT ATTAINING TEMPERATURE | LAG, MMA2 | Others | Breakdown | TONA OGUNS | CHEST FREEZER | HVAC | 2024-08-14 | 1 | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 | 1 |  |  | Completed | 2024-08-15 | 0
161 | COLDROOM AND FREEZER ROOM NOT ATTAINING TEMPRATURE | LAG, OPEBI | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-08-14 | 1 | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 | 1 |  |  | Completed | 2024-08-15 | 0
162 | BROKEN WALL TILES AT THE STORE | LAG, FESTAC | Others | Breakdown | ARISMAYA | OTHERS | OTHERS | 2024-08-09 | 223 | 2024-08-09 | 0 | 2024-08-15 | 6 | 2024-09-11 | 2024-09-20 | 9 | 2024-09-20 | 181 |  |  |  | 400000 | Overdue
163 | LOBBY AIR CURTAIN | LAG, IDIMU | Others | Breakdown | EKNOR | OTHERS | OTHERS | 2024-08-05 | 21 | 2024-08-05 | 0 | 2024-08-08 | 3 | 2024-08-09 | 2024-08-14 | 5 | 2024-08-14 | 0 | 2024-08-14 | 12 |  | 829840 | Completed | 2024-08-26 | 0
164 | BROKEN ENTRANCE DOOR GLASS | IBADAN, VENTURA MALL | Others | Breakdown | DE FAVOUR | OTHERS | OTHERS | 2024-07-27 | 52 | 2024-07-28 | 1 | 2024-08-08 | 11 | 2024-08-09 | 2024-08-14 | 5 | 2024-08-14 | 2 | 2024-08-16 | 32 |  | 350000 | Completed | 2024-09-17 | 0
165 | FAULTY FOUR HEAD MACHINES | LAG, ONIRU | Others | Breakdown | KITCHTECH | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-08-07 | 8 | 2024-08-13 | 6 | 2024-08-15 | 2 | 2024-08-15 | 2024-08-15 | 0 | 2024-08-15 | 0 | 2024-08-15 | 0 |  |  | Completed | 2024-08-15 | 0
166 | DEAD BULB IN THE DRYSTORE | LAG, MAGODO | Electrical Surge | Breakdown | KOLA | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 | 0 |  |  | Completed | 2024-08-14 | 0
167 | REQUEST FOR GENERATOR SERVICING | AKWA IBOM, ORON RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-08-14 | 218 | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 | 218 | 2024-08-15 |  | Overdue
168 | REPLACEMENT OF FADED LOBBY ENTRANCE FLOOR TILES | LAG, IDIMU | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-08-13 | 219 | 2024-08-14 | 1 |  | 218 | [9 empty] | Overdue
169 | INVERTER NOT WORKING | LAG, TEJUOSHO | Others | Breakdown | TIMILEYIN | INVERTER SYSTEM | INVERTER | 2024-08-12 | 7 | 2024-08-14 | 2 | 2024-08-14 | 0 | 2024-08-14 | 2024-08-14 | 0 | 2024-08-14 | 0 | 2024-08-14 | 5 | 2024-08-15 |  | Completed | 2024-08-19 | 0
170 | REQUEST FOR INDUSTRIAL CLEANING OF OIL | LAG, JOEL OGUNNAIKE | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-08-15 | 1 | 2024-08-15 | 0 | 2024-08-15 | 0 | 2024-08-15 | 2024-08-15 | 0 | 2024-08-15 | 1 | 2024-08-16 | 0 | 2024-08-17 | 120000 | Completed | 2024-08-16 | 1
171 | PRESSURE FRYER NOT FRYING | PH, ONNE RD, GRA | Others | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-08-15 | 2 | 2024-08-15 | 0 | 2024-08-17 | 2 | 2024-08-17 | 2024-08-17 | 0 | 2024-08-17 | 0 | 2024-08-17 | 0 |  |  | Completed | 2024-08-17 | 0
172 | INSECTOCUTOR BULB FAULTY | LAG, IKEJA MALL | Electrical Surge | Breakdown | TAYO ALBERT | INSECT KILLER BOH | ELECTRICAL | 2024-08-16 | 1 | 2024-08-16 | 0 | 2024-08-17 | 1 | 2024-08-17 | 2024-08-17 | 0 | 2024-08-17 | 0 | 2024-08-17 | 0 | 2024-08-17 |  | Completed | 2024-08-17 | 1
173 | FAULTY PUMPING MACHINE | LAG, BADORE | Others | Breakdown | JOEL OMOTOSHO | WATER TREATMENT PLANT BLD | BUILDING | 2024-08-15 | 1 | 2024-08-16 | 1 | 2024-08-16 | 0 | 2024-08-16 | 2024-08-16 | 0 | 2024-08-16 | 0 | 2024-08-16 | 0 | 2024-08-17 |  | Completed | 2024-08-16 | 1
174 | CR ILUPEJU TILING OF BOH | LAG, ILUPEJU | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-08-15 | 2 | 2024-08-15 | 0 | 2024-08-15 | 0 | 2024-08-15 | 2024-08-16 | 1 | 2024-08-16 | 0 | 2024-08-16 | 1 | 2024-08-17 | 1338250 | Completed | 2024-08-17 | 1
175 | GENERATOR SERVICING | AKWA IBOM, ABAK RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-08-16 | 0 | 2024-08-16 | 0 | 2024-08-16 | 0 | 2024-08-16 | 2024-08-16 | 0 | 2024-08-16 | 0 | 2024-08-16 | 0 |  |  | Completed | 2024-08-16 | 0
176 | GENERATOR SERVICING | ENUGU, NSUKKA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-08-16 | 1 | 2024-08-16 | 0 | 2024-08-16 | 0 | 2024-08-16 | 2024-08-16 | 0 | 2024-08-16 | 0 | 2024-08-16 | 1 |  |  | Completed | 2024-08-17 | 0
177 | LEAKING SINK | LAG, LATEEF JAKANDE | Others | Breakdown | ADEREMI | KITCHEN WASH HAND SINK | PLUMBING | 2024-08-16 | 1 | 2024-08-16 | 0 | 2024-08-16 | 0 | 2024-08-17 | 2024-08-17 | 0 | 2024-08-17 | 0 | 2024-08-17 | 0 |  |  | Completed | 2024-08-17 | 0
178 | EVACUATION OF SEPTIC TANK | LAG, MAGODO | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-08-12 | 5 | 2024-08-12 | 0 | 2024-08-15 | 3 | 2024-08-15 | 2024-08-15 | 0 | 2024-08-15 | 1 | 2024-08-16 | 1 | 2024-08-17 | 265525 | Completed | 2024-08-17 | 1
179 | COLD ROOM AND FREEZER ROOM NOT ATTAINING TEMP | LAG, FREEDOMWAY | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-08-15 | 15 | 2024-08-15 | 0 | 2024-08-16 | 1 | 2024-08-16 | 2024-08-16 | 0 | 2024-08-16 | 13 | 2024-08-29 | 1 |  |  | Completed | 2024-08-30 | 0
180 | RUSTED WATER TREATMENT AERATION TANK | LAG, AWOLOWO 2 | Others | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-08-16 | 18 | 2024-08-16 | 0 | 2024-09-03 | 18 | 2024-09-03 | 2024-09-03 | 0 | 2024-09-03 | 0 | 2024-09-03 | 0 |  |  | Completed | 2024-09-03 | 0
181 | REPLACEMENT OF GAS BURNER | LAG, DOMINO E-CENTRE | Others | Breakdown | BERRADE | GAS CYLINDER | GAS | 2024-08-06 | 10 | 2024-08-06 | 0 | 2024-08-16 | 10 | 2024-08-16 | 2024-08-16 | 0 | 2024-08-16 | 216 |  |  |  | 103350 | Completed | 2024-08-16 | 0
182 | DRIP PAN NOT IN GOOD CONDITION | DELTA, EFFURUN | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-08-15 | 217 | 2024-08-15 | 0 |  | 217 | [9 empty] | Overdue
183 | FAULTY ICE CREAM MACHINE | PH AGGREY | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-08-10 | 46 | 2024-08-10 | 0 | 2024-09-24 | 45 | 2024-09-24 | 2024-09-24 | 0 | 2024-09-24 | 0 | 2024-09-24 | 1 |  |  | Completed | 2024-09-25 | 0
184 | BLOCKING OF KITCHEN SINK | LAG, LEKKI PHASE 1 | Others | Breakdown | JOEL OMOTOSHO | KITCHEN WASH HAND SINK | PLUMBING | 2024-08-18 | 0 | 2024-08-18 | 0 | 2024-08-18 | 0 | 2024-08-18 | 2024-08-18 | 0 | 2024-08-18 | 0 | 2024-08-18 | 0 | 2024-08-19 |  | Completed | 2024-08-18 | 1
185 | POLARITY ISSUE | LAG, FREEDOMWAY | Others | Breakdown | ISMAIL ODEDELE | OTHERS | OTHERS | 2024-08-18 | 1 | 2024-08-18 | 0 | 2024-08-19 | 1 | 2024-08-19 | 2024-08-19 | 0 | 2024-08-19 | 0 | 2024-08-19 | 0 | 2024-08-19 |  | Completed | 2024-08-19 | 1
186 | DOOR HANDLE PX | LAG, BODE THOMAS | Others | Breakdown | VENYS | OTHERS | OTHERS | 2024-08-12 | 8 | 2024-08-12 | 0 | 2024-08-16 | 4 | 2024-08-16 | 2024-08-16 | 0 | 2024-08-16 | 3 | 2024-08-19 | 1 |  | 61000 | Completed | 2024-08-20 | 0
187 | FAULTY ROLLER SHUTTER HARD TO CLOSE PX | LAG, JOEL OGUNNAIKE | Others | Breakdown | VENYS | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-08-17 | 3 | 2024-08-17 | 0 | 2024-08-18 | 1 | 2024-08-18 | 2024-08-18 | 0 | 2024-08-18 | 1 | 2024-08-19 | 1 |  | 64500 | Completed | 2024-08-20 | 0
188 | FAULTY CUSTOMERS RESTROOM FLUSHER | LAG, IDIMU | Others | Breakdown | OLATUNDE | OTHERS | OTHERS | 2024-08-18 | 1 | 2024-08-18 | 0 | 2024-08-19 | 1 | 2024-08-19 | 2024-08-19 | 0 | 2024-08-19 | 0 | 2024-08-19 | 0 |  |  | Completed | 2024-08-19 | 0
189 | BROKEN FLOOR TILES AT WATER TREATMNT PLANT | LAG, JOEL OGUNNAIKE | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-08-18 | 214 | 2024-08-18 | 0 | 2024-08-19 | 1 | [9 empty] | Overdue
190 | GENERATOR DUE FOR SERVICING | PH, ONNE RD, GRA | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-08-18 | 1 | 2024-08-18 | 0 | 2024-08-19 | 1 | 2024-08-19 | 2024-08-19 | 0 | 2024-08-19 | 0 | 2024-08-19 | 0 |  |  | Completed | 2024-08-19 | 0
191 | REQUEST FOR WHITE STONE GRANITE | LAG, MMA2 | Others | Breakdown | VENYS | OTHERS | OTHERS | 2024-08-10 | 8 | 2024-08-10 | 0 | 2024-08-18 | 8 | 2024-08-18 | 2024-08-18 | 0 | 2024-08-18 | 0 | 2024-08-18 | 0 |  | 185069.77 | Completed | 2024-08-18 | 0
192 | Critical Situation with the Tank at Fatgbems | OGUN, FATGBEMS IBB WAY | Others | Breakdown | PRO EQUIP | OTHERS | OTHERS | 2024-08-14 | 16 | 2024-08-14 | 0 | 2024-08-24 | 10 | 2024-08-24 | 2024-08-24 | 0 | 2024-08-24 | 0 | 2024-08-24 | 6 | 2024-08-26 | 307250 | Completed | 2024-08-30 | 0
193 | OVERHAULING OF WATER TREATMENT PLANT | OGUN, FATGBEMS IBB WAY | Others | Breakdown | PRO EQUIP | WATER TREATMENT PLANT BLD | BUILDING | 2024-08-18 | 214 | 2024-08-18 | 0 |  | 214 | [9 empty] | Overdue
194 | LEAKING SINK | LAG, LATEEF JAKANDE | Others | Breakdown | ADEREMI WAHAB | KITCHEN WASH HAND SINK | PLUMBING | 2024-08-16 | 2 | 2024-08-16 | 0 | 2024-08-16 | 0 | 2024-08-18 | 2024-08-18 | 0 | 2024-08-18 | 0 | 2024-08-18 | 0 | 2024-08-18 |  | Completed | 2024-08-18 | 1
195 | REQUEST FOR CEILING AT WATER TREATMENT PLANT | IBADAN, RING-ROAD | Others | Breakdown | DEFAVOUR | ROOF | BUILDING | 2024-08-08 | 224 | 2024-08-09 | 1 | 2024-08-09 | 0 | 2024-08-10 | 2024-08-29 | 19 | 2024-08-29 | 18 | 2024-09-16 | 185 |  | 468800 | Overdue
196 | FAULTY SAFE ROOM DOOR | LAG, LEKKI PHASE 1 | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-08-13 | 219 | 2024-08-13 | 0 | 2024-08-18 | 5 | [9 empty] | Overdue
197 | FAULTY ICE CREAM MACHINE | ILORIN, ASA DAM | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-08-16 | 13 | 2024-08-16 | 0 | 2024-08-19 | 3 | 2024-08-19 | 2024-08-19 | 0 | 2024-08-24 | 1 | 2024-08-25 | 4 | 2024-08-26 | 101684 | Completed | 2024-08-29 | 0
198 | FALLEN LOBBY CEILING | LAG, AJAH | Others | Breakdown | VENYS | ROOF | BUILDING | 2024-08-16 | 216 | 2024-08-16 | 0 | 2024-08-16 | 0 | 2024-08-17 | 2024-08-17 | 0 | 2024-08-19 | 213 |  |  |  | 3500000 | Overdue
199 | CONSTANT SEWAGE DISPOSAL | EBONYI, WATERWORKS, ABAKALIKI | Others | Breakdown | STANQUANT | SEPTIC TANK | EVACUATION | 2024-08-19 | 213 | 2024-08-19 | 0 |  | 213 | [9 empty] | Overdue
200 | FAULTY SHREDDING MACHINE | PH, RUKPOKWU | Others | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-08-12 | 220 | 2024-08-12 | 0 | 2024-08-19 | 7 | [9 empty] | Overdue
201 | FAULTY GENERATOR DISPLAY PANEL PPU MOKOLA | IBADAN, MOKOLA | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-08-08 | 11 | 2024-08-08 | 0 | 2024-08-15 | 7 | 2024-08-15 | 2024-08-15 | 0 | 2024-08-15 | 0 | 2024-08-15 | 4 | 2024-08-17 | 1337512.5 | Completed | 2024-08-19 | 0
202 | CEILING LEAKAGE | LAG, AWOLOWO | Others | Breakdown | ACORN | ROOF | BUILDING | 2024-08-19 | 213 | 2024-08-19 | 0 | 2024-08-20 | 1 | [9 empty] | Overdue
203 | FREEZER ROOM AND COLD ROOM DRAINAGE | LAG, OGUNLANA DRIVE | Others | Breakdown | BB COMMERCIAL | OTHERS | OTHERS | 2024-08-06 | 14 | 2024-08-06 | 0 | 2024-08-20 | 14 | 2024-08-20 | 2024-08-20 | 0 | 2024-08-20 | 0 | 2024-08-20 | 0 |  |  | Completed | 2024-08-20 | 0
204 | FAULTY GAS BURNER | LAG, AWOLOWO 2 | Others | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-08-19 | 3 | 2024-08-19 | 0 | 2024-08-20 | 1 | 2024-08-20 | 2024-08-20 | 0 | 2024-08-20 | 32 | 2024-09-21 | -30 | 2024-08-22 | 56600 | Completed | 2024-08-22 | 1
205 | Emergency call from CR Isawo 135KVA Gen set | LAG, ISAWO-IKORODU | Corrective Action | Corrective | DELIGHTSOME | GENERATOR | GENERATOR | 2024-08-19 | 0 | 2024-08-19 | 0 | 2024-08-19 | 0 | 2024-08-19 | 2024-08-19 | 0 | 2024-08-19 | 0 | 2024-08-19 | 0 | 2024-08-20 | 25500 | Completed | 2024-08-19 | 1
206 | FAULTY CABINET TABLE PX | LAG, IRE-AKARI | Others | Breakdown | MATOLAD | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-08-07 | 225 | 2024-08-07 | 0 | 2024-08-20 | 13 | 2024-08-20 | 2024-08-20 | 0 | 2024-08-20 | 10 | 2024-08-30 | 202 |  | 110000 | Overdue
207 | MALE CUSTOMER TOILET DOOR | LAG, IDI-IROKO RD | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-08-05 | 15 | 2024-08-05 | 0 | 2024-08-20 | 15 | 2024-08-20 | 2024-08-20 | 0 | 2024-08-20 | 0 | 2024-08-20 | 0 |  |  | Completed | 2024-08-20 | 0
208 | GLASS DOOR GASKET | LAG, OGUDU | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-08-05 | 15 | 2024-08-05 | 0 | 2024-08-20 | 15 | 2024-08-20 | 2024-08-20 | 0 | 2024-08-20 | 0 | 2024-08-20 | 0 |  |  | Completed | 2024-08-20 | 0
209 | BAD DOOR NET AT WATER TREATMENT PLANT | LAG, JOEL OGUNNAIKE | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-08-02 | 18 | 2024-08-05 | 3 | 2024-08-20 | 15 | 2024-08-20 | 2024-08-20 | 0 | 2024-08-20 | 0 | 2024-08-20 | 0 |  |  | Completed | 2024-08-20 | 0
210 | URGENT MAINTENANCE ACTION REQUIRED | PPU Opebi | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-08-06 | 14 | 2024-08-06 | 0 | 2024-08-20 | 14 | 2024-08-20 | 2024-08-20 | 0 | 2024-08-20 | 0 | 2024-08-20 | 0 |  |  | Completed | 2024-08-20 | 0
211 | TAYLOR MACHINE STRANGE SOUND | LAG, OBA AKRAN | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-08-16 | 6 | 2024-08-16 | 0 | 2024-08-20 | 4 | 2024-08-20 | 2024-08-20 | 0 | 2024-08-20 | 0 | 2024-08-20 | 2 |  |  | Completed | 2024-08-22 | 0
212 | GENRATOR DUE FOR SERVICING | LAG, EKORO | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-08-17 | 3 | 2024-08-17 | 0 | 2024-08-19 | 2 | 2024-08-19 | 2024-08-19 | 0 | 2024-08-19 | 1 | 2024-08-20 | 0 |  |  | Completed | 2024-08-20 | 0
213 | FREEZER ROOM ISSUE | IBADAN, RING-ROAD | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-08-19 | 213 | 2024-08-19 | 0 | 2024-09-20 | 32 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 181 | 2024-09-20 |  | Overdue
214 | GENERATOR CHECK | OGUN, HEYDEN IBAFO | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-08-14 | 17 | 2024-08-14 | 0 | 2024-08-20 | 6 | 2024-08-20 | 2024-08-20 | 0 | 2024-08-20 | 212 |  |  |  |  | Completed | 2024-08-31 | 0
215 | RUSTED PYLON | LAG, AJAH | Others | Breakdown | WESTERN DESIGN | OTHERS | OTHERS | 2024-08-08 | 224 | 2024-08-08 | 0 | 2024-08-20 | 12 | [9 empty] | Overdue
216 | FAULTY CASHIER DOOR HINGES | LAG, LATEEF JAKANDE | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-08-16 | 4 | 2024-08-16 | 0 | 2024-08-20 | 4 | 2024-08-20 | 2024-08-20 | 0 | 2024-08-20 | 0 | 2024-08-20 | 0 |  |  | Completed | 2024-08-20 | 0
217 | FAULTY GAS BURNER | LAG, OGUNLANA DRIVE | Others | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-08-12 | 1 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 2024-08-12 | 0 | 2024-08-12 | 0 | 2024-08-12 | 1 | 2024-08-13 | 70250 | Completed | 2024-08-13 | 1
218 | TEMPRATURE DROP IN COLLECTROMATIC MACHINE | LAG, JIBOWU | Others | Breakdown | BCE | COLLECTRAMATIC OIL PUMP MACHINE | KITCHEN_EQUIPMENT | 2024-08-08 | 2 | 2024-08-10 | 2 | 2024-08-10 | 0 | 2024-08-10 | 2024-08-10 | 0 | 2024-08-10 | 0 | 2024-08-10 | 0 | 2024-08-11 |  | Completed | 2024-08-10 | 1
219 | DIESEL LEAKAGE | LAG, JIBOWU | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-08-06 | 4 | 2024-08-07 | 1 | 2024-08-10 | 3 | 2024-08-10 | 2024-08-10 | 0 | 2024-08-10 | 0 | 2024-08-10 | 0 |  |  | Completed | 2024-08-10 | 0
220 | BURNING AND FAULTY WARMR | LAG, JIBOWU | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-08-21 | 1 | 2024-08-21 | 0 | 2024-08-22 | 1 | 2024-08-22 | 2024-08-22 | 0 | 2024-08-22 | 0 | 2024-08-22 | 0 | 2024-08-23 |  | Completed | 2024-08-22 | 1
221 | ROUGH EDGES IN THE STORE | LAG, MAGODO | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-08-16 | 216 | 2024-08-16 | 0 | 2024-08-28 | 12 | 2024-08-28 | 2024-08-30 | 2 | 2024-08-30 | 0 | 2024-08-30 | 202 |  | 80000 | Overdue
222 | OPENED ROOF AT DUSTBIN AREA | LAG, OMOLE | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-08-24 | 5 | 2024-08-24 | 0 | 2024-08-29 | 5 | 2024-08-29 | 2024-08-29 | 0 | 2024-08-29 | 0 | 2024-08-29 | 0 |  | 227400 | Completed | 2024-08-29 | 0
223 | FAULTY INVERTER | IBADAN, CHALLENGE | Others | Breakdown | NISTECH | INVERTER SYSTEM | INVERTER | 2024-08-26 | 206 | 2024-08-26 | 0 | 2024-08-27 | 1 | [9 empty] | Overdue
224 | SERVICING OF GAS PIPE | LAG, MOBIL OGBA | Others | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-08-25 | 207 | 2024-08-25 | 0 | 2024-08-28 | 3 | 2024-08-29 | 2024-08-29 | 0 | [5 empty] | 126000 | Overdue
225 | RUSTED SEPTIC TANK SLAB | LAG, VGC | Others | Breakdown | MODEL | SEPTIC TANK | EVACUATION | 2024-08-16 | 216 | 2024-08-16 | 0 |  | 216 | [9 empty] | Overdue
226 | FAULTY CABINET | LAG, TOTAL LEKKI | Others | Breakdown | ISMAIL ODEDELE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-08-27 | 1 | 2024-08-27 | 0 | 2024-08-28 | 1 | 2024-08-28 | 2024-08-28 | 0 | 2024-08-28 | 0 | 2024-08-28 | 0 | 2024-08-28 |  | Completed | 2024-08-28 | 1
227 | BROKEN WALL TILES | OGUN, SOKENU | Others | Breakdown | VENYS | OTHERS | OTHERS | 2024-08-26 | 206 | 2024-08-26 | 0 | 2024-08-27 | 1 | 2024-08-27 | 2024-08-28 | 1 | [5 empty] | 200000 | Overdue
228 | FAULTY FREEZER ROOM SAFE LOCK | LAG, LATEEF JAKANDE | Others | Breakdown | TRIPPLE O | FREEZER ROOM | HVAC | 2024-08-13 | 10 | 2024-08-13 | 0 | 2024-08-23 | 10 | 2024-08-23 | 2024-08-23 | 0 | 2024-08-23 | 0 | 2024-08-23 | 0 |  |  | Completed | 2024-08-23 | 0
229 | CLEARING OF DRAINAGE AT THE CAR PARK | LAG, TOTAL ONIGBAGBO | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-08-07 | 225 | 2024-08-08 | 1 | 2024-08-13 | 5 | 2024-08-13 | 2024-08-15 | 2 | [6 empty] | Overdue
230 | BURNT RATIONAL PUMPING SOCKET | LAG, LEKKI PHASE 1 | Electrical Surge | Breakdown | JOEL OMOTOSHO | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-08-29 | 203 | 2024-08-29 | 0 |  | 203 | [9 empty] | Overdue
231 | SEVERAL DEAD BULBS IN THE LOBBY | LAG, AWOLOWO | Electrical Surge | Breakdown | ISMAIL ODEDELE | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-08-26 | 4 | 2024-08-26 | 0 | 2024-08-30 | 4 | 2024-08-30 | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 | 0 |  |  | Completed | 2024-08-30 | 0
232 | PX OKIGWE REPAIR FOR DISPLAY CABINET | IMO, OKIGWE | Others | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-08-06 | 226 | 2024-08-06 | 0 | 2024-08-29 | 23 | [9 empty] | Overdue
233 | REPLACEMENT OF FAULTY AIR VENT | LAG, EJIGBO | Others | Breakdown | ABBEY | OTHERS | OTHERS | 2024-08-27 | 205 | 2024-08-27 | 0 | 2024-08-28 | 1 | 2024-08-28 | 2024-08-28 | 0 | [6 empty] | Overdue
234 | FAULTY CHEST FREEZER | OGUN, HEYDEN IBAFO | Others | Breakdown | MOSES | CHEST FREEZER | HVAC | 2024-08-28 | 1 | 2024-08-28 | 0 | 2024-08-29 | 1 | 2024-08-29 | 2024-08-29 | 0 | 2024-08-29 | 0 | 2024-08-29 | 0 | 2024-08-29 |  | Completed | 2024-08-29 | 1
235 | DEAD SECURITY BULB IN CAR PARK | LAG, IKOTUN | Electrical Surge | Breakdown | EMMANUEL | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-08-24 | 5 | 2024-08-25 | 1 | 2024-08-29 | 4 | 2024-08-29 | 2024-08-29 | 0 | 2024-08-29 | 0 | 2024-08-29 | 0 |  |  | Completed | 2024-08-29 | 0
236 | BAD LOBBY ENTRANCE DOOR | LAG, ABULE EGBA | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-08-27 | 1 | 2024-08-27 | 0 | 2024-08-28 | 1 | 2024-08-28 | 2024-08-28 | 0 | 2024-08-28 | 0 | 2024-08-28 | 0 | 2024-08-29 |  | Completed | 2024-08-28 | 1
237 | FAULTY ENTRANCE DOOR | LAG, OBA AKRAN | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-08-27 | 1 | 2024-08-27 | 0 | 2024-08-28 | 1 | 2024-08-28 | 2024-08-28 | 0 | 2024-08-28 | 0 | 2024-08-28 | 0 |  |  | Completed | 2024-08-28 | 0
238 | FEMALE TOILET CANNOT FLUSH | LAG, OGUDU | Others | Breakdown | ADEREMI WAHAB | OTHERS | OTHERS | 2024-08-25 | 3 | 2024-08-26 | 1 | 2024-08-28 | 2 | 2024-08-28 | 2024-08-28 | 0 | 2024-08-28 | 0 | 2024-08-28 | 0 |  |  | Completed | 2024-08-28 | 0
239 | GENERATOR SERVICING | IBADAN, OJOO | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-08-20 | 212 | 2024-08-20 | 0 | 2024-08-20 | 0 | 2024-08-20 | 2024-08-20 | 0 | 2024-08-20 | 8 | 2024-08-28 | 204 |  | 215000 | Overdue
240 | GENERATOR SERVICING | LAG, OSOLOWAY | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-08-28 | 1 | 2024-08-28 | 0 | 2024-08-28 | 0 | 2024-08-28 | 2024-08-28 | 0 | 2024-08-28 | 0 | 2024-08-28 | 1 |  |  | Completed | 2024-08-29 | 0
241 | SHATTERED ROTISSERIE MACHINE GLASS | LAG, CONOIL IKEJA | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-08-28 | 2 | 2024-08-28 | 0 | 2024-08-29 | 1 | 2024-08-29 | 2024-08-29 | 0 | 2024-08-29 | 0 | 2024-08-29 | 1 | 2024-08-30 |  | Completed | 2024-08-30 | 1
242 | REQUEST FOR COLLECTOR GASKETS | ANAMBRA, ZIK AVENUE, AWKA | Others | Breakdown | BCE | COLLECTRAMATIC OIL PUMP MACHINE | KITCHEN_EQUIPMENT | 2024-08-29 | 203 | 2024-08-29 | 0 | 2024-08-29 | 0 | 2024-08-29 | 2024-08-29 | 0 | 2024-08-29 | 1 | 2024-08-30 | 202 |  |  | Overdue
243 | FAULTY ROLLER SHUTTER | LAG, IDIMU | Others | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-08-28 | 204 | 2024-08-28 | 0 | 2024-08-30 | 2 | [9 empty] | Overdue
244 | ATTENTION ON INSECT KILLER | LAG, AWOLOWO | Others | Breakdown | ISMAIL ODEDELE | INSECT KILLER BOH | ELECTRICAL | 2024-08-29 | 1 | 2024-08-29 | 0 | 2024-08-30 | 1 | 2024-08-30 | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 | 0 |  |  | Completed | 2024-08-30 | 0
245 | FAULTY GENERATOR DISPLAY | ABIA, AZIKIWE RD, UMUAHIA | Others | Breakdown | MID TECH | GENERATOR | GENERATOR | 2024-08-28 | 204 | 2024-08-28 | 0 | 2024-08-29 | 1 | 2024-08-29 | 2024-08-29 | 0 | 2024-08-29 | 0 | 2024-08-29 | 203 |  | 440750 | Overdue
246 | LOBBY AC PIPE LEAKAGE | LAG, MARINA | Others | Breakdown | FOLLTEC | 5HP STANDING AC UNIT 1 | HVAC | 2024-08-29 | 203 | 2024-08-29 | 0 |  | 203 | [9 empty] | Overdue
247 | BURNT SERVICE CABLE | LAG, ONIRU | Electrical Surge | Breakdown | GATMO | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-08-24 | 9 | 2024-08-24 | 0 | 2024-08-26 | 2 | 2024-08-26 | 2024-08-29 | 3 | 2024-08-29 | 0 | 2024-08-29 | 4 |  | 550000 | Completed | 2024-09-02 | 0
248 | GENERATOR SERVICING | PH, RUKPOKWU | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-08-29 | 1 | 2024-08-29 | 0 | 2024-08-29 | 0 | 2024-08-29 | 2024-08-29 | 0 | 2024-08-29 | 0 | 2024-08-29 | 1 | 2024-08-30 |  | Completed | 2024-08-30 | 1
249 | BROKEN HW8 NEWLY INTSTALLED | LAG, JIBOWU | Others | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-08-10 | 222 | 2024-08-10 | 0 | 2024-08-30 | 20 | 2024-08-30 | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 | 202 |  |  | Overdue
250 | SHAKING BALCONY AT THE MALL | LAG, DOMINO E-CENTRE | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-08-20 | 212 | 2024-08-20 | 0 | 2024-08-29 | 9 | 2024-08-30 | 2024-08-30 | 0 | 2024-08-30 | 202 |  |  |  | 4850000 | Overdue
251 | REQUEST FOR GRANITE | LAG, OMOLE | Others | Breakdown | CRADLEVIEW | OTHERS | OTHERS | 2024-08-21 | 211 | 2024-08-21 | 0 | 2024-08-26 | 5 | 2024-08-26 | 2024-08-26 | 0 | [6 empty] | Overdue
252 |  | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | JOEL OMOTOSHO | AERATION TANK | WTP | 2024-08-28 | 1 | 2024-08-28 | 0 | 2024-08-29 | 1 | 2024-08-28 | 2024-08-28 | 0 | 2024-08-28 | 0 | 2024-08-28 | 1 | 2024-08-29 | 0 | Completed | 2024-08-29 | 1
253 | Rusted septic tank slabs and faulty metal door inches and lock | LAG, VGC | Wear & Tear | Breakdown | MODEL | SLAB | BUILDING | 2024-08-16 | 216 | 2024-08-16 | 0 | 2024-08-30 | 14 | 2024-08-30 | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 | 202 | 2024-08-30 |  | Overdue
254 | DOSING TANKS FAULTY AND ELECTRICAL SHOCKS | ENUGU, NSUKKA | Wear & Tear | Breakdown | PRO EQUIP | DOSING TANK | WTP | 2024-08-27 | 205 | 2024-08-28 | 1 | 2024-09-19 | 22 | 2024-09-21 | 2024-09-21 | 0 | 2024-09-21 | 0 | 2024-09-21 | 180 |  |  | Overdue
255 | REQUEST FOR UNDERBAR CHILLER ENGINE COVER | IMO, WETHERAL RD, OWERRI | Corrective Action | Corrective | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-08-14 | 218 | 2024-08-14 | 0 | 2024-08-20 | 6 | [9 empty] | Overdue
256 | FAULTY BACK OF HOUSE DOOR HANDLE | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-08-28 | 15 | 2024-08-28 | 0 | 2024-09-06 | 9 | 2024-09-06 | 2024-09-06 | 0 | 2024-09-06 | 0 | 2024-09-06 | 6 |  |  | Completed | 2024-09-12 | 0
257 | BAD UNDERBAR FRIDGE LID GASKET | EDO, UGBOWO, BENIN | Users Misuse | Breakdown | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-08-27 | 205 | 2024-08-27 | 0 | 2024-08-28 | 1 | [9 empty] | Overdue
258 | Request for replacement of faded lobby tiles | ABIA, FACTORY RD, ABA | Others | Breakdown | DT CONSULT | OTHERS | OTHERS | 2024-06-03 | 290 | 2024-06-03 | 0 |  | 290 | [9 empty] | Overdue
259 | URGENT REPAIR OF COLLAPSE WALL TILES | DELTA, ISOKO RD | Wear & Tear | Breakdown | FULL TURN | WALL | BUILDING | 2024-07-07 | 256 | 2024-07-08 | 1 | 2024-07-24 | 16 | 2024-07-24 | 2024-08-14 | 21 | 2024-08-15 | 0 | 2024-08-15 | 217 | 2024-08-26 | 367166.25 | Overdue
260 | LEAKING DIESEL PIPE CAUSING DISEL SPILL | LAG, OPEBI | Corrective Action | Corrective | PROPEARJEFF | OTHERS | OTHERS | 2024-08-28 | 204 | 2024-08-28 | 0 |  | 204 | [9 empty] | Overdue
261 | BURNT SERVICE CABLE (NEPA) | LAG, ONIRU | Electrical Surge | Breakdown | GBATMO | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-08-24 | 9 | 2024-08-24 | 0 | 2024-08-26 | 2 | 2024-08-26 | 2024-08-29 | 3 | 2024-08-29 | 0 | 2024-08-29 | 4 |  | 550000 | Completed | 2024-09-02 | 0
262 | COLD ROOM TEMPERATURE NOT ATTAINING | PH, GRA BIRABI | Corrective Action | Corrective | MOFEEN | COLD ROOM UNIT | HVAC | 2024-08-24 | 208 | 2024-08-24 | 0 |  | 208 | [9 empty] | Overdue
263 | CR OMOLE FAULTY PYLON LIGHT | LAG, OMOLE | Electrical Surge | Breakdown | TIMI AJALA | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-08-30 | 18 | 2024-08-30 | 0 | 2024-09-10 | 11 | 2024-09-10 | 2024-09-10 | 0 | 2024-09-10 | 7 | 2024-09-17 | 0 |  | 58500 | Completed | 2024-09-17 | 0
264 | FIXING OF LOBBY BENCHES | AKWA IBOM, ABAK RD | Others | Breakdown | FULL TURN | OTHERS | OTHERS | 2024-08-20 | 212 | 2024-08-20 | 0 |  | 212 | [9 empty] | Overdue
265 | FAULTY UV LIGHT STERILIZER AND LAEKING WTP | PH, RUMUBIAKANI | Electrical Surge | Breakdown | SAPAT | UV LIGHT | WTP | 2024-08-29 | 203 | 2024-08-29 | 0 |  | 203 | [9 empty] | Overdue
266 | BROKEN TILES | LAG, ALIMOSHO | Others | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-08-28 | 204 | 2024-08-28 | 0 | 2024-09-13 | 16 | 2024-09-13 | 2024-09-20 | 7 | 2024-09-20 | 181 |  |  |  | 190000 | Overdue
267 | COLLAPSED PARKING LOT FLOOR | IMO, IKENEGBU, OWERRI | Others | Breakdown | DEACONESS | OTHERS | OTHERS | 2024-08-28 | 204 | 2024-08-29 | 1 | 2024-09-19 | 21 | 2024-09-19 | 2024-09-20 | 1 | 2024-09-20 | 181 |  |  |  | 700000 | Overdue
268 | PENDING ISSUES AT OPEBI (PAINTING) | PPU Opebi | Others | Breakdown | ARIZMAYAN | PAINTING | BUILDING | 2024-08-23 | 209 | 2024-08-23 | 0 | 2024-09-10 | 18 | 2024-09-11 | 2024-09-20 | 9 | [5 empty] | 270000 | Overdue
269 | PENDING ISSUES AT OPEBI (LEAKING PIPE) | PPU Opebi | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-08-23 | 209 | 2024-08-23 | 0 | 2024-09-10 | 18 | 2024-09-11 | 2024-09-20 | 9 | [5 empty] | 120000 | Overdue
270 | PENDING ISSUES AT OPEBI (LEAKING ROOF) | PPU Opebi | Others | Breakdown | ARIZMAYAN | ROOF | BUILDING | 2024-08-23 | 209 | 2024-08-23 | 0 | 2024-09-10 | 18 | 2024-09-11 | 2024-09-20 | 9 | [5 empty] | 225000 | Overdue
271 | NEED FOR BOH REFLOORING | LAG, GBAGADA | Others | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-08-24 | 208 | 2024-08-24 | 0 | 2024-09-13 | 20 | 2024-09-13 | 2024-09-20 | 7 | [6 empty] | Overdue
272 | DISEL WATER LEAKAGE | LAG, IRE-AKARI | Wear & Tear | Breakdown | DAMI FOTE | GENERATOR | GENERATOR | 2024-08-31 | 20 | 2024-09-01 | 1 | 2024-09-20 | 19 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 |  | Completed | 2024-09-20 | 1
273 | STOLEN DRAINAGE COVER | LAG, FREEDOMWAY | Others | Breakdown | BAMOCOON | DRAIN COVER | BUILDING | 2024-08-03 | 229 | 2024-08-05 | 2 | 2024-08-12 | 7 | 2024-08-12 | 2024-08-28 | 16 | 2024-08-28 | 19 | 2024-09-16 | 185 |  | 560000 | Overdue
274 | FAULTY ICE CREAM MACHINE | EDO, UGBOWO, BENIN | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-08-31 | 27 | 2024-08-31 | 0 | 2024-09-24 | 24 | 2024-09-24 | 2024-09-24 | 0 | 2024-09-24 | 0 | 2024-09-24 | 3 |  |  | Completed | 2024-09-27 | 0
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
Formulas:
Days Since Request = IF([Request Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Request Date],TODAY()-[Request Date]))
Days Delayed by Helpdesk = IF([Date Shared by Helpdesk]<>"",[Date Shared by Helpdesk]-[Request Date],IF([Request Date]="","",TODAY()-[Request Date]))
Days Delayed by Vendor/Technician = IF(M6<>"",M6-[Date Shared by Helpdesk],IF([Date Shared by Helpdesk]="","",TODAY()-[Date Shared by Helpdesk]))
Days Since Negotiation Request = TODAY() - [Date Negotiated]
Days Since Negotiation Request = IF([Date Negotiated]<>"",[Date Negotiated]-[Date Sent for Negotiation],IF([Date Sent for Negotiation]="","",TODAY()-[Date Sent for Negotiation]))
Days Since Approval Request = IF([Approved Date]<>"",[Approved Date]-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval = IF([Approved Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Approved Date],TODAY()-[Approved Date]))
Status = IF([Request Date]="","",IF([Actual delivery date]<>"","Completed",IF(TODAY()<[Expected Delivery Date],"Planned",IF(TODAY()=[Expected Delivery Date],"Due","Overdue"))))
Note on AA6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vendor gave feedback thaat part is not available on 18 of Jan

## SEPTEMPER
Legend
Completed on time
Completed late
S/N | ACTION/TASK | Store | Reason for Breakdown | Maintenance Category | Responsible | Specific Equipment | Category | Request Date | Days Since Request | Date Shared by Helpdesk | Days Delayed by Helpdesk | Date Attended/Checked by Vendor/Technician | Days Delayed by Vendor/Technician | Date Sent for Negotiation | Date Negotiated | Days Since Negotiation Request | Date Approval Requested | Days Since Approval Request | Approved Date | Days Since Approval | Expected Delivery Date | Cost | Status | Actual delivery date | Compliance check | Insert Comment
1 | FAULTY ROTISERIE MACHINE SOCKET | LAG, VGC | Electrical Surge | Breakdown | JOEL OMOTOSHO | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-09-19 | 1 | 2024-09-19 | 0 | 2024-09-20 | 1 | 2024-09-20 | 2024-09-20 | 181 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 |  | Completed | 2024-09-20 | 1
2 | FAULTY WARMER HANDLE | AKWA IBOM, NWANIBA | Others | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2024-09-13 | 188 | 2024-09-13 | 0 | 2024-09-20 | 7 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 181 |  |  | Overdue
3 | FAULTY OVEN AND COLDROOM | PPU Opebi | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-09-06 | 14 | 2024-09-16 | 10 | 2024-09-20 | 4 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 0 |  |  | Completed | 2024-09-20 | 0
4 | FAULTY OVEN AND COLDROOM | PPU Opebi | Others | Breakdown | MACADAMS | OTHERS | OTHERS | 2024-09-06 | 195 | 2024-09-20 | 14 |  | 181 | [9 empty] | Overdue
5 | INVERTER NOT CHARGING PX VGC | LAG, VGC | Electrical Surge | Breakdown | CURRENT DATA | INVERTER BATTERIES | INVERTER | 2024-09-11 | 190 | 2024-09-11 | 0 | 2024-09-13 | 2 | [9 empty] | Overdue
6 | FAULTY INVERTER | LAG, BADORE | Electrical Surge | Breakdown | DALEMATRIX | INVERTER SYSTEM | INVERTER | 2024-09-04 | 5 | 2024-09-05 | 1 | 2024-09-09 | 4 | 2024-09-09 | 2024-09-09 | 0 | 2024-09-09 | 0 | 2024-09-09 | 0 |  |  | Completed | 2024-09-09 | 0
7 | FAULTY CABINET | LAG, BADORE | Electrical Surge | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-09-04 | 5 | 2024-09-05 | 1 | 2024-09-20 | 15 | 2024-09-09 | 2024-09-09 | 0 | 2024-09-09 | 0 | 2024-09-09 | 0 |  |  | Completed | 2024-09-09 | 0
8 | FAULTY FREEZER ROOM IN RUKPOKKWU | PH, RUKPOKWU | Others | Breakdown | MOFFEN | FREEZER ROOM | HVAC | 2024-09-18 | 7 | 2024-09-18 | 0 | 2024-09-20 | 2 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 5 |  |  | Completed | 2024-09-25 | 0
9 | FAULTY INVERTER | LAG, OKOTA | Electrical Surge | Breakdown | NISTECH | INVERTER SYSTEM | INVERTER | 2024-08-13 | 219 | 2024-08-13 | 0 | 2024-08-21 | 8 | 2024-09-25 | 2024-09-25 | 0 | 2024-09-25 | 0 | 2024-09-25 | 176 |  |  | Overdue
10 | FOH ROLLER SHUTTER | ABIA, ABA-OWERRI RD | Others | Breakdown | BASSCOM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-09-12 | 189 | 2024-09-12 | 0 | 2024-09-20 | 8 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 181 |  |  | Overdue
12 | PESTWALK BULB DEAD PX DIYA STREET | LAG, DIYA STREET | Others | Breakdown | KOLA ABODUNRIN | INSECT KILLER BOH | ELECTRICAL | 2024-09-19 | 1 | 2024-09-19 | 0 | 2024-09-20 | 1 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 0 |  |  | Completed | 2024-09-20 | 0
13 | DISPLAY CABINET PX DIYA STREET | LAG, DIYA STREET | Electrical Surge | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-09-19 | 182 | 2024-09-19 | 0 |  | 182 | [9 empty] | Overdue
14 | PYLON LIGHTS BAD | LAG, BODE THOMAS | Electrical Surge | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-09-13 | 188 | 2024-09-14 | 1 | 2024-09-15 | 1 | 2024-09-15 | 2024-09-20 | 5 | 2024-09-20 | 181 |  |  |  | 250000 | Overdue
15 | TILING OF FLOWER BED AND PROVISION OF POTTED PLANTS | LAG, OMOLE | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-09-21 | 180 | 2024-09-21 | 0 | 2024-09-21 | 0 | 2024-09-21 | 2024-09-23 | 2 | 2024-08-23 | 209 |  |  |  | 780000 | Overdue
16 | FAULTY GENERATOR FAN BELT | OYO, OWODE | Wear & Tear | Breakdown | DELIGHTSOME | GENERATOR | GENERATOR | 2024-09-20 | 181 | 2024-09-20 | 0 | 2024-09-20 | 0 | [9 empty] | Overdue
17 | GENERATOR SERVICE REQUEST | ANAMBRA, ZIK AVENUE, AWKA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-09-20 | 181 | 2024-09-20 | 0 |  | 181 | [9 empty] | Overdue
18 | WEAK STAFF ROOMS WALL | ANAMBRA, ZIK AVENUE, AWKA | Others | Breakdown | ARIZMAYAN | WALL | BUILDING | 2024-09-20 | 181 | 2024-09-20 | 0 |  | 181 | [9 empty] | Overdue
19 | CHANGING OF WATER TREATMENT UVS | LAG, OPEBI | Routine Servicing | Preventive | EMMANUL | OTHERS | OTHERS | 2024-09-18 | 183 | 2024-09-19 | 1 |  | 182 | [9 empty] | Overdue
20 | CONNECTING OF EXIT PATHWAY LIGHT ON INVERTER | LAG, OPEBI | Electrical Surge | Breakdown | FRIDAY | DROPPING LIGHT | ELECTRICAL | 2024-09-17 | 184 | 2024-09-18 | 1 |  | 183 | [9 empty] | Overdue
21 | WATER HEATER SWITCH FOR AC AND INSECT KILER BULB | LAG, BADORE | Electrical Surge | Breakdown | ADEREMI | WATER HEATER | PLUMBING | 2024-09-20 | 181 | 2024-09-20 | 0 |  | 181 | [9 empty] | Overdue
22 | AYETORO FREEZER ROOM NOT ATTAINING TEPERATURE | OSUN, GBONGAN | Routine Servicing | Preventive | TONA OGUNS | FREEZER ROOM | HVAC | 2024-09-19 | 2 | 2024-09-19 | 0 | 2024-09-20 | 1 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 1 | 2024-09-21 |  | Completed | 2024-09-21 | 1
23 | LEAKING GEEPEE TANK | LAG, ABULE EGBA | Others | Breakdown | PROPEARJEFF | AERATION TANK | WTP | 2024-09-19 | 5 | 2024-09-19 | 0 | 2024-09-21 | 2 | 2024-09-21 | 2024-09-21 | 0 | 2024-09-21 | 0 | 2024-09-21 | 3 | 2024-09-22 |  | Completed | 2024-09-24 | 0
24 | ELECTRICAL ISSUES IN STORE | LAG, FESTAC | Electrical Surge | Breakdown | TIMILEYIN | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-09-17 | 3 | 2024-09-17 | 0 | 2024-09-20 | 3 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 |  | Completed | 2024-09-20 | 1
25 | CHANGE OF SOME LOBBY TABLE HEAD | LAG, ABULE EGBA | Others | Breakdown | MATOLAD | CUSTOMER TABLE | FURNITURE | 2024-09-20 | 1 | 2024-09-20 | 0 | 2024-09-21 | 1 | 2024-09-21 | 2024-09-21 | 0 | 2024-09-21 | 0 | 2024-09-21 | 0 | 2024-09-21 |  | Completed | 2024-09-21 | 1
26 | FAULTY FREEZER ROOM LIGHT | LAG, FESTAC | Electrical Surge | Breakdown | TIMILEYIN | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-09-19 | 1 | 2024-09-19 | 0 | 2024-09-20 | 1 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 |  | Completed | 2024-09-20 | 1
28 | ELECTRICAL HAZARD PX OBA AKRAN | LAG, OBA AKRAN | Electrical Surge | Breakdown | TIMILEYIN | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 |  | Completed | 2024-09-20 | 1
29 | FAULTY TOILET PIPE | LAG, TEJUOSHO | Others | Breakdown | OLATUNDE | OTHERS | OTHERS | 2024-09-18 | 2 | 2024-09-18 | 0 | 2024-09-20 | 2 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 |  | Completed | 2024-09-20 | 1
30 | FAULTY INSECTOCUTOR AND LOBBY LIGHT | LAG, IRE-AKARI | Electrical Surge | Breakdown | FRIDAY | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-09-20 | 181 | 2024-09-20 | 0 |  | 181 | [9 empty] | Overdue
31 | ROLLER SHUTTER NOT WORKING | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | BASSCOM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-09-02 | 199 | 2024-09-05 | 3 | 2024-09-19 | 14 | 2024-09-19 | 2024-09-19 | 0 | 2024-09-19 | 0 | 2024-09-19 | 182 |  |  | Overdue
32 | FALLING CEILING BOARD | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | FULL TURN | CEILING BOARD | BUILDING | 2024-09-19 | 182 | 2024-09-19 | 0 |  | 182 | [9 empty] | Overdue
33 | CLOSING OF OPENED GENERATOR AREA | LAG, LATEEF JAKANDE | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-09-18 | 183 | 2024-09-18 | 0 |  | 183 | [9 empty] | Overdue
34 | WOBBLING LOBBY TABLE | LAG, AKOWONJO | Others | Breakdown | MATOLAD | CUSTOMER TABLE | FURNITURE | 2024-09-20 | 1 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 1 |  |  | Completed | 2024-09-21 | 0
35 | FREEZER ROOM NOT LATCHING | LAG, AGUNGI | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-09-20 | 181 | 2024-09-20 | 0 |  | 181 | [9 empty] | Overdue
36 | BOOK KEEPING SHELF PX VGC | LAG, VGC | Others | Breakdown | MATOLAD | WALL MOUNTED SHELVE | FURNITURE | 2024-09-17 | 184 | 2024-09-17 | 0 | 2024-09-17 | 0 | 2024-09-17 | 2024-09-17 | 0 | 2024-09-17 | 0 | 2024-09-17 | 184 | 2024-09-25 | 105000 | Overdue
37 | BOOK KEEPING SHELF PX BADORE | LAG, BADORE | Others | Breakdown | MATOLAD | WALL MOUNTED SHELVE | FURNITURE | 2024-09-17 | 184 | 2024-09-17 | 0 | 2024-09-17 | 0 | 2024-09-17 | 2024-09-17 | 0 | 2024-09-17 | 0 | 2024-09-17 | 184 | 2024-09-25 | 105000 | Overdue
38 | BOOK KEEPING SHELF PX MARINA | LAG, MARINA | Others | Breakdown | MATOLAD | WALL MOUNTED SHELVE | FURNITURE | 2024-09-17 | 184 | 2024-09-17 | 0 | 2024-09-17 | 0 | 2024-09-17 | 2024-09-17 | 0 | 2024-09-17 | 0 | 2024-09-17 | 184 | 2024-09-25 | 105000 | Overdue
39 | BROKEN WOOD CHEMICAL BOARD | LAG, TEJUOSHO | Others | Breakdown | MATOLAD | CHEMICAL CUPBOARD | FURNITURE | 2024-09-18 | 3 | 2024-09-18 | 0 | 2024-09-20 | 2 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 1 | 2024-09-21 |  | Completed | 2024-09-21 | 1
40 | DAMAGED CHEMICAL CUPBOARD PX | LAG, OKOTA | Others | Breakdown | MATOLAD | CHEMICAL CUPBOARD | FURNITURE | 2024-09-17 | 184 | 2024-09-17 | 0 | 2024-09-17 | 0 | 2024-09-17 | 2024-09-17 | 0 | 2024-09-17 | 1 | 2024-09-18 | 183 |  |  | Overdue
41 | JIBOWU STAFF LOCKER | LAG, JIBOWU | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-09-19 | 2 | 2024-09-19 | 0 | 2024-09-20 | 1 | 2024-09-21 | 2024-09-21 | 0 | 2024-09-21 | 0 | 2024-09-21 | 0 | 2024-09-21 |  | Completed | 2024-09-21 | 1
42 | CR OMOLE FAULTY BOH CHILLER | LAG, OMOLE | Others | Breakdown | G.B BOYEJO | OTHERS | OTHERS | 2024-09-20 | 181 | 2024-09-20 | 0 |  | 181 | [9 empty] | Overdue
43 | PX VGC INVERTER NOT CHARGING | LAG, VGC | Electrical Surge | Breakdown | CURRENT DATA | INVERTER BATTERIES | INVERTER | 2024-09-13 | 188 | 2024-09-13 | 0 | 2024-09-13 | 0 | [9 empty] | Overdue
44 | DAMAGED WARMER HANDLE | LAG, FREEDOMWAY | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-09-10 | 191 | 2024-09-10 | 0 |  | 191 | [9 empty] | Overdue
45 | LEAKING SINK | LAG, ALIMOSHO | Others | Breakdown | OLATUNDE | KITCHEN WASH HAND SINK | PLUMBING | 2024-09-18 | 2 | 2024-09-18 | 0 | 2024-09-20 | 2 | 2024-09-20 | 2024-09-20 | #REF! | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 |  | Completed | 2024-09-20 | 1
46 | ROTISSERIE MACHINE NOT ATTAINING TEMPERATURE | PH, ONNE | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-09-13 | 4 | 2024-09-13 | 0 | 2024-09-17 | 4 | 2024-09-17 | 2024-09-17 | 0 | 2024-09-17 | 0 | 2024-09-17 |  | 2024-09-17 |  | Completed | 2024-09-17 | 1
47 | DETACHED WALL TILES | LAG, NNPC ALAPERE | Others | Breakdown | ACORN | WALL | BUILDING | 2024-09-19 | 182 | 2024-09-20 | 1 |  | 181 | [9 empty] | Overdue
48 | BAD STAFF CHANGING ROOM LOCKERS LOCKS | LAG, MAGODO | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-09-20 | 181 | 2024-09-20 | 0 |  | 181 | [9 empty] | Overdue
49 | COLD ROOM NOT ATTAINING TEMPERATURE | IBADAN, CHALLENGE | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-09-20 | 181 | 2024-09-20 | 0 |  | 181 | [9 empty] | Overdue
50 | FAULTY DOOR FOR DRY STORE | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-09-18 | 2 | 2024-09-19 | 1 | 2024-09-20 | 1 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 |  | Completed | 2024-09-20 | 1
51 | SINK LEAKAGE | LAG, IDIMU | Others | Breakdown | OLATUNDE | KITCHEN WASH HAND SINK | PLUMBING | 2024-09-19 | 1 | 2024-09-19 | 0 | 2024-09-20 | 1 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 |  | Completed | 2024-09-20 | 1
52 | SCRAPER BLADE | LAG, OKOTA | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-09-12 | 8 | 2024-09-12 | 0 | 2024-09-19 | 7 | 2024-09-19 | 2024-09-19 | 0 | 2024-09-19 | 0 | 2024-09-19 | 1 |  |  | Completed | 2024-09-20 | 0
53 | FAULTY INVERTER | LAG, OKOTA | Electrical Surge | Breakdown | NISTECH | INVERTER SYSTEM | INVERTER | 2024-09-13 | 188 | 2024-09-17 | 4 |  | 184 | [9 empty] | Overdue
54 | PYLON LIGHTS BAD | LAG, BODE THOMAS | Others | Breakdown | ARIZMAYAN | DROPPING LIGHT | ELECTRICAL | 2024-09-13 | 188 | 2024-09-14 | 1 | 2024-09-14 | 0 | 2024-09-15 | 2024-09-20 | 5 | [5 empty] | 250000 | Overdue
55 | FREEZER ROOM NOT ATTAINING TEMPERTURE | BAYELSA, YENAGOA | Others | Breakdown | MOFFEN | FREEZER ROOM | HVAC | 2024-09-18 | 6 | 2024-09-18 | 0 | 2024-09-24 | 6 | 2024-09-24 | 2024-09-24 | 0 | 2024-09-24 | 0 | 2024-09-24 | 0 |  |  | Completed | 2024-09-24 | 0
56 | FAULTY LOGO LIGHT | LAG, JOEL OGUNNAIKE | Electrical Surge | Breakdown | ARIZMAYAN | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-09-19 | 182 | 2024-09-20 | 1 | 2024-09-20 | 0 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 181 |  |  | Overdue
57 | SEPTIC TANK EVACUTION EGBE RD | LAG, IKOTUN | Wear & Tear | Breakdown | MOOLIGHT | SEPTIC TANK | EVACUATION | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-21 |  | Completed | 2024-09-20 | 1
58 | BROKEN SLABS AT CAR PARK | ANAMBRA, LIMCA RD, ONITSHA | Others | Breakdown | DEACONESS | SLAB | BUILDING | 2024-09-20 | 181 | 2024-09-20 | 0 | 2024-09-20 | 0 | 2024-09-20 | 2024-09-20 | 0 | 2024-09-20 | 181 |  |  |  |  | Overdue
59 | LOBBY AC NOT WORKING | IBADAN, VENTURA MALL | Others | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-09-20 | 181 | 2024-09-20 | 0 |  | 181 | [9 empty] | Overdue
60 | FAULTY BULB AND FAN IN FEMALE CHANGE ROOM | LAG, OGUNLANA DRIVE | Electrical Surge | Breakdown | TIMILEYIN | WALL FAN | HVAC | 2024-09-19 | 6 | 2024-09-20 | 1 | 2024-09-25 | 5 | 2024-09-25 | 2024-09-25 | 0 | 2024-09-25 | 0 | 2024-09-25 | 0 |  |  | Completed | 2024-09-25 | 0
61 | URGENT GENERATOR OVERHEATING | OYO, OGBOMOSHO | Wear & Tear | Breakdown | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-09-22 | 179 | 2024-09-22 | 0 | 2024-09-24 | 2 | 2024-09-24 | 2024-09-24 | 0 | 2024-09-24 | 1 | 2024-09-25 | 176 |  |  | Overdue
62 | LEAKAGE OF A PUMPING MACHINE IN WTP | LAG, AKOWONJO | Others | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-09-11 | 190 | 2024-09-11 | 0 | 2024-09-25 | 14 | [9 empty] | Overdue
63 | REQUEST FOR FOUR WALL FAN | IBADAN, RING-ROAD | Others | Breakdown | RANEX4WARD | WALL FAN | HVAC | 2024-09-23 | 178 | 2024-09-24 | 1 | 2024-09-25 | 1 | [9 empty] | Overdue
64 | OFFICE AC AND LOBBY AC LEAKING | LAG, OGUDU | Others | Breakdown | PROPEARJEFF | 5HP STANDING AC UNIT 1 | HVAC | 2024-09-24 | 1 | 2024-09-24 | 0 | 2024-09-25 | 1 | 2024-09-25 | 2024-09-25 | 0 | 2024-09-25 | 0 | 2024-09-25 | 0 | 2024-09-26 |  | Completed | 2024-09-25 | 1
65 | FAULTY INVERTER | IBADAN, MOKOLA | Others | Breakdown | NISTECH | INVERTER SYSTEM | INVERTER | 2024-09-19 | 7 | 2024-09-19 | 0 | 2024-09-25 | 6 | 2024-09-25 | 2024-09-25 | 0 | 2024-09-25 | 1 | 2024-09-26 | 0 | 2024-09-27 | 86000 | Completed | 2024-09-26 | 1
66 | BAD ENTRANCE DOOR | LAG, ONIRU | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-09-23 | 178 | 2024-09-24 | 1 | 2024-09-25 | 1 | [9 empty] | Overdue
67 | FAULTY LOBBY ENTRANCE DOOR | LAG, DIYA STREET | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-09-23 | 178 | 2024-09-24 | 1 | 2024-09-24 | 0 | 2024-09-24 | 2024-09-24 | 0 | [6 empty] | Overdue
68 | DISCOLOURED WATER | LAG, HEYDEN ALAPERE | Others | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-09-14 | 187 | 2024-09-14 | 0 | 2024-09-16 | 2 | 2024-09-16 | 2024-09-16 | 0 | 2024-09-16 | 185 |  |  |  |  | Overdue
69 | STORE TRANSFORMER BLOW | LAG, AJAH | Electrical Surge | Breakdown | AUSBETH | TRANSFORMER | ELECTRICAL | 2024-09-12 | 4 | 2024-09-12 | 0 | 2024-09-16 | 4 | 2024-09-16 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 | 0 |  |  | Completed | 2024-09-16 | 0
70 | GENERATOR BREAKDOWN PPU RHAMAT PARK |  | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-09-15 | 2 | 2024-09-15 | 0 | 2024-09-16 | 1 | 2024-09-16 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 |  |  |  | Completed | 2024-09-17 | 0
71 | BURNT ACs CABLES | LAG, MARINA | Electrical Surge | Breakdown | ISMAIL | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-09-11 | 5 | 2024-09-11 | 0 | 2024-09-14 | 3 | 2024-09-14 | 2024-09-14 | 0 | 2024-09-14 | 0 | 2024-09-14 | 2 |  |  | Completed | 2024-09-16 | 0
72 | GENERATOR SERVICING | IBADAN, BODIJA | Routine Servicing | Preventive | SYMINERTIAS | GENERATOR | GENERATOR | 2024-09-11 | 190 | 2024-09-13 | 2 | 2024-09-15 | 2 | 2024-09-15 | 2024-09-15 | 0 | 2024-09-16 | 0 | 2024-09-16 | 185 |  |  | Overdue
73 | FAULTY TEA BOILER DISPENSER | LAG, OSOLOWAY | Electrical Surge | Breakdown |  | OTHERS | OTHERS | 2024-09-16 | 185 | 2024-09-16 | 0 |  | 185 | [9 empty] | Overdue
74 | FAULTY FREEZER ROOM | CALABAR, NDIDEM | Others | Breakdown | BCE | FREEZER ROOM | HVAC | 2024-09-11 | 190 | 2024-09-11 | 0 |  | 190 | [9 empty] | Overdue
75 | OPENED SOCKETS IN THE STORE | LAG, IKORODU | Electrical Surge | Breakdown | ADEREMI | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 | 0 |  |  | Completed | 2024-09-16 | 0
76 | REPAIR OF PLUMBING FITTINGS | LAG, ISAWO-IKORODU | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-09-21 | 180 | 2024-09-21 | 0 | 2024-09-22 | 1 | 2024-09-22 | 2024-09-23 | 1 | 2024-09-24 | 1 | 2024-09-25 | 176 |  | 53750 | Overdue
77 | FIXING OF OPEN AND BROKEN WALL TILES | LAG, ABULE EGBA | Others | Breakdown | PENTECOSTAL | WALL | BUILDING | 2024-09-03 | 198 | 2024-09-03 | 0 | 2024-09-16 | 13 | 2024-09-16 |  | 185 | [6 empty] | Overdue
78 | LED LIGHT REQUEST | IBADAN, RING-ROAD | Electrical Surge | Breakdown | RANEX4WARD | DROPPING LIGHT | ELECTRICAL | 2024-09-16 | 1 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 | 1 | 2024-10-17 |  | Completed | 2024-09-17 | 1
79 | FAULTY COLD ROOM BULB | LAG, EKORO | Electrical Surge | Breakdown | TAYO ALBERT | DROPPING LIGHT | ELECTRICAL | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-17 |  | Completed | 2024-09-16 | 1
80 | REQUEST FOR ELECTRICAL MATERIALS | IBADAN, IDI-APE (IWO RD) | Electrical Surge | Breakdown | RANEX4WARD | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-09-16 | 185 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 | 2024-09-16 | 0 | 2024-09-16 | 185 |  |  |  | 112875 | Overdue
81 | BROKEN FREEZER ROOM DOOR HANDLE | AKWA IBOM, IKOT EKPENE RD | Others | Breakdown | MOFFEN | FREEZER ROOM | HVAC | 2024-09-13 | 188 | 2024-09-13 | 0 |  | 188 | [9 empty] | Overdue
82 | FAULTY ROTISERIE MACHINE | LAG, OSOLOWAY | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-10-16 |  | Completed | 2024-09-16 | 1
83 | REQUEST FOR INVERTER AND BATTERY STAND | LAG, LATEEF JAKANDE | Electrical Surge | Breakdown | DALEMATRIX | INVERTER SYSTEM | INVERTER | 2024-09-10 | 191 | 2024-09-10 | 0 | 2024-09-15 | 5 | 2024-09-15 | 2024-09-15 | 0 | 2024-09-16 | 0 | 2024-09-16 | 185 |  |  | Overdue
84 | FAULTY TAPS AT BOH | LAG, IKOTUN | Others | Breakdown | PROPEARJEFF | TAP | PLUMBING | 2024-09-12 | 4 | 2024-09-16 | 4 | 2024-09-16 | 0 | 2024-09-16 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 | 0 | 2024-09-16 |  | Completed | 2024-09-16 | 1
85 | FLOODED BOH BACAUSE OF BLOCKED DRAINAGE | LAG, AJAH | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-09-15 | 186 | 2024-09-16 | 1 |  | 185 | [9 empty] | Overdue
86 | COLD ROOM DOOR NOT CLOSING TIGHTLY | LAG, ILUPEJU | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-09-16 | 185 | 2024-09-16 | 0 | 2024-09-16 | 0 | [9 empty] | Overdue
87 | WATER TREATMENT NOT WORKING | LAG, HEYDEN ALAPERE | Others | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-09-23 | 2 | 2024-09-23 | 0 | 2024-09-23 | 0 | 2024-09-23 | 2024-09-23 | 0 | 2024-09-23 | 0 | 2024-09-23 | 2 | 2024-09-25 |  | Completed | 2024-09-25 | 1
88 | HOT WATER NOT ATTAINING TMP | LAG, OPEBI | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-09-25 | 0 | 2024-09-25 | 0 | 2024-09-25 | 0 | 2024-09-25 | 2024-09-25 | 0 | 2024-09-25 | 0 | 2024-09-25 | 0 | 2024-10-25 |  | Completed | 2024-09-25 | 1
89 | CHANGING OF WATER TREATMENT UVS | LAG, OPEBI | Others | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-09-18 | 183 | 2024-09-19 | 1 | 2024-09-26 | 7 | [9 empty] | Overdue
90 | FAULTY TAYLOR MACHINE | LAG, MOBIL OGBA | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-09-19 | 182 | 2024-09-19 | 0 |  | 182 | [9 empty] | Overdue
91 | FAULTY ROTISEERIE MACHINE | ENUGU, NSUKKA | Others | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-09-15 | 10 | 2024-09-15 | 0 | 2024-09-25 | 10 | 2024-09-25 | 2024-09-25 | 0 | 2024-09-25 | 0 | 2024-09-25 | 0 | 2024-09-25 |  | Completed | 2024-09-25 | 1
92 | GAS LEAKAGE AT BACK OF HOUSE | LAG, FESTAC | Others | Breakdown | BERRADE | GAS CYLINDER | GAS | 2024-09-25 | 176 | 2024-09-25 | 0 |  | 176 | [9 empty] | Overdue
93 | REQUEST FOR ICE CREAM MACHINE PARTS | LAG, OMOLE | Others | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-09-24 | 177 | 2024-09-24 | 0 | 2024-09-26 | 2 | [9 empty] | Overdue
94 | FAULTY DIESEL FILTER | EBONYI, AFIKPO, ABAKALIKI | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-09-25 | 176 | 2024-09-25 | 0 | 2024-09-25 | 0 | [9 empty] | Overdue
95 | FAULTY SECURITY LIGHT CAR PARK | LAG, FESTAC | Electrical Surge | Breakdown | TIMILEYIN | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-09-26 | 11 | 2024-09-27 | 1 |  | 174 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 |  | Completed | 2024-10-07 | 1
96 | GENERATOR CONSUMING HIGH DIESEL | LAG, AGUNGI | Corrective Action | Corrective | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-09-15 | 186 | 2024-09-15 | 0 | 2024-09-19 | 4 | 2024-09-25 | 2024-09-25 | 0 | 2024-09-25 | 2 | 2024-09-27 | 174 |  |  | Overdue
97 | BLOWN INSECTICUTOR BULB | LAG, ONIRU | Electrical Surge | Breakdown | ADEREMI | INSECT KILLER BOH | ELECTRICAL | 2024-09-27 | 174 | 2024-09-27 | 0 |  | 174 | [9 empty] | Overdue
98 | HOT WATER NOT ATTAINING TEMP | LAG, ONIRU | Others | Breakdown | JOEL OMOTOSHO | OTHERS | OTHERS | 2024-09-27 | 174 | 2024-09-27 | 0 |  | 174 | [9 empty] | Overdue
99 | GENERATOR DUE FOR SERVICING | OSUN, AYETORO | Routine Servicing | Preventive | SYMINERTIAS | GENERATOR | GENERATOR | 2024-09-26 | 175 | 2024-09-26 | 0 |  | 175 | [9 empty] | Overdue
100 | FREEZER ROOM NOT ATTAINNING MAXIMUM TEMP | LAG, MARINA | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-09-26 | 175 | 2024-09-27 | 1 |  | 174 | [9 empty] | Overdue
101 | FREEZER ROOM NOT WORKING | IBADAN, BODIJA | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-09-24 | 177 | 2024-09-27 | 3 |  | 174 | [9 empty] | Overdue
102 | GENERATOR BREAKDOWN AKOBO | IBADAN, AKOBO | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR |  |  | 2024-09-26 | 45561 | 2024-09-26 | 0 | 2024-09-26 | 2024-09-26 | 0 | 2024-09-26 | #REF! | 2024-09-27 | #REF!
103 | FAULTY FREEZER ROOM BLADE | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-09-10 | 17 | 2024-09-10 | 0 | 2024-09-11 | 1 | 2024-09-13 | 2024-09-19 | 6 | 2024-09-24 | -3 | 2024-09-24 | 3 |  |  | Completed | 2024-09-27 | 0
104 | CEILING COLLPASE AT VGC | LAG, VGC | Others | Breakdown | CRADLEVIEW | CEILING BOARD | BUILDING | 2024-09-27 | 174 | 2024-09-27 | 0 | 2024-09-27 | 0 | [9 empty] | Overdue
105 | FULL SOAK AWAY | LAG, JIBOWU | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-09-21 | 180 | 2024-09-21 | 0 | 2024-09-27 | 6 | [9 empty] | Overdue
106 | FAULTY COLLECTRAMATIC | LAG, OGUDU | Electrical Surge | Breakdown | BCE | COLLECTRAMATIC OIL PUMP MACHINE | KITCHEN_EQUIPMENT | 2024-09-21 | 180 | 2024-09-21 | 0 |  | 180 | [9 empty] | Overdue
107 | CONNECTION OF DISEL LINE DIRECTLY TO GEN | UGBOWO | Others | Breakdown | PRO EQUIP | GENERATOR | GENERATOR | 2024-09-04 | 197 | 2024-09-04 | 0 | 2024-10-03 | 29 | 2024-10-04 |  | 167 | [6 empty] | Overdue
108 | LEAKING CEILING | LAG, TOTAL LEKKI | Others | Breakdown | ARIZMAYAN | CEILING BOARD | BUILDING | 2024-09-25 | 19 | 2024-09-26 | 1 | 2024-10-03 | 7 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-04 | 0 | 2024-10-04 | 10 | 2024-10-14 | 101000 | Completed | 2024-10-14 | 1
109 | OVERHEATING OF THE GENSET | ANAMBRA, AWKA RD, ONITSHA | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-09-30 | 171 | 2024-10-01 | 1 | 2024-10-01 | 0 | [9 empty] | Overdue
110 | LOBBY AC NOT WORKING INFECTIVELY | LAG, ETERNA LEKKI | Electrical Surge | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-09-28 | 173 | 2024-10-02 | 4 |  | 169 | [9 empty] | Overdue
111 | FAULTHY WATER HEARTER | LAG, IRE-AKARI | Electrical Surge | Breakdown | PROEQUIPTECH | WATER HEATER | PLUMBING | 2024-09-27 | 174 | 2024-09-28 | 1 | 2024-10-02 | 4 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 169 |  |  |  |  | Overdue
112 | RELOCATION OF CR OMOLE DOZING DRUM/UV LIGHT IN THE WATER TREATMENT PLANT | LAG, OMOLE | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-09-23 | 178 | 2024-09-23 | 0 | 2024-09-25 | 2 | [9 empty] | Overdue
113 | FAULTY ROLLER SHUTTER | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-09-30 | 171 | 2024-09-30 | 0 | 2024-09-30 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 169 |  |  | 2024-10-02 | 71593.75 | Overdue
114 | ENTRANCE DOOR | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | FULLTURN | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-09-25 | 14 | 2024-09-25 | 0 | 2024-10-04 | 9 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 |  | Completed | 2024-10-09 | 1
115 | FAULTY INVERTER PANEL | CALABAR, NDIDEM | Others | Breakdown | PETOJA | INVERTER DB | ELECTRICAL | 2024-09-30 | 171 | 2024-10-06 | 6 | 2024-10-06 | 0 | [9 empty] | Overdue
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
Formulas:
Days Since Request = IF([Request Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Request Date],TODAY()-[Request Date]))
Days Delayed by Helpdesk = IF([Date Shared by Helpdesk]<>"",[Date Shared by Helpdesk]-[Request Date],IF([Request Date]="","",TODAY()-[Request Date]))
Days Delayed by Vendor/Technician = IF(M6<>"",M6-[Date Shared by Helpdesk],IF([Date Shared by Helpdesk]="","",TODAY()-[Date Shared by Helpdesk]))
Days Since Negotiation Request = TODAY() - [Date Negotiated]
Days Since Negotiation Request = IF([Date Negotiated]<>"",[Date Negotiated]-[Date Sent for Negotiation],IF([Date Sent for Negotiation]="","",TODAY()-[Date Sent for Negotiation]))
Days Since Approval Request = IF([Approved Date]<>"",[Approved Date]-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval Request = IF(#REF!<>"",#REF!-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval = IF([Approved Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Approved Date],TODAY()-[Approved Date]))
Days Since Approval = IF(#REF!="","",IF([Actual delivery date]<>"",[Actual delivery date]-#REF!,TODAY()-#REF!))
Status = IF([Request Date]="","",IF([Actual delivery date]<>"","Completed",IF(TODAY()<[Expected Delivery Date],"Planned",IF(TODAY()=[Expected Delivery Date],"Due","Overdue"))))
Note on AA6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vendor gave feedback thaat part is not available on 18 of Jan

## OCTOBER
Legend
Completed on time
Completed late
258000 | ACTION/TASK | Store | Reason for Breakdown | Maintenance Category | Responsible | Specific Equipment | Category | Request Date | Days Since Request | Date Shared by Helpdesk | Days Delayed by Helpdesk | Date Attended/Checked by Vendor/Technician | Days Delayed by Vendor/Technician | Date Sent for Negotiation | Date Negotiated | Days Since Negotiation Request | Date Approval Requested | Days Since Approval Request | Approved Date | Days Since Approval | Expected Delivery Date | Cost | Status | Actual delivery date | Compliance check | Insert Comment
1 | EVACUATION OF CAR PARK DRAINAGE | LAG, ILUPEJU | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-10-03 | 168 | 2024-10-03 | 0 | 2024-10-04 | 1 |  |  | 45736 | [6 empty] | Overdue
2 | BOLLARD POLE CONSTRUCTION AT PX IGANDO |  | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-10-04 | 167 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 2 | 2024-10-06 | 165 |  |  | Overdue
3 | AYETORO STORE GENERATOR BREAKDOWN | OSUN, AYETORO | Wear & Tear | Breakdown | SYMINERTIAS | GENERATOR | GENERATOR | 2024-10-04 | 3 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-05 | 2024-10-07 | 2 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 207875 | Completed | 2024-10-07 | 1
4 | CARPENTRY CEILING AND HVAC JOBS | LAG, MOBIL OGBA | Others | Breakdown | ACORN | CEILING BOARD | BUILDING | 2024-10-04 | 167 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 2024-10-15 | 11 | 2024-10-15 | 0 | 2024-10-15 | 156 |  | 720000 | Overdue
5 | REQUEST FOR ELECTRICAL MATERIALS | IBADAN, MOKOLA | Electrical Surge | Breakdown | RANEX4WARD | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-10-04 | 1 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 1 | 2024-10-05 | 0 | 2024-10-05 |  | Completed | 2024-10-05 | 1
6 | FAULTY HENNY PENNY FORE HEAD MACHINE | LAG, LATEEF JAKANDE | Others | Breakdown | HEFHEM | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-01 | 2 | 2024-10-01 | 0 | 2024-10-03 | 2 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 |  | Completed | 2024-10-03 | 1
7 | FULL SEPTIC TANK | LAG, ABULE EGBA | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-10-03 | 5 | 2024-10-04 | 1 | 2024-10-04 | 0 | 2024-10-04 |  | 167 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 225750 | Completed | 2024-10-08 | 1
8 | SERVICING OF GENERATOR | OYO, OWODE | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-10-04 | 167 | 2024-10-04 | 0 |  | 167 | [9 empty] | Overdue
9 | OVERHEATING OF THE GENSET | ANAMBRA, AWKA RD, ONITSHA | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | NIL | Completed | 2024-10-01 | 1
10 | Fallen CR signage | LAG, OSOLOWAY | Others | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-10-01 | 6 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-03 | 2024-10-04 | 1 | 2024-10-04 | 0 | 2024-10-04 | 3 | 2024-10-07 | 120000 | Completed | 2024-10-07 | 1
11 | REPAINTING OF INTERIOR AND EXTERIOR WALL | IMO, OKIGWE | Wear & Tear | Breakdown | JOWYN | PAINTING | BUILDING | 2024-09-30 | 171 | 2024-10-01 | 1 | 2024-10-01 | 0 | 2024-10-10 | 2024-10-13 | 3 | 2024-10-14 | 0 | 2024-10-14 | 157 |  |  | Overdue
12 | OPEN BODY OF KIOSK | LAG, OBA AKRAN | Wear & Tear | Breakdown | PENTECOSTAL | WALL | BUILDING | 2024-09-30 | 171 | 2024-10-01 | 1 | 2024-10-17 | 16 | 2024-10-17 | 2024-10-17 | 0 | 2024-10-17 | 0 | 2024-10-17 | 154 | 2024-10-17 |  | Overdue
13 | ELECTRICAL ISSUES | LAG, BODE THOMAS | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 136095 | Completed | 2024-10-01 | 1
14 | GENERATOR DUE FOR SERVICING | IBADAN, MOKOLA | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 189500 | Completed | 2024-10-01 | 1
15 | LEAKING BOH BCE CHILLER | LAG, SKYMALL | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2024-10-01 | 170 | 2024-10-01 | 0 |  | 170 | [9 empty] | Overdue
16 | FAULTY OFFICE AC | PH, DOX RD | Wear & Tear | Breakdown | MOFEEN | OTHERS | OTHERS | 2024-10-01 | 18 | 2024-10-01 | 0 | 2024-10-04 | 3 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 15 | 2024-10-19 | 310000 | Completed | 2024-10-19 | 1
17 | REQUEST FOR RESPRAYING OF LOBBY WASTE BIN | LAG, SKYMALL | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-10-01 | 170 | 2024-10-01 | 0 |  | 170 | [9 empty] | Overdue
18 | Electrical materials request for ogbor hill cr | ABIA, OGBOR HILLS | Others | Breakdown | RANEX4WARD | OTHERS | OTHERS | 2024-09-30 | 6 | 2024-10-01 | 1 | 2024-10-01 | 0 | 2024-10-01 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 5 | 2024-10-06 | 74712.5 | Completed | 2024-10-06 | 1
19 | REQUEST FOR REPAINTING OF BOH NET DOOR | LAG, SKYMALL | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-10-01 | 170 | 2024-10-01 | 0 |  | 170 | [9 empty] | Overdue
20 | COLDROOM NOT WORKING | LAG, ILUPEJU | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-10-01 | 170 | 2024-10-01 | 0 |  | 170 | [9 empty] | Overdue
21 | LEAKING COOK TAP | LAG, MMA2 | Wear & Tear | Breakdown | PROPEARJEFF | TAP | PLUMBING | 2024-10-01 | 170 | 2024-10-01 | 0 |  | 170 | [9 empty] | Overdue
22 | FAULTY HOT WATER | LAG, ABULE EGBA | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-05-25 | 151 | 2024-10-01 | 129 | 2024-10-18 | 17 | 2024-10-18 | 2024-10-18 | 0 | 2024-10-18 | 0 | 2024-10-18 | 5 | 2024-10-23 | 65000 | Completed | 2024-10-23 | 1
23 | Faulty glass door handle | LAG, OSOLOWAY | Wear & Tear | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-10-01 | 1 | 2024-10-01 | 0 | 2024-10-02 | 1 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 43000 | Completed | 2024-10-02 | 1
24 | DOOR LOCK REPAIR NEEDED | LAG, OSOLOWAY | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-10-06 | 2 | 2024-10-06 | 0 | 2024-10-08 | 2 | 2024-10-09 |  | 162 | 2024-10-09 | 162 |  |  |  | 31300 | Completed | 2024-10-08 | 0
25 | LOBBY AC AND DRY STORE AC NOT COOLING | LAG, ABULE EGBA | Routine Servicing | Preventive | G.B BOYEJO | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-01 | 170 | 2024-10-01 | 0 |  | 170 | [9 empty] | Overdue
26 | BAD FREEZER ROOM AND COLD ROOM ENTRANCE | LAG, ABULE EGBA | Users Misuse | Breakdown | DYNAMITE | COLD ROOM UNIT | HVAC | 2024-10-01 | 170 | 2024-10-01 | 0 |  | 170 | [9 empty] | Overdue
27 | FAULTY GENERATOR AT CR ISAWO | LAG, ISAWO-IKORODU | Corrective Action | Corrective | DELIGHTSOME | GENERATOR | GENERATOR | 2024-09-25 | 22 | 2024-09-25 | 0 | 2024-10-01 | 6 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-04 | 0 | 2024-10-04 | 13 | 2024-10-07 | 1051350 | Completed | 2024-10-17 | 0
28 | CHANGE OF INDUSTRIAL SOCKETS | LAG, ABULE EGBA | Wear & Tear | Breakdown | TAYO ALBERT | OTHERS | OTHERS | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 |  | Completed | 2024-10-01 | 1
29 | BAD ENTRANCE DOOR HANDLE | LAG, ABULE EGBA | Users Misuse | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-10-01 | 8 | 2024-10-01 | 0 | 2024-10-06 | 5 | 2024-10-06 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 3 | 2024-10-06 | 32000 | Completed | 2024-10-09 | 0
30 | BREAD TOASTER NOT WORKING | LAG, OKOTA | Wear & Tear | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2024-10-01 | 9 | 2024-10-01 | 0 | 2024-10-07 | 6 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 3 | 2024-10-10 | 54825 | Completed | 2024-10-10 | 1
31 | LEAKING AC IN THE LOBBY | LAG, MOBIL OGBA | Routine Servicing | Preventive | TRIPPLE O | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-01 | 170 | 2024-10-01 | 0 | 2024-10-03 | 2 | 2024-10-04 | 2024-10-04 | 0 | [5 empty] | 519000 | Overdue
32 | FAULTY HENNY PENNY FORE HEAD MACHINE | LAG, LATEEF JAKANDE | Electrical Surge | Breakdown | HEFHEM | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-01 | 3 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 3 | 2024-10-04 |  | Completed | 2024-10-04 | 1
33 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-01 | 3 | 2024-10-01 | 0 | 2024-10-02 | 1 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2 | 2024-10-04 | 184900 | Completed | 2024-10-04 | 1
36 | BOTTOM HEAT OF DISPLAY CABINET NOT ATTAINING TEMPERATURE | LAG, OGUDU | Users Misuse | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-02 | 15 | 2024-10-02 | 0 | 2024-10-16 | 14 | 2024-10-16 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-10-16 | 1 | 2024-10-17 | 130075 | Completed | 2024-10-17 | 1
37 | CABINET SHOCKING | LAG, JIBOWU | Electrical Surge | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-01 | 1 | 2024-10-02 | 1 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 230000 | Completed | 2024-10-02 | 1
38 | FADED GANGWAY AT CARPARK (INTERIOR & EXTERIOR PAINTING | LAG, EKORO | Wear & Tear | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-10-02 | 1 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 2 | 2024-10-04 | -1 | 2024-10-04 | 266125 | Completed | 2024-10-03 | 1
39 | REQUEST FOR GENERATOR SERVICING, WASHING OF GENERATOR RADIATOR AND CHANGING OF GENERATOR WATER FILTER. LIMCA ROAD | ANAMBRA, LIMCA RD, ONITSHA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-01 | 9 | 2024-10-01 | 0 | 2024-10-02 | 1 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 8 | 2024-10-10 | 392160 | Completed | 2024-10-10 | 1
40 | BLOCKED PIPE IN CUSTOMER RESTROOM | LAG, ETERNA LEKKI | Corrective Action | Corrective | JOEL OMOTOSHO | SPLIT UNIT TOILET | HVAC | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | [7 empty] | 2024-10-02 |  | Completed | 2024-10-02 | 1
41 | BLOWN BULB IN THE LOBBY | LAG, ONIRU | Electrical Surge | Breakdown | ADEREMI KAZEEM | DROPPING LIGHT | ELECTRICAL | 2024-10-02 | 169 | 2024-10-02 | 0 |  | 169 | [9 empty] | Overdue
42 | FREEZER ROOM NOT ATTAINIG TEMPERATURE | PH AGGREY | Routine Servicing | Preventive | MOFEEN | FREEZER ROOM | HVAC | 2024-10-02 | 11 | 2024-10-02 | 0 | 2024-10-03 | 1 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 10 | 2024-10-13 | 90000 | Completed | 2024-10-13 | 1
43 | FAULTY FREEZER ROOM DOOR LACK | PH, GRA BIRABI | Users Misuse | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-09-29 | 3 | 2024-09-29 | 0 | 2024-10-02 | 3 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 70000 | Completed | 2024-10-02 | 1
44 | FAULTY ROLLER SHUTTER | LAG, OKOTA | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-03 | 20 | 2024-10-04 | 1 | 2024-10-04 | 0 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 13 | 2024-10-10 | 71593.75 | Completed | 2024-10-23 | #REF!
45 | FAULTY ROLLER SHUTTER | LAG, ILUPEJU | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-07 | 3 | 2024-10-07 | 0 | 2024-10-08 | 1 | 2024-10-10 | 2024-10-10 | #REF! | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 87827.5 | Completed | 2024-10-10 | 1
46 | FAULTY ROLLER SHUTTER | LAG, OSOLOWAY | Corrective Action | Corrective | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 |  | 2024-10-08 |  | Completed | 2024-10-08 | 1
47 | Faulty Roller Shutter key | LAG, IDIMU | Wear & Tear | Breakdown | VENYS | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-09 | 162 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 2024-10-14 | 5 | 2024-10-14 | 157 |  |  |  | 80000 | Overdue
48 | Stuck Roller Shutter at Px Ogunnaike | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | ACORN | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-11 | 3 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-10 | 4 | 2024-10-14 | 0 | 2024-10-14 | 86875 | Completed | 2024-10-14 | 1
49 | SEWAGE EVACUATION | LAG, EJIGBO | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-02 | 169 | 2024-10-02 | 0 |  | 169 | [9 empty] | Overdue
50 | SEWAGE EVACUATION | LAG, TOTAL LEKKI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 |  | Completed | 2024-10-02 | 1
51 | SEWAGE EVACUATION | LAG, TOTAL LEKKI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-13 | 158 | 2024-10-13 | 0 |  | 158 | [9 empty] | Overdue
52 | GENERATOR SHUTDOWN DURING USAGE | LAG, EKORO | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | Completed | 2024-10-02 | 1
53 | FAUTLY INSECT KILLER | LAG, MARINA | Corrective Action | Corrective | ISMAIL | INSECT KILLER LOBBY 1 | ELECTRICAL | 2024-10-02 | 1 | 2024-10-02 | 0 | 2024-10-03 | 1 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 |  | Completed | 2024-10-03 | 1
54 | AC SERVICING | LAG, JIBOWU | Routine Servicing | Preventive | FOLLTEC | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-02 | 169 | 2024-10-02 | 0 | 2024-10-03 | 1 | [9 empty] | Overdue
55 | AC SERVICING | LAG, JIBOWU | Routine Servicing | Preventive | FOLLTEC | 5HP STANDING AC UNIT 2 | HVAC | 2024-10-03 | 168 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 168 | 2024-10-03 |  | Overdue
56 | REQUEST FOR AC SERVICING | ANAMBRA, ZIK AVENUE, AWKA | Routine Servicing | Preventive | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-09 | 10 | 2024-10-09 | 0 | 2024-10-15 | 6 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 4 | 2024-10-19 | 170000 | Completed | 2024-10-19 | 1
57 | AC SERVICING | PH, ABA | Routine Servicing | Preventive | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-13 | 158 | 2024-10-13 | 0 |  | 158 | [9 empty] | Overdue
58 | CHEST FREEZER NOT WORKING. | IBADAN, CHALLENGE | Wear & Tear | Breakdown | NURUDEEN | CHEST FREEZER | HVAC | 2024-09-30 | 171 | 2024-09-30 | 0 | 2024-10-02 | 2 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 2 | 2024-10-05 | 166 |  | 195757.5 | Overdue
59 | Supply of K-ROD | LAG, OSOLOWAY | Corrective Action | Corrective | PROPEARJEFF | WATER HEATER | PLUMBING | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 |  | Completed | 2024-10-02 | 1
60 | CR ZONE 6 GENERATOR DUE FOR SERVICE | ABUJA, OANDO ZONE 6 | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-10-01 | 9 | 2024-10-02 | 1 | 2024-10-03 | 1 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-04 | 0 | 2024-10-04 | 6 | 2024-10-10 | 236500 | Completed | 2024-10-10 | 1
61 | SEPTIC TANK EVACUATION | LAG, IKORODU | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-01 | 1 | 2024-10-02 | 1 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 |  | Completed | 2024-10-02 | 1
62 | SEPTIC TANK EVACUATION | LAG, ISAWO-IKORODU | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 215375 | Completed | 2024-10-10 | 1
63 | SEPTIC TANK EVACUATION | LAG, LATEEF JAKANDE | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-10-05 | 1 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 1 | 2024-10-06 |  | Completed | 2024-10-06 | 1
64 | LEAKING LOBBY ROOF - CR NSUKKA | ENUGU, NSUKKA | Wear & Tear | Breakdown | DT CONSULT | CEILING BOARD | BUILDING | 2024-10-01 | 170 | 2024-10-02 | 1 | 2024-10-09 | 7 | 2024-10-10 | 2024-10-13 | 3 | 2024-10-13 | 1 | 2024-10-14 | 157 |  | 400000 | Overdue
65 | AC DUE FOR SERVICING; CR AWKA ROAD | ANAMBRA, AWKA RD, ONITSHA | Routine Servicing | Preventive | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-01 | 16 | 2024-10-02 | 1 | 2024-10-17 | 15 | 2024-10-17 | 2024-10-17 | 0 | 2024-10-17 | 0 | 2024-10-17 | 0 | 2024-10-17 | 319000 | Completed | 2024-10-17 | 1
66 | FAULTY DISPLAY CABINET & DETACHED FLAP | LAG, AGUNGI | Electrical Surge | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-01 | 1 | 2024-10-02 | 1 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 25958.5 | Completed | 2024-10-02 | 1
67 | DEAD SECURITY LIGHT AT CAR PARK / LED LIGHT AT PRODCUTION FLOOR | LAG, EKORO | Wear & Tear | Breakdown | TAYO | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-10-01 | 1 | 2024-10-02 | 1 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | Completed | 2024-10-02 | 1
68 | FAULTY MACADAMS PRESSURE | LAG, LATEEF JAKANDE | Wear & Tear | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-01 | 2 | 2024-10-02 | 1 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 1 | 2024-10-03 |  | Completed | 2024-10-03 | 1
69 | CONSTRUCTION OF STAND FOR THE FREE STANDING BANNER AND PYLON LIGHT | LAG, IDI-IROKO RD | Others | Breakdown | PENTECOSTAL | BALOON STAND | OTHERS | 2024-10-01 | 170 | 2024-10-02 | 1 | 2024-10-14 | 12 | 2024-10-14 | 2024-10-15 | 1 | 2024-10-15 | 156 |  |  |  |  | Overdue
70 | REPLCEMENT OF THE LOBBY TABLES AND REPAINTING OF THE CAHIER COUNTER TOP AND LOBBY FAMILY CHAIRS | LAG, IDI-IROKO RD | Users Misuse | Breakdown | MATOLAD | CUSTOMER TABLE | FURNITURE | 2024-10-01 | 170 | 2024-10-02 | 1 | 2024-10-03 | 1 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 168 |  |  |  | 768625 | Overdue
71 | ELECTRIC ISSUE IN THE STORE | LAG, LEKKI PHASE 1 | Electrical Surge | Breakdown | ISMAIL | CHANGE OVER | ELECTRICAL | 2024-10-01 | 1 | 2024-10-02 | 1 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 |  | Completed | 2024-10-02 | 1
72 | CR OMOLE FAULTY BOH CHILELR | LAG, OMOLE | Wear & Tear | Breakdown | G.B BOYEJO | NBC CHILLER | HVAC | 2024-10-06 | 165 | 2024-10-06 | 0 |  | 165 | [9 empty] | Overdue
73 | BROKEN CABINET BULB GLASS | LAG, WAREHOUSE RD, APAPA | Users Misuse | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-06 | 8 | 2024-10-06 | 0 | 2024-10-08 | 2 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 6 | 2024-10-11 | 66000 | Completed | 2024-10-14 | 0
74 | VEGETABLE SHREDDER NOT WORKING | OGUN, OKE-ILEWO | Wear & Tear | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-10-14 | 1 | 2024-10-14 | 0 | 2024-10-15 | 1 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 105550 | Completed | 2024-10-15 | 1
75 | BACK OF HOUSE DOOR NET HANDLE | LAG, FESTAC | Corrective Action | Corrective | TAIDAV | OTHERS | OTHERS | 2024-10-04 | 10 | 2024-10-04 | 0 | 2024-10-11 | 7 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 3 | 2024-10-11 | 48000 | Completed | 2024-10-14 | 0
76 | LEAKING ROOF | LAG, EJIGBO | Wear & Tear | Breakdown | PENTECOSTAL | ROOF | BUILDING | 2024-10-01 | 170 | 2024-10-02 | 1 |  | 169 | [9 empty] | Overdue
77 | Leaking roof PPU Mokola | IBADAN, MOKOLA | Wear & Tear | Breakdown | REVELATION | ROOF | BUILDING | 2024-10-14 | 157 | 2024-10-14 | 0 |  | 157 | [9 empty] | Overdue
78 | RACK NEEDED FOR MALE AND FEMALE CHANGING ROOM | LAG, FESTAC | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-10-01 | 15 | 2024-10-02 | 1 | 2024-10-14 | 12 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 2 | 2024-10-16 |  | Completed | 2024-10-16 | 1
79 | FAULTY COLDROOM | LAG, ILUPEJU | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-10-01 | 1 | 2024-10-02 | 1 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 |  | Completed | 2024-10-02 | 1
80 | STORE FAN NOT WORKING |  | Wear & Tear | Breakdown | ADEREMI KAZEEM | WALL FAN | HVAC | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 |  | Completed | 2024-10-02 | 1
81 | SOCKETS NOT WORKING | LAG, AJAH | Electrical Surge | Breakdown | ADEREMI KAZEEM | OTHERS | OTHERS | 2024-10-02 | 1 | 2024-10-02 | 0 | 2024-10-03 | 1 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 |  | Completed | 2024-10-03 | 1
82 | FAULTY HINGE OF WARMER | LAG, MARINA | Users Misuse | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 |  | Completed | 2024-10-02 | 1
83 | GENERATOR SERVICE REQUEST | IMO, OKIGWE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 |  | Completed | 2024-10-02 | 1
84 | GENERATOR SERVICE REQUEST CR OGBOR HILL | ABIA, OGBOR HILLS | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-10-03 | 2 | 2024-10-04 | 1 | 2024-10-04 | 0 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 1 | 2024-10-05 | 0 | 2024-10-05 | 225750 | Completed | 2024-10-05 | 1
85 | Direct Diesel line Piping Work Request (Chicken Republic TOMBIA) | BAYELSA, TOMBIA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-09-23 | 21 | 2024-09-23 | 0 | 2024-10-02 | 9 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 12 | 2024-10-14 | 230000 | Completed | 2024-10-14 | 1
86 | Direct Diesel line Piping Work Request (Chicken Republic Yenagoa) | BAYELSA, YENAGOA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-09-23 | 178 |  | 178 | [11 empty] | Overdue
87 | DEAD CABINET BULB | LAG, AJAH | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 24187.5 | Completed | 2024-10-02 | 1
88 | EVACUATION OF BOH DRAINAGAE | LAG, LEKKI PHASE 1 | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 |  | Completed | 2024-10-02 | 1
89 | FAULTY CUSTOMER RESTROOM. | LAG, NNPC ALAPERE | Users Misuse | Breakdown | ADEREMI WAHAB | OTHERS | OTHERS | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 |  | Completed | 2024-10-02 | 1
90 | FAULTY/OVERFILLED SEPTIC TANK | LAG, MARINA | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-02 | 10 | 2024-10-02 | 0 | 2024-10-07 | 5 | 2024-10-06 | 2024-10-06 | 0 | 2024-10-06 | 5 | 2024-10-11 | 1 | 2024-10-12 |  | Completed | 2024-10-12 | 1
91 | FADED SIGNAGE |  | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-09-24 | 22 | 2024-10-02 | 8 | 2024-10-05 | 3 | 2024-10-06 | 2024-10-06 | 0 | 2024-10-06 | 5 | 2024-10-11 | 5 | 2024-10-16 | 110000 | Completed | 2024-10-16 | 1
92 | PX IGANDO FADED SIGNAGE |  | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-10-08 | 163 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-15 | 156 |  |  |  | 100000 | Overdue
93 | URGENT EVACUATION OF SEPTIC TANK | LAG, OSOLOWAY | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-02 | 1 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 1 | 2024-10-03 |  | Completed | 2024-10-03 | 1
94 | FAULTY PRICE LIST FRAME |  | Others | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-10-02 | 11 | 2024-10-02 | 0 | 2024-10-07 | 5 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 5 | 2024-10-13 | 65375 | Completed | 2024-10-13 | 1
95 | CABINET NOT ATTAINING TEMPERATURE | LAG, ONIRU | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-02 | 13 | 2024-10-02 | 0 | 2024-10-11 | 9 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 4 | 2024-10-15 | 258000 | Completed | 2024-10-15 | 1
96 | CABINET NOT ATTAINING TEMPERATURE | LAG, AJOSE ADEOGUN | Users Misuse | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-03 | 4 | 2024-10-03 | 0 | 2024-10-07 | 4 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 |  | Completed | 2024-10-07 | 1
97 | CABINET NOT ATTAINING TEMPERATURE | LAG, ABULE EGBA | Users Misuse | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-08 | 163 | 2024-10-08 | 0 |  | 163 | [9 empty] | Overdue
98 | CABINET NOT ATTAINING TEMPERATURE |  | Users Misuse | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-10 | 161 | 2024-10-10 | 0 |  | 161 | [9 empty] | Overdue
99 | FAULTY INSECT KILLER BULB AND CABINET KNOP |  | Users Misuse | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-02 | 169 | 2024-10-02 | 0 |  | 169 | [9 empty] | Overdue
100 | FAULTY INSECT KILLER BULB AND CABINET KNOP |  | Wear & Tear | Breakdown | TIMILEHIN | INSECT KILLER BOH | ELECTRICAL | 2024-10-02 | 169 | 2024-10-02 | 0 |  | 169 | [9 empty] | Overdue
101 | FAULTY GENERETOR | LAG, NNPC ALAPERE | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 104000 | Completed | 2024-10-02 | 1
102 | GENERATOR SERVICE REQUEST | EDO, AIRPORT RD, BENIN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-13 | 1 | 2024-10-13 | 0 | 2024-10-13 | 0 | 2024-10-13 | 2024-10-13 | 0 | 2024-10-13 | #REF! | 2024-10-13 | #REF! | 2024-10-14 | 202450 | Completed | 2024-10-14 | 1
103 | COLD ROOM NOT ATTAIN TEMPERATURE | LAG, FREEDOMWAY | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-10-03 | 168 | 2024-10-03 | 0 | 2024-10-08 | 5 | 2024-10-18 | 2024-10-18 | 0 | 2024-10-18 | 5 | 2024-10-18 | 153 |  |  | Overdue
104 | GENERATOR LEAKING DIESEL | LAG, HEYDEN ALAPERE | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-10-03 | 1 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 1 | 2024-10-04 |  | Completed | 2024-10-04 | 1
105 | CUSTOMER REST ROOM NOT WORKING | LAG, BODE THOMAS | Others | Breakdown | TOSIN OLATUNDE | OTHERS | OTHERS | 2024-10-16 | 155 | 2024-10-16 | 0 |  | 155 | [9 empty] | Overdue
106 | EVACUATION OF SEPTIC TANK | LAG, OGUNLANA DRIVE | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-03 | 1 | 2024-10-03 | 0 | 2024-10-04 | 1 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 |  | Completed | 2024-10-04 | 1
107 | EVACUATION OF SEPTIC TANK | LAG, HEYDEN ALAPERE | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-06 | 1 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 |  | Completed | 2024-10-07 | 1
108 | EVACUATION OF SEPTIC TANK | LAG, ETERNA LEKKI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-04 | 167 | 2024-10-04 | 0 |  | 167 | [9 empty] | Overdue
109 | EVACUATION OF SEPTIC TANK | LAG, NNPC ALAPERE | Others | Breakdown | CHIS OWOLABI | SEPTIC TANK | EVACUATION | 2024-10-06 | 15 | 2024-10-06 | 0 | 2024-10-09 | 3 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 12 | 2024-10-12 |  | Completed | 2024-10-21 | 0
110 | EVACUATION OF SEPTIC TANK | LAG, NNPC ALAPERE | Others | Breakdown | PROEQUIP | OTHERS | OTHERS | 2024-10-12 | 5 | 2024-10-12 | 0 | 2024-10-14 | 2 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 3 | 2024-10-15 | 128000 | Completed | 2024-10-17 | 0
111 | EVACUATION OF SEPTIC TANK | ILORIN, MM WAY | Others | Breakdown | REVELATION | SEPTIC TANK | EVACUATION | 2024-10-09 | 162 | 2024-10-09 | 0 |  | 162 | [9 empty] | Overdue
112 | IMMEDIATE EVACUATION OF SEPTIC TANK | LAG, OMOLE | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 115375 | Completed | 2024-10-15 | 1
113 | Evacuation of septic tank and lasting solution to the shallow septic tank | LAG, OSOLOWAY | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-10-08 | 163 | 2024-10-08 | 0 | 2024-10-10 | 2 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 161 |  |  |  |  | Overdue
114 | EVACUATION OF SEPTIC TANK | LAG, LEKKI PHASE 1 | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-12 | 1 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 1 | 2024-10-13 |  | Completed | 2024-10-13 | 1
115 | FREQUENT EVACUATION OF SEPTIC TANK | LAG, IKORODU | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-12 | 12 | 2024-10-12 | 0 | 2024-10-21 | 9 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-21 | 31 | 2024-11-21 | -28 | 2024-10-24 | 435000 | Completed | 2024-10-24 | 1
116 | EVACUATION OF SEPTIC TANK | LAG, NNPC ALAPERE | Others | Breakdown | CHRIS OWOLABI | SEPTIC TANK | EVACUATION | 2024-10-17 | 154 | 2024-10-17 | 0 | 2024-10-17 | 0 | 2024-10-17 | 2024-10-17 | 0 | 2024-10-17 | 0 | 2024-10-17 | 154 | 2024-10-18 |  | Overdue
117 | FAULTY LAMPHOLDERS IN THE DISPLAY CABINET | LAG, OMOLE | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-16 | 1 | 2024-10-16 | 0 | 2024-10-17 | 1 | 2024-10-17 | 2024-10-17 | 0 | 2024-10-17 | 0 | 2024-10-17 | 0 | 2024-10-17 | 64500 | Completed | 2024-10-17 | 1
118 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | LAG, OMOLE | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-18 | 0 | 2024-10-18 | 0 | 2024-10-18 | 0 | 2024-10-18 | 2024-10-18 | 0 | 2024-10-18 | 0 | 2024-10-18 | 0 | 2024-10-18 | 17200 | Completed | 2024-10-18 | 1
119 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | LAG, OPEBI | Users Misuse | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-14 | 1 | 2024-10-15 | 1 | 2024-10-15 | 0 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 |  | Completed | 2024-10-15 | 1
120 | DISPLAY CABINET NOT ATTAINING TEMPERATURE (DOWN SECTION) | LAG, AKOWONJO | Wear & Tear | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-14 | 157 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 157 |  |  | Overdue
121 | FAULTY WALL SOCKET AT BOH | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-10-03 | 168 | 2024-10-03 | 0 |  | 168 | [9 empty] | Overdue
122 | FAULTY ITEMS | PPU Ilupeju | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-10-03 | 168 | 2024-10-03 | 0 | 2024-10-18 | 15 | 2024-10-14 |  | 157 | [6 empty] | Overdue
123 | FAULTY FREEZER ROOM | BAYELSA, OPOLO | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-09-20 | 49 | 2024-09-20 | 0 | 2024-10-03 | 13 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 36 | 2024-10-08 | 410000 | Completed | 2024-11-08 | 0
124 | FULL SEPTIC TANK | LAG, ABULE EGBA | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-10-03 | 168 | 2024-10-04 | 1 | 2024-10-04 | 0 | 2024-10-06 |  | 165 | [6 empty] | Overdue
125 | REQUEST FOR REPLACEMENT OF ELECTRICAL MATERIALS | LAG, IDI-IROKO RD | Others | Breakdown | TAYO | OTHERS | OTHERS | 2024-10-03 | 18 | 2024-10-03 | 0 |  | 168 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 |  | Completed | 2024-10-21 | 1
126 | Servicing of PH warehouse generator for the month of October 2024. |  | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-14 | 18 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-23 | 2024-10-23 | 0 | 2024-10-23 | 0 | 2024-10-23 | 9 | 2024-11-01 |  | Completed | 2024-11-01 | 1
127 | SERVICING OF GENERATOR | PH, RUMUOLA | Routine Servicing | Preventive
128 | SERVICING OF GENERATOR | CALABAR, NDIDEM | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-10-11 | 1 | 2024-10-11 | 0 | 2024-10-12 | 1 | 2024-10-12 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 317125 | Completed | 2024-10-12 | 1
129 | SERVICING OF GENERATOR | IBADAN, MOKOLA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-18 | 8 | 2024-10-18 | 0 | 2024-10-26 | 8 | 2024-10-26 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 198500 | Completed | 2024-10-26 | 1
130 | FAUTY COLDROOM | LAG, ISAWO-IKORODU | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-10-15 | 156 | 2024-10-15 | 0 |  | 156 | [9 empty] | Overdue
131 | PEELING OF WALL AT PX EKORO 2 | LAG, EKORO | Wear & Tear | Breakdown | PENTECOSTAL | WALL | BUILDING | 2024-05-02 | 322 | 2024-05-02 | 0 | 2024-05-02 | 0 | 2024-05-02 | 2024-10-13 | 164 | 2024-10-14 | 157 |  |  |  |  | Overdue
132 | Direct Diesel line Piping Work Request (Chicken Republic TOMBIA) | BAYELSA, TOMBIA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-19 | 1 | 2024-10-19 | 0 | 2024-10-20 | 1 | 2024-10-20 | 2024-10-20 | 0 | 2024-10-20 | 0 | 2024-10-20 | 0 | 2024-10-20 | 202450 | Completed | 2024-10-20 | 1
133 | VEGETABLE SHREDDER NOT WORKING | EDO, SAKPOMBA | Wear & Tear | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-10-14 | 1 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 1 | 2024-10-15 | 116100 | Completed | 2024-10-15 | 1
134 | VEGETABLE SHREDDER IS FAULTY | LAG, FESTAC | Wear & Tear | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-10-13 | 40 | 2024-10-13 | 0 | 2024-10-21 | 8 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 32 | 2024-11-22 | 88150 | Completed | 2024-11-22 | 1
135 | DAILY EQUIPMENT STATUS | LAG, AJAH
136 | Trunking of Exposed Wires | LAG, VGC | Corrective Action | Corrective | ADEREMI KAZEEM | OTHERS | OTHERS | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 |  | Completed | 2024-10-11 | 1
137 | DETACHED BOH FAN | LAG, MMA2 | Wear & Tear | Breakdown | TIMILEHIN | WALL FAN | HVAC | 2024-10-25 | 146 | 2024-10-25 | 0 | 2024-10-25 | 0 | [9 empty] | Overdue
138 | FAULTY GREASE TRAP WITH BAD DRAIN NET. | LAG, JOEL OGUNNAIKE | Others | Breakdown | ZEBRA G3 | GREASE TRAP | GREASE_TRAP | 2024-10-10 | 64 | 2024-10-10 | 0 | 2024-11-05 | 26 | 2024-11-05 | 2024-12-06 | 31 | 2024-12-06 | 0 | 2024-12-06 | 7 | 2024-12-13 | 420000 | Completed | 2024-12-13 | 1
139 | FAULTY GREASE TRAP | LAG, AJOSE ADEOGUN | Others | Breakdown | ZEBRA G3 | GREASE TRAP | GREASE_TRAP | 2024-10-14 | 4 | 2024-10-14 | 0 | 2024-10-18 | 4 | 2024-10-18 | 2024-10-18 | 0 | 2024-10-18 | 0 | 2024-10-18 | 0 | 2024-10-18 |  | Completed | 2024-10-18 | 1
140 | Servicing of Acs | PPU Opebi | Routine Servicing | Preventive | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-03 | 168 | 2024-10-03 | 0 |  | 168 | [9 empty] | Overdue
141 | Faulty 4-Head | LAG, TEJUOSHO | Corrective Action | Corrective | KITCHTECH | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-03 | 168 | 2024-10-03 | 0 |  | 168 | [9 empty] | Overdue
142 | Faulty 4-Head | LAG, OKE-AFA | Corrective Action | Corrective | KITCHTECH | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-03 | 168 | 2024-10-03 | 0 |  | 168 | [9 empty] | Overdue
143 | Faulty 4-Head | LAG, FESTAC | Corrective Action | Corrective | KITCHTECH | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-03 | 168 | 2024-10-03 | 0 | 2024-10-08 | 5 | [9 empty] | Overdue
144 | FAULTY ICE CREAM MACHINE | CALABAR, NDIDEM | Wear & Tear | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-10-10 | 161 | 2024-10-10 | 0 |  | 161 | [9 empty] | Overdue
145 | FAULTY ICE CREAM MACHINE | PH, DOX RD | Wear & Tear | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-10-12 | 159 | 2024-10-12 | 0 | 2024-10-16 | 4 | [9 empty] | Overdue
146 | Installation of new water heater | IMO, OKIGWE | Others | Breakdown | JOWYN | WATER HEATER | PLUMBING | 2024-10-03 | 168 | 2024-10-03 | 0 | 2024-10-08 | 5 | 2024-10-10 | 2024-10-13 | 3 | 2024-10-14 | 4 | 2024-10-18 | 153 |  |  | Overdue
147 | REPLACEMENT OF WALL TILES AT THE BACK OF WASHING AREA | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | ARIZMAYAN | PAVEMENT | BUILDING
148 | GENERATOR DUE FOR SERVICING AT AWKA ROAD | ANAMBRA, AWKA RD, ONITSHA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 390000 | Completed | 2024-10-03 | 1
149 | Daily Equipment Status | LAG, ONIRU | Wear & Tear | Breakdown | BCE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2024-10-03 | 168 | 2024-10-03 | 0 | 2024-10-22 | 19 | 2024-10-22 | 2024-10-22 | 0 | 2024-10-29 | 142 |  |  |  | 455800 | Overdue
150 | Daily Equipment Status | LAG, ONIRU | Wear & Tear | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-10-03 | 11 | 2024-10-03 | 0 | 2024-10-10 | 7 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 4 | 2024-10-14 | 184000 | Completed | 2024-10-14 | 1
151 | Daily Equipment Status | LAG, ONIRU | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-10-03 | 168 | 2024-10-03 | 0 |  | 168 | [9 empty] | Overdue
152 | Daily Equipment Status | LAG, ONIRU | Wear & Tear | Breakdown | PROEQUIP | GROUND WATER TANK | WTP | 2024-10-03 | 168 | 2024-10-03 | 0 | 2024-10-14 | 11 | [9 empty] | Overdue
153 | Daily Equipment Status | PPU Ajah | Wear & Tear | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-10-09 | 1 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 408500 | Completed | 2024-10-10 | 1
154 | Daily Equipment Status | LAG, ONIRU | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-10-10 | 4 | 2024-10-10 | 0 | 2024-10-14 | 4 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 245100 | Completed | 2024-10-14 | 1
155 | Daily Equipment Status | PPU Ajah | Wear & Tear | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-10-10 | 161 | 2024-10-24 | 14 | 2024-10-24 | 0 | 2024-10-24 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 147 |  |  | Overdue
156 | GAS LEAKAGE. | LAG, WAREHOUSE RD, APAPA | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-10-03 | 168 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 167 |  |  |  | 158750 | Overdue
157 | GAS LEAKAGE. | LAG, VGC | Wear & Tear | Breakdown | JOEL OMOTOSHO | GAS HOSE & SUNDRIES | GAS | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 |  | Completed | 2024-10-04 | 1
158 | GAS LEAKAGE. | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-10-07 | 164 | 2024-10-07 | 0 | 2024-10-08 | 1 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 1 | 2024-10-10 | 161 |  | 72250 | Overdue
159 | GAS LEAKAGE. | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-10-08 | 163 | 2024-10-08 | 0 | 2024-10-15 | 7 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 15 | 2024-10-30 | 141 | 2024-10-30 | 47000 | Overdue
160 | GAS LEAKAGE. | LAG, VGC | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-10-14 | 157 | 2024-10-14 | 0 | 2024-10-15 | 1 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 1 | 2024-10-16 | 155 |  | 108000 | Overdue
161 | Generator Servicing | DELTA, EFFURUN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-03 | 5 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 5 | 2024-10-08 | 202450 | Completed | 2024-10-08 | 1
162 | GENERATOR SERVICING | OYO, OWODE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-04 | 6 | 2024-10-04 | 0 | 2024-10-10 | 6 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 412047 | Completed | 2024-10-10 | 1
163 | GENERATOR SERVICING | IBADAN, BODIJA | Routine Servicing | Preventive | SYMINERTIAS | GENERATOR | GENERATOR | 2024-10-06 | 2 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 2 | 2024-10-08 | 265166.25 | Completed | 2024-10-08 | 1
164 | GENERATOR SERVICING FOR CR OKIGWE | IBADAN, BODIJA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-07 | 4 | 2024-10-07 | 0 | 2024-10-09 | 2 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 2 | 2024-10-11 | 202450 | Completed | 2024-10-11 | 1
165 | REQUEST FOR GENERATOR SERVICING EMERGENCY | AKWA IBOM, ORON RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-14 | 1 | 2024-10-14 | 0 | 2024-10-15 | 1 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 202450 | Completed | 2024-10-15 | 1
166 | GENERATOR SERVICING | BAYELSA, TOMBIA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-15 | 4 | 2024-10-15 | 0 | 2024-10-19 | 4 | 2024-10-19 | 2024-10-19 | 0 | 2024-10-19 | 0 | 2024-10-19 | 0 | 2024-10-19 | 202450 | Completed | 2024-10-19 | 1
167 | GENERATOR SERVICING | BAYELSA, YENAGOA | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-10-16 | 8 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-10-16 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-10-16 | 8 | 2024-10-24 | 202000 | Completed | 2024-10-24 | 1
168 | GENERATOR SERVICING- CR OJOO | IBADAN, OJOO | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-10-21 | 1 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 1 | 2024-10-22 | 236500 | Completed | 2024-10-22 | 1
169 | GENERATOR SERVICING REQUEST | IMO, OKIGWE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-21 | 2 | 2024-10-21 | 0 | 2024-10-22 | 1 | 2024-10-22 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 | 1 | 2024-10-23 | 202450 | Completed | 2024-10-23 | 1
170 | REQUEST FOR GENERATOR SERVICING | ABIA, AZIKIWE RD, UMUAHIA | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-10-22 | 2 | 2024-10-22 | 0 | 2024-10-23 | 1 | 2024-10-23 | 2024-10-23 | 0 | 2024-10-23 | 0 | 2024-10-23 | 1 | 2024-10-24 | 247250 | Completed | 2024-10-24 | 1
171 | REQUEST FOR GENERATOR SERVICING | LAG, ONIRU | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-23 | 1 | 2024-10-23 | 0 | 2024-10-23 | 0 | 2024-10-23 | 2024-10-23 | 0 | 2024-10-23 | 0 | 2024-10-23 | 1 | 2024-10-24 | 104000 | Completed | 2024-10-24 | 1
172 | DETACHED CHANGE OVER SWITCH BOARD FROM WALL | LAG, IDI-IROKO RD | Wear & Tear | Breakdown | TAYO | OTHERS | OTHERS | 2024-10-03 | 1 | 2024-10-03 | 0 | 2024-10-04 | 1 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 |  | Completed | 2024-10-04 | 1
173 | LOBBY LIGHT DEAD | LAG, JOEL OGUNNAIKE | Electrical Surge | Breakdown | MOSES | OTHERS | OTHERS | 2024-10-03 | 168 | 2024-10-03 | 0 |  | 168 | [9 empty] | Overdue
174 | REQUEST FOR A NEW CABBAGE SHREDDING BLADE | ILORIN, GRA | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-10-03 | 5 | 2024-10-03 | 0 | 2024-10-08 | 5 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 405275 | Completed | 2024-10-08 | 1
175 | GENERATOR DUE FOR SERVICE | LAG, IDI-IROKO RD | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-10-03 | 4 | 2024-10-03 | 0 | 2024-10-07 | 4 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 |  | Completed | 2024-10-07 | 1
176 | ALL EQUIPMENTS NOT COMING UP | LAG, OKOTA | Others | Breakdown | MID TECH | GENERATOR | GENERATOR | 2024-10-03 | 15 | 2024-10-03 | 0 | 2024-10-13 | 10 | 2024-10-13 | 2024-10-13 | 0 | 2024-10-13 | 0 | 2024-10-13 | 5 | 2024-10-18 | 450000 | Completed | 2024-10-18 | 1
177 | GENERATOR NOT STARTING | LAG, OKOTA | Others | Breakdown | MID TECH | GENERATOR | GENERATOR | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 |  | Completed | 2024-10-10 | 1
178 | GENERATOR NOT STARTING | ABIA, AZIKIWE RD, UMUAHIA | Others | Breakdown | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 |  | Completed | 2024-10-21 | 1
179 | STORE INVERTER MALFUNCTIONING. | LAG, AJAH | Electrical Surge | Breakdown | DALEMATRIX | INVERTER SYSTEM | INVERTER | 2024-10-03 | 10 | 2024-10-03 | 0 | 2024-10-04 | 1 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 9 | 2024-10-13 | 158750 | Completed | 2024-10-13 | 1
180 | FILLED SEPTIC TANK | LAG, IDI-IROKO RD | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-03 | 1 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 1 | 2024-10-04 |  | Completed | 2024-10-04 | 1
181 | FILLED SEPTIC TANK | LAG, IDI-IROKO RD | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-12 | 2 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 2 | 2024-10-14 | 812250 | Completed | 2024-10-14 | 1
182 | EVACUATION OF FILLED SEPTIC TANK | LAG, IPAJA RD | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-21 | 6 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 6 | 2024-10-27 | 305375 | Completed | 2024-10-27 | 1
183 | FILLED SEPTIC TANK | LAG, IDI-IROKO RD | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-21 | 1 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 1 | 2024-10-22 |  | Completed | 2024-10-22 | 1
184 | FILLED SEPTIC TANK | LAG, IDI-IROKO RD | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-25 | 1 | 2024-10-25 | 0 | 2024-10-25 | 0 | 2024-10-25 | 2024-10-25 | 0 | 2024-10-25 | 0 | 2024-10-25 | 1 | 2024-10-26 |  | Completed | 2024-10-26 | 1
185 | OVERFILLED SEPTIC TANK | LAG, OSOLOWAY | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-05 | 2 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 2 | 2024-10-07 |  | Completed | 2024-10-07 | 1
186 | EVACUATION OF SOAK AWAY AND SEPTIC TANK | LAG, OKE-AFA | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-07 | 20 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 20 | 2024-10-27 | 340750 | Completed | 2024-10-27 | 1
187 | SEPTIC TANK | LAG, BODE THOMAS | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-10 | 1 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 1 | 2024-10-11 | 115375 | Completed | 2024-10-11 | 1
188 | DRAINAGE BLOCKAGE. | LAG, VGC | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-10-11 | 4 | 2024-10-11 | 0 | 2024-10-13 | 2 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 150000 | Completed | 2024-10-15 | 1
189 | FULL SOAK AWAY( UNDER 2WEEKS OF LAST EVACUATION) | LAG, JIBOWU | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-10-08 | 163 | 2024-10-09 | 1 | 2024-10-11 | 2 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 160 |  |  |  | 129000 | Overdue
190 | PX AGUNGI ROLLER SHUTTER NOT WORKING | LAG, AGUNGI | Others | Breakdown | VENYS | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-07 | 2 | 2024-10-07 | 0 | 2024-10-08 | 1 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 2 | 2024-10-09 |  | Completed | 2024-10-09 | 1
191 | FLOODED BOH BECUASE OF BLOCKED DAINAGE PIPE | PPU Ajah | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-10-13 | 3 | 2024-10-14 | 1 | 2024-10-15 | 1 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 1 | 2024-10-16 | 0 | 2024-10-16 | 43000 | Completed | 2024-10-16 | 1
192 | BROKEN LOBBY AND CUSTOMER RESTROOM MIRROR | LAG, FESTAC | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-10-04 | 167 | 2024-10-04 | 0 |  | 167 | [9 empty] | Overdue
193 | DETACHED HAND WASH SINK | LAG, FESTAC | Wear & Tear | Breakdown | PROEQUIP | KITCHEN WASH HAND SINK | PLUMBING | 2024-10-03 | 168 | 2024-10-03 | 0 |  | 168 | [7 empty] | 2024-10-05 |  | Overdue
194 | EVACUTION OF SEPTIC TANK | LAG, OSOLOWAY | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-14 | 1 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 1 | 2024-10-15 |  | Completed | 2024-10-15 | 1
195 | REQUEST FOR THE EVACUTION OF SEPTIC TANK | LAG, BADORE | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-23 | 1 | 2024-10-23 | 0 | 2024-10-24 | 1 | 2024-10-24 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 |  | Completed | 2024-10-24 | 1
196 | REPORT OF DAILY HYGIENE WALKTHROUGH AND CLOSURE ACTION PLAN FOR OPEN OPPORTUNITIES FROM PPU AJAH | PPU Ajah | Others | Breakdown | ACORN | WALL | BUILDING | 2024-10-04 | 20 | 2024-10-04 | 0 | 2024-10-13 | 9 | 2024-10-14 | 2024-10-23 | 9 | 2024-10-23 | 0 | 2024-10-23 | 1 | 2024-10-24 | 258050 | Completed | 2024-10-24 | 1
197 | EVACUATION OF SEPTIC TANK | LAG, MAGODO | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-10-14 | 157 | 2024-10-14 | 0 | 2024-10-15 | 1 | 2024-10-15 | 2024-10-30 | 15 | 2024-10-29 | 1 | 2024-10-30 | 141 | 2024-10-30 | #258,000.00 | Overdue
198 | EVACUATION OF SEPTIC TANK | LAG, EKORO | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-10-15 | 156 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 1 | 2024-10-16 | 155 |  | 258000 | Overdue
199 | EVACUATION OF SEPTIC TANK | ILORIN, MM WAY | Others | Breakdown | MODEL | SEPTIC TANK | EVACUATION | 2024-10-09 | 162 | 2024-10-09 | 0 | 2024-10-20 | 11 | 2024-10-21 |  | 150 | [6 empty] | Overdue
200 | EVACUATION OF SEPTIC TANK | LAG, AWOLOWO 2 | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-26 | 1 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 1 | 2024-10-27 |  | Completed | 2024-10-27 | 1
201 | REQEUST FOR SEWAGE SEPTIC TANK ESCAVATION | LAG, OKE-AFA | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-14 | 1 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 1 | 2024-10-15 |  | Completed | 2024-10-15 | 1
202 | SEWAGE EVACUATION | LAG, EJIGBO | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-17 | 1 | 2024-10-17 | 0 | 2024-10-17 | 0 | 2024-10-17 | 2024-10-17 | 0 | 2024-10-17 | 0 | 2024-10-17 | 1 | 2024-10-18 | 511125 | Completed | 2024-10-18 | 1
203 | SEWAGE EVACUATION |  | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-21 | 1 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 1 | 2024-10-22 |  | Completed | 2024-10-22 | 1
204 | SEWAGE EVACUATION | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-22 | 1 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 | 1 | 2024-10-23 |  | Completed | 2024-10-23 | 1
205 | SEPTIC TANK EVACUATION | LAG, IKORODU | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-20 | 1 | 2024-10-20 | 0 | 2024-10-20 | 0 | 2024-10-20 | 2024-10-20 | 0 | 2024-10-20 | 0 | 2024-10-20 | 1 | 2024-10-21 |  | Completed | 2024-10-21 | 1
206 | STORE AUDIT ACTION PLAN. | LAG, ALIMOSHO | Others | Breakdown | TAIDAV | WATER TREATMENT PLANT BLD | BUILDING | 2024-10-18 | 153 | 2024-10-20 | 2 |  | 151 | [9 empty] | Overdue
207 | Urgent septic tank evacuation | LAG, OSOLOWAY | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 |  | Completed | 2024-10-21 | 1
208 | SEPTIC TANK EVACUATION | LAG, ETERNA LEKKI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-10-22 | 1 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 | 1 | 2024-10-23 |  | Completed | 2024-10-23 | 1
209 | SEPTIC TANK IS FULL | LAG, OBA AKRAN | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-23 | 1 | 2024-10-23 | 0 | 2024-10-23 | 0 | 2024-10-23 | 2024-10-23 | 0 | 2024-10-23 | 0 | 2024-10-23 | 1 | 2024-10-24 | 105375 | Completed | 2024-10-24 | 1
210 | OPEN GROUND AREA | LAG, NNPC ALAPERE | Corrective Action | Corrective | ACORN | PAVEMENT | BUILDING | 2024-10-24 | 147 | 2024-10-24 | 0 | 2024-10-24 | 0 | [9 empty] | Overdue
211 | FAULTY EXTRACTOR LIGHT | LAG, IRE-AKARI | Electrical Surge | Breakdown | FRIDAY ONWUBUYA | OTHERS | OTHERS | 2024-10-08 | 163 | 2024-10-08 | 0 |  | 163 | [9 empty] | Overdue
212 | Electrical discharge | LAG, AJOSE ADEOGUN | Electrical Surge | Breakdown | ISMAIL ODEDELE | OTHERS | OTHERS | 2024-10-28 | 143 | 2024-10-28 | 0 |  | 143 | [9 empty] | Overdue
213 | NOISY AIR CURTAIN | LAG, MARINA | Corrective Action | Corrective | EKNOR | OTHERS | OTHERS | 2024-10-09 | 162 | 2024-10-09 | 0 | 2024-10-22 | 13 | 2024-10-22 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 | 149 |  | N509,000 | Overdue
214 | FALLEN COVINGS OF THE EXTERIOR BIN SHED | LAG, IRE-AKARI | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-10-08 | 163 | 2024-10-08 | 0 |  | 163 | [9 empty] | Overdue
215 | UNDER BAR CHILLER NOT FUNCTIONAL | PH, OMOKU | Others | Breakdown | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-10-28 | 5 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 5 | 2024-11-02 | 105350 | Completed | 2024-11-02 | 1
216 | LEAKING CEILING AT THE KITCHEN | LAG, AGIDINGBI | Corrective Action | Corrective | ARIZMAYAN | CEILING BOARD | BUILDING | 2024-10-28 | 14 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-11-03 | 2024-11-03 | 0 | 2024-11-04 | 2 | 2024-11-06 | 5 | 2024-11-11 | 130000 | Completed | 2024-11-11 | 1
217 | EVACUATION OF SEPTIC TANK | LAG, MAGODO | Others | Breakdown | PENTICOSTAL | SEPTIC TANK | EVACUATION | 2024-10-14 | 157 | 2024-10-14 | 0 |  | 157 | 2024-10-14 | 2024-10-16 | 2 | 2024-10-16 | 0 | 2024-10-16 | 155 |  | #258,000.00 | Overdue
218 | REQUESTING OF NEW INVERTER | LAG, ISAWO-IKORODU | Electrical Surge | Breakdown | DALEMATRIX | INVERTER DB | ELECTRICAL | 2024-08-01 | 69 | 2024-08-01 | 0 | 2024-08-06 | 5 | 2024-10-03 | 2024-10-07 | 4 | 2024-10-13 | -6 | 2024-10-07 | 2 | 2024-10-09 | #426,875.00 | Completed | 2024-10-09 | 1
219 | INVERTER NOT CHARGING | LAG, MOBIL OGBA | Corrective Action | Corrective | DALEMATRIX | INVERTER DB | ELECTRICAL | 2024-07-09 | 106 | 2024-07-09 | 0 | 2024-07-12 | 3 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 14 | 2024-10-23 | 1,102,625.00 ₦ | Completed | 2024-10-23 | 1
220 | FAULTY ROLLER SHUTTER | LAG, ONIRU | Others | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-24 | 147 | 2024-10-24 | 0 | 2024-10-25 | 1 | 2024-10-30 | 2024-10-30 | 0 | 2024-10-30 | 0 | 2024-10-30 | 141 |  | 80302.5 | Overdue
221 | FAULTY ROLLER SHUTTER | AKWA IBOM, IKOT EKPENE RD | Others | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-03 | 57 | 2024-10-28 | 25 | 2024-10-28 | 0 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 9 | 2024-11-14 | 15 | 2024-11-29 | 280575 | Completed | 2024-11-29 | 1
222 | FIXING OF GREASE TRAP HANDLE | LAG, OPEBI | Wear & Tear | Breakdown | ZEBRA G3 | GREASE TRAP | GREASE_TRAP | 2024-10-29 | 142 | 2024-10-29 | 0 |  | 142 | [9 empty] | Overdue
223 | FAULTY LOBBY STANDING UNIT AC | ENUGU, POLO MALL | Others | Breakdown | BASSCOMM | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-29 | 142 |  | 142 | [11 empty] | Overdue
224 | FAULTY CABINET TEMPRERATURE TURNER |  | Others | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-29 | 142 | 2024-10-29 | 0 |  | 142 | [9 empty] | Overdue
225 | SPICE ROOM FAULTY AC | LAG, ILUPEJU | Corrective Action | Corrective | TONA OGUNS | OTHERS | OTHERS | 2024-10-23 | 148 | 2024-10-23 | 0 | 2024-10-29 | 6 | 2024-10-29 |  | 142 | [5 empty] | 664000 | Overdue
226 | LOBBY HAND DRYER NOT WORKING | LAG, AJOSE ADEOGUN | Others | Breakdown | JOEL OMOTOSHO | HAND DRYER LOBBY | ELECTRICAL | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 |  | 142 |  |  |  |  | 2024-10-29 |  | Completed | 2024-10-29 | 1
227 | DAMAGED KIOSK ROOF | LAG, BODE THOMAS | Others | Breakdown | ARIZMAYAN | ROOF | BUILDING | 2024-10-12 | 159 | 2024-10-14 | 2 | 2024-10-29 | 15 | 2024-10-29 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 142 | 2024-10-29 | 510000 | Overdue
228 | FAULTY FREEZER ROOM - CR NSUKKA | ENUGU, NSUKKA | Others | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-10-20 | 4 | 2024-10-21 | 1 | 2024-10-21 | 0 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 3 | 2024-10-24 | 145000 | Completed | 2024-10-24 | 1
229 | BAD CHEMICAL CUPBOARD DOOR | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | MATOLAD | CHEMICAL CUPBOARD | FURNITURE | 2024-10-29 | 142 | 2024-10-29 | 0 |  | 142 | [9 empty] | Overdue
230 | FAULTY LAMB HOLDER BULB | LAG, MARINA | Wear & Tear | Breakdown | ISMAIL ODEDELE | OTHERS | OTHERS | 2024-10-29 | 142 | 2024-10-29 | 0 |  | 142 | [9 empty] | Overdue
231 | TOASTER MACHINE FAULTY | PH, OYIGBO | Wear & Tear | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2024-10-25 | 11 | 2024-10-25 | 0 | 2024-10-25 | 0 | 2024-10-28 | 2024-11-28 | 31 | 2024-10-29 | 6 | 2024-11-04 | 1 | 2024-11-05 | 101050 | Completed | 2024-11-05 | 1
232 | WATER NOT PUMPING | LAG, MOBIL OGBA | Others | Breakdown | PROEQUIP | OTHERS | OTHERS | 2024-10-29 | 1 | 2024-10-29 | 0 | 2024-10-30 | 1 | [7 empty] | 2024-10-30 |  | Completed | 2024-10-30 | 1
233 | LEAKING DIESEL PIPE | LAG, HEYDEN IPAJA | Wear & Tear | Breakdown | THIO & PARTNERS | OTHERS | OTHERS | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 |  | Completed | 2024-10-29 | 1
234 | COLD ROOM NOT WORKING | LAG, BADORE | Others | Breakdown | ECS | COLD ROOM UNIT | HVAC | 2024-10-17 | 154 | 2024-10-17 | 0 |  | 154 | [9 empty] | Overdue
235 | COLD ROOM NOT WORKING | LAG, ABULE EGBA | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-10-17 | 154 | 2024-10-17 | 0 | 2024-10-20 | 3 | [9 empty] | Overdue
236 | COLD ROOM NOT WORKING | LAG, HEYDEN IPAJA | Others | Breakdown | THIO & PARTNERS | COLD ROOM UNIT | HVAC | 2024-10-29 | 142 | 2024-10-29 | 0 | 2024-10-30 | 1 | [9 empty] | Overdue
237 | BROKEN MALE CUSTOMER MIRROR | LAG, LEKKI PHASE 1 | Users Misuse | Breakdown | MATOLAD | TOILET WALL MIRROR | OTHERS | 2024-10-24 | 19 | 2024-10-24 | 0 | 2024-10-30 | 6 | 2024-10-30 | 2024-10-30 | 0 | 2024-10-30 | 0 | 2024-10-30 | 13 | 2024-11-07 |  | Completed | 2024-11-12 | 0
238 | REQUEST FOR ICE-CREAM SIDE TRAY REPLACEMENT | LAG, IDIMU | Others | Breakdown | JUSTFOOD | OTHERS | OTHERS | 2024-10-16 | 155 | 2024-10-16 | 0 |  | 155 | [9 empty] | Overdue
239 | Grease Trap not working effectively | DELTA, ISOKO RD | Corrective Action | Corrective | PROEQUIP | GREASE TRAP | GREASE_TRAP | 2024-10-16 | 155 | 2024-10-17 | 1 |  | 154 | [9 empty] | Overdue
240 | GENERATOR DUE FOR SERVICING | OSUN, AYETORO | Routine Servicing | Preventive | SYMINERTIAS | GENERATOR | GENERATOR | 2024-10-27 | 144 | 2024-10-28 | 1 | 2024-10-29 | 1 | [7 empty] | 2024-10-30 | 340437.5 | Overdue
241 | OPENED WIRES THAT REQUIRES TRUNKING IN THE STORE | LAG, OGUDU | Corrective Action | Corrective | KOLA | OTHERS | OTHERS | 2024-10-28 | 143 | 2024-10-28 | 0 | 2024-10-29 | 1 | [9 empty] | Overdue
242 | NO HOT WATER IN THE STORE | LAG, TOTAL LEKKI | Others | Breakdown | JOEL OMOTSHO | FAULTY WATER HEATER |  | 2024-10-27 | 3 | 2024-10-27 | 0 | 2024-10-30 | 3 | 2024-10-30 | 2024-10-30 | 0 | 2024-10-30 | 0 | 2024-10-30 | 0 | 2024-10-30 |  | Completed | 2024-10-30 | 1
243 | STORE AUDIT FINDINGS CR BODE THOMAS | LAG, BODE THOMAS | OTHERS | Breakdown | ACORNFACILITIES | OTHERS | OTHERS | 2024-10-03 | 168 | 2024-10-03 | 0 | 2024-10-05 | 2 | 2024-10-10 | 2024-10-14 | 4 | [5 empty] | 950000 | Overdue
244 | STORE AUDIT FINDINGS CR BODE THOMAS | LAG, BODE THOMAS | Others | Breakdown | TRIFIRMILIAR | FIRE ALARM PANEL | FIRE | 2024-10-03 | 168 | 2024-10-10 | 7 | 2024-10-22 | 12 | [8 empty] | 410000 | Overdue
245 | PAINTING OF PEELED WALL IN DRY STORE AND MALE STAFF ROOM | LAG, ILUPEJU | Corrective Action | Corrective | ARIZMAYAN | PAINTING | BUILDING | 2024-10-13 | 158 | 2024-10-28 | 15 | 2024-10-28 | 0 | 2024-10-30 | 2024-10-30 | 0 | 2024-10-30 | 141 |  |  | 2024-10-30 | 164600 | Overdue
246 | FAULTY ICE CREAM MECHINE | LAG, LEKKI PHASE 1 | Users Misuse | Breakdown | JUSTFOOD | FAULTY ICE CREAM MACHINE |  | 2024-10-23 | 148 | 2024-10-23 | 0 | 2024-10-30 | 7 | [9 empty] | Overdue
247 | REQUEST FOR LED BULBS TO REPLACE DEAD BULBS IN THE STORE | LAG, AKOWONJO | Electrical Surge | Breakdown | FRIDAY ONWUBUYA | OTHERS | OTHERS | 2024-10-07 | 164 | 2024-10-07 | 0 |  | 164 | [9 empty] | Overdue
248 | FAULTY AIR CURTAIN AT BOH | LAG, MOBIL OGBA | Others | Breakdown | EKNOR | OTHERS | OTHERS | 2024-10-28 | 143 | 2024-10-28 | 0 | 2024-10-30 | 2 | 2024-10-30 |  | 141 | [6 empty] | Overdue
249 | FAULTY MALE CUSTOMER RESTROOM | LAG, IKOTUN | Others | Breakdown | OLUWATOSIN | SPLIT UNIT TOILET | HVAC | 2024-10-21 | 9 | 2024-10-21 | 0 | 2024-10-30 | 9 | 2024-10-30 | 2024-10-30 | 0 | 2024-10-30 | 0 | 2024-10-30 | 0 | 2024-10-30 |  | Completed | 2024-10-30 | 1
250 | GAS LEAKAGE | LAG, FREEDOMWAY | Others | Breakdown | JOEL OMOTOSHO | GAS HOSE & SUNDRIES | GAS | 2024-10-28 | 1 | 2024-10-28 | 0 | 2024-10-29 | 1 | 2024-10-29 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 |  | Completed | 2024-10-29 | 1
251 | NEED FOR TRUCK STRIP CURTAIN REPLACEMENT | LAG, ILUPEJU | Others | Breakdown | TONA OGUNS | OTHERS | OTHERS | 2024-10-22 | 149 | 2024-10-22 | 0 | 2024-10-22 | 0 | [9 empty] | Overdue
252 | FALLING CEILING | LAG, TEJUOSHO | Wear & Tear | Breakdown | ACORN | CEILING BOARD | BUILDING | 2024-10-30 | 141 | 2024-10-30 | 0 | 2024-11-18 | 19 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-19 | 121 |  |  |  | 370000 | Overdue
253 | FAULTY UPRIGHT CHILLER | LAG, HEYDEN IPAJA | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2024-10-30 | 141 | 2024-10-30 | 0 |  | 141 | [9 empty] | Overdue
254 | FAULTY LOBBY AC | LAG, HEYDEN IPAJA | Electrical Surge | Breakdown | THIO & PARTNERS | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-30 | 141 | 2024-10-30 | 0 |  | 141 | [9 empty] | Overdue
255 | FAULTY LOBBY AC- CR AFIKPO | EBONYI, AFIKPO, ABAKALIKI | Routine Servicing | Preventive | MOFEEN | OTHERS | OTHERS | 2024-10-22 | 149 | 2024-10-22 | 0 |  | 149 | [9 empty] | Overdue
256 | BAD PPU EXTRACTOR FAN | EDO, SAPELE RD, BENIN | Wear & Tear | Breakdown | BEN SEASONED | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2024-10-18 | 153 | 2024-10-18 | 0 | 2024-10-22 | 4 | [9 empty] | Overdue
257 | SERVICING OF AC | IBADAN, CHALLENGE | Routine Servicing | Preventive | TONA OGUNS | OTHERS | OTHERS | 2024-10-30 | 141 | 2024-10-30 | 0 |  | 141 | [9 empty] | Overdue
258 | WOBBLING AND PEALED TABLE IN THE LOBBY | LAG, HEYDEN IPAJA | Wear & Tear | Breakdown | MATOLAD | CUSTOMER TABLE | FURNITURE | 2024-10-14 | 157 | 2024-10-14 | 0 |  | 157 | [9 empty] | Overdue
259 | FAULTY AC | EDO, SAPELE RD, BENIN | Wear & Tear | Breakdown | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-30 | 141 | 2024-10-30 | 0 |  | 141 | [9 empty] | Overdue
260 | Grease Trap not functioning | DELTA, EFFURUN | Others | Breakdown | PROEQUIP | GREASE TRAP | GREASE_TRAP | 2024-10-30 | 141 | 2024-10-30 | 0 |  | 141 | [9 empty] | Overdue
261 | DAMAGED FEMALE CHANGING ROOM | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-10-08 | 163 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-10 | 2024-10-13 | 3 | 2024-10-25 | 9 | 2024-11-03 | 137 |  | 120000 | Overdue
262 | COLDROOM NOT ATTAINING TEMPERATURE | LAG, AGUNGI | Others | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-10-30 | 141 | 2024-10-30 | 0 |  | 141 | [9 empty] | Overdue
263 | UNDER BAR AND FREEZER ROOM NOT ATTAINING TEMPRETURE | LAG, IRE-AKARI | Others | Breakdown | THIO & PARTNERS | FREEZER ROOM | HVAC | 2024-10-23 | 148 | 2024-10-24 | 1 |  | 147 | [9 empty] | Overdue
264 | BLOCKED DRAINAGE AT STORE BACK OF HOUSE WASH AREA | LAG, OPEBI | Others | Breakdown | ZEBRA G3 | OTHERS | OTHERS | 2024-10-30 | 141 | 2024-10-30 | 0 |  | 141 | [9 empty] | Overdue
265 | REPAINTING OF THE FREEZER ROOM DOOR | LAG, IDI-IROKO RD | Wear & Tear | Breakdown | SULIAMON | PAINTING | BUILDING | 2024-10-03 | 11 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 11 | 2024-10-14 | 100750 | Completed | 2024-10-14 | 1
266 | REQUEST FOR CABINET BULBS | LAG, ETERNA LEKKI | Others | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 209625 | Completed | 2024-10-03 | 1
267 | REQUEST FOR CABINET BULBS | LAG, IKOTUN | Electrical Surge | Breakdown | EMMANUEL JOHN
268 | PX OGUDU BROKEN TILES | LAG, OGUDU | Wear & Tear | Breakdown | FULL TURN | OTHERS | OTHERS | 2024-10-02 | 169 | 2024-10-03 | 1 | 2024-10-07 | 4 | 2024-10-07 |  | 164 | [6 empty] | Overdue
269 | REPLACEMENT OF BAD SOAP DISPENSER | LAG, AKOWONJO | Users Misuse | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-10-02 | 169 | 2024-10-03 | 1 |  | 168 | [9 empty] | Overdue
270 | WATER ANALYSIS REPORT - CHOLERA OUTBREAK VALIDATION | LAG, ONIRU | Corrective Action | Corrective | PROEQUIP | OTHERS | OTHERS | 2024-10-02 | 169 | 2024-10-03 | 1 | 2024-10-30 | 27 | 2024-10-20 | 2024-10-21 | 1 | 2024-10-24 | 1 | 2024-10-25 | 146 | 2024-10-25 | 700000 | Overdue
271 | LEAKING WATER TREATMENT FILTERATION TANK | PH, WOJI | Corrective Action | Corrective | KASIM MURITALA | FILTRATION TANK | WTP | 2024-08-18 | 214 | 2024-08-20 | 2 | 2024-10-22 | 63 | [9 empty] | Overdue
272 | COLD ROOM NOT ATTAINIG TEMPERATURE | LAG, EJIGBO | Corrective Action | Corrective | LANRE | COLD ROOM UNIT | HVAC | 2024-10-03 | 168 | 2024-10-03 | 0 | 2024-10-03 | 0 | [9 empty] | Overdue
273 | FRYER SINK LEAKING OUT WATER | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | JOEL OMOTOSHO | KITCHEN WASH HAND SINK | PLUMBING | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 |  | Completed | 2024-10-03 | 1
274 | REQUEST FOR SOAP DISPENSER | LAG, CONOIL IKEJA | Users Misuse | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-10-03 | 12 | 2024-10-03 | 0 | 2024-10-09 | 6 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 144500 | Completed | 2024-10-15 | 1
275 | FAULTY CHLORINE DOZING PUMP | LAG, OMOLE | Corrective Action | Corrective | PROPEARJEFF | DOSING PUMP | WTP | 2024-10-18 | 153 | 2024-10-18 | 0 |  | 153 | [9 empty] | Overdue
276 | FAULTY ENTRANCE DOOR | LAG, ISAWO-IKORODU | Wear & Tear | Breakdown | FULL TURN | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-27 | 144 | 2024-10-28 | 1 | 2024-10-30 | 2 | 2024-10-30 | 2024-10-30 | 0 | 2024-10-30 | 5 | 2024-11-04 | 136 |  |  | Overdue
277 | Bad door shutter | LAG, IDIMU | Users Misuse | Breakdown | OLUWATOSIN
278 | FAULTY CHIPS FRYER | LAG, DOMINO E-CENTRE | Others | Breakdown | BCE | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-10-04 | 167 | 2024-10-04 | 0 | 2024-10-24 | 20 | 2024-10-24 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 147 |  |  | Overdue
279 | FAULTY CHIPS FRYER MACHINE | IMO, WETHERAL RD, OWERRI | Others | Breakdown | BCE | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-10-08 | 1 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 1 | 2024-10-09 | 0 | 2024-10-09 | 53750 | Completed | 2024-10-09 | 1
280 | FAULTY CHIPS FRYER MACHINE | LAG, AJAH | Others | Breakdown | BCE | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-10-18 | 153 | 2024-10-20 | 2 |  | 151 | [9 empty] | Overdue
281 | FAULTY CHIPS FRYER MACHINE | LAG, IKORODU | Others | Breakdown | BCE | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-05-22 | 302 | 2024-10-24 | 155 | 2024-10-24 | 0 | [9 empty] | Overdue
282 | FAULTY CHIPS FRYER MACHINE AND COLLECTRAMATIC FRYER MACHINE | LAG, IDI-IROKO RD | Others | Breakdown | BCE | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-10-26 | 6 | 2024-10-26 | 0 | 2024-10-31 | 5 | 2024-10-31 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 1 | 2024-11-01 | 491275 | Completed | 2024-11-01 | 1
283 | FAULTY CHIPS FRYER | DELTA, OKPE RD | Others | Breakdown | BCE | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-10-27 | 5 | 2024-10-28 | 1 | 2024-10-30 | 2 | 2024-10-31 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 1 | 2024-11-01 | 36550 | Completed | 2024-11-01 | 1
284 | FAULTY CHIPS FRYER MACHINE | EDO, SAPELE RD, BENIN | Others | Breakdown | BCE | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-10-28 | 143 | 2024-10-28 | 0 |  | 143 | [9 empty] | Overdue
285 | FAULTY CHIPS FRYER COMPARTMENT | LAG, OMOLE | Others | Breakdown | KITCHTECH | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-10-28 | 143 | 2024-10-28 | 0 | 2024-11-08 | 11 | [9 empty] | Overdue
286 | FAUTY INVERTER | IBADAN, OJOO | Others | Breakdown | DALEMATRIX | INVERTER SYSTEM | INVERTER | 2024-10-11 | 11 | 2024-10-11 | 0 | 2024-10-16 | 5 | 2024-10-16 | 2024-10-16 | 0 | 2024-10-17 | 5 | 2024-10-22 | 0 | 2024-10-22 | 126500 | Completed | 2024-10-22 | 1
287 | GEBNERATOR DUE FOR SERVICING | EDO, SAPELE RD, BENIN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-03 | 2 | 2024-10-04 | 1 | 2024-10-04 | 0 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 1 | 2024-10-05 | 202450 | Completed | 2024-10-05 | 1
288 | GENERATOR DUE FOR FIRST SERVICING |  | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-04 | 1 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 1 | 2024-10-05 |  | Completed | 2024-10-05 | 1
289 | GENERATOR DUE FOR SERVICING | LAG, FESTAC | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-05 | 3 | 2024-10-05 | 0 | 2024-10-07 | 2 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 1 | 2024-10-08 | 193125 | Completed | 2024-10-08 | 1
290 | GENERATOR DUE FOR SERVICING | LAG, OPEBI | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-06 | 1 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 1 | 2024-10-07 | 184125 | Completed | 2024-10-07 | 1
291 | GENERATOR DUE FOR SERVICE | LAG, AJAH | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-05 | 3 | 2024-10-06 | 1 | 2024-10-07 | 1 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 1 | 2024-10-08 | 181700 | Completed | 2024-10-08 | 1
292 | GENERATOR OIL LEVEL /OIL LEAKAGE | PH, ABA | Wear & Tear | Breakdown | PAGISEL | GENERATOR | GENERATOR | 2024-10-04 | 19 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 19 | 2024-10-23 |  | Completed | 2024-10-23 | 1
293 | GENERATOR OVER DUE FOR SERVICING | LAG, IPAJA RD | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 184125 | Completed | 2024-10-06 | 1
294 | GENERATOR DUE FOR SERVICING | LAG, AWOLOWO 2 | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-07 | 1 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 1 | 2024-10-08 | 181700 | Completed | 2024-10-08 | 1
295 | GENERATOR DUE FOR SERVICING | LAG, ILUPEJU | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-10-08 | 2 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 2 | 2024-10-10 | 313147.5 | Completed | 2024-10-10 | 1
296 | GENERATOR DUE FOR SERVICE | LAG, BADORE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-08 | 1 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 1 | 2024-10-09 | 181700 | Completed | 2024-10-09 | 1
297 | GENERATOR DUE FOR SERVICING | LAG, HEYDEN IPAJA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-09 | 1 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 1 | 2024-10-10 | 184125 | Completed | 2024-10-10 | 1
298 | Generator breakdown @CR Onne FOT | PH, ONNE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-08 | 2 | 2024-10-09 | 1 | 2024-10-09 | 0 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 1 | 2024-10-10 | 232450 | Completed | 2024-10-10 | 1
299 | GENERATOR DUE FOR SERVICING | IBADAN, IDI-APE (IWO RD) | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-09 | 1 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 1 | 2024-10-10 | 202450 | Completed | 2024-10-10 | 1
300 | GENERATOR DUE FOR SERVICING | LAG, IRE-AKARI | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-10 | 1 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 1 | 2024-10-11 | 208125 | Completed | 2024-10-11 | 1
301 | GENERATOR DUE FOR SERVICING | LAG, EKORO | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-10-10 | 4 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 4 | 2024-10-14 | 409897.5 | Completed | 2024-10-14 | 1
302 | GENERATOR DUE FOR SERVICING | DELTA, EFFURUN | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-10-11 | 2 | 2024-10-11 | 0 | 2024-10-12 | 1 | 2024-10-12 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 1 | 2024-10-13 | 284875 | Completed | 2024-10-13 | 1
303 | GENERATOR DUE FOR SERVICING | LAG, ISAWO-IKORODU | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-10-11 | 7 | 2024-10-11 | 0 | 2024-10-18 | 7 | 2024-10-18 | 2024-10-18 | 0 | 2024-10-18 | 0 | 2024-10-18 | 0 | 2024-10-18 | 243487.5 | Completed | 2024-10-18 | 1
304 | Generator Due for Service | LAG, VGC | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-10-12 | 4 | 2024-10-14 | 2 | 2024-10-16 | 2 | 2024-10-16 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-10-16 | 240638.75 | Completed | 2024-10-16 | 1
305 | GENERATOR DUE FOR SERVICING - PPU TOMBIA | PPU Tombia | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-10-15 | 156 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 156 |  |  | Overdue
306 | HEAD OFFICE GENERATOR DUE FOR SERVICE | Head Office | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-10-14 | 2 | 2024-10-14 | 0 | 2024-10-15 | 1 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 1 | 2024-10-16 |  | Completed | 2024-10-16 | 1
307 | GENERATOR DUE FOR SERVICING | ILORIN, OFFA GARAGE | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-16 | 1 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-10-16 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-10-16 | 1 | 2024-10-17 | 233500 | Completed | 2024-10-17 | 1
308 | GENERATOR DUE FOR SERVICING | LAG, AWOLOWO | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-18 | 1 | 2024-10-18 | 0 | 2024-10-18 | 0 | 2024-10-18 | 2024-10-18 | 0 | 2024-10-18 | 0 | 2024-10-18 | 1 | 2024-10-19 | 237160 | Completed | 2024-10-19 | 1
309 | WATER PUMP FAULTY/GENERATOR DUE FOR SERVICING | ILORIN, TAIWO RD | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-18 | 2 | 2024-10-18 | 0 | 2024-10-20 | 2 | 2024-10-20 | 2024-10-20 | 0 | 2024-10-20 | 0 | 2024-10-20 | 0 | 2024-10-20 | 448500 | Completed | 2024-10-20 | 1
310 | GENERATOR DUE FOR SERVICING | LAG, GBAGADA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-20 | 2 | 2024-10-20 | 0 | 2024-10-20 | 0 | 2024-10-20 | 2024-10-20 | 0 | 2024-10-20 | 0 | 2024-10-20 | 2 | 2024-10-22 | 181700 | Completed | 2024-10-22 | 1
311 | GENERATOR DUE FOR SERVICING | IBADAN, RING-ROAD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-20 | 2 | 2024-10-20 | 0 | 2024-10-20 | 0 | 2024-10-20 | 2024-10-20 | 0 | 2024-10-20 | 0 | 2024-10-20 | 2 | 2024-10-22 | 202450 | Completed | 2024-10-22 | 1
312 | GENERATOR DUE FOR SERVICE | LAG, HEYDEN ALAPERE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-22 | 1 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 | 1 | 2024-10-23 | 181700 | Completed | 2024-10-23 | 1
313 | CHICKEN REPUBLIC LETTERING NOT LIGHTED | LAG, MARINA | Wear & Tear | Breakdown | ARIZMANYA | OTHERS | OTHERS | 2024-10-11 | 22 | 2024-10-14 | 3 | 2024-10-25 | 11 | 2024-10-26 | 2024-10-26 | 0 | 2024-10-26 | 1 | 2024-10-27 | 6 | 2024-11-02 | 200000 | Completed | 2024-11-02 | 1
314 | SERVICING OF GREASE TRAP | LAG, AWOLOWO | Routine Servicing | Preventive | ZEBRA G3 | GREASE TRAP | GREASE_TRAP | 2024-10-04 | 167 | 2024-10-04 | 0 | 2024-10-12 | 8 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-14 | 4 | 2024-10-18 | 153 | 2024-10-18 | 350000 | Overdue
315 | FAULTY SWITCH FOR LIGHTS AT THE CASHPOINT | LAG, AKOWONJO | Wear & Tear | Breakdown | FRIDAY ONWUBUYA | OTHERS | OTHERS | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 |  | Completed | 2024-10-04 | 1
316 | REQUEST FOR ENGINE OIL | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | GAMMA | OTHERS | OTHERS | 2024-10-04 | 167 | 2024-10-04 | 0 |  | 167 | [9 empty] | Overdue
317 | LED LIGHT REQUEST | IBADAN, RING-ROAD | Others | Breakdown | RANEX | OTHERS | OTHERS | 2024-10-04 | 6 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 6 | 2024-10-10 | 43000 | Completed | 2024-10-10 | 1
318 | ROTISSERIE MACHINE NOT WORKING | OSUN, GBONGAN | Users Misuse | Breakdown | ECS | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-10-04 | 35 | 2024-10-04 | 0 | 2024-10-04 | #REF! | 2024-10-08 |  | 163 |  |  |  |  | 2024-11-08 |  | Completed | 2024-11-08 | 1
319 | PX IGANDO INVERTER ISSUE |  | Corrective Action | Corrective | CURRENTDATA | INVERTER BATTERIES | INVERTER | 2024-10-04 | 167 | 2024-10-04 | 0 |  | 167 | [9 empty] | Overdue
320 | REQUEST FOR COCK-HEAD PAINTING AND WASHING OF STORE EXTERIOR | LAG, ONIRU | Wear & Tear | Breakdown | ARIZMAYAN | PAINTING | BUILDING | 2024-10-04 | 167 | 2024-10-04 | 0 | 2024-10-13 | 9 | 2024-10-14 | 2024-10-18 | 4 | 2024-10-18 | 0 | 2024-10-18 | 153 | 2024-10-18 | 250000 | Overdue
321 | LOBBY AC BLOW OUT GAS | LAG, AJAH | Corrective Action | Corrective | TONAOGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-04 | 167 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 167 | 2024-10-04 | 95000 | Overdue
322 | FAULTY INSECTICUTOR IN THE LOBBY. | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | ISMAIL ODEDELE | INSECT KILLER LOBBY 1 | ELECTRICAL | 2024-10-04 | 4 | 2024-10-04 | 0 | 2024-10-08 | 4 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 |  | Completed | 2024-10-08 | 1
323 | FAULTY ENTRANCE DOOR GASKET | LAG, JIBOWU | Users Misuse | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-10-17 | 7 | 2024-10-17 | 0 | 2024-10-24 | 7 | 2024-10-24 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 30000 | Completed | 2024-10-24 | 1
324 | FAULTY ENTRANCE DOOR SELF LOCK | LAG, LATEEF JAKANDE | Users Misuse | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 30000 | Completed | 2024-10-28 | 1
325 | FAULTY SOCKET & NBC CHILLER | LAG, ONIRU | Electrical Surge | Breakdown | ADEREMI | OTHERS | OTHERS | 2024-10-04 | 1 | 2024-10-04 | 0 | 2024-10-05 | 1 | 2024-10-05 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 |  | Completed | 2024-10-05 | 1
326 | LOW ENGINE OIL | LAG, OGUNLANA DRIVE | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 104000 | Completed | 2024-10-06 | 1
327 | GENERATOR DUE FOR SERVICE | LAG, OSOLOWAY | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-07 | 1 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 1 | 2024-10-08 | 181700 | Completed | 2024-10-08 | 1
328 | GENERATOR DUE FOR SERVICE | LAG, AKOWONJO | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-09 | 1 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 1 | 2024-10-10 | 202450 | Completed | 2024-10-10 | 1
329 | CR ABA OWERRI ROAD GENERATOR NEEDS SEVICING | PH, ABA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-10 | 2 | 2024-10-11 | 1 | 2024-10-12 | 1 | 2024-10-12 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 177450 | Completed | 2024-10-12 | 1
330 | FAULTY GENERATOR BATTERY. | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 140000 | Completed | 2024-10-12 | 1
331 | FAULTY DIESEL `LINE PIPE | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 20000 | Completed | 2024-10-12 | 1
332 | RUNHOUR NOT READING | IMO, WETHERAL RD, OWERRI | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-10-20 | 1 | 2024-10-20 | 0 | 2024-10-20 | 0 | 2024-10-20 | 2024-10-20 | 0 | 2024-10-20 | 0 | 2024-10-20 | 1 | 2024-10-21 | 202450 | Completed | 2024-10-21 | 1
333 | Water Separator filter replacement Request (PPU TOMBIA | PPU Tombia | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-10-18 | 13 | 2024-10-18 | 0 | 2024-10-18 | 0 | 2024-10-18 | 2024-10-18 | 0 | 2024-10-18 | 0 | 2024-10-18 | 13 | 2024-10-31 | 210000 | Completed | 2024-10-31 | 1
334 | GENERATOR DUE FOR SERVICING | PH, GRA BIRABI | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-23 | 2 | 2024-10-23 | 0 | 2024-10-23 | 0 | 2024-10-23 | 2024-10-23 | 0 | 2024-10-23 | 0 | 2024-10-23 | 2 | 2024-10-25 | 202450 | Completed | 2024-10-25 | 1
335 | REQUEST FOR GENERATOR SERVICING | LAG, ONIRU | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-23 | 1 | 2024-10-23 | 0 | 2024-10-23 | 0 | 2024-10-23 | 2024-10-23 | 0 | 2024-10-23 | 0 | 2024-10-23 | 1 | 2024-10-24 | 104000 | Completed | 2024-10-24 | 1
336 | GENERATOR DUE FOR SERVICING | LAG, FREEDOMWAY | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-24 | 1 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 1 | 2024-10-25 | 181750 | Completed | 2024-10-25 | 1
337 | GENERATOR BREAK DOWN | LAG, LEKKI PHASE 1 | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-24 | 1 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 1 | 2024-10-25 | 145350 | Completed | 2024-10-25 | 1
338 | GENERATOR NOT COMING ON | EDO, AIRPORT RD, BENIN | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-10-25 | 1 | 2024-10-25 | 0 | 2024-10-26 | 1 | 2024-10-26 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 |  | Completed | 2024-10-26 | 1
339 | URGENT ATTENTION ON GENERATOR | LAG, AWOLOWO | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-10-25 | 1 | 2024-10-25 | 0 | 2024-10-25 | 0 | 2024-10-26 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 |  | Completed | 2024-10-26 | 1
340 | FAULTY GENERATOR | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 181700 | Completed | 2024-10-26 | 1
341 | GENERATOR DUE FOR SERVICING | IBADAN, AKOBO | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-26 | 2 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 2 | 2024-10-28 | 202450 | Completed | 2024-10-28 | 1
342 | Direct Diesel line water separator filter Request (Chicken Republic Yenagoa) | BAYELSA, YENAGOA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 220000 | Completed | 2024-10-28 | 1
343 | ICE CREAM MACHINE NOT WORKING | IBADAN, MOKOLA | Users Misuse | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-10-04 | 167 | 2024-10-04 | 0 |  | 167 | [9 empty] | Overdue
344 | GENERATOR NOT COMING UP | EDO, UGBOWO, BENIN | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-10-28 | 1 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 1 | 2024-10-29 | 717350 | Completed | 2024-10-29 | 1
345 | ICE CREAM MACHINE NOT WORKING | OGUN, OKE-ILEWO | Users Misuse | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-10-24 | 147 | 2024-10-24 | 0 |  | 147 | [9 empty] | Overdue
346 | ICE CREAM MACHINE NOT WORKING | OGUN, SOKENU | Users Misuse | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-10-27 | 144 | 2024-10-28 | 1 |  | 143 | [9 empty] | Overdue
347 | GENERATOR SERVICING | PH, ONNE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-29 | 1 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 1 | 2024-10-30 | 202450 | Completed | 2024-10-30 | 1
348 | GENERATOR DUE FOR SERVICING |  | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-26 | 4 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 4 | 2024-10-30 |  | Completed | 2024-10-30 | 1
349 | GENSET SERVICING | BAYELSA, TOMBIA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-30 | 2 | 2024-10-30 | 0 | 2024-10-31 | 1 | 2024-10-31 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 1 | 2024-11-01 |  | Completed | 2024-11-01 | 1
350 | DEAD LIGHT IN CASH POINT | LAG, ILUPEJU | Wear & Tear | Breakdown | KOLA | OTHERS | OTHERS | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 |  | Completed | 2024-10-04 | 1
351 | Generator Service Request Format CR IKOT_EKPENE RD 2024.xlsx | AKWA IBOM, IKOT EKPENE RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-31 | 1 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 1 | 2024-11-01 | 202450 | Completed | 2024-11-01 | 1
352 | GENERATOR DUE FOR SERVICING | LAG, NNPC ALAPERE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-31 | 1 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 1 | 2024-11-01 | 130350 | Completed | 2024-11-01 | 1
353 | Generator Service Request_.xlsx | IMO, IKENEGBU, OWERRI | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-31 | 1 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 1 | 2024-11-01 | 202450 | Completed | 2024-11-01 | 1
354 | GENERATOR SERVICING | LAG, AJOSE ADEOGUN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-29 | 3 | 2024-10-30 | 1 | 2024-10-31 | 1 | 2024-10-31 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 1 | 2024-11-01 | 403125 | Completed | 2024-11-01 | 1
355 | GENERATOR DUE FOR SERVICE | LAG, OGUDU | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-11 | 1 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 1 | 2024-10-12 |  | Completed | 2024-10-12 | 1
356 | DEAD BULB 💡 IN CUSTOMER REST ROOM | LAG, MMA2 | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-10-28 | 4 | 2024-10-28 | 0 | 2024-11-01 | 4 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 |  | Completed | 2024-11-01 | 1
357 | DEAD BULB INSECTOCUTOR | LAG, CONOIL IKEJA | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-10-23 | 2 | 2024-10-23 | 0 | 2024-10-25 | 2 | 2024-10-25 | 2024-10-25 | 0 | 2024-10-25 | 0 | 2024-10-25 | 0 | 2024-10-25 |  | Completed | 2024-10-25 | 1
358 | DEAD BULB IN COLD ROOM | LAG, CONOIL IKEJA | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-10-26 | 3 | 2024-10-28 | 2 | 2024-10-29 | 1 | 2024-10-29 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 |  | Completed | 2024-10-29 | 1
359 | PX IGANDO DEAD BULB |  | Electrical Surge | Breakdown | FRIDAY | OTHERS | OTHERS | 2024-10-22 | 6 | 2024-10-22 | 0 | 2024-10-28 | 6 | 2024-10-28 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 |  | Completed | 2024-10-28 | 1
360 | Faulty Changing room door handle | LAG, OSOLOWAY | Wear & Tear | Breakdown | MATTHEW | OTHERS | OTHERS | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 |  | Completed | 2024-10-05 | 1
361 | GENERATOR DUE FOR SERVICE | LAG, OKOTA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-11 | 3 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 3 | 2024-10-14 | 193125 | Completed | 2024-10-14 | 1
362 | GENERATOR FAN BELT | LAG, IRE-AKARI | Wear & Tear | Breakdown | MIDTECH | GENERATOR | GENERATOR | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 |  | Completed | 2024-10-12 | 1
363 | GENERATOR IS DUE FOR SERVICE | LAG, MAGODO | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-13 | 5 | 2024-10-13 | 0 | 2024-10-13 | 0 | 2024-10-17 | 2024-10-17 | 0 | 2024-10-17 | 0 | 2024-10-17 | 1 | 2024-10-18 | 208125 | Completed | 2024-10-18 | 1
364 | DIESEL PIPE LEAKAGE | LAG, MARINA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-12 | 159 | 2024-10-12 | 0 | 2024-10-16 | 4 | [9 empty] | Overdue
365 | WATER PUMP FAULTY | ILORIN, TAIWO RD | Wear & Tear | Breakdown | MIDTECH | GENERATOR | GENERATOR | 2024-10-18 | 2 | 2024-10-18 | 0 | 2024-10-20 | 2 | 2024-10-20 | 2024-10-20 | 0 | 2024-10-20 | 0 | 2024-10-20 | 0 | 2024-10-20 |  | Completed | 2024-10-20 | 1
366 | FAULTY GENERATOR FILTERS | LAG, IDIMU | Wear & Tear | Breakdown | MIDTECH | GENERATOR | GENERATOR | 2024-10-21 | 2 | 2024-10-21 | 0 | 2024-10-23 | 2 | 2024-10-23 | 2024-10-23 | 0 | 2024-10-23 | 0 | 2024-10-23 | 0 | 2024-10-23 |  | Completed | 2024-10-23 | 1
367 | REQUEST FOR A NEW BATTERY. | ILORIN, MM WAY | Wear & Tear | Breakdown | MIDTECH | GENERATOR | GENERATOR | 2024-10-24 | 3 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 3 | 2024-10-27 |  | Completed | 2024-10-27 | 1
368 | GENERATOR SERVICING | LAG, IKOTUN | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-24 | 1 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 1 | 2024-10-25 |  | Completed | 2024-10-25 | 1
369 | ERECTING OF TEMPORARY HOUSE ON BACKUP GENERATOR | LAG, ABULE EGBA | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-10-26 | 2 | 2024-10-26 | 0 | 2024-10-28 | 2 | 2024-10-28 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 |  | Completed | 2024-10-28 | 1
370 | BOH WATER TAP FAULTY | LAG, MAGODO | Wear & Tear | Breakdown | ADEREMI | TAP | PLUMBING | 2024-10-05 | 2 | 2024-10-05 | 0 | 2024-10-07 | 2 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 |  | Completed | 2024-10-07 | 1
371 | Servicing of generator | IBADAN, MOKOLA | Wear & Tear | Breakdown | MIDTECH | GENERATOR | GENERATOR | 2024-10-26 | 145 | 2024-10-26 | 0 | 2024-10-30 | 4 | [9 empty] | Overdue
372 | GENERATOR OVER DUE FOR SERVICING | LAG, IPAJA RD | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-29 | 8 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 8 | 2024-11-06 | 193125 | Completed | 2024-11-06 | 1
373 | GENERATOR DUE FOR SERVICE | LAG, FESTAC | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-30 | 1 | 2024-10-30 | 0 | 2024-10-30 | 0 | 2024-10-30 | 2024-10-30 | 0 | 2024-10-30 | 0 | 2024-10-30 | 1 | 2024-10-31 |  | Completed | 2024-10-31 | 1
374 | GENERATOR DUE FOR SERVICING | LAG, HEYDEN IPAJA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-30 | 1 | 2024-10-30 | 0 | 2024-10-31 | 1 | 2024-10-31 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 184125 | Completed | 2024-10-31 | 1
375 | Cracked door glass | LAG, ILUPEJU | Others | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-10-05 | 5 | 2024-10-05 | 0 | 2024-10-10 | 5 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 30000 | Completed | 2024-10-10 | 1
376 | GENERATOR DUE FOR SERVICING | LAG, IDIMU | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-30 | 1 | 2024-10-30 | 0 | 2024-10-30 | 0 | 2024-10-30 | 2024-10-30 | 0 | 2024-10-30 | 0 | 2024-10-30 | 1 | 2024-10-31 |  | Completed | 2024-10-31 | 1
377 | GENERATOR DUE FOR SERVICING | ILORIN, OLOFAWAY | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-31 | 1 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 1 | 2024-11-01 |  | Completed | 2024-11-01 | 1
378 | FAULTY GENERATOR | LAG, OKE-AFA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-31 | 140 | 2024-10-31 | 0 | 2024-10-31 | 0 | [9 empty] | Overdue
379 | Faulty Generator at Ndidem | CALABAR, NDIDEM | Wear & Tear | Breakdown | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 |  | Completed | 2024-10-06 | 1
380 | Faulty Generator | ABIA, OGBOR HILLS | Wear & Tear | Breakdown | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-10-08 | 163 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 |  | 163 | [6 empty] | Overdue
381 | DIESEL TANK LEAKAGE | LAG, AGUNGI | Wear & Tear | Breakdown | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-10-11 | 160 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 160 |  |  |  |  | Overdue
382 | OCTOBER GEN MAINTAINACE | IMO, OKIGWE | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-10-26 | 2 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 2024-10-26 | 0 | 2024-10-27 | 0 | 2024-10-27 | 1 | 2024-10-28 | 225750 | Completed | 2024-10-28 | 1
383 | SERVICING OF GENERATOR | LAG, AGUNGI | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-10-31 | 1 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 1 | 2024-11-01 | 236500 | Completed | 2024-11-01 | 1
384 | SPOILT DISPLAY CABINET FLAP HINGE | OGUN, HEYDEN IBAFO | Wear & Tear | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-12 | 9 | 2024-10-13 | 1 | 2024-10-21 | 8 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 40000 | Completed | 2024-10-21 | 1
385 | SERVICING OF ICE CREAM MACHINE | KADUNA, YAKUBU GOWON | Routine Servicing | Preventive | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-10-16 | 155 | 2024-10-16 | 0 | 2024-10-16 | 0 | [9 empty] | Overdue
386 | FAULTY GENERATOR | OYO, OWODE | Wear & Tear | Breakdown | DELIGHTSOME | GENERATOR | GENERATOR | 2024-10-19 | 152 | 2024-10-20 | 1 |  | 151 | [9 empty] | Overdue
387 | GENERATOR DUE FOR SERVICE | LAG, DIYA STREET | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-10-17 | 11 | 2024-10-17 | 0 | 2024-10-24 | 7 | 2024-10-24 | 2024-10-24 | 0 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 156573.75 | Completed | 2024-10-28 | 1
388 | URGENT MAINTENANCE ATTENTION FOR PPU ONIRU GENERATOR SET | PPU Oniru | Wear & Tear | Breakdown | DELIGHTSOME | GENERATOR | GENERATOR | 2024-10-17 | 7 | 2024-10-17 | 0 | 2024-10-23 | 6 | 2024-10-23 | 2024-10-23 | 0 | 2024-10-23 | 0 | 2024-10-23 | 1 | 2024-10-24 | 1313488.75 | Completed | 2024-10-24 | 1
389 | ELECTRICAL SHOCK FROM EQUIPMENT | LAG, EKORO | Electrical Surge | Breakdown | TAYO | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-10-24 | 9 | 2024-10-24 | 0 | 2024-10-25 | 1 | 2024-10-26 | 2024-10-26 | 0 | 2024-10-26 | 145 |  |  | 2024-11-02 |  | Completed | 2024-11-02 | 1
390 | GENERATOR SERVICING | OYO, OWODE | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-10-04 | 11 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 11 | 2024-10-15 | 412047 | Completed | 2024-10-15 | 1
391 | GENERATOR DUE FOR SERVICING | OSUN, AYETORO | Routine Servicing | Preventive | SYMINERTIAS | GENERATOR | GENERATOR | 2024-10-27 | 4 | 2024-10-27 | 0 | 2024-10-28 | 1 | 2024-10-28 | 2024-10-28 | 0 | 2024-10-30 | 0 | 2024-10-30 | 1 | 2024-10-31 | 340437.5 | Completed | 2024-10-31 | 1
392 | FAULTY PEKINS GENERATOR MODULE | BAYELSA, OPOLO | Wear & Tear | Breakdown | PAGISEL | GENERATOR | GENERATOR | 2024-10-31 | 1 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 1 | 2024-11-01 |  | Completed | 2024-11-01 | 1
393 | FAULTY GENERATOR | PH AGGREY | Wear & Tear | Breakdown | CNOS TECH | GENERATOR | GENERATOR | 2024-10-28 | 143 | 2024-10-29 | 1 | 2024-10-29 | 0 | 2024-10-29 |  | 142 | [5 empty] | 900000 | Overdue
394 | LOW VOLTAGE SUPPLY | LAG, MARINA | Electrical Surge | Breakdown | ISMAIL ODEDELE | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-10-29 | 4 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 4 | 2024-11-02 |  | Completed | 2024-11-02 | 1
395 | PHCN LIGHT | LAG, ETERNA LEKKI | Electrical Surge | Breakdown | GBATMO | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-10-28 | 1 | 2024-10-28 | 0 | 2024-10-29 | 1 | 2024-10-29 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 |  | Completed | 2024-10-29 | 1
396 | Potato Peeler Repair | PPU Oniru | Wear & Tear | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 2024-10-29 | 0 | 2024-10-29 | 5 | 2024-11-03 | -5 | 2024-11-03 | 194575 | Completed | 2024-10-29 | 1
397 | NEW GENERATOR BATTERY REQUEST | PH, ONNE | Wear & Tear | Breakdown | PAGISEL | GENERATOR | GENERATOR | 2024-10-17 | 44 | 2024-10-29 | 12 | 2024-10-29 | 0 | 2024-11-29 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 1 | 2024-11-30 |  | Completed | 2024-11-30 | 1
398 | SPARKING TRANSFORMER | LAG, ALIMOSHO | Electrical Surge | Breakdown | AUSBETH | TRANSFORMER | ELECTRICAL | 2024-10-27 | 3 | 2024-10-28 | 1 | 2024-10-30 | 2 | 2024-10-30 | 2024-10-30 | 0 | 2024-10-30 | 0 | 2024-10-30 | 0 | 2024-10-30 |  | Completed | 2024-10-30 | 1
399 | EXPLOSION OF EXTERNAL JUCTION BOX | LAG, ONIRU | Electrical Surge | Breakdown | GBATMO | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-10-30 | 141 | 2024-10-30 | 0 | 2024-10-30 | 0 | [9 empty] | Overdue
400 | FAULTY GENERATOR | PH, IWOFE | Wear & Tear | Breakdown |  | GENERATOR | GENERATOR | 2024-10-31 | 140 | 2024-10-31 | 0 |  | 140 | [9 empty] | Overdue
401 | UPDATED PENDING MAINTAINANCE ISSUES | LAG, ONIRU | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-10-19 | 152 | 2024-10-21 | 2 |  | 150 | [9 empty] | Overdue
402 | FAULTY DISPLAY CABINET - CR NSUKKA | ENUGU, NSUKKA | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-08 | 3 | 2024-10-08 | 0 | 2024-10-10 | 2 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 1 | 2024-10-11 | 30100 | Completed | 2024-10-11 | 1
403 | DETACHED DISPLAY CABINET FLAP/LID | OGUN, FATGBEMS IBB WAY | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-10 | 2 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 2 | 2024-10-12 | 58000 | Completed | 2024-10-12 | 1
404 | PX APAPA THINGS THAT TO BE FIXED | LAG, WAREHOUSE RD, APAPA | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-12 | 159 | 2024-10-12 | 0 |  | 159 | [9 empty] | Overdue
405 | FAULTY CHEST FREEZER FUSE AND DISPLAY LAMP HOLDER | LAG, MAGODO | Wear & Tear | Breakdown | KOLA | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-14 | 1 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 1 | 2024-10-15 |  | Completed | 2024-10-15 | 1
406 | FAULTY DISPLAYED CABINET BULB | LAG, TEJUOSHO | Wear & Tear | Breakdown | TIMILEHIN | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-14 | 1 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 1 | 2024-10-15 | 43000 | Completed | 2024-10-15 | 1
407 | DISPLAY CABINET OVER-HEATING AND WITHOUT CONTROL | OGUN, OKE-ILEWO | Wear & Tear | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT
408 | FAULTY ENTRANCE DOOR | LAG, ISAWO-IKORODU | Wear & Tear | Breakdown | FULLTURN | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-27 | 144 | 2024-10-28 | 1 | 2024-10-29 | 1 | 2024-10-30 | 2024-10-30 | 0 | 2024-10-30 | 5 | 2024-11-04 | 136 |  |  | Overdue
409 | UPDATED PENDING MAINTAINANCE ISSUES | LAG, ONIRU | Routine Servicing | Preventive | FOLLTEC | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-22 | 1 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 | 1 | 2024-10-23 |  | Completed | 2024-10-23 | 1
410 | FREEZER ROOM NOT ATTAINING TEMPRETURE | LAG, BADORE | Wear & Tear | Breakdown | ECS | FREEZER ROOM | HVAC | 2024-10-30 | 141 | 2024-10-30 | 0 |  | 141 | [9 empty] | Overdue
411 | COLD AND FREEZER ROOM NOT ATTAINING TEMPERATURE | PH, WOJI | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-10-24 | 4 | 2024-10-28 | 4 | 2024-10-28 | 0 | 2024-10-28 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 80000 | Completed | 2024-10-28 | 1
412 | AC SERVICING | IBADAN, BODIJA | Routine Servicing | Preventive | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-22 | 7 | 2024-10-22 | 0 | 2024-10-29 | 7 | 2024-10-29 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 |  | Completed | 2024-10-29 | 1
413 | AC SERVICING | IMO, WETHERAL RD, OWERRI | Routine Servicing | Preventive | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-26 | 4 | 2024-10-26 | 0 | 2024-10-29 | 3 | 2024-10-29 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 1 | 2024-10-30 | 130000 | Completed | 2024-10-30 | 1
414 | STORE AUDIT REPORT (03.10.24) | LAG, MMA2 | Users Misuse | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-04 | 167 | 2024-10-04 | 0 |  | 167 | [9 empty] | Overdue
415 | BROKEN CABINET GLASS |  | Users Misuse | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-04 | 167 | 2024-10-04 | 0 |  | 167 | [9 empty] | Overdue
416 | BROKEN CABINET GLASS | LAG, FESTAC | Users Misuse | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-05 | 166 | 2024-10-05 | 0 |  | 166 | [9 empty] | Overdue
417 | FAULTY CABINET GLASS HANDLE | LAG, IRE-AKARI | Wear & Tear | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-05 | 166 | 2024-10-06 | 1 |  | 165 | [9 empty] | Overdue
418 | SPOILT BARICADE AT THE BACK OF HOUSE | LAG, IRE-AKARI | Wear & Tear | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-10-05 | 166 | 2024-10-06 | 1 |  | 165 | [9 empty] | Overdue
419 | BROKEN FILES WITHIN THE STORE | LAG, AGUNGI | Wear & Tear | Breakdown | ACORN | OTHERS | OTHERS | 2024-10-04 | 167 | 2024-10-04 | 0 | 2024-10-06 | 2 | 2024-10-14 |  | 157 | [6 empty] | Overdue
420 | RESTROOM DRAINAGE BLOCKAGE | LAG, ONIRU | Users Misuse | Breakdown | JOEL OMOTOSHO | OTHERS | OTHERS | 2024-10-04 | 1 | 2024-10-05 | 1 | 2024-10-05 | 0 | 2024-10-05 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 |  | Completed | 2024-10-05 | 1
421 | FAULTY CABINET LAMP HOLDER | LAG, AWOLOWO | Users Misuse | Breakdown | KITCHTECH | OTHERS | OTHERS | 2024-10-01 | 9 | 2024-10-05 | 4 | 2024-10-10 | 5 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 47000 | Completed | 2024-10-10 | 1
422 | FAULTY CABINET LAMP HOLDER AND BULBS | LAG, IRE-AKARI | Others | Breakdown | FRIDAY | OTHERS | OTHERS | 2024-10-28 | 143 | 2024-10-29 | 1 |  | 142 | [9 empty] | Overdue
423 | FAULTY CABINET LAMP HOLDER | LAG, AKOWONJO | Others | Breakdown | HEFHEM | OTHERS | OTHERS | 2024-10-30 | 141 | 2024-10-30 | 0 | 2024-11-06 | 7 | [9 empty] | Overdue
424 | FAULTY FREEZER ROOM AND COLD ROOM | LAG, OGUNLANA DRIVE | Users Misuse | Breakdown | BB COMMERCIAL | FREEZER ROOM | HVAC | 2024-10-29 | 2 | 2024-10-29 | 0 | 2024-10-31 | 2 | [7 empty] | 2024-10-31 |  | Completed | 2024-10-31 | 1
425 | FAULTY FREEZER ROOM | LAG, MARINA | Others | Breakdown | TONAOGUNS | FREEZER ROOM | HVAC | 2024-10-23 | 148 | 2024-10-23 | 0 | 2024-10-29 | 6 | 2024-10-29 |  | 142 | [6 empty] | Overdue
426 | FAULTY FREEZER ROOM IN RUKPOKWU STORE | PH, RUKPOKWU | Others | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-10-31 | 140 | 2024-10-31 | 0 |  | 140 | [9 empty] | Overdue
427 | RUSTY COLD ROOM DOOR AND WALLS | LAG, OSOLOWAY | Wear & Tear | Breakdown | THIO&PARTHERS | COLD ROOM UNIT | HVAC | 2024-10-06 | 165 | 2024-10-06 | 0 |  | 165 | [9 empty] | Overdue
428 | De weeding of transformer House | LAG, OSOLOWAY | Others | Breakdown | GBATMO VENTURES | OTHERS | OTHERS | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 |  | Completed | 2024-10-08 | 1
429 | REQUEST FOR LED LIGHT | IBADAN, OJOO | Others | Breakdown | RANEX | OTHERS | OTHERS | 2024-10-08 | 163 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 163 | 2024-10-08 | 86000 | Overdue
430 | REQUEST FOR LED LIGHT | OSUN, AYETORO | Others | Breakdown | RANEX | OTHERS | OTHERS | 2024-10-14 | 157 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-14 | 1 | 2024-10-15 | 156 | 2024-10-15 | 51600 | Overdue
431 | FAULTY WATER CLOSET | LAG, IRE-AKARI | Corrective Action | Corrective | PROEQUIP | OTHERS | OTHERS | 2024-10-08 | 163 | 2024-10-08 | 0 | 2024-11-04 | 27 | [9 empty] | Overdue
432 | BROKEN LOBBY TV | LAG, AJOSE ADEOGUN | Users Misuse | Breakdown | ACORN | TELEVISION | AUDIOVISUAL | 2024-10-07 | 164 | 2024-10-07 | 0 | 2024-10-09 | 2 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 162 |  |  |  | 678362 | Overdue
433 | PAINTING OF LOBBY TABLES FOR LEKKI TOTAL | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | MATOLAD | PAINTING | BUILDING | 2024-10-17 | 154 | 2024-10-17 | 0 | 2024-10-19 | 2 | [9 empty] | Overdue
434 | Electrical materials | IBADAN, VENTURA MALL | Others | Breakdown | RANEX | OTHERS | OTHERS | 2024-10-28 | 143 | 2024-10-28 | 0 | 2024-10-29 | 1 | 2024-10-29 |  | 142 | [6 empty] | Overdue
435 | REPLACEMENT OF COLLETRAMATIC PRESSURE FRYER LEAD GASKET | PH, OMOKU | Others | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-07 | 26 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-28 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 5 | 2024-11-02 | 112875 | Completed | 2024-11-02 | 1
436 | DAMAGED ROOF IN FEMALE CHANGING ROOM | LAG, CONOIL IKEJA | Others | Breakdown
437 | COMPLETION OF COLLAPSED DRAINAGE | LAG, OMOLE | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-10-06 | 19 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-07 | 2024-10-08 | 1 | 2024-10-09 | 7 | 2024-10-16 | 9 | 2024-10-25 | 850000 | Completed | 2024-10-25 | 1
438 | LEAKING LOBBY AND DRYSTORE ROOF | LAG, MAGODO | Wear & Tear | Breakdown | ACORN | OTHERS | OTHERS | 2024-10-07 | 164 | 2024-10-07 | 0 | 2024-10-11 | 4 | 2024-10-11 | 2024-10-14 | 3 | 2024-10-14 | 157 |  |  |  | 650000 | Overdue
439 | BOH INSECTICUTOR BULB NOT WORKING | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | ISMAIL | INSECT KILLER BOH | ELECTRICAL | 2024-10-07 | 1 | 2024-10-07 | 0 | 2024-10-08 | 1 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 |  | Completed | 2024-10-08 | 1
440 | OPEN SOCKET IN STORE | LAG, MARINA | Users Misuse | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-10-07 | 1 | 2024-10-07 | 0 | 2024-10-08 | 1 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 |  | Completed | 2024-10-08 | 1
441 | FAULTY WARMER GASKET | LAG, IRE-AKARI | Users Misuse | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2024-10-05 | 166 | 2024-10-06 | 1 | 2024-10-08 | 2 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 163 |  |  |  |  | Overdue
442 | ELECTRICAL ITEMS NEEDED FOR RATIONAL MACHINE | LAG, AWOLOWO | Electrical Surge | Breakdown | Ismail | OTHERS | OTHERS | 2024-10-14 | 2 | 2024-10-14 | 0 | 2024-10-16 | 2 | 2024-10-16 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-10-16 |  | Completed | 2024-10-16 | 1
443 | ELECTRICAL ITEMS |  | Electrical Surge | Breakdown | RANEX | OTHERS | OTHERS | 2024-10-07 | 1 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 1 | 2024-10-08 |  | Completed | 2024-10-08 | 1
444 | DEAD INSECTOCUTOR BULB. | LAG, OGUDU | Electrical Surge | Breakdown | KOLA | OTHERS | OTHERS | 2024-10-16 | 5 | 2024-10-16 | 0 | 2024-10-19 | 3 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 |  | Completed | 2024-10-21 | 1
445 | WATER NOT RUNNING IN THE STORE | LAG, VGC | Corrective Action | Corrective | PROEQUIP | OTHERS | OTHERS | 2024-10-07 | 2 | 2024-10-08 | 1 | 2024-10-09 | 1 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 60000 | Completed | 2024-10-09 | 1
446 | DAMAGED STORE COMPARTMENT | LAG, OKOTA | Wear & Tear | Breakdown | PENTICOSTAL | OTHERS | OTHERS | 2024-10-07 | 164 | 2024-10-07 | 0 | 2024-11-09 | 33 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-11 | 8 | 2024-11-19 | 121 | 2024-11-25 | 300000 | Overdue
447 | FAULTY CABINET LIGHTS | LAG, FREEDOMWAY | Electrical Surge | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-07 | 3 | 2024-10-07 | 0 | 2024-10-10 | 3 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 28487.5 | Completed | 2024-10-10 | 1
448 | LEAKING FRYER'S SINK |  | Wear & Tear | Breakdown | JOEL | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-06 | 16 | 2024-10-06 | 0 | 2024-10-22 | 16 | 2024-10-22 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 |  | Completed | 2024-10-22 | 1
449 | HAND SANITIZER DISPENSERS NEEDED AND THERE BAD SOAP DISPENSERS TO BE REPLACED | LAG, OBA AKRAN | Users Misuse | Breakdown | AKINOLA | OTHERS | OTHERS | 2024-10-05 | 4 | 2024-10-06 | 1 | 2024-10-09 | 3 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 |  | Completed | 2024-10-09 | 1
450 | CHIPS FRYER DOOR | LAG, TEJUOSHO | Users Misuse | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-09 | 162 | 2024-10-09 | 0 | 2024-10-11 | 2 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 160 | 2024-10-11 | 33325 | Overdue
451 | FAULTY WARMER WALL SOCKET | LAG, JOEL OGUNNAIKE | Corrective Action | Corrective | TIMILEHIN | OTHERS | OTHERS | 2024-10-06 | 2 | 2024-10-06 | 0 | 2024-10-08 | 2 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 |  | Completed | 2024-10-08 | 1
452 | CHIPPED EDGES WALLS IN THE STORE | LAG, OGUDU | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-10-05 | 18 | 2024-10-06 | 1 | 2024-10-09 | 3 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 14 | 2024-10-23 | 0 | 2024-10-23 |  | Completed | 2024-10-23 | 1
453 | INSECTOCUTOR WITH DAMAGED TRAY | LAG, OBA AKRAN | Users Misuse | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-10-05 | 5 | 2024-10-06 | 1 | 2024-10-10 | 4 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 99975 | Completed | 2024-10-10 | 1
454 | LOW VOLTAGE |  | Electrical Surge | Breakdown | EMMANUEL JOHN | OTHERS | OTHERS | 2024-10-05 | 8 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-13 | 2024-10-13 | 0 | 2024-10-13 | 0 | 2024-10-13 | 0 | 2024-10-13 |  | Completed | 2024-10-13 | 1
455 | LOW VOLTAGE POWER SUPPLY | LAG, ONIRU | Electrical Surge | Breakdown | ADEREMI | OTHERS | OTHERS | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 | 0 | 2024-10-26 |  | Completed | 2024-10-26 | 1
456 | FAULTY CABINET BULB | LAG, JOEL OGUNNAIKE | Electrical Surge | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-08 | 9 | 2024-10-08 | 0 | 2024-10-17 | 9 | 2024-10-17 | 2024-10-17 | 0 | 2024-10-17 | 0 | 2024-10-17 | 0 | 2024-10-17 |  | Completed | 2024-10-17 | 1
457 | FAULTY HAND DRYER IN MALE RESTROOM | LAG, MOBIL OGBA | Users Misuse | Breakdown | PROEQUIP | HAND DRYER TOILET | ELECTRICAL | 2024-10-28 | 143 | 2024-10-28 | 0 |  | 143 | [9 empty] | Overdue
458 | FAULTY HAND DRYER AND COMPOSITE PANEL | LAG, JOEL OGUNNAIKE | Others | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-10-13 | 19 | 2024-10-28 | 15 | 2024-11-01 | 4 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 |  | Completed | 2024-11-01 | 1
459 | FAULTY HAND DRYER AND INSECT EXOCUTOR | LAG, OBA AKRAN | Others | Breakdown | TAYO | OTHERS | OTHERS | 2024-10-17 | 12 | 2024-10-17 | 0 | 2024-10-17 | 0 | 2024-10-29 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 |  | Completed | 2024-10-29 | 1
460 | WARMER AND HOLDING CABINET NOT ATTAINING TEMPERATURE | DELTA, ISOKO RD | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-10-22 | 10 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-28 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 4 | 2024-11-01 | 64500 | Completed | 2024-11-01 | 1
461 | REQUEST FOR LED LIGHTS | OYO, OWODE | Electrical Surge | Breakdown | RANEX | OTHERS | OTHERS | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 43000 | Completed | 2024-10-08 | 1
462 | SMOKE COMING OUT OF THE CABINET AT THE FRONT OF HOUSE | LAG, FESTAC | Others | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-08 | 1 | 2024-10-08 | 0 | 2024-10-09 | 1 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 |  | Completed | 2024-10-09 | 1
463 | FAULTY FLAMMED GRILLED MACHINE. | LAG, JOEL OGUNNAIKE | Corrective Action | Corrective | BERRADE | OTHERS | OTHERS | 2024-10-08 | 163 | 2024-10-22 | 14 |  | 149 | [9 empty] | Overdue
464 | PX FESTAC COUNTER | LAG, FESTAC | Wear & Tear | Breakdown | MATOLAD | CASHIER COUNTER | BUILDING | 2024-10-09 | 31 | 2024-10-09 | 0 | 2024-10-19 | 10 | 2024-10-19 |  | 3 | 2024-10-19 | 0 | 2024-10-19 | 21 | 2024-11-09 | 140000 | Completed | 2024-11-09 | 1
465 | Broken wash hand sink stand | LAG, OSOLOWAY | Wear & Tear | Breakdown | PROPEARJEFF | KITCHEN WASH HAND SINK | PLUMBING | 2024-10-08 | 14 | 2024-10-08 | 0 | 2024-10-22 | 14 | 2024-10-22 | 2024-10-22 | #REF! | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 |  | Completed | 2024-10-22 | 1
466 | REQUEST TO FIX HANDWASH AND SANITIZER DISPENSER | OSUN, GBONGAN | Users Misuse | Breakdown | PROEQUIP | OTHERS | OTHERS | 2024-10-08 | 163 | 2024-10-08 | 0 |  | 163 | [9 empty] | Overdue
467 | DAMAGED FRYER TABLE | LAG, MARINA | Users Misuse | Breakdown | MODEL INT | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-07 | 164 | 2024-10-08 | 1 | 2024-10-08 | 0 | 2024-10-17 | 2024-10-17 | 0 | 2024-10-17 | 154 |  |  |  | 230000 | Overdue
468 | 2 FAULTY LOBBY AIR CONDITION | LAG, ONIRU | Routine Servicing | Preventive | FOLLTEC | OTHERS | OTHERS | 2024-10-07 | 164 | 2024-10-07 | 0 |  | 164 | [9 empty] | Overdue
469 | ELECTRICAL BULB REPLACEMENT | LAG, ILUPEJU | Others | Breakdown | KOLA | OTHERS | OTHERS | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 |  | Completed | 2024-10-07 | 1
470 | OPENED AND RUSTY FRESH AIR VENT | LAG, OGUDU | Wear & Tear | Breakdown | ABBEYELECTRICAL | OTHERS | OTHERS | 2024-10-05 | 3 | 2024-10-08 | 3 | 2024-10-08 | 0 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 |  | Completed | 2024-10-08 | 1
471 | FALLING OF HAND DRYER IN THE CUSTOMERS TOILET | LAG, OBA AKRAN | Users Misuse | Breakdown | TIMILEHIN | HAND DRYER TOILET | ELECTRICAL | 2024-10-05 | 3 | 2024-10-06 | 1 | 2024-10-08 | 2 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 |  | Completed | 2024-10-08 | 1
472 | STORE AUDIT FINDINGS | LAG, GBAGADA | Wear & Tear | Breakdown | PENTICOSTAL | OTHERS | OTHERS | 2024-10-10 | 161 | 2024-10-10 | 0 | 2024-10-10 | 0 | [9 empty] | Overdue
473 | BLINKING LIGHT AT BOH PRODUCTION FLOOR AND CUSTOMER RESTROOM. | LAG, JOEL OGUNNAIKE | Others | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 |  | Completed | 2024-10-08 | 1
474 | BROKEN TILES IN THE STORE | EDO, UGBOWO, BENIN | Wear & Tear | Breakdown | DEACONESS | OTHERS | OTHERS | 2024-10-06 | 165 | 2024-10-06 | 0 |  | 165 | [9 empty] | Overdue
475 | NO WATER IN THE STORE | LAG, MOBIL OGBA | Others | Breakdown | PROEQUIP | TAP | PLUMBING | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 |  | Completed | 2024-10-06 | 1
476 | NO WATER IN THE STORE | LAG, MAGODO | Others | Breakdown | ADEREMI | FILTRATION PUMP 1 | WTP | 2024-10-11 | 1 | 2024-10-12 | 1 | 2024-10-12 | 0 | 2024-10-12 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 |  | Completed | 2024-10-12 | 1
477 | PX IDIMU DEAD INSECUTOR BULB | LAG, IDIMU | Electrical Surge | Breakdown | FRIDAY | OTHERS | OTHERS | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 19350 | Completed | 2024-10-06 | 1
478 | FAULTY SOAP DISPENSER | LAG, IRE-AKARI | Users Misuse | Breakdown | PROEQUIP | OTHERS | OTHERS | 2024-10-06 | 165 | 2024-10-06 | 0 |  | 165 | [9 empty] | Overdue
479 | FAULTY SOAP DISPENSER | LAG, ILUPEJU | Users Misuse | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-10-11 | 5 | 2024-10-12 | 1 | 2024-10-16 | 4 | 2024-10-16 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-10-16 | 38750 | Completed | 2024-10-16 | 1
480 | FAULTY KITCHEN BULB IN THE STORE | LAG, IPAJA RD | Electrical Surge | Breakdown | TAYO | OTHERS | OTHERS | 2024-10-05 | 1 | 2024-10-06 | 1 | 2024-10-06 | 0 | 2024-10-06 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 0 | 2024-10-06 | 23650 | Completed | 2024-10-06 | 1
481 | Electrical materials | IBADAN, AKOBO | Others | Breakdown | RANEX | OTHERS | OTHERS | 2024-10-07 | 1 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 1 | 2024-10-08 | 115025 | Completed | 2024-10-08 | 1
482 | LOBBY AC NOT COOLING |  | Routine Servicing | Preventive | TONAOGUNS | OTHERS | OTHERS | 2024-10-07 | 164 | 2024-10-07 | 0 |  | 164 | [9 empty] | Overdue
483 | LOBBY AC NOT COOLING DRIPPING OUT WATER | LAG, ABULE EGBA | Routine Servicing | Preventive | G.B BOYEJO | OTHERS | OTHERS | 2024-10-29 | 8 | 2024-10-29 | 0 | 2024-11-06 | 8 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 185000 | Completed | 2024-11-06 | 1
484 | CRACKED WALLS AND FENCE | BAYELSA, OPOLO | Wear & Tear | Breakdown | DEACONESS | WALL | BUILDING | 2024-10-06 | 165 | 2024-10-06 | 0 | 2024-10-08 | 2 | [9 empty] | Overdue
485 | FREEZER ROOM AND COLD ROOM NOT ATTAINING TEMPERATURE | LAG, AKOWONJO | Routine Servicing | Preventive | TONAOGUNS | OTHERS | OTHERS | 2024-10-21 | 150 | 2024-10-21 | 0 | 2024-10-21 | 0 | [9 empty] | Overdue
486 | COLD ROOM NOT ATTAINING TEMPERATURE | PPU Oniru | Routine Servicing | Preventive | TONAOGUNS | COLD ROOM UNIT | HVAC | 2024-10-21 | 1 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-21 | 1 | 2024-10-22 | 0 | 2024-10-22 | 193,000.00 | Completed | 2024-10-22 | 1
487 | FREEZER ROOM & COLD ROOM NOT ATTAINING TEMPERATURE | LAG, DIYA STREET | Routine Servicing | Preventive | THIO&PARTNERS | OTHERS | OTHERS | [6 empty] | 2024-10-09 |  | 162
488 | DISFIGURED CASHIER CABINET AT FOH | LAG, OGUDU | Wear & Tear | Breakdown | MATOLAD | CASHIER COUNTER | BUILDING | 2024-10-05 | 18 | 2024-10-06 | 1 | 2024-10-09 | 3 | 2024-10-09 | 2024-10-09 | 2 | 2024-10-09 | 5 | 2024-10-14 | 9 | 2024-10-23 | 250000 | Completed | 2024-10-23 | 1
489 | DEAD BULBS AND INSECTROCUTOR BULBS | LAG, DIYA STREET | Others | Breakdown | KOLA | OTHERS | OTHERS | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 2024-10-07 | #REF! | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 |  | Completed | 2024-10-07 | 1
490 | CUSTOMER RESTROOM AC NOT WORKING | LAG, MARINA | Routine Servicing | Preventive | FOLLTEC | 5HP STANDING AC UNIT 4 | HVAC | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 |  | Completed | 2024-10-09 | 1
491 | BROKEN TILES IN THE STORE | LAG, AJAH | Wear & Tear | Breakdown | VENYS | OTHERS | OTHERS | 2024-10-10 | 161 | 2024-10-10 | 0 |  | 161 | [9 empty] | Overdue
492 | PX IDIMU PEELING WALL | LAG, IDIMU | Wear & Tear | Breakdown | SULAIMON | WALL | BUILDING | 2024-10-06 | 13 | 2024-10-06 | 0 | 2024-10-19 | 13 | 2024-10-19 | 2024-10-19 | 0 | 2024-10-19 | 0 | 2024-10-19 | 0 | 2024-10-19 | 750000 | Completed | 2024-10-19 | 1
493 | BURNT WIRE AT COOK SECTION (WARMER) | LAG, ALIMOSHO | Wear & Tear | Breakdown | FRIDAY | UPRIGHT WARMER MACHINE | HVAC | 2024-10-08 | 163 | 2024-10-09 | 1 |  | 162 | [9 empty] | Overdue
494 | REQUEST FOR DRAINAGE COVER AT THE CAR PARK. | LAG, LEKKI PHASE 1 | Corrective Action | Corrective | BAMOCON | OTHERS | OTHERS | 2024-03-20 | 365 | 2024-10-04 | 198 | 2024-10-09 | 5 | 2024-10-14 | 2024-10-15 | 1 | 2024-10-15 | 156 |  |  |  |  | Overdue
495 | INSTALLATION OF SANITIZER DISPENSER | LAG, MMA2 | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-10-07 | 8 | 2024-10-07 | 0 | 2024-10-15 | 8 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 118000 | Completed | 2024-10-15 | 1
496 | CHANGE OF DIESEL TANK READING PIPE | LAG, ABULE EGBA | Corrective Action | Corrective | DAMIFORTE | OTHERS | OTHERS | 2024-10-06 | 165 | 2024-11-06 | 31 |  | 134 | [9 empty] | Overdue
497 | REQUEST FOR LID GASKET | IBADAN, BODIJA | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 202525 | Completed | 2024-10-05 | 1
498 | MISSING BASE COVER OF STAYCOLD UNDER BAR CHILLER | LAG, OGUDU | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-10-05 | 166 | 2024-10-06 | 1 | 2024-10-10 | 4 | [9 empty] | Overdue
499 | REQUEST FOR TISSUE HANGER AND HAND SANITIZER DISPENSER | LAG, OGUDU | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-10-05 | 166 | 2024-10-06 | 1 | 2024-10-09 | 3 | [9 empty] | Overdue
500 | Faulty Hand wash sink tap | LAG, ILUPEJU | Users Misuse | Breakdown | PROPEARJEFF | KITCHEN WASH HAND SINK | PLUMBING | 2024-10-05 | 11 | 2024-10-06 | 1 | 2024-10-16 | 10 | 2024-10-16 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-10-16 |  | Completed | 2024-10-16 | 1 | cost added to number 479
501 | URGENT; PARTIAL LIGHTING OUTAGE AFFECTING STORE EQUIPMENTS. | IMO, IKENEGBU, OWERRI | Electrical Surge | Breakdown | LEONARD | OTHERS | OTHERS | 2024-10-06 | 165 | 2024-10-06 | 0 | 2024-10-06 | 0 | [9 empty] | Overdue
502 | GV | LAG, OPEBI | Others | Breakdown | PENTICOSTAL | OTHERS | OTHERS | 2024-10-07 | 164 | 2024-10-08 | 1 | 2024-10-15 | 7 | 2024-10-15 |  | 156 | [6 empty] | Overdue
503 | Cabinet bulb not working |  | Others | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-28 | 143 | 2024-10-28 | 0 |  | 143 | [9 empty] | Overdue
504 | WOBBLING LOBBY TABLE | LAG, MOBIL OGBA | Wear & Tear | Breakdown | MATOLAD | CUSTOMER TABLE | FURNITURE | 2024-10-08 | 163 | 2024-10-09 | 1 |  | 162 | [9 empty] | Overdue
505 | Replacement of chemical cupboard and repairs to fascia board and ceiling | LAG, ABULE EGBA | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-10-09 | 1 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 1 | 2024-10-10 | 450000 | Completed | 2024-10-10 | 1
506 | Drop light not working |  | Others | Breakdown | MOSES | DROPPING LIGHT | ELECTRICAL | 2024-10-09 | 162 | 2024-10-09 | 0 |  | 162 | [9 empty] | Overdue
507 | Broken body of the kiosk |  | Wear & Tear | Breakdown | ADEWALE | OTHERS | OTHERS | 2024-10-09 | 162 | 2024-10-09 | 0 | 2024-10-09 | 0 | [9 empty] | Overdue
508 | FLUSHER REPLACEMENT | IBADAN, MOKOLA | Users Misuse | Breakdown | PROEQUIP | OTHERS | OTHERS | 2024-10-09 | 162 | 2024-10-09 | 0 |  | 162 | [9 empty] | Overdue
509 | LEAKING AC PIPE THAT CAUSE DAMAGED CEILING IN DRYSTORE | LAG, MOBIL OGBA | Corrective Action | Corrective | HAMMEDS | SPLIT UNIT DRY STORE | HVAC | 2024-10-09 | 162 | 2024-10-09 | 0 | 2024-10-09 | 0 | [9 empty] | Overdue
510 | FAULTY INSECTOCUTOR BULB. | LAG, AWOLOWO 2 | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 |  | Completed | 2024-10-24 | 1
511 | FAULTY INSECTOCUTOR BULB | LAG, BODE THOMAS | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-10-09 | 2 | 2024-10-09 | 0 | 2024-10-11 | 2 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 |  | Completed | 2024-10-11 | 1
512 | REPLACEMENT OF COLD ROOM CURTAIN | LAG, AWOLOWO | Wear & Tear | Breakdown | TONAOGUNS | COLD ROOM UNIT | HVAC | 2024-10-09 | 5 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 1 | 2024-10-10 | 4 | 2024-10-14 | 111500 | Completed | 2024-10-14 | 1
513 | DISPLAY CABINET AND CHIPS CHEST FREEZER NOT ATTAINING TEMPERATURE | LAG, DOMINO E-CENTRE | Others | Breakdown | G.B BOYEJO | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-19 | 152 | 2024-10-20 | 1 |  | 151 | [9 empty] | Overdue
514 | FAULTY AUTOMATIC HAND WASH SINK AT BOH AND LOBBY DOWN STAIRS | LAG, BADORE | Wear & Tear | Breakdown | PROEQUIP | OTHERS | OTHERS | 2024-10-16 | 29 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-11-14 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 107000 | Completed | 2024-11-14 | 1
515 | FAULTY WATER HEATER | LAG, OPEBI | Electrical Surge | Breakdown | PROPEARJEFF | WATER HEATER | PLUMBING | 2024-10-17 | 14 | 2024-10-17 | 0 | 2024-10-31 | 14 | 2024-10-31 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 |  | Completed | 2024-10-31 | 1
516 | FAULTY WATER HEATER | LAG, OKE-AFA | Others | Breakdown | PROPEARJEFF | WATER HEATER | PLUMBING | 2024-10-21 | 10 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-31 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 |  | Completed | 2024-10-31 | 1
517 | FAULTY WATER HEATER | LAG, OMOLE | Others | Breakdown | ADEREMI | WATER HEATER | PLUMBING | 2024-10-21 | 1 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-22 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 |  | Completed | 2024-10-22 | 1
518 | FREEZER ROOM AND COLD ROOM LEAKAGE CAUSING OFFENSIVE ODOUR IN THE RESTAURANT | LAG, OMOLE | Others | Breakdown | TONAOGUNS | OTHERS | OTHERS | 2024-10-16 | 28 | 2024-10-17 | 1 | 2024-11-17 | 31 | [7 empty] | 2024-11-13 |  | Completed | 2024-11-13 | 1
519 | BROKEN WALL TILES IN THE DTORE | LAG, OGUDU | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-10-23 | 148 | 2024-10-23 | 0 | 2024-10-23 | 0 | 2024-10-27 | 2024-11-03 | 7 | 2024-11-04 | 136 |  |  |  | 200000 | Overdue
520 | OPEN CEILING IN THE LOBBY | LAG, HEYDEN IPAJA | Wear & Tear | Breakdown | ACORN | CEILING BOARD | BUILDING | 2024-09-29 | 11 | 2024-09-29 | 0 | 2024-10-09 | 10 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 1 | 2024-10-10 | 334400 | Completed | 2024-10-10 | 1
521 | FAULTY CHIPS AND PRESSURE FRYERS | ABIA, AZIKIWE RD, UMUAHIA | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-10-09 | 1 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-11 | 49450 | Completed | 2024-10-10 | 1
522 | PLUMBING ISSUES |  | Others | Breakdown | OLUWATOSIN | OTHERS | OTHERS | 2024-10-09 | 6 | 2024-10-09 | 0 | 2024-10-10 | 1 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 |  | Completed | 2024-10-15 | 1
523 | OPEN CEILING ONTOP OF EXTRACTOR | OGUN, HEYDEN IBAFO | Wear & Tear | Breakdown | ARIZMAYAN | CEILING BOARD | BUILDING | 2024-10-08 | 57 | 2024-10-08 | 0 | 2024-10-17 | 9 | 2024-10-17 | 2024-10-17 | 0 | 2024-11-22 | 5 | 2024-11-27 | 7 | 2024-12-04 | 121875 | Completed | 2024-12-04 | 1
524 | LEAKAGE IN THE DRYSTORE ROOFINGS | LAG, AKOWONJO | Wear & Tear | Breakdown | MATOLAD | ROOF | BUILDING | 2024-10-07 | 164 | 2024-10-07 | 0 |  | 164 | [9 empty] | Overdue
525 | DEAD BULBS IN THE LOBBY | LAG, MMA2 | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 |  | Completed | 2024-10-11 | 1
526 | REPLACEMENT OF DRAINAGE COVERS | LAG, AWOLOWO | Corrective Action | Corrective | MODEL INL | DRAIN COVER | BUILDING | 2024-10-09 | 162 | 2024-10-09 | 0 | 2024-10-10 | 1 | 2024-10-09 | 2024-10-18 | 9 | 2024-10-18 | 12 | 2024-10-30 | 141 | 2024-10-30 | 300000 | Overdue
527 | FAULTY CABINET REGULATOR | LAG, AJAH | Electrical Surge | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-10 | 161 | 2024-10-10 | 0 |  | 161 | [8 empty] | 24187.5 | Overdue
528 | CABINET REGULATOR | LAG, DIYA STREET | Electrical Surge | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-09 | 162 | 2024-10-09 | 0 |  | 162 | [9 empty] | Overdue
529 | LED LIGHTS NOT WORKING | LAG, BODE THOMAS | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-10-09 | 2 | 2024-10-09 | 0 | 2024-10-11 | 2 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 |  | Completed | 2024-10-11 | 1
530 | SERVICING OF OFFICE AC AND DRY STORE AC | LAG, MMA2 | Routine Servicing | Preventive | G.B BOYEJO | OTHERS | OTHERS | 2024-10-07 | 2 | 2024-10-07 | 0 | 2024-10-09 | 2 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 181000 | Completed | 2024-10-09 | 1
531 | ROLLER SHUTTER NOT WORKING | LAG, OGUNLANA DRIVE | Users Misuse | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-09 | 162 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 2024-10-10 | 1 | 2024-11-01 | 139 |  |  |  | 87827.5 | Overdue
532 | DAMAGED MIRROR FRAME AT THE LOBBY | LAG, EKORO | Users Misuse | Breakdown | MATOLAD | LOBBY WALL MIRROR | OTHERS | 2024-10-10 | 161 | 2024-10-10 | 0 | 2024-10-22 | 12 | [9 empty] | Overdue
533 | FAULTY HOT WATER PIPE | LAG, OPEBI | Corrective Action | Corrective | ADEREMI | WATER HEATER | PLUMBING | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 |  | Completed | 2024-10-11 | 1
534 | LEAKING AERATION TANK | ABIA, ADAZI RD | Wear & Tear | Breakdown | ADMIN | AERATION TANK | WTP | 2024-10-22 | 149 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-23 | 2024-10-23 | 0 | 2024-10-23 | 148 |  |  |  | 2200000 | Overdue
535 | Leaking aeration tank | ABIA, ABA-OWERRI RD | Wear & Tear | Breakdown | PROEQUIP | AERATION TANK | WTP | 2024-10-10 | 161 | 2024-10-10 | 0 | 2024-10-11 | 1 | [9 empty] | Overdue
536 | FAULTY SHREDDING BLADE- CR OKIGWE | IMO, OKIGWE | Wear & Tear | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-10-08 | 9 | 2024-10-09 | 1 | 2024-10-09 | 0 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 8 | 2024-10-17 | 299925 | Completed | 2024-10-17 | 1
537 | OPENED DRAINAGE IRON COVER | LAG, OPEBI | Wear & Tear | Breakdown | MODEL INT | DRAIN COVER | BUILDING | 2024-10-07 | 29 | 2024-10-09 | 2 | 2024-10-09 | 0 | 2024-10-09 | 2024-10-15 | 6 | 2024-10-17 | 14 | 2024-10-31 | 5 | 2024-11-05 | 200000 | Completed | 2024-11-05 | 1
538 | LOBBY BULBS,INSECTICUTOR BULB AND KITCHEN BULBS CRITICALLY BAD | LAG, IKEJA MALL | Others | Breakdown | TAYO | OTHERS | OTHERS | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 |  | Completed | 2024-10-08 | 1
539 | FAULTY ROLLER SHUTTER/ REMOTE | LAG, OKOTA | Others | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-18 | 9 | 2024-10-19 | 1 | 2024-10-21 | 2 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-23 | 3 | 2024-10-26 | 1 | 2024-10-27 | 247465 | Completed | 2024-10-27 | 1
540 | FAULTY ROLLER SHUTTER | LAG, ILUPEJU | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-14 | 21 | 2024-10-14 | 0 | 2024-10-15 | 1 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 1 | 2024-11-02 | 2 | 2024-11-04 | 245100 | Completed | 2024-11-04 | 1
541 | FAULTY ROLLER SHUTTER | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-09 | 23 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 139 |  |  | 2024-11-01 | 247465 | Completed | 2024-11-01 | 1
542 | FAULTY ROLLER SHUTTER | LAG, GBAGADA | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-31 | 6 | 2024-10-31 | 0 | 2024-11-01 | 1 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 4 | 2024-11-05 | 1 | 2024-11-06 | 87827.5 | Completed | 2024-11-06 | 1
543 | FAULTY ROLLER SHUTTER | LAG, ONIRU | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-24 | 147 | 2024-10-24 | 0 | 2024-10-25 | 1 | 2024-10-30 | 2024-10-30 | 0 | 2024-10-30 | 141 |  |  |  | 80302.5 | Overdue
544 | FAULTY ROLLER SHUTTER | LAG, JIBOWU | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-30 | 9 | 2024-10-30 | 0 | 2024-10-30 | 0 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 1 | 2024-11-05 | 3 | 2024-11-08 | 87827.5 | Completed | 2024-11-08 | 1
545 | BROKEN DRAIN COVER FOR FREEZER ROOM | LAG, AJOSE ADEOGUN | Users Misuse | Breakdown | TONAOGUNS | FREEZER ROOM | HVAC | 2024-10-04 | 6 | 2024-10-04 | 0 | 2024-10-10 | 6 | 2024-10-10 |  | 161 |  |  |  |  | 2024-10-10 |  | Completed | 2024-10-10 | 1
546 | FREEZER ROOM DOOR FAULTY | PH, WOJI | Others | Breakdown | SEADOLF | FREEZER ROOM | HVAC | 2024-10-07 | 164 | 2024-10-09 | 2 | 2024-10-09 | 0 | [8 empty] | 61662.5 | Overdue
547 | COVER OF FAT TRAP STOLEN | LAG, AWOLOWO 2 | Users Misuse | Breakdown | MODEL INT | OTHERS | OTHERS | 2024-10-09 | 17 | 2024-10-09 | 0 | 2024-10-17 | 8 | 2024-10-17 | 2024-10-17 | 0 | 2024-10-17 | 0 | 2024-10-17 | 9 | 2024-10-26 | 180000 | Completed | 2024-10-26 | 1
548 | REQUEST FOR LED BULB LIGHTS | OSUN, GBONGAN | Electrical Surge | Breakdown | RANEX | OTHERS | OTHERS | 2024-10-08 | 1 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 43000 | Completed | 2024-10-09 | 1
549 | UNSAFE CONDITION AT THE BACK OF HOUSE AJAH | LAG, AJAH | Others | Breakdown | TONAOGUNS | OTHERS | OTHERS | 2024-10-03 | 7 | 2024-10-04 | 1 | 2024-10-10 | 6 | 2024-10-10 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 66500 | Completed | 2024-10-10 | 1
550 | CR ABA-OWERRI ROAD BOH EXTRACTOR NOT FUNCTIONING | PH, ABA | Others | Breakdown | SEASONED | OTHERS | OTHERS | 2024-10-09 | 7 | 2024-10-09 | 0 | 2024-10-10 | 1 | [7 empty] | 2024-10-16 |  | Completed | 2024-10-16 | 1
551 | FAULTY INVERTER | IBADAN, IDI-APE (IWO RD) | Others | Breakdown | NISTECHLTD | INVERTER DB | ELECTRICAL | 2024-10-16 | 3 | 2024-10-17 | 1 | 2024-10-19 | 2 | 2024-10-28 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | -9 | 2024-10-19 | 129000 | Completed | 2024-10-19 | 1
552 | REPLACEMENT OF TAYLOR MACHINE COVER | LAG, TEJUOSHO | Others | Breakdown | KITCHTECH | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-10-10 | 11 | 2024-10-10 | 0 | 2024-10-11 | 1 | 2024-10-13 | 2024-10-14 | 1 | 2024-10-14 | 0 | 2024-10-14 | 7 | 2024-10-21 | 137868.75 | Completed | 2024-10-21 | 1
553 | FAULTY RATIONAL WATER OUTLET | LAG, JIBOWU | Wear & Tear | Breakdown | BCE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2024-10-31 | 1 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 1 | 2024-11-01 | 174150 | Completed | 2024-11-01 | 1
554 | FAULTY TILTINGPAN AND RATIONAL OVEN | PH, GRA BIRABI | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-10-31 | 11 | 2024-10-31 | 0 | 2024-11-08 | 8 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 3 | 2024-11-11 | 0 | 2024-11-11 | 231125 | Completed | 2024-11-11 | 1
555 | FAULTY TILTINGPAN AND RATIONAL OVEN | PH, GRA BIRABI | Others | Breakdown | BCE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2024-10-31 | 140 | 2024-10-31 | 0 | 2024-11-11 | 11 | [9 empty] | Overdue
556 | PAINTING OF RUSTY COLD ROOM WALL AND CEILING | LAG, FREEDOMWAY | Wear & Tear | Breakdown | TONAOGUNS | PAINTING | BUILDING | 2024-10-09 | 5 | 2024-10-09 | 0 | 2024-10-10 | 1 | 2024-10-10 | 2024-10-13 | 3 | 2024-11-14 | 126 |  |  | 2024-11-14 | 180000 | Completed | 2024-10-14 | 1
557 | FAULTY INVERTER | LAG, NNPC ALAPERE | Others | Breakdown | DALEMATRIX | INVERTER BATTERIES | INVERTER | 2024-10-06 | 10 | 2024-10-06 | 0 | 2024-10-09 | 3 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 2 | 2024-10-11 | 5 | 2024-10-16 | 1367125 | Completed | 2024-10-16 | 1
558 | COLD ROOM AND FREEZER ROOM NOT ATTAINING TEMPERATURE | PPU Kaduna | Others | Breakdown | ECS | OTHERS | OTHERS | 2024-10-17 | 154 | 2024-10-17 | 0 | 2024-11-22 | 36 | [9 empty] | Overdue
559 | FUALTY CABINET BULB | LAG, JIBOWU | Wear & Tear | Breakdown | KITCHTECH | OTHERS | OTHERS | 2024-10-09 | 1 | 2024-10-09 | 0 | 2024-10-17 | 8 | [7 empty] | 2024-10-10 |  | Completed | 2024-10-10 | 1
560 | FREEZE ROOM NOT WORKING | LAG, IKEJA MALL | Routine Servicing | Preventive | TONAOGUNS | FREEZER ROOM | HVAC | 2024-10-08 | 6 | 2024-10-08 | 0 | 2024-10-09 | 1 | 2024-10-09 | 2024-10-13 | 4 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 530000 | Completed | 2024-10-14 | 1
561 | CHEST FREEZER NOT ATTAINING TEMPERATURE | LAG, MMA2 | Routine Servicing | Preventive | TAYO |  |  | 2024-10-09 | 162 | 2024-10-09 | 0 |  | 162 | [9 empty] | Overdue
562 | THE FREEZER AND THE COLD ROOM NOT WORKING | IBADAN, CHALLENGE | Routine Servicing | Preventive | TONAOGUNS | OTHERS | OTHERS | 2024-10-04 | 5 | 2024-10-04 | 0 | 2024-10-08 | 4 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 390000 | Completed | 2024-10-09 | 1
563 | HENNY PENNY ROTESSEIRE MACHINE SAYING CENSOR FAILED | IBADAN, RING-ROAD | Routine Servicing | Preventive | KITCHTECH | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-10-05 | 166 | 2024-10-05 | 0 |  | 166 | [9 empty] | Overdue
564 | FAULTY FREEZER ROOM AND COLD ROOM | LAG, OGUNLANA DRIVE | Routine Servicing | Preventive | TRIPPLEO | OTHERS | OTHERS | 2024-10-31 | 140 | 2024-11-05 | 5 | 2024-11-05 | 0 | 2024-11-06 |  | 134 | [5 empty] | 290250 | Overdue
565 | FAULTY FREEZER ROOM | BAYELSA, YENAGOA | Others | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-10-28 | 8 | 2024-10-28 | 0 | 2024-11-04 | 7 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 1 | 2024-11-05 | 0 | 2024-11-05 | 483000 | Completed | 2024-11-05 | 1
566 | FAULTY RATIONAL | LAG, ILUPEJU | Wear & Tear | Breakdown | BCE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2024-10-10 | 2 | 2024-10-10 | 0 | 2024-10-10 | 0 | [7 empty] | 2024-10-12 |  | Completed | 2024-10-12 | 1
567 | FAULTY INSECT ELECTROCUTORS | LAG, OMOLE | Others | Breakdown | TIMILEHIN | INSECT KILLER BOH | ELECTRICAL | 2024-10-10 | 36 | 2024-10-10 | 0 | 2024-11-15 | 36 | 2024-11-15 | 2024-11-15 | 0 | 2024-11-15 | 0 | 2024-11-15 | 0 | 2024-11-15 | 30100 | Completed | 2024-11-15 | 1
568 | Plumbing and tiling at CR Challenge Ibadan | IBADAN, CHALLENGE | Wear & Tear | Breakdown | ACORN | OTHERS | OTHERS | 2024-10-13 | 5 | 2024-10-13 | 0 | 2024-10-13 | 0 | 2024-10-13 | 2024-10-13 | 0 | 2024-10-14 | 4 | 2024-10-18 | 0 | 2024-10-18 | 567300 | Completed | 2024-10-18 | 1
569 | REQUEST OF FLOOD LIGHT | IBADAN, OJOO | Users Misuse | Breakdown | RANEX | FLOODLIGHT | ELECTRICAL | 2024-10-11 | 21 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 18 | 2024-10-29 | 3 | 2024-11-01 | 161250 | Completed | 2024-11-01 | 1
570 | AULTY DOOR OF MALE AND FEMALE CLOAKROOM. |  | Wear & Tear | Breakdown | ACORN | OTHERS | OTHERS | 2024-10-11 | 160 | 2024-10-11 | 0 | 2024-10-13 | 2 | 2024-10-20 | 2024-10-20 | 0 | 2024-10-20 | 151 |  |  | 2024-10-20 | 48900 | Overdue
571 | FAULTY FRYER MACHINE SWITCH | LAG, DIYA STREET | Users Misuse | Breakdown | KOLA | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-10 | 1 | 2024-10-10 | 0 | 2024-10-11 | 1 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 |  | Completed | 2024-10-11 | 1
572 | PEELED OFFICE WALLS | LAG, OGUDU | Wear & Tear | Breakdown | ARIZMAYAN | PAINTING | BUILDING | 2024-10-10 | 15 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-13 | 2024-10-15 | 2 | 2024-10-15 | 1 | 2024-10-16 | 9 | 2024-10-25 | 81750 | Completed | 2024-10-25 | 1
573 | Faulty Contactor and Control Panel Switch | LAG, JOEL OGUNNAIKE | Others | Breakdown | ACORN | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-11 | 160 | 2024-10-12 | 1 |  | 159 | [8 empty] | 86875 | Overdue
574 | SEPTIC TANK EVACUATION | LAG, LATEEF JAKANDE | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-10-24 | 3 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 3 | 2024-10-27 | 281500 | Completed | 2024-10-27 | 1
575 | FAULTY G&P | LAG, AJOSE ADEOGUN | Electrical Surge | Breakdown | GBATMO | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-10-21 | 7 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 2024-11-21 | 31 | 2024-10-21 | 0 | 2024-10-21 | 7 | 2024-10-28 | 101000 | Completed | 2024-10-28 | 1
576 | G & P | LAG, VGC | Electrical Surge | Breakdown | GBATMO | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-10-10 | 6 | 2024-10-10 | 0 | 2024-10-12 | 2 | 2024-10-12 | 2024-10-12 | 0 | 2024-10-16 | 0 | 2024-10-16 | 0 | 2024-10-16 | 125000 | Completed | 2024-10-16 | 1
577 | GENERATOR DUE FOR SERVICING | PPU Tombia | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-10-15 | 9 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 9 | 2024-10-24 | 202000 | Completed | 2024-10-24 | 1
578 | faulty hand dryer | LAG, ILUPEJU | Wear & Tear | Breakdown | KOLA | HAND DRYER LOBBY | ELECTRICAL | 2024-10-09 | 1 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 2024-10-09 | 0 | 2024-10-09 | 0 | 2024-10-09 | 1 | 2024-10-10 | 64500 | Completed | 2024-10-10 | 1
579 | BROKEN CABINET BULB GLASS | LAG, WAREHOUSE RD, APAPA | Users Misuse | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-06 | 5 | 2024-10-06 | 0 | 2024-10-11 | 5 | 2024-10-11 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 66000 | Completed | 2024-10-11 | 1
580 | REPLACEMENT OF ENTRANCE DOOR GUIDE | LAG, OKOTA | Users Misuse | Breakdown | TAIDAV | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 21000 | Completed | 2024-10-02 | 1
581 | BROKEN ENTRANCE DOOR | LAG, OSOLOWAY | Users Misuse | Breakdown | TAIDAV | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 0 | 2024-10-02 | 18000 | Completed | 2024-10-02 | 1
582 | BCE EQUIPMENT DUE FOR SERVICE | LAG, DIYA STREET | Routine Servicing | Preventive | BCE | UPRIGHT WARMER MACHINE | HVAC | 2024-10-07 | 2 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 2024-10-07 | 0 | 2024-10-07 | 0 | 2024-10-07 | 2 | 2024-10-09 | 270900 | Completed | 2024-10-09 | 1
583 | FAULTY COLLECTRAMATIC MACHINE | LAG, OGUDU | Wear & Tear | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-11 | 5 | 2024-10-11 | 0 | 2024-10-13 | 2 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-14 | 1 | 2024-10-15 | 1 | 2024-10-16 | 1421150 | Completed | 2024-10-16 | 1
584 | ROTISSERIE MACHINE NOT ATTAINING TEMPERATURE | PH, RUKPOKWU | Wear & Tear | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-10-11 | 3 | 2024-10-11 | 0 | 2024-10-14 | 3 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 23650 | Completed | 2024-10-14 | 1
585 | BAD WARMER GASKET AND UNDERBAR CHILLER GASKET | PH, ABA | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2024-10-04 | 4 | 2024-10-04 | 0 | 2024-10-08 | 4 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 115025 | Completed | 2024-10-08 | 1
586 | REQUEST FOR CRUMBS COLLECTOR LID GASKET | ILORIN, MM WAY | Wear & Tear | Breakdown | BCE | CHIPS DUMP | KITCHEN_EQUIPMENT | 2024-10-05 | 3 | 2024-10-06 | 1 | 2024-10-08 | 2 | 2024-10-08 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 0 | 2024-10-08 | 116100 | Completed | 2024-10-08 | 1
587 | GAS LEAKAGE. | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-10-04 | 29 | 2024-10-04 | 0 | 2024-10-04 | 0 | 2024-10-04 | 2024-10-04 | 0 | 2024-10-04 | 26 | 2024-10-30 | 3 | 2024-11-02 | 158750 | Completed | 2024-11-02 | 1
588 | BROKEN WALL TILES AND SEALING OF SOCKET TO WALL | LAG, ILUPEJU | Others | Breakdown | ACORN | WALL | BUILDING | 2024-10-28 | 143 | 2024-10-28 | 0 | 2024-11-15 | 18 | 2024-10-16 | 2024-10-16 | 0 | 2024-10-16 | 114 | 2025-02-07 | 41 |  | 85125 | Overdue
589 | PPU GENERATOR BREAKDOWN | AKWA IBOM, ORON RD | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-10-27 | 15 | 2024-10-27 | 0 | 2024-10-27 | 0 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-08 | 0 | 2024-11-08 | 3 | 2024-11-11 | 474700 | Completed | 2024-11-11 | 1
590 | FAULTY HAND DRYER AND WARMER HANDLE | PH, IWOFE | Users Misuse | Breakdown | BCE | OTHERS | OTHERS | 2024-10-23 | 12 | 2024-11-04 | 12 | 2024-11-04 | 0 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 118250 | Completed | 2024-11-04 | 1
591 | BREAKDOWN OF PH WAREHOUSE GENERATOR |  | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-10-25 | 14 | 2024-10-25 | 0 | 2024-11-08 | 14 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 258350 | Completed | 2024-11-08 | 1
592 | LEAKINNG CEILING AT THE KITCHEN | LAG, LATEEF JAKANDE | Wear & Tear | Breakdown | ARIZMAYAN | CEILING BOARD | BUILDING | 2024-10-28 | 20 | 2024-10-28 | 0 | 2024-11-03 | 6 | 2024-11-03 | 2024-11-03 | 0 | 2024-11-03 | 3 | 2024-11-06 | 11 | 2024-11-17 | 130000 | Completed | 2024-11-17 | 1
593 | REQUEST FOR CAUTION SIGNAL FOR TRANSFORMER | LAG, LATEEF JAKANDE | Others | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-10-24 | 18 | 2024-10-24 | 0 | 2024-10-27 | 3 | 2024-10-27 | 2024-10-27 | 0 | 2024-10-28 | 6 | 2024-11-03 | 8 | 2024-11-11 | 650000 | Completed | 2024-11-11 | 1
594 | REQUEST FOR CAUTION SIGNAL FOR TRANSFORMER | LAG, LATEEF JAKANDE | Others | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-10-24 | 18 | 2024-10-24 | 0 | 2024-10-27 | 3 | 2024-10-27 | 2024-10-27 | 0 | 2024-10-28 | 6 | 2024-11-03 | 8 | 2024-11-11 | 40000 | Completed | 2024-11-11 | 1
595 | UNDERBAR CHILLER NOT ATTAINING TEMPERATURE | EDO, AIRPORT RD, BENIN | Routine Servicing | Preventive | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-10-27 | 5 | 2024-10-28 | 1 | 2024-11-01 | 4 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 34400 | Completed | 2024-11-01 | 1
596 | FAULTY CABINET | IMO, WETHERAL RD, OWERRI | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-23 | 9 | 2024-10-23 | 0 | 2024-11-01 | 9 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 290250 | Completed | 2024-11-01 | 1
597 | FAULTY FREEZER ROOM LOCK/TEMPERATURE CLOCK | EBONYI, WATERWORKS, ABAKALIKI | Routine Servicing | Preventive | BCE | FREEZER ROOM | HVAC | 2024-10-29 | 8 | 2024-10-29 | 0 | 2024-11-06 | 8 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 122550 | Completed | 2024-11-06 | 1
598 | BROKEN UNDERBAR UPRIGHT CHILLER BULB AND NOT ATTAINING TEMPERATURE WITH DEGRADED INTERIOR - CR IKOT EKPENE | AKWA IBOM, IKOT EKPENE RD | Corrective Action | Corrective | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-10-21 | 11 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 2024-10-21 | 0 | 2024-10-21 | 0 | 2024-10-21 | 11 | 2024-11-01 | 354750 | Completed | 2024-11-01 | 1
599 | BOH CHILLER NOT ATTAINING TEMPERATURE | CALABAR, NDIDEM | Routine Servicing | Preventive | BCE | NBC CHILLER | HVAC | 2024-10-16 | 16 | 2024-10-16 | 0 | 2024-11-01 | 16 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 118250 | Completed | 2024-11-01 | 1
600 | CABINET NOT ATTAINING TO TEMPERATURE | EBONYI, WATERWORKS, ABAKALIKI | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-25 | 7 | 2024-10-25 | 0 | 2024-11-01 | 7 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 36550 | Completed | 2024-11-01 | 1
601 | FAULTY WARMER HANDLE - ENUGU, CHIME AVENUE | ENUGU, CHIME AVENUE | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-10-28 | 4 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 2024-10-28 | 0 | 2024-10-28 | 0 | 2024-10-28 | 4 | 2024-11-01 | 152650 | Completed | 2024-11-01 | 1
602 | FAULTY UNDERBAR CHILLER | EDO, SILUKO | Routine Servicing | Preventive | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-10-31 | 1 | 2024-10-31 | 0 | 2024-11-01 | 1 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 66650 | Completed | 2024-11-01 | 1
603 | MAINTENANCE ISSUES - IDU | ABUJA, IDU | Others | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-31 | 1 | 2024-10-31 | 0 | 2024-11-01 | 1 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 161250 | Completed | 2024-11-01 | 1
604 | FAULTY SHREDDING MACHINE | SOKOTO, BANK RD | Wear & Tear | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-10-23 | 9 | 2024-10-23 | 0 | 2024-11-01 | 9 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 806250 | Completed | 2024-11-01 | 1
605 | REQUEST FOR THE SUPPLY OF GASKET | KANO, MM WAY | Others | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-23 | 9 | 2024-10-23 | 0 | 2024-11-01 | 9 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 311750 | Completed | 2024-11-01 | 1
606 | REPLACING OF DEAD WEIGHT VALVE | ABUJA, AMINU KANO | Wear & Tear | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-24 | 8 | 2024-10-24 | 0 | 2024-11-01 | 8 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 17200 | Completed | 2024-11-01 | 1
607 | CABINET NOT WORKING |  | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-25 | 17 | 2024-10-25 | 0 | 2024-11-11 | 17 | 2024-11-14 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | -3 | 2024-11-11 | 987925 | Completed | 2024-11-11 | 1
608 | BAD WARMER HANDLE | ABIA, ABA-OWERRI RD | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-10-22 | 10 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 | 2024-11-22 | 31 | 2024-10-22 | 0 | 2024-10-22 | 10 | 2024-11-01 | 178450 | Completed | 2024-11-01 | 1
609 | BACK OF HOUSE UNDERBAR CHILLER NOT ATTAINING TEMPERATURE | LAG, JOEL OGUNNAIKE | Routine Servicing | Preventive | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-10-28 | 9 | 2024-10-28 | 0 | 2024-11-06 | 9 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 698750 | Completed | 2024-11-06 | 1
610 | Unable to open shutter roller | LAG, DIYA STREET | Wear & Tear | Breakdown | VENYS | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-31 | 140 | 2024-10-31 | 0 | 2024-10-31 | 0 | 2024-10-31 | 2024-11-01 | 1 | 2024-11-01 | 0 | 2024-11-01 | 139 |  | 180000 | Overdue
611 | CHLORINE AND ALUMN NOT DOSING | LAG, MAGODO | Corrective Action | Corrective | PRO-EQUIP | DOSING PUMP | WTP | 2024-10-25 | 146 | 2024-10-25 | 0 | 2024-11-07 | 13 | 2024-11-07 | 2024-11-07 | 0 | 2024-11-07 | 26 | 2024-12-03 | 107 |  | 381500 | Overdue
612 | FAULTY SHREDDING MACHINE | PH, RUKPOKWU | Wear & Tear | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-10-24 | 10 | 2024-10-24 | 0 | 2024-11-24 | 31 | 2024-10-24 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 10 | 2024-11-03 | 192425 | Completed | 2024-11-03 | 1
613 | FAULTY DICING AND GRINDING MACHINE | Central Kitchen | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-10-15 | 31 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-24 | 0 | 2024-10-24 | 22 | 2024-11-15 | 537800 | Completed | 2024-11-15 | 1
614 | FAULTY SIX HEAD MACHINE | LAG, GBAGADA | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-10-18 | 31 | 2024-10-18 | 0 | 2024-11-18 | 31 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 64500 | Completed | 2024-11-18 | 1
615 | GASKET FOR UPRIGHT CHILLER AND WARMER | IBADAN, RING-ROAD | Routine Servicing | Preventive | BCE | OTHERS | OTHERS | 2024-10-14 | 21 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 2024-10-14 | 0 | 2024-10-14 | 0 | 2024-10-14 | 21 | 2024-11-04 | 223650 | Completed | 2024-11-04 | 1
616 | ALL EQUIPMENTS IN THE STORE NOT ATTAINING TEMPERATURE | PH, RUMUBIAKANI | Corrective Action | Corrective | BCE | OTHERS | OTHERS | 2024-10-29 | 4 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-10-29 | 4 | 2024-11-02 | 73100 | Completed | 2024-11-02 | 1
617 | REQUEST FOR COLLECTOR GASKETS | ABIA, ABA-OWERRI RD | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-10-13 | 27 | 2024-10-13 | 0 | 2024-10-16 | 3 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 1 | 2024-11-09 | 115250 | Completed | 2024-11-09 | 1
618 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | PH, WOJI | Others | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-24 | 10 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 2024-10-24 | 0 | 2024-10-24 | 0 | 2024-10-24 | 10 | 2024-11-03 | 806250 | Completed | 2024-11-03 | 1
619 | WARMER NOT ATTAINNING REQUIRED TEMPERATURE | EDO, UGBOWO, BENIN | Corrective Action | Corrective | BCE | OTHERS | OTHERS | 2024-10-23 | 9 | 2024-10-23 | 0 | 2024-11-01 | 9 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 68800 | Completed | 2024-11-01 | 1
620 | UPRIGHT CHILLER WITHOUT HANDLE | PH, UST | Users Misuse | Breakdown | BCE | NBC CHILLER | HVAC | 2024-10-15 | 19 | 2024-10-15 | 0 | 2024-11-03 | 19 | 2024-11-03 | 2024-11-03 | 0 | 2024-11-03 | 0 | 2024-11-03 | 0 | 2024-11-03 | 60200 | Completed | 2024-11-03 | 1
621 | FAULTY DISPLAY CABINET | PH, UST | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-15 | 19 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 19 | 2024-11-03 | 172000 | Completed | 2024-11-03 | 1
622 | FAULTY PRESSURE FRYER MACHINE | BAYELSA, YENAGOA | Wear & Tear | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-10-15 | 18 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 2024-10-15 | 0 | 2024-10-15 | 0 | 2024-10-15 | 18 | 2024-11-02 | 5424450 | Completed | 2024-11-02 | 1
623 | FAULTY ICE CREAM MECHINE. | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-10-23 | 148 | 2024-10-23 | 0 | 2024-10-30 | 7 | 2024-10-30 | 2024-10-30 | 0 | 2024-10-30 | 4 | 2024-11-03 | 137 | 2024-11-07 | 324474.51 | Overdue
624 | MAINTENANCE ISSUES STILL PENDING IN THE STORE 1 | LAG, ONIRU | Others | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-10-29 | 142 | 2024-10-30 | 1 | 2024-11-10 | 11 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-11 | 129 |  |  |  | 370000 | Overdue
625 | MAINTENACE ISSUES | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-10-29 | 142 | 2024-10-29 | 0 | 2024-10-29 | 0 | 2024-11-10 | 2024-11-10 | 0 | [5 empty] | 1245000 | Overdue
626 | SERVICING OF ICE-CREAM MACHINE | BAYELSA, OPOLO | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-10-22 | 20 | 2024-10-22 | 0 | 2024-10-22 | 0 | 2024-10-22 | 2024-10-22 | 0 | 2024-10-22 | 20 | 2024-11-11 | 0 | 2024-11-11 |  | Completed | 2024-11-11 | 1
627 | CRACK GLASS |  | Users Misuse | Breakdown | KITCHTEC | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-28 | 143 | 2024-10-28 | 0 | 2024-11-27 | 30 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 38 |  | 56679.37 | Overdue
628 | BOH CHILLER NOT ATTAINING TEMPERATURE | LAG, ONIRU | Wear & Tear | Breakdown | TECHNICAL | NBC CHILLER | HVAC | 2024-10-31 | 11 | 2024-10-31 | 0 | 2024-11-01 | 1 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 |  | Completed | 2024-11-11 | 1
629 | FAULTY COLD ROOM DOOR HANDLE | LAG, DIYA STREET | Wear & Tear | Breakdown | THIO & PARTNERS | COLD ROOM UNIT | HVAC | 2024-10-28 | 143 | 2024-10-28 | 0 | 2024-11-01 | 4 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 139 |  |  |  |  | Overdue
630 | FAULTY CUSTOMER RESTROOM DOOR | LAG, DIYA STREET | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-10-28 | 4 | 2024-10-28 | 0 | 2024-11-01 | 4 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 |  | Completed | 2024-11-01 | 1
631 | ROLLER SHUTTER NOT ROLLING UP | LAG, OGUNLANA DRIVE | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-10-09 | 23 | 2024-10-09 | 0 | 2024-10-10 | 1 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 87827.5 | Completed | 2024-11-01 | 1
632 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | LAG, OKOTA | Electrical Surge | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-10-25 | 12 | 2024-10-25 | 0 | 2024-11-01 | 7 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 |  | Completed | 2024-11-06 | 1
633 | FADED PYLON LIGHT AND SIGNAGE | LAG, HEYDEN IPAJA | Electrical Surge | Breakdown | ARIZMANYA | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-10-14 | 37 | 2024-10-19 | 5 | 2024-11-10 | 22 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-11 | 1 | 2024-11-12 | 8 | 2024-11-18 | 220000 | Completed | 2024-11-20 | 0
634 | LOBBY CEILING LEAKAGE | EDO, SILUKO | Wear & Tear | Breakdown | DEACONESS TAIWO | CEILING BOARD | BUILDING | 2024-10-02 | 169 | 2024-10-03 | 1 | 2024-11-13 | 41 | 2024-11-14 | 2024-11-14 | 0 | 2024-11-14 | 126 |  |  |  | 400000 | Overdue
635 | PAINTING OF TABLES,SPRAYING OF LEGS AND FIXING OF WOBBLING TABLE LEGS, | LAG, BADORE | Others | Breakdown | MATOLAD | PAINTING | BUILDING | 2024-10-14 | 157 | 2024-10-14 | 0 | 2024-11-29 | 46 | 2024-11-29 | 2024-12-05 | 6 | 2024-12-05 | 4 | 2024-12-09 | 101 | 2024-12-19 | 510000 | Overdue
636 | Urgent need for re- painting PPU Mokola | IBADAN, MOKOLA | Others | Breakdown | REVELATION | PAINTING | BUILDING | 2024-10-14 | 157 | 2024-10-14 | 0 | 2024-10-28 | 14 | 2024-12-07 | 2024-12-09 | 2 | 2024-12-09 | 0 | 2024-12-09 | 101 |  | 500000 | Overdue
637 | LOBBY AC NOT FUNCTIONING WELL | LAG, AJAH | Wear & Tear | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-11 | 160 | 2024-10-11 | 0 | 2024-11-09 | 29 | 2024-11-10 | 2024-11-14 | 4 | 2024-11-14 | 1 | 2024-11-15 | 125 |  | 446500 | Overdue
638 | REQUEST FOR TINTED NYLON ON CUSTOMER TOILET WINDOW | LAG, AJAH | Corrective Action | Corrective | TAIDAV | WINDOW | BUILDING | 2024-10-15 | 30 | 2024-10-16 | 1 | 2024-11-13 | 28 | 2024-11-13 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 1 | 2024-11-14 |  | Completed | 2024-11-14 | 1
639 | RUSTY COLDROOM INTERIOR AND DIRTY WALL IN THE DRY STORE | LAG, IKEJA MALL | Wear & Tear | Breakdown | ARIZMANYA | WALL | BUILDING | 2024-10-31 | 12 | 2024-10-31 | 0 | 2024-11-01 | 1 | 2024-11-01 | 2024-11-03 | 2 | 2024-11-04 | 1 | 2024-11-05 | 7 | 2024-11-12 | 270000 | Completed | 2024-11-12 | 1
640 | TORN WATER TREAMENT NET MESH | LAG, AKOWONJO | Wear & Tear | Breakdown | TAIDAV | WATER TREATMENT PLANT BLD | BUILDING | 2024-10-22 | 15 | 2024-10-22 | 0 | 2024-11-06 | 15 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 |  | Completed | 2024-11-06 | 1
641 | FAULTY EXTRACTOR AT BOH | LAG, BADORE | Wear & Tear | Breakdown | SEASON BENDAN | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2024-10-16 | 155 | 2024-10-17 | 1 |  | 154 | [9 empty] | Overdue
642 | SERVICING OF AC | IBADAN, CHALLENGE | Routine Servicing | Preventive | TONAOGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-10-30 | 12 | 2024-10-30 | 0 | 2024-11-11 | 12 | [7 empty] | 2024-11-11 | 73375 | Completed | 2024-11-11 | 1
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
Formulas:
Days Since Request = IF([Request Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Request Date],TODAY()-[Request Date]))
Days Delayed by Helpdesk = IF([Date Shared by Helpdesk]<>"",[Date Shared by Helpdesk]-[Request Date],IF([Request Date]="","",TODAY()-[Request Date]))
Days Delayed by Vendor/Technician = IF(M6<>"",M6-[Date Shared by Helpdesk],IF([Date Shared by Helpdesk]="","",TODAY()-[Date Shared by Helpdesk]))
Days Delayed by Vendor/Technician = IF(#REF!<>"",#REF!-[Date Shared by Helpdesk],IF([Date Shared by Helpdesk]="","",TODAY()-[Date Shared by Helpdesk]))
Days Since Negotiation Request = TODAY() - [Date Negotiated]
Days Since Negotiation Request = IF([Date Negotiated]<>"",[Date Negotiated]-[Date Sent for Negotiation],IF([Date Sent for Negotiation]="","",TODAY()-[Date Sent for Negotiation]))
Days Since Approval Request = IF([Approved Date]<>"",[Approved Date]-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval Request = IF(#REF!<>"",#REF!-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval = IF([Approved Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Approved Date],TODAY()-[Approved Date]))
Days Since Approval = IF(#REF!="","",IF([Actual delivery date]<>"",[Actual delivery date]-#REF!,TODAY()-#REF!))
Status = IF([Request Date]="","",IF([Actual delivery date]<>"","Completed",IF(TODAY()<[Expected Delivery Date],"Planned",IF(TODAY()=[Expected Delivery Date],"Due","Overdue"))))
Status = IF([Request Date]="","",IF([Actual delivery date]<>"","Completed",IF(TODAY()<[Expected Delivery Date, row below],"Planned",IF(TODAY()=[Expected Delivery Date, row below],"Due","Overdue"))))
Note on AA6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vendor gave feedback thaat part is not available on 18 of Jan
Note on C80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ppu
Note on C83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX Reply: ADEOLA ODEKU
Note on C90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: px
Note on M93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This was due to a back and forth from the store refusing to allow the vendor evacuate the septic tank
Note on Y93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This job was complete by NNPC management due to delay in negotiation
Note on C94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ADEOLA ODEKU
Note on C95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX IGANDO
Note on C97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX EBUTEMETA
Note on C100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX
Note on C101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ADEOLA ODEKU
Note on C102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX EBUTE META
Note on C129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PPU UYO
Note on C227: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX Reply: EBUTE METTA
Note on C291: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IYANA IYESI
Note on C322: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX IGANDO
Note on B345: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: number 86 of the sheet
Note on C351: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IYANA IYESI
Note on C362: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX IGANDO
Note on C370: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ppu
Note on C418: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX IRE AKARI
Note on C446: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IBADAN IWOROAD
Note on C451: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR SANGOTEDO
Note on C457: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR EGBE ROAD
Note on C485: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR SANGOTEDO
Note on B503: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: cost added to number 479
Note on C506: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PIE EXPRESS FAGBA
Note on C509: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PIE EXPRESS AGIDINGBI
Note on C510: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PIE UXPRESS AGIDINGBI
Note on C525: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR EGBE ROAD
Note on C526: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR EGBE ROAD
Note on C554: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IBADAN IWO ROAD
Note on C573: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CHOP BOX AGUNYI
Note on C594: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PH WAREHOUSE
Note on C630: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pie Express Igando
Note on C635: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX OKOTA
Note on C639: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ppu

## NOVEMBER
Legend
Completed on time
| Completed late |  |  |  |  | TH
S/N | ACTION/TASK | Store | Reason for Breakdown | Maintenance Category | Responsible | Specific Equipment | Category | Request Date | Days Since Request | Date Shared by Helpdesk | Days Delayed by Helpdesk | Date Attended/Checked by Vendor/Technician | Days Delayed by Vendor/Technician | Date Sent for Negotiation | Date Negotiated | Days Since Negotiation Request | Date Approval Requested | Days Since Approval Request | Approved Date | Days Since Approval | Expected Delivery Date | Cost | Status | Actual delivery date | Compliance check | Insert Comment
1 | GENERATOR DUE FOR SERVICING | LAG, HEYDEN IPAJA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-11-01 | 6 | 2024-11-01 | 0 | 2024-11-05 | 4 | 2024-11-05 | 2024-11-05 | 135 | 2024-11-05 | 0 | 2024-11-05 | 2 | 2024-11-07 |  | Completed | 2024-11-07 | 1
2 | GENERATOR DUE FOR SERVICE | LAG, ETERNA LEKKI | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-11-01 | 9 | 2024-11-01 | 0 | 2024-11-08 | 7 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 2 | 2024-11-08 | 208125 | Completed | 2024-11-10 | 0
3 | LEAKING GENERATOR FILTER | LAG, VGC | Wear & Tear | Breakdown | DELIGHTSOME | GENERATOR | GENERATOR | 2024-11-01 | 5 | 2024-11-01 | 0 | 2024-11-06 | 5 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 |  | Completed | 2024-11-06 | 1
4 | GENERATOR DUE FOR SERVICING | LAG, EKORO | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-11-01 | 11 | 2024-11-02 | 1 | 2024-11-08 | 6 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 4 | 2024-11-12 | 330347 | Completed | 2024-11-12 | 1
5 | REQUEST FOR GENERATOR SERVICING (CR LIMCA RD) | ANAMBRA, LIMCA RD, ONITSHA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-01 | 3 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 3 | 2024-11-04 | 237160 | Completed | 2024-11-04 | 1
6 | SERVICING OF GENERATOR | PH, RUMUOLA | Routine Servicing | Preventive |  | GENERATOR | GENERATOR | 2024-11-01 | 139 | 2024-11-01 | 0 |  | 139 | [9 empty] | Overdue
7 | GENERATOR SERVICING | DELTA, EFFURUN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-01 | 9 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 9 | 2024-11-10 | 0 | 2024-11-10 | 202450 | Completed | 2024-11-10 | 1
8 | GENERATOR DUE FOR SERVICING AT AWKA ROAD | ANAMBRA, AWKA RD, ONITSHA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-01 | 3 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 3 | 2024-11-04 | 237160 | Completed | 2024-11-04 | 1
9 | ELECTRICITY SUPPLY NOT SUFFICIENT | LAG, AWOLOWO 2 | Electrical Surge | Breakdown | GBATMO | TRANSFORMER | ELECTRICAL | 2024-11-02 | 138 | 2024-11-02 | 0 |  | 138 | [9 empty] | Overdue
10 | AC SERVICING - CR OJOO | IBADAN, OJOO | Routine Servicing | Preventive | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-11-03 | 8 | 2024-11-03 | 0 | 2024-11-11 | 8 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 |  | Completed | 2024-11-11 | 1
12 | FAULTY CABINET LAMP HOLDER | LAG, OSOLOWAY | Others | Breakdown | HEFHEM | OTHERS | OTHERS | 2024-11-05 | 135 | 2024-11-05 | 0 | 2024-11-08 | 3 | [9 empty] | Overdue |  |  | WORK WAS GIVEN TO KITCHTECH INSTEAD
13 | BROKEN PIPE | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | JOEL OMOTOSHO | OTHERS | OTHERS | 2024-11-06 | 1 | 2024-11-06 | 0 | 2024-11-07 | 1 | 2024-11-07 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 |  | Completed | 2024-11-07 | 1
14 | BROKEN PIPE IN WATER TREATMENT PLANT | LAG, MOBIL OGBA | Wear & Tear | Breakdown | PROEQUIP | WATER TREATMENT PLANT BLD | BUILDING | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 184500 | Completed | 2024-11-07 | 1
15 | BROKEN PIPE IN WATER TREATMENT PLANT | LAG, WAREHOUSE RD, APAPA | Wear & Tear | Breakdown | OLUWATOSIN | WATER TREATMENT PLANT BLD | BUILDING | 2024-11-07 | 133 | 2024-11-07 | 0 |  | 133 | [9 empty] | Overdue
16 | Daily Equipment Status | PPU Oniru | Routine Servicing | Preventive | FOLLTEC | OTHERS | OTHERS | 2024-11-07 | 133 | 2024-11-07 | 0 | 2024-11-07 | 0 | [9 empty] | Overdue
17 | FAULTY WARMER GASKET. | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-11-08 | 2 | 2024-11-08 | 0 |  | 132 | [7 empty] | 2024-11-10 |  | Completed | 2024-11-10 | 1
18 | WATER NOT RUNNING IN THE STORE. | LAG, VGC | Others | Breakdown | JOEL OMOTOSHO | OTHERS | OTHERS | 2024-11-07 | 1 | 2024-11-07 | 0 | 2024-11-08 | 1 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 |  | Completed | 2024-11-08 | 1
19 | CHIPS FRYER DOOR REPLACEMENT | LAG, IDIMU | Users Misuse | Breakdown | BCE | OTHERS | OTHERS | 2024-11-07 | 133 | 2024-11-07 | 0 |  | 133 | [9 empty] | Overdue
20 | FAULTY MAIN ENTRANCE DOOR HANDLE | LAG, HEYDEN IPAJA | Users Misuse | Breakdown | TAIDAV | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-11-06 | 134 | 2024-11-06 | 0 | 2024-11-06 | 0 | [9 empty] | Overdue
21 | FAULTY ENTRANCE DOOR HANDLE. | LAG, WAREHOUSE RD, APAPA | Users Misuse | Breakdown | TAIDAV | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-11-02 | 138 | 2024-11-02 | 0 |  | 138 | [9 empty] | Overdue
22 | FAULTY CABINET LAMP HOLDER | LAG, IRE-AKARI | Electrical Surge | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-25 | 2 | 2024-11-25 | 0 | 2024-11-27 | 2 | 2024-11-27 | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 | 269935.5 | Completed | 2024-11-27 | 1
26 | REQUEST FOR LED LIGHTS | OYO, OWODE | Others | Breakdown | RANEX | OTHERS | OTHERS | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 172,430 | Completed | 2024-11-06 | 1
28 | Generator Not Coming up - Faulty Nozzles-Yenagoa | BAYELSA, YENAGOA | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-11-05 | 1 | 2024-11-06 | 1 | 2024-11-06 | 0 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 140000 | Completed | 2024-11-06 | 1
29 | GENERATOR NOT COMING UP | OGUN, SOKENU | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-11-11 | 129 | 2024-11-11 | 0 |  | 129 | [9 empty] | Overdue
30 | BROKEN TILES IN THE STORE | LAG, OPEBI | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-11-04 | 136 | 2024-11-04 | 0 |  | 136 | [9 empty] | Overdue
31 | FAULTY SOAP DISPENSER | LAG, IPAJA RD | Users Misuse | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-10-30 | 9 | 2024-11-06 | 7 | 2024-11-08 | 2 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 60737.5 | Completed | 2024-11-08 | 1
32 | LOBBY AC NOT COOLING | PH, TRANS AMADI | Routine Servicing | Preventive | ODERINDE | 5HP STANDING AC UNIT 1 | HVAC | 2024-11-06 | 134 | 2024-11-06 | 0 | 2024-11-06 | 0 | [9 empty] | Overdue
33 | LOBBY AC NOT COOLING | LAG, AGUNGI | Routine Servicing | Preventive | TONAOGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-11-13 | 5 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 5 | 2024-11-18 | 111500 | Completed | 2024-11-18 | 1
34 | FREEZER ROOM AND COLD ROOM NOT ATTAINING TEMPERATURE | OSUN, AYETORO | Routine Servicing | Preventive | TONAOGUNS | OTHERS | OTHERS | 2024-11-06 | 13 | 2024-11-06 | 0 | 2024-11-10 | 4 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-15 | 63 | 2025-01-17 | -59 | 2024-11-18 | 136875 | Completed | 2024-11-19 | 0
35 | COLD ROOM NOT ATTAINING TEMPERATURE- CR AFIKPO | EBONYI, AFIKPO, ABAKALIKI | Routine Servicing | Preventive | BCE | COLD ROOM UNIT | HVAC | 2024-11-04 | 10 | 2024-11-04 | 0 | 2024-11-05 | 1 | 2024-11-14 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 230050 | Completed | 2024-11-14 | 1
36 | COLD ROOM NOT ATTAINING TEMPERATURE. | LAG, JIBOWU | Routine Servicing | Preventive | DYNAMITE | COLD ROOM UNIT | HVAC | 2024-11-08 | 132 | 2024-11-08 | 0 | 2024-11-08 | 0 | [9 empty] | Overdue
37 | FREEZER ROOM AND COLD ROOM NOT ATTAINING TEMPERATURE | LAG, OBA AKRAN | Routine Servicing | Preventive | BCE | OTHERS | OTHERS | 2024-11-08 | 21 | 2024-11-08 | 0 | 2024-11-29 | 21 | 2024-11-29 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 118250 | Completed | 2024-11-29 | 1
39 | FW: FREEZER ROOM AND COLD ROOM NOT ATTAINING TEMPERATURE | PH, OMOKU | Routine Servicing | Preventive | MOFEEN | OTHERS | OTHERS | 2024-11-03 | 2 | 2024-11-04 | 1 | 2024-11-05 | 1 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 240000 | Completed | 2024-11-05 | 1
40 | RUSTY COLD ROOM DOOR | LAG, OGUDU | Wear & Tear | Breakdown | SARAJUDEEN | COLD ROOM UNIT | HVAC | 2024-11-04 | 136 | 2024-11-04 | 0 | 2024-11-04 | 0 | [8 empty] | 109000 | Overdue
41 | FAULTY CANINET LAMP HOLDER |  | Wear & Tear | Breakdown | KITCHTEC | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-07 | 133 | 2024-11-07 | 0 |  | 133 | [9 empty] | Overdue
42 | REQUEST FOR LID GASKET | ABIA, OGBOR HILLS | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-11-07 | 2 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 1 | 2024-11-09 | 166625 | Completed | 2024-11-09 | 1
43 | FAULTY DISPLAY CABINET BULB HOLDER | LAG, IDIMU | Wear & Tear | Breakdown | EMMANUEL | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-11 | 129 | 2024-11-11 | 0 | 2024-11-12 | 1 | [9 empty] | Overdue
44 | BURNT DISPLAY CABINET BULB | OGUN, HEYDEN IBAFO | Electrical Surge | Breakdown | MOSES | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-12 | 128 | 2024-11-12 | 0 |  | 128 | [9 empty] | Overdue
45 | FAULTY CABINET BULB | LAG, ONIRU | Electrical Surge | Breakdown | KITCHTEC | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 2024-11-12 | #REF! | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 73530 | Completed | 2024-11-12 | 1
46 | BROKEN CABINET BULB GLASS COVER |  | Users Misuse | Breakdown | KITCHTEC | OTHERS | OTHERS | 2024-11-11 | 129 | 2024-11-11 | 0 |  | 129 | [9 empty] | Overdue
47 | CABINET BULB LAP HOLDER IS FAULTY | LAG, FESTAC | Others | Breakdown | TIMILEHIN | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-04 | 4 | 2024-11-04 | 0 | 2024-11-11 | 7 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 |  | 2024-11-08 |  | Completed | 2024-11-08 | 1
48 | Blown out Cabinet Bulb | DELTA, EFFURUN | Electrical Surge | Breakdown | FRANK | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-04 | 17 | 2024-11-04 | 0 | 2024-11-21 | 17 | 2024-11-21 | 2024-11-21 | 0 | 2024-11-21 | 0 | 2024-11-21 | 0 | 2024-11-21 | 311750 | Completed | 2024-11-21 | 1
49 | FAULTY EXTRACTOR | ABIA, AZIKIWE RD, UMUAHIA | Others | Breakdown | JONNYTECG | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2024-11-14 | 3 | 2024-11-14 | 0 | 2024-11-17 | 3 | 2024-11-17 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-17 | 150000 | Completed | 2024-11-17 | 1
50 | CHIP FRYER NOT WORKING - CR RINGROAD | IBADAN, RING-ROAD | Users Misuse | Breakdown | KITCHTEC | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-11-08 | 5 | 2024-11-08 | 0 | 2024-11-11 | 3 | 2024-11-12 | 2024-11-12 | 0 | 2024-11-12 | 1 | 2024-11-13 | 0 | 2024-11-13 | 257312 | Completed | 2024-11-13 | 1
51 | OPEN PIPE AT THE LOBBY AREA | LAG, VGC | Wear & Tear | Breakdown | ADEREMI | OTHERS | OTHERS | 2024-11-14 | 126 | 2024-11-14 | 0 |  | 126 | [9 empty] | Overdue
52 | BAD MALE CHANGING ROOM ENTRANCE AND RESTROOM DOOR KNOB | LAG, MAGODO | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-11-14 | 1 | 2024-11-14 | 0 | 2024-11-15 | 1 | 2024-11-15 | 2024-11-15 | 0 | 2024-11-15 | 0 | 2024-11-15 | 0 | 2024-11-15 | 30000 | Completed | 2024-11-15 | 1
53 | REQUEST FOR LED LIGHT | IBADAN, RING-ROAD | Others | Breakdown | RANEX | OTHERS | OTHERS | 2024-11-08 | 6 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 6 | 2024-11-14 | 22575 | Completed | 2024-11-14 | 1
54 | FAULTY WATER HEATER | DELTA, ISOKO RD | Others | Breakdown | PROEUIP | WATER HEATER | PLUMBING | 2024-11-02 | 138 | 2024-11-02 | 0 | 2024-11-04 | 2 | [9 empty] | Overdue
55 | FAULTY WATER HEATER | LAG, JIBOWU | Others | Breakdown | PROPEARJEFF | WATER HEATER | PLUMBING | 2024-11-07 | 4 | 2024-11-08 | 1 | 2024-11-11 | 3 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 33262.5 | Completed | 2024-11-11 | 1
56 | FAULTY WATER HEATER | PPU Ajah | Others | Breakdown | PROEUIPTEC | WATER HEATER | PLUMBING | 2024-11-07 | 133 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 2024-11-07 | 0 | 2024-11-07 | 133 |  |  |  | 261500 | Overdue
57 | BROKEN WATER STORAGE PIPE | LAG, AWOLOWO | Wear & Tear | Breakdown | JOEL | GROUND WATER TANK | WTP | 2024-11-13 | 1 | 2024-11-13 | 0 | 2024-11-14 | 1 | 2024-11-14 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 |  | Completed | 2024-11-14 | 1
58 | FAULTY PEST KILLER BULB AND CABINET BULB | LAG, GBAGADA | Others | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-11-12 | 1 | 2024-11-13 | 1 | 2024-11-13 | 0 | 2024-11-13 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 |  | Completed | 2024-11-13 | 1
59 | FAUTY INVERTER | IBADAN, OJOO | Corrective Action | Corrective | DALEMATRIX | INVERTER DB | ELECTRICAL | 2024-11-03 | 19 | 2024-11-11 | 8 | 2024-11-17 | 6 | 2024-11-17 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-17 | 5 | 2024-11-17 | 90250 | Completed | 2024-11-22 | 0
60 | BROKEN UNDER BAR UPRIGHT CHILLER BULB AND NOT ATTAINING TEMPERATURE WITH DEGRADED INTERIOR- CR IKOT EKPENE | AKWA IBOM, IKOT EKPENE RD | Others | Breakdown | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-17 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-17 | 354750 | Completed | 2024-11-17 | 1
61 | BROKEN DISPLAY CABINET SLIDING GLASS | LAG, OPEBI | Users Misuse | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-11 | 6 | 2024-11-11 | 0 | 2024-11-16 | 5 | 2024-11-16 | 2024-11-16 | 0 | 2024-11-16 | 0 | 2024-11-16 | 1 | 2024-11-17 |  | Completed | 2024-11-17 | 1
62 | FAULTY DOOR HANDLE | LAG, IRE-AKARI | Users Misuse | Breakdown | TAIDAV | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-11-04 | 9 | 2024-11-04 | 0 | 2024-11-13 | 9 | 2024-11-13 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 98000 | Completed | 2024-11-13 | 1
63 | SPACK DRY STORE A C | LAG, LEKKI PHASE 1 | Routine Servicing | Preventive | G.B BOYEJO | SPLIT UNIT DRY STORE | HVAC | 2024-11-04 | 136 | 2024-11-04 | 0 | 2024-11-15 | 11 | [9 empty] | Overdue
64 | LEAKING AERATION TANK | LAG, GBAGADA | Wear & Tear | Breakdown | PROEQUIP | AERATION TANK | WTP | 2024-11-09 | 131 | 2024-11-10 | 1 |  | 130 | [9 empty] | Overdue
65 | Faulty Roller Shutter - CR Olofa | ILORIN, OLOFAWAY | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-11-01 | 6 | 2024-11-01 | 0 | 2024-11-01 | 0 | [7 empty] | 2024-11-07 |  | Completed | 2024-11-07 | 1
67 | FAULTY ROLLER SHUTTER | LAG, AJAH | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-11-16 | 42 | 2024-11-16 | 0 | 2024-11-18 | 2 | 2024-11-22 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 36 | 2024-12-28 | 226000 | Completed | 2024-12-28 | 1
68 | REQUEST FOR CABINET BULB |  | Others | Breakdown | RANEX | OTHERS | OTHERS | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 134 |  |  | 2024-11-06 | 21500 | Completed | 2024-11-06 | 1
69 | FAULTY INVERTER | ILORIN, GRA | Others | Breakdown | NISTECHLTD | INVERTER DB | ELECTRICAL | 2024-11-04 | 50 | 2024-11-04 | 0 | 2024-11-07 | 3 | 2024-11-07 | 2024-11-19 | 12 | 2024-11-19 | 2 | 2024-11-21 | 33 | 2024-12-24 | 1784500 | Completed | 2024-12-24 | 1
70 | Re: Faulty inverter | ABIA, FACTORY RD, ABA | Others | Breakdown | LEONARD | INVERTER DB | ELECTRICAL | 2024-11-19 | 2 | 2024-11-20 | 1 | 2024-11-21 | 1 | 2024-11-21 | 2024-11-21 | 0 | 2024-11-21 | 0 | 2024-11-21 |  | 2024-11-21 |  | Completed | 2024-11-21 | 1
71 | FAULTY INVERTER BATTERY | ILORIN, OLOFAWAY | Others | Breakdown | NISTECHLTD | INVERTER BATTERIES | INVERTER | 2024-11-04 | 50 | 2024-11-04 | 0 | 2024-11-07 | 3 | 2024-11-07 | 2024-11-19 | 12 | 2024-11-19 | 28 | 2024-12-17 | 7 | 2024-12-24 | 1010500 | Completed | 2024-12-24 | 1
72 | CR ASA DAM : FAULTY INVERTER | ILORIN, ASA DAM | Others | Breakdown | NISTECHLTD | INVERTER BATTERIES | INVERTER | 2024-11-05 | 49 | 2024-11-05 | 0 | 2024-11-07 | 2 | 2024-11-07 | 2024-11-19 | 12 | 2024-11-19 | 0 | 2024-11-19 | 35 | 2024-11-27 | 1010500 | Completed | 2024-12-24 | 0
73 | LEAKING WASHING HAND BASIN | PPU Ilupeju | Wear & Tear | Breakdown | PROPEARJEFF | LOBBY WASH HAND BASIN | PLUMBING | 2024-11-02 | 138 | 2024-11-03 | 1 |  | 137 | [9 empty] | Overdue
74 | FAULTY INVERTER BATTERY | ILORIN, OFFA GARAGE | Others | Breakdown | NISTECHLTD | INVERTER BATTERIES | INVERTER | 2024-11-04 | 136 | 2024-11-04 | 0 | 2024-11-04 | 0 | [9 empty] | Overdue
75 | FAULTY INVERTER | LAG, IDIMU | Others | Breakdown | DALEMATRIX | INVERTER DB | ELECTRICAL | 2024-11-12 | 2 | 2024-11-12 | 0 | 2024-11-14 | 2 | 2024-11-14 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 165000 | Completed | 2024-11-14 | 1
76 | FAULTY INVERTER - MMWAY ILORIN | ILORIN, MM WAY | Others | Breakdown | NISTECHLTD | INVERTER DB | ELECTRICAL | 2024-11-04 | 20 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-07 | 2024-11-07 | 0 | 2024-11-07 | 14 | 2024-11-21 | 3 | 2024-11-24 | 1784500 | Completed | 2024-11-24 | 1
77 | COLD ROOM AND FREEZER ROOM NOT ATTAINING TEMPERATURE | PH, ONNE | Others | Breakdown | MOFEEN | OTHERS | OTHERS | 2024-11-15 | 125 | 2024-11-15 | 0 | 2024-11-16 | 1 | [9 empty] | Overdue
78 | FREEZER ROOM NOT ATTAINING TEMPERATURE | IMO, IKENEGBU, OWERRI | Others | Breakdown | BCE | FREEZER ROOM | HVAC | 2024-11-21 | 10 | 2024-11-21 | 0 | 2024-11-22 | 1 | 2024-11-22 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 9 | 2024-12-01 | 12900 | Completed | 2024-12-01 | 1
79 | NVERTER NOT CHARGING | LAG, AKOWONJO | Others | Breakdown | DALEMATRIX | INVERTER DB | ELECTRICAL | 2024-11-20 | 1 | 2024-11-21 | 1 | 2024-11-21 | 0 | 2024-11-21 | 2024-11-21 | 0 | 2024-11-21 | 0 | 2024-11-21 | 0 | 2024-11-21 | 45500 | Completed | 2024-11-21 | 1
80 | FUALTY CABINET BULB | LAG, FREEDOMWAY | Others | Breakdown | KITCHTEC | OTHERS | OTHERS | 2024-11-19 | 121 | 2024-11-20 | 1 |  | 120 | [9 empty] | Overdue
82 | FAULTY FREEZER ROOM & Coldroom | IBADAN, AKOBO | Routine Servicing | Preventive | TONAOGUNS | FREEZER ROOM | HVAC | 2024-11-02 | 57 | 2024-11-02 | 0 | 2024-11-08 | 6 | 2024-12-02 | 2024-12-29 | 27 | 2024-12-29 | 0 | 2024-12-29 | 0 | 2024-12-29 | 510250 | Completed | 2024-12-29 | 1
83 | Faulty Freezer room |  | Routine Servicing | Preventive | TONAOGUNS | FREEZER ROOM | HVAC | 2024-11-01 | 10 | 2024-11-01 | 0 | 2024-11-02 | 1 | 2024-11-02 | 2024-11-03 | 1 | 2024-11-03 | 0 | 2024-11-03 | 8 | 2024-11-11 | 203750 | Completed | 2024-11-11 | 1
84 | FAULTY FREEZER ROOM 1 AND COLD ROOM READING | PPU Ilupeju | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-11-06 | 134 | 2024-11-08 | 2 | 2024-11-11 | 3 | [9 empty] | Overdue
85 | Faulty Freezer room | Yenagoa CR | Corrective Action | Corrective | Mofeen | FREEZER ROOM | HVAC | 2024-10-26 | 9 |  | 145 | [9 empty] | 2024-11-04 |  | Completed | 2024-11-04 | 1
86 | Generator servicing | Yenagoa CR | Routine Servicing | Preventive | Pagisel |  |  | 2024-10-29 | 4 |  | 142 | [9 empty] | 2024-11-01 |  | Completed | 2024-11-02 | 0
87 | Repair of faulty Injector pump | Yenagoa CR | Wear & Tear | Breakdown | Pagisel |  |  | 2024-11-06 | 1 |  | 134 | [9 empty] | 2024-11-07 |  | Completed | 2024-11-07 | 1
88 | Replaced 2 Nos of insecutor tube | Yenagoa CR | Corrective Action | Corrective | Mudiaga | INSECT KILLER BOH | ELECTRICAL | 2024-11-12 | 0 |  | 128 | [9 empty] | 2024-11-12 |  | Completed | 2024-11-12 | 1
89 | Generator servicing | Yenagoa CR | Routine Servicing | Preventive | Pagisel |  |  | 2024-11-18 | 5 |  | 122 | [9 empty] | 2024-11-20 |  | Completed | 2024-11-23 | 0
90 | Faulty Roteserie machine | Yenagoa CR | Corrective Action | Corrective | ECS | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-11-06 | 15 |  | 134 | [9 empty] | 2024-11-21 |  | Completed | 2024-11-21 | 1
91 | Septic tank Evacuation | Yenagoa CR | Routine Servicing | Preventive | Bright | SEPTIC TANK | EVACUATION | 2024-11-19 | 4 |  | 121 | [9 empty] | 2024-11-23 |  | Completed | 2024-11-23 | 1
92 | Mounting of OPS Alert Folders | PPU Tombia | Others | Breakdown | Mudiaga | OTHERS | OTHERS | 2024-11-11 | 129 |  | 129 | [11 empty] | Overdue
93 | Generator servicing | PPU Tombia | Routine Servicing | Preventive | Pagisel |  |  | 2024-11-15 | 125 |  | 125 | [11 empty] | Overdue
94 | Fixed door handles for dry Store | PPU Tombia | Corrective Action | Corrective | Mudiaga | OTHERS | OTHERS | 2024-11-21 | 119 |  | 119 | [11 empty] | Overdue
95 | Resolved issue of underground water leakages | PPU Tombia | Corrective Action | Corrective |  | OTHERS | OTHERS | 2024-11-21 | 119 |  | 119 | [11 empty] | Overdue
96 | Fixed outside washing sink tap | PPU Tombia | Users Misuse | Breakdown |  | OTHERS | OTHERS | 2024-11-21 | 119 |  | 119 | [11 empty] | Overdue
97 | FAULTY CABINET LAMP HOLDER | LAG, OSOLOWAY | Others | Breakdown | KITCHTEC | OTHERS | OTHERS | 2024-11-12 | 6 | 2024-11-12 | 0 | 2024-11-18 | 6 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 |  | Completed | 2024-11-18 | 1
98 | ROTISSERIE MACHINE NOT ATTAINING TEMPERATURE | PH, RUKPOKWU | Corrective Action | Corrective | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-11-01 | 21 | 2024-11-01 | 0 | 2024-11-22 | 21 | 2024-11-22 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 953525 | Completed | 2024-11-22 | 1
99 | FOOD CABINET SHOCKING | PH, TRANS AMADI | Electrical Surge | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-07 | 15 | 2024-11-07 | 0 | 2024-11-08 | 1 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 14 | 2024-11-18 | 165550 | Completed | 2024-11-22 | 0
100 | FAULTY CHIPS FRYER | DELTA, EFFURUN | Electrical Surge | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-11-17 | 2 | 2024-11-18 | 1 | 2024-11-18 | 0 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 1 | 2024-11-19 | 58050 | Completed | 2024-11-19 | 1
101 | DETACHED DOOR HINGES IN CHIPS FRYER | PH, DOX RD | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-11-11 | 7 | 2024-11-11 | 0 | 2024-11-18 | 7 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 34400 | Completed | 2024-11-18 | 1
102 | HYGIENE AND PROCESS COMPLIANCE REPORT AT PPU ONIRU | PPU Oniru | Wear & Tear | Breakdown | BCE |  |  |  | #VALUE! |  | #VALUE! | 2024-11-19 | 45615 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 |  | Completed | 19/11/2024 | 0
103 | REQUEST FOR GENERATOR SERVICING. | LAG, ALIMOSHO | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-11-29 | 111 | 2024-11-29 | 0 | 2024-11-30 | 1 |  |  |  |  | 121 |  |  |  |  | Overdue
104 | GENERATOR SERVICING | OYO, OWODE | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-11-27 | 6 | 2024-11-27 | 0 | 2024-12-01 | 4 | 2024-12-05 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 | -2 | 2024-12-03 | 401082.5 | Completed | 2024-12-03 | 1
105 | GENERATOR SERVICING | PH, DOX RD | Routine Servicing | Preventive | PROPARTEC | GENERATOR | GENERATOR | 2024-11-23 | 8 | 2024-11-24 | 1 | 2024-11-29 | 5 | 2024-11-29 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 2 | 2024-12-01 | 199750 | Completed | 2024-12-01 | 1
106 | CR OKIGWE GENERATOR SERVICING | IMO, OKIGWE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-27 | 3 | 2024-11-27 | 0 | 2024-11-28 | 1 | 2024-11-28 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 2 | 2024-11-30 | 202450 | Completed | 2024-11-30 | 1
107 | GENERATOR SERVICING | ABIA, FACTORY RD, ABA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-27 | 2 | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-29 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 202450 | Completed | 2024-11-29 | 1
108 | GENERATOR SERVICING + AIR FILTER ELEMENT - CR-PPU, OKIGWE ROAD, ORJI, IMO STATE |  | Routine Servicing | Preventive | KB | GENERATOR | GENERATOR | 2024-11-26 | 0 | 2024-11-26 | 0 | 2024-11-26 | 0 | 2024-11-26 | 2024-11-26 | 0 | 2024-11-26 | 0 | 2024-11-26 | 0 | 2024-11-26 | 268750 | Completed | 2024-11-26 | 1
109 | SEWAGE EVACUATION | LAG, TOTAL LEKKI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-11-03 | 137 | 2024-11-04 | 1 |  | 136 | [9 empty] | Overdue
110 | FAULTY GAS BURNER | LAG, OKE-AFA | Others | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-11-21 | 1 | 2024-11-21 | 0 | 2024-11-22 | 1 | 2024-11-22 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 154000 | Completed | 2024-11-22 | 1
111 | GENERATOR SERVICING | IMO, WETHERAL RD, OWERRI | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-11-24 | 1 | 2024-11-24 | 0 | 2024-11-25 | 1 | 2024-11-25 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 | 202450 | Completed | 2024-11-25 | 1
112 | BROKEN WALL TILES | LAG, TEJUOSHO | Wear & Tear | Breakdown | ACORN | WALL | BUILDING | 2024-11-18 | 122 | 2024-11-22 | 4 | 2024-11-28 | 6 | 2024-11-28 | 2024-12-04 | 6 | 2024-12-04 | 0 | 2024-12-04 | 106 |  | 165000 | Overdue
113 | Fire in cook section | LAG, MOBIL OGBA | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2024-11-10 | 130 | 2024-11-10 | 0 |  | 130 | [9 empty] | Overdue
114 | BROKEN WALL TILES IN THE STORE. | LAG, GBAGADA | Wear & Tear | Breakdown | ARIZMAYAN | WALL | BUILDING | 2024-11-11 | 129 | 2024-11-11 | 0 | 2024-11-11 | 0 | [9 empty] | Overdue
115 | GAS PICK TAIL IS LEAKING | LAG, BADORE | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-11-12 | 1 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 1 | 2024-11-12 | 48000 | Completed | 2024-11-13 | 0
116 | FAULTY COOKING BURNERS | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2024-11-21 | 119 | 2024-11-21 | 0 | 2024-11-25 | 4 | 2024-11-27 | 2024-11-27 | 0 | 2024-11-27 | 1 | 2024-11-28 | 112 |  | 95000 | Overdue
117 | GAS BURNER SERVICING | LAG, FREEDOMWAY | Routine Servicing | Preventive | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2024-11-29 | 111 | 2024-11-29 | 0 | 2024-11-29 | 0 | [9 empty] | Overdue
118 | GENERATOR SERVICING- CR - EKET, ORON ROAD, AKWA-IBOM STATE. | AKWA IBOM, EKET-ORON RD | Routine Servicing | Preventive | KB | GENERATOR | GENERATOR | 2024-11-17 | 1 | 2024-11-17 | 0 | 2024-11-18 | 1 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 258000 | Completed | 2024-11-18 | 1
119 | DEAD ROTISIERIE MACHINE HALOGEN BULB | OGUN, FATGBEMS IBB WAY | Electrical Surge | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-11-27 | 113 | 2024-11-27 | 0 | 2024-12-04 | 7 | [8 empty] | 561150 | Overdue
120 | SEWAGE EVACUATION | LAG, OSOLOWAY | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-11-15 | 125 | 2024-11-15 | 0 |  | 125 | [9 empty] | Overdue
121 | SEWAGE EVACUATION | LAG, ETERNA LEKKI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-11-16 | 0 | 2024-11-16 | 0 | 2024-11-16 | 0 | 2024-11-16 | 2024-11-16 | 0 | 2024-11-16 | 0 | 2024-11-16 | 0 | 2024-11-16 | 161500 | Completed | 2024-11-16 | 1
122 | SEWAGE EVACUATION | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-11-22 | 118 | 2024-11-22 | 0 |  | 118 | [9 empty] | Overdue
123 | SEWAGE EVACUATION | LAG, EJIGBO | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-11-25 | 5 | 2024-11-25 | 0 | 2024-11-30 | 5 | 2024-11-30 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 681500 | Completed | 2024-11-30 | 1
124 | SEWAGE EVACUATION | LAG, TOTAL LEKKI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-11-26 | 114 | 2024-11-26 | 0 |  | 114 | [9 empty] | Overdue
125 | SEWAGE EVACUATION | LAG, OKE-AFA | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-11-28 | 1 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 1 | 2024-11-29 | 545000 | Completed | 2024-11-29 | 1
126 | FAULTY MOBIL WARMER DOOR GASKET. LIMCA ROAD | ANAMBRA, LIMCA RD, ONITSHA | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-11-03 | 6 | 2024-11-03 | 0 | 2024-11-08 | 5 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 1 | 2024-11-09 | 0 | 2024-11-09 | 115025 | Completed | 2024-11-09 | 1
127 | REQUEST FOR ENGINE OIL | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-11-02 | 2 | 2024-11-03 | 1 | 2024-11-04 | 1 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 |  | Completed | 2024-11-04 | 1
128 | GENEERATOR NOT STARTING. | LAG, JOEL OGUNNAIKE | Corrective Action | Corrective | GAMMA | GENERATOR | GENERATOR | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 |  | Completed | 2024-11-04 | 1
129 | GENERATOR SERVICING | ABIA, ADAZI RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-05 | 6 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 6 | 2024-11-11 | 202450 | Completed | 2024-11-11 | 1
130 | GENERATOR DUE FOR SERVICE | LAG, JOEL OGUNNAIKE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 150000 | Completed | 2024-11-05 | 1
131 | GENERATOR DUE FOR SERVICING | LAG, OBA AKRAN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-05 | 7 | 2024-11-06 | 1 | 2024-11-10 | 4 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 2 | 2024-11-12 | 181700 | Completed | 2024-11-12 | 1
132 | GENERATOR SERVING | LAG, AWOLOWO 2 | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-06 | 5 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 5 | 2024-11-11 | 81700 | Completed | 2024-11-11 | 1
133 | GENERATOR SHOCKING | LAG, JOEL OGUNNAIKE | Electrical Surge | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-11-06 | 6 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 6 | 2024-11-12 | 181700 | Completed | 2024-11-12 | 1
134 | generator due for servicing | DELTA, ISOKO RD | Electrical Surge | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-11-08 | 3 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 3 | 2024-11-11 | 202450 | Completed | 2024-11-11 | 1
135 | GENERATOR SERVICING | EDO, SILUKO | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-09 | 6 | 2024-11-09 | 0 | 2024-11-09 | 0 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 5 | 2024-11-15 | 207330 | Completed | 2024-11-15 | 1
136 | GENERATOR DUE FOR SERVICING | OGUN, FATGBEMS IBB WAY | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-10 | 130 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 130 |  |  | Overdue
137 | GENERATOR DUE FOR SERVICE | LAG, ONIRU | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-10 | 2 | 2024-11-10 | 0 | 2024-11-12 | 2 | 2024-11-12 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 181700 | Completed | 2024-11-12 | 1
138 | GENERATOR BREAKDOWN | EDO, RAHMAT PARK, BENIN | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-11-10 | 18 | 2024-11-10 | 0 | 2024-11-28 | 18 | 2024-11-28 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 1000950 | Completed | 2024-11-28 | 1
139 | GENERATOR DUE FOR SERVICE | LAG, ONIRU | Others | Breakdown
140 | MAINTENACE ISSUE | LAG, AGUNGI | Others | Breakdown | VENYS | OTHERS | OTHERS | 2024-11-12 | 128 | 2024-11-12 | 0 |  | 128 | [9 empty] | Overdue
141 | CR NSUKKA MAINTENANCE ISSUES | ENUGU, NSUKKA | Electrical Surge | Breakdown | PETOJO | INVERTER DB | ELECTRICAL | 2024-11-05 | 29 | 2024-11-05 | 0 | 2024-11-25 | 20 | 2024-11-25 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 | 9 | 2024-12-04 | 1055000 | Completed | 2024-12-04 | 1
142 | FAULTY SAFE ROOM DOOR. | LAG, LEKKI PHASE 1 | Users Misuse | Breakdown | JOEL | OTHERS | OTHERS | 2024-11-18 | 16 | 2024-11-22 | 4 | 2024-11-22 | 0 | 2024-12-04 | 2024-12-04 | 0 | 2024-12-04 | 0 | 2024-12-04 | 0 | 2024-12-04 |  | Completed | 2024-12-04 | 1
143 | TOASTER MACHINE FAULTY | PH, OYIGBO | Others | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2024-11-10 | -5 | 2024-11-10 | 0 | 2024-11-11 | 1 | 2024-11-03 | 2024-11-03 | 0 | 2024-11-03 | 0 | 2024-11-03 | 2 | 2024-11-05 | 101050 | Completed | 2024-11-05 | 1
144 | FAULTY GREASE TRAP WITH BAD DRAIN NET. | LAG, JOEL OGUNNAIKE | Others | Breakdown | ZEBRA | GREASE TRAP | GREASE_TRAP | 2024-11-03 | 73 | 2024-11-03 | 0 | 2024-11-04 | 1 | 2024-11-05 | 2024-12-06 | 31 | 2024-12-06 | 0 | 2024-12-06 | 40 | 2025-01-15 | 420000 | Completed | 2025-01-15 | 1
145 | Generator Service Request.xlsx | ANAMBRA, ZIK AVENUE, AWKA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-09 | 2 | 2024-11-10 | 1 | 2024-11-10 | 0 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 342450 | Completed | 2024-11-11 | 1
146 | GENERATOR SERVICE | EDO, UGBOWO, BENIN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-09 | 6 | 2024-11-10 | 1 | 2024-11-15 | 5 | 2024-11-15 | 2024-11-15 | 0 | 2024-11-15 | 0 | 2024-11-15 | 0 | 2024-11-15 | 202450 | Completed | 2024-11-15 | 1
147 | GENERATOR TRIPPING OFF AT INTERVAL | ANAMBRA, AWKA RD, ONITSHA | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-12 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | -2 | 2024-11-12 | 412550 | Completed | 2024-11-10 | 1
148 | GENERATOR DUE FOR SERVICE | LAG, OSOLOWAY | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-10 | 130 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 130 | 2024-11-12 |  | Overdue
149 | Generator Service Request | PH, OMOKU | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-11 | 129 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 129 |  |  | Overdue
150 | Generator Service Request.xlsx | ANAMBRA, ZIK AVENUE, AWKA | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 342450 | Completed | 2024-11-11 | 1
151 | GENERATOR SHUT DOWN AND DUE FOR SERVICING | LAG, GBAGADA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-13 | 1 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 1 | 2024-11-14 | 181700 | Completed | 2024-11-14 | 1
152 | GENERATOR SERVICING | EDO, SAKPOMBA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-13 | 7 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 2024-11-13 | 0 | 2024-11-13 | 2024-11-13 | 2024-11-13 | 7 | 2024-11-20 | 207330 | Completed | 2024-11-20 | 1
153 | REQUEST FOR ENGINE OIL/GENERATOR DUE FOR SERVICING | LAG, WAREHOUSE RD, APAPA | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-11-13 | 127 | 2024-11-13 | 0 | 2024-11-13 | 0 | [9 empty] | Overdue
154 | GENERATOR DUE FOR SERVICING | LAG, AKOWONJO | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-12 | 2 | 2024-11-14 | 2 | 2024-11-14 | 0 | 2024-11-14 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 45000 | Completed | 2024-11-14 | 1
155 | GENERATOR SERVICING | LAG, JIBOWU | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-14 | 4 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 4 | 2024-11-18 | 181700 | Completed | 2024-11-18 | 1
156 | GENSET SERVICING | BAYELSA, TOMBIA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-16 | 3 | 2024-11-16 | 0 | 2024-11-18 | 2 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 1 | 2024-11-19 | 242450 | Completed | 2024-11-19 | 1
157 | GENERATOR SERVINCING | LAG, OGUNLANA DRIVE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-08 | 8 | 2024-11-15 | 7 | 2024-11-16 | 1 | 2024-11-16 | 2024-11-16 | 0 | 2024-11-16 | 0 | 2024-11-16 | 0 | 2024-11-16 | 114500 | Completed | 2024-11-16 | 1
158 | REQUEST FOR CABINET BULB | LAG, AJOSE ADEOGUN | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-11-18 | 7 | 2024-11-18 | 0 | 2024-11-25 | 7 | 2024-11-25 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 |  | Completed | 2024-11-25 | 1
159 | FAULTY ROLLER SHUTTER | LAG, IKORODU | Routine Servicing | Preventive | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-11-26 | 3 | 2024-11-26 | 0 | 2024-11-27 | 1 | 2024-11-29 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 66327.5 | Completed | 2024-11-29 | 1
160 | FAULTY ROLLER SHUTTER | LAG, AKOWONJO | Routine Servicing | Preventive | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-11-26 | 42 | 2024-11-26 | 0 | 2024-11-27 | 1 | 2024-12-09 | 2024-12-10 | 1 | 2024-12-10 | 1 | 2024-12-11 | 27 | 2024-12-23 | 82506.25 | Completed | 2025-01-07 | 0
161 | FAULTY ROLLER SHUTTER | AKWA IBOM, IKOT EKPENE RD | Routine Servicing | Preventive | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-11-04 | 46 | 2024-11-05 | 1 | 2024-11-05 | 0 | 2024-11-05 | 2024-11-05 | 0 | 2024-12-05 | 7 | 2024-12-12 | 8 | 2024-12-20 | 142190.89 | Completed | 2024-12-20 | 1
162 | FAULTY ROLLER SHUTTER | LAG, OSOLOWAY | Routine Servicing | Preventive | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-11-28 | 112 | 2024-11-28 | 0 | 2024-12-05 | 7 | 2024-12-05 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 | 105 |  | 225965 | Overdue
163 | REQUEST FOR LED LIGHT,MOTOR STARTER AND SOCKET | IBADAN, VENTURA MALL | Others | Breakdown | RANEX | OTHERS | OTHERS | 2024-11-29 | 6 | 2024-12-02 | 3 | 2024-12-03 | 1 | 2024-12-03 | 2024-12-03 | 0 | 2024-12-03 | 2 | 2024-12-05 | 0 | 2024-12-05 | 160175 | Completed | 2024-12-05 | 1
164 | SPOILED STAFF RESTROOM DOOR | LAG, HEYDEN ALAPERE | Users Misuse | Breakdown | FULL TURN | OTHERS | OTHERS | 2024-11-06 | 30 | 2024-11-10 | 4 | 2024-11-11 | 1 | 2024-11-12 | 2024-11-18 | 6 | 2024-11-18 | 1 | 2024-11-19 | 17 | 2024-12-06 | 300000 | Completed | 2024-12-06 | 1
165 | FAULTY WARMER HANDLE | ILORIN, OLOFAWAY | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-11-15 | 6 | 2024-11-15 | 0 | 2024-11-18 | 3 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 3 | 2024-11-21 | 0 | 2024-11-21 | 152650 | Completed | 2024-11-21 | 1
166 | FAULTY WARMER HANDLE | LAG, FREEDOMWAY | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-11-12 | 38 | 2024-11-12 | 0 | 2024-12-17 | 35 | 2024-12-18 | 2024-12-18 | 0 | 2024-12-19 | 0 | 2024-12-19 | 1 | 2024-12-20 | 136450 | Completed | 2024-12-20 | 1
167 | FAULTY WARMER HANDLE | LAG, AKOWONJO | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 47300 | Completed | 2024-11-06 | 1
168 | FAULTY WARMER HANDLE | PH, IWOFE | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-11-04 | 1 | 2024-11-04 | 0 | 2024-11-05 | 1 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 135450 | Completed | 2024-11-05 | 1
169 | OPEN CEILING AT BACK OF HOUSE | LAG, AKOWONJO | Wear & Tear | Breakdown | MATOLAD | CEILING BOARD | BUILDING | 2024-11-19 | 3 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 3 | 2024-11-22 | 84000 | Completed | 2024-11-22 | 1
170 | FAULTY CHIPS FRYER MACHINE | LAG, AJAH | Electrical Surge | Breakdown | ADEREMI | OTHERS | OTHERS | 2024-11-29 | 4 | 2024-11-29 | 0 | 2024-11-30 | 1 | 2024-12-03 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-03 |  | Completed | 2024-12-03 | 1
171 | CABINET NOT ATTAINING TEMPERATURE | EDO, SAPELE RD, BENIN | Electrical Surge | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-26 | 36 | 2024-11-26 | 0 | 2024-11-29 | 3 | 2024-11-29 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 33 | 2024-12-23 | 480525 | Completed | 2025-01-01 | 0
172 | PIE EXPRESS OKE AFA CABINET NOT ATTAINING TEMPERATURE | LAG, OKE-AFA | Electrical Surge | Breakdown | KITCHTEC | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-20 | 8 | 2024-11-20 | 0 | 2024-11-27 | 7 | 2024-11-27 | 2024-11-27 | 0 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 71595 | Completed | 2024-11-28 | 1
173 | FREEZER ROOM BREAKDOWN |  | Routine Servicing | Preventive | TONAOGUNS | FREEZER ROOM | HVAC | 2024-11-20 | 16 | 2024-11-21 | 1 | 2024-11-22 | 1 | 2024-11-22 | 2024-11-24 | 2 | 2024-11-25 | 0 | 2024-11-25 | 11 | 2024-12-06 | 200000 | Completed | 2024-12-06 | 1
174 | FREEZER ROOM BREAKDOWN | LAG, OGUDU | Routine Servicing | Preventive | TONAOGUNS | FREEZER ROOM | HVAC | 2024-11-20 | 2 | 2024-11-20 | 0 | 2024-11-22 | 2 | 2024-11-22 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-12-22 | 111125 | Completed | 2024-11-22 | 1
175 | FAULTY WARMER AND SHREDDING MACHINE |  | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-11-24 | 116 | 2024-11-25 | 1 |  | 115 | [9 empty] | Overdue
176 | FAULTY WARMER LID SEAL. | LAG, LEKKI PHASE 1 | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-11-29 | 3 | 2024-11-30 | 1 | 2024-12-02 | 2 | 2024-12-02 | 2024-12-02 | 0 | 2024-12-02 | 0 | 2024-12-02 | 0 | 2024-12-02 | 113950 | Completed | 2024-12-02 | 1
177 | FAULTY WARMER | DELTA, EFFURUN | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-11-17 | 9 | 2024-11-18 | 1 | 2024-11-20 | 2 | 2024-11-26 | 2024-11-26 | 0 | 2024-11-26 | 0 | 2024-11-26 | 0 | 2024-11-26 | 94600 | Completed | 2024-11-26 | 1
178 | FAULTY WARMER | LAG, FREEDOMWAY | Others | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-12-25 | 30 | 2024-11-25 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 |  | Completed | 2024-11-25 | 1
179 | FAULTY CUSTOMER REST ROOM DOOR | LAG, TEJUOSHO | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-11-06 | 134 | 2024-11-07 | 1 |  | 133 | [9 empty] | Overdue
180 | FAULTY TOASTER | AKWA IBOM, IKOT EKPENE RD | Wear & Tear | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2024-11-11 | 39 | 2024-11-11 | 0 | 2024-12-13 | 32 | 2024-12-02 | 2024-12-02 | 0 | 2024-12-05 | 7 | 2024-12-12 | 8 |  |  | Completed | 2024-12-20 | 0
181 | EXTRACTOR NOT WORKING PROPERLY | LAG, CONOIL IKEJA | Corrective Action | Corrective | ABBEY | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2024-11-12 | 34 | 2024-11-12 | 0 | 2024-11-30 | 18 | 2024-11-30 | 2024-11-30 | 0 | 2024-11-30 | 1 | 2024-12-01 | 15 | 2024-12-16 | 370000 | Completed | 2024-12-16 | 1
182 | GAS LEAKAGE | LAG, DIYA STREET | Corrective Action | Corrective | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-11-23 | 9 | 2024-11-23 | 0 | 2024-11-23 | 0 | 2024-11-24 | 2024-11-25 | 1 | 2024-11-25 | 1 | 2024-11-26 | 6 | 2024-12-02 | 123000 | Completed | 2024-12-02 | 1
183 | GAS LEAKAGE | LAG, BADORE | Corrective Action | Corrective | JOEL | GAS HOSE & SUNDRIES | GAS | 2024-11-21 | 4 | 2024-11-21 | 0 | 2024-11-25 | 4 | 2024-11-25 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 |  | Completed | 2024-11-25 | 1
184 | GAS LEAKAGE IN CK | Central Kitchen | Corrective Action | Corrective | BERRADE | OTHERS | OTHERS | 2024-11-20 | 5 | 2024-11-20 | 0 | 2024-11-21 | 1 | 2024-11-21 | 2024-11-23 | 2 | 2024-11-23 | 2 | 2024-11-25 | 0 | 2024-11-25 | 420000 | Completed | 2024-11-25 | 1
185 | CR ASA DAM: FREEZER ROOM AND COLDROOM NOT ATTAINING TEMPERATURE | ILORIN, ASA DAM | Corrective Action | Corrective | TONAOGUNS | OTHERS | OTHERS | 2024-11-18 | 35 | 2024-11-18 | 0 | 2024-12-25 | 37 | 2024-12-04 | 2024-12-09 | 5 | 2024-12-09 | 2 | 2024-12-11 | 12 | 2024-12-04 | 580000 | Completed | 2024-12-23 | 0
186 | FAULTY UNDER-BAR CHILLER AND REPLACEMENT OF COLD ROOM AC FLAP | ABIA, FACTORY RD, ABA | Routine Servicing | Preventive | BCE | OTHERS | OTHERS | 2024-11-13 | 127 | 2024-11-26 | 13 | 2024-12-02 | 6 | 2024-12-02 | 2024-12-02 | 0 | 2024-12-02 | 108 |  |  |  | 540725 | Overdue
187 | GENERATOR DUE FOR SERVICING | LAG, FESTAC | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-10-30 | 15 | 2024-10-30 | 0 | 2024-10-30 | 0 | 2024-10-30 | 2024-10-30 | 0 | 2024-10-30 | 7 | 2024-11-06 | 8 | 2024-11-14 | 193125 | Completed | 2024-11-14 | 1
188 | GENERATOR DUE FOR SERVICING |  | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 |  | Completed | 2024-11-30 | 1
189 | GENERATOR DUE FOR SERVICING | LAG, IKOTUN | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-11-29 | 4 | 2024-11-29 | 0 | 2024-12-03 | 4 | 2024-12-03 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-03 | 193125 | Completed | 2024-12-03 | 1
190 | GENERATOR DUE FOR SERVICING | OGUN, OKE-ILEWO | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-11-28 | 112 | 2024-11-28 | 0 |  | 112 | [9 empty] | Overdue
191 | GENERATOR DUE FOR SERVICING | OGUN, HEYDEN IBAFO | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-19 | 1 | 2024-11-20 | 1 | 2024-11-20 | 0 | [7 empty] | 2024-11-20 |  | Completed | 2024-11-20 | 1
192 | GENERATOR DUE FOR SERVICING | LAG, IDI-IROKO RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-11 | 9 | 2024-11-11 | 0 | 2024-12-19 | 38 | [7 empty] | 2024-11-20 |  | Completed | 2024-11-20 | 1
193 | GENERATOR DUE FOR SERVICING - CR-TAKIE ROAD, OGBPOMOSHO, OYO STATE |  | Routine Servicing | Preventive | KB | GENERATOR | GENERATOR | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 252625 | Completed | 2024-11-18 | 1
194 | BOH UNDERBAR\UPRIGHT CHILLER NOT ATTAINING TEMPERATURE AND BAD LID GASKET | ABUJA, DAWAKI | Routine Servicing | Preventive | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-11-05 | 1 | 2024-11-05 | 0 | 2024-11-06 | 1 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 17200 | Completed | 2024-11-06 | 1
195 | BREAKDOWN OF PH WAREHOUSE GENERATOR |  | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 148350 | Completed | 2024-11-08 | 1
195 | BROKEN TILES | LAG, OMOLE | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-11-10 | 12 | 2024-11-10 | 0 | 2024-11-11 | 1 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 11 | 2024-11-22 | 150000 | Completed | 2024-11-22 | 1
195 | NEED TO CHANGE LID GASKETS FOR PRESSURE FRYER | ABUJA, AMINU KANO | Corrective Action | Corrective | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-11-11 | 3 | 2024-11-11 | 0 | 2024-11-14 | 3 | 2024-11-14 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 249400 | Completed | 2024-11-14 | 1
195 | FAULTY CHIPS FRYER | IMO, WETHERAL RD, OWERRI | Users Misuse | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-11-04 | 1 | 2024-11-05 | 1 | 2024-11-05 | 0 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 94600 | Completed | 2024-11-05 | 1
199 | FAULTY CHIPS FRYER | EDO, UGBOWO, BENIN | Users Misuse | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-11-10 | 4 | 2024-11-11 | 1 | 2024-11-14 | 3 | 2024-11-14 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 124700 | Completed | 2024-11-14 | 1
200 | FAULTY CABINET | IMO, WETHERAL RD, OWERRI | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-02 | 0 | 2024-11-02 | 0 | 2024-11-02 | 0 | 2024-11-02 | 2024-11-02 | 0 | 2024-11-02 | 0 | 2024-11-02 | 0 | 2024-11-02 | 290250 | Completed | 2024-11-02 | 1
201 | FAULTY CABINET | EDO, AIRPORT RD, BENIN | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-08 | 7 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-15 | 2024-11-15 | 0 | 2024-11-15 | 0 | 2024-11-15 | 0 | 2024-11-15 | 30100 | Completed | 2024-11-15 | 1
202 | PPU MIXER | DELTA, SAPELE-WARRI RD | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-11-06 | 2 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 2 | 2024-11-08 | 253700 | Completed | 2024-11-08 | 1
203 | PX GWARIMPA CABINET KNOT | ABUJA, GWARIMPA | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 23650 | Completed | 2024-11-08 | 1
204 | BOH WARMER NOT WORKING | ABUJA, GWARIMPA | Routine Servicing | Preventive | BCE | OTHERS | OTHERS | 2024-11-05 | 3 | 2024-11-05 | 0 | 2024-11-08 | 3 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 154800 | Completed | 2024-11-08 | 1
205 | DOUBLE DOOR CHILLER DOOR MAT REPLACEMENT | PH, OYIGBO | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2024-11-07 | 4 | 2024-11-07 | 0 | 2024-11-08 | 1 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 3 | 2024-11-11 | 120400 | Completed | 2024-11-11 | 1
206 | FAULTY LOBBY AC | LAG, FREEDOMWAY | Routine Servicing | Preventive | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-11-13 | 127 | 2024-11-13 | 0 | 2024-11-13 | 0 | [9 empty] | Overdue
207 | FAULTY TAP HEAD FOR MALE AND FEMALE RESTROOM | LAG, FREEDOMWAY | Others | Breakdown | PRO-EQUIP | TAP | PLUMBING | 2024-11-28 | 112 | 2024-11-28 | 0 |  | 112 | [9 empty] | Overdue
208 | STORE AUDIT FINDINGS | LAG, DIYA STREET | Others | Breakdown | PENTECOSTAL | WASTE BIN HOUSE | BUILDING | 2024-11-19 | 50 | 2024-11-19 | 0 | 2024-12-06 | 17 | 2024-12-06 | 2025-01-06 | 31 | 2025-01-06 | 0 | 2025-01-06 | 2 | 2025-01-08 | 286810 | Completed | 2025-01-08 | 1
209 | COLLECTROMATTRIC MACHINE FAULTY | LAG, FREEDOMWAY | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS
210 | REQUEST FOR SOAP DISPENSER | LAG, EJIGBO | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-11-05 | 135 | 2024-11-05 | 0 |  | 135 | [9 empty] | Overdue
211 | REQUEST FOR SOAP DISPENSER | OGUN, OKE-ILEWO | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-11-10 | 130 | 2024-11-10 | 0 |  | 130 | [9 empty] | Overdue
212 | VEGETABLE CUTTER BLADE | PPU Oniru | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-11-17 | 2 | 2024-11-17 | 0 | 2024-11-19 | 2 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 396567.5 | Completed | 2024-11-19 | 1
213 | FAULTY TILTING PAN | PPU Ajah | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-11-16 | 3 | 2024-11-16 | 0 | 2024-11-19 | 3 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 23650 | Completed | 2024-11-19 | 1
214 | EQUIPMENT STATUS | PPU Ilupeju | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-11-20 | 1 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 1 | 2024-11-21 | 132225 | Completed | 2024-11-21 | 1
215 | FAULTY CHIPS FRYER | IBADAN, OJOO | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 49450 | Completed | 2024-11-04 | 1
216 | CHIPS FRYER MACHINE SHOCKING AGAIN | LAG, JOEL OGUNNAIKE | Electrical Surge | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-11-18 | 2 | 2024-11-18 | 0 | 2024-11-20 | 2 | 2024-11-20 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 23650 | Completed | 2024-11-20 | 1
217 | BOH CHILLER UNEFFECTIVE | LAG, AWOLOWO | Routine Servicing | Preventive | BCE | NBC CHILLER | HVAC | 2024-11-20 | 1 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 1 | 2024-11-21 | 83850 | Completed | 2024-11-21 | 1
218 | FAULTY SIX HEAD MACHINE | LAG, BODE THOMAS | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-11-16 | 4 | 2024-11-16 | 0 | 2024-11-16 | 0 | 2024-11-16 | 2024-11-16 | 0 | 2024-11-16 | 4 | 2024-11-20 | 0 | 2024-11-20 | 17200 | Completed | 2024-11-20 | 1
219 | REQUEST FOR 6HEAD GASKET | LAG, ISAWO-IKORODU | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 118250 | Completed | 2024-11-20 | 1
220 | FOUR HEAD MACHINE LID GASKET BAD | LAG, IKEJA MALL | Corrective Action | Corrective | BCE | OTHERS | OTHERS | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 | 252625 | Completed | 2024-11-27 | 1
221 | REPLACEMENT OF TORN FOOD WARMER DOOR NAT | PH, OYIGBO | Users Misuse | Breakdown | BCE | OTHERS | OTHERS | 2024-11-04 | 1 | 2024-11-04 | 0 | 2024-11-05 | 1 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 104275 | Completed | 2024-11-05 | 1
222 | BOH CHILLER HANDLE | BAYELSA, TOMBIA | Users Misuse | Breakdown | BCE | NBC CHILLER | HVAC | 2024-11-06 | 4 | 2024-11-06 | 0 | 2024-11-10 | 4 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 49450 | Completed | 2024-11-10 | 1
223 | BOH CHILLER NOT ATTAINING TEMPERATURE | LAG, ONIRU | Users Misuse | Breakdown | BCE | NBC CHILLER | HVAC | 2024-11-01 | 7 | 2024-11-01 | 0 | 2024-11-08 | 7 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 118250 | Completed | 2024-11-08 | 1
224 | DISPLAY CABINET NOT COMING UP | BAYELSA, TOMBIA | Users Misuse | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-05 | 5 | 2024-11-05 | 0 | 2024-11-10 | 5 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 36500 | Completed | 2024-11-10 | 1
225 | ROTISSERIES MACHINE NOT HEATING PROPERLY | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-11-08 | 3 | 2024-11-11 | 3 | 2024-11-11 | 0 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 337550 | Completed | 2024-11-11 | 1
226 | FAULTY TOASTER MACHINE KNOB | LAG, JOEL OGUNNAIKE | Users Misuse | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2024-11-05 | 1 | 2024-11-05 | 0 | 2024-11-06 | 1 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 86000 | Completed | 2024-11-06 | 1
227 | MAINTENANCE ISSUES IN THE STORE. | OGUN, OKE-ILEWO | Others | Breakdown | RANEX | OTHERS | OTHERS | 2024-11-26 | 6 | 2024-11-26 | 0 | 2024-11-28 | 2 | 2024-11-29 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 3 | 2024-12-02 | 116637.5 | Completed | 2024-12-02 | 1
228 | FAU.LTY DICING MACHINE |  | Wear & Tear | Breakdown | BCE | DICING MACHINE | KITCHEN_EQUIPMENT | 2024-11-08 | 132 | 2024-11-08 | 0 | 2024-11-09 | 1 | [9 empty] | Overdue
229 | FAULTY ICE CREAM MACHINE |  | Routine Servicing | Preventive | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-25 | 115 | 2024-11-25 | 0 | 2024-11-26 | 1 | 2024-12-09 | 2024-12-09 | 0 | 2024-12-09 | 101 |  |  |  |  | Overdue
230 | FAULTY CHIPS FRYER MECHINE (CR LIMCA RD) | ANAMBRA, LIMCA RD, ONITSHA | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-11-04 | 5 | 2024-11-04 | 0 | 2024-11-09 | 5 | 2024-11-09 | 2024-11-09 | 0 | 2024-11-09 | 0 | 2024-11-09 | 0 | 2024-11-09 | 115025 | Completed | 2024-11-09 | 1
231 | FAULTY CHIPS FRYER | IBADAN, OJOO | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 49450 | Completed | 2024-11-04 | 1
232 | FAULTY CHIPS FRYER BREAKER (LEKKI PHASE 1) | LAG, LEKKI PHASE 1 | Users Misuse | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-11-09 | 11 | 2024-11-10 | 1 | 2024-11-20 | 10 | 2024-11-20 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 23650 | Completed | 2024-11-20 | 1
233 | FAULTY CHIPS FRYER | LAG, AKOWONJO | Wear & Tear | Breakdown | HEFHEM
234 | AIR CONDITIONERS NOT FUNCTIONING | PH, ABACHA RD | Others | Breakdown | MOFFEEN | 5HP STANDING AC UNIT 2 | HVAC | 2024-11-01 | 139 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 139 |  |  | Overdue
235 | PX IGANDO FADED SIGNAGE
236 | GENERATOR DUE FOR SERVICING | IBADAN, AKOBO | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-17 | 3 | 2024-11-17 | 0 | 2024-11-19 | 2 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 1 | 2024-11-20 | 202450 | Completed | 2024-11-20 | 1
237 | GENERATOR DUE FOR SERVICING | LAG, AWOLOWO | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-17 | 3 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 1 | 2024-11-20 | 237160 | Completed | 2024-11-20 | 1
238 | GENERATOR DUE FOR SERVICING | IBADAN, IDI-APE (IWO RD) | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-17 | 3 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 1 | 2024-11-20 | 202450 | Completed | 2024-11-20 | 1
239 | GENERATOR DUE FOR SERIVICING | LAG, BADORE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-17 | 2 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 181700 | Completed | 2024-11-19 | 1
240 | GENERATOR BREAKDOWN | EDO, RAHMAT PARK, BENIN | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-11-18 | 3 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 1 | 2024-11-19 | 2 | 2024-11-21 | 717350 | Completed | 2024-11-21 | 1
241 | GENERATOR CHECK | OGUN, HEYDEN IBAFO | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-18 | 4 | 2024-11-19 | 1 | 2024-11-19 | 0 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 3 | 2024-11-22 |  | Completed | 2024-11-22 | 1
242 | GENERATOR DUE FOR SERVICE | LAG, FREEDOMWAY | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-20 | 120 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 120 |  |  | Overdue
243 | GENERATOR BATTERY DOWN | LAG, OGUNLANA DRIVE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-20 | 4 | 2024-11-20 | 0 | 2024-11-24 | 4 | 2024-11-24 | 2024-11-24 | 0 | 2024-11-24 | 0 | 2024-11-24 | 0 | 2024-11-24 | 181750 | Completed | 2024-11-24 | 1
244 | Generator servicing | PH, GRA BIRABI | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-20 | 120 | 2024-11-20 | 0 | 2024-11-22 | 2 | [9 empty] | Overdue
245 | GENERATOR DUE FOR SERVICING | PH, UST | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-18 | 122 | 2024-11-20 | 2 |  | 120 | [9 empty] | Overdue
246 | REQUEST FOR GENERATOR SERVICING | AKWA IBOM, NWANIBA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-19 | 64 | 2024-11-20 | 1 | 2024-11-20 | 0 | 2024-11-20 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 63 | 2025-01-22 | 237160 | Completed | 2025-01-22 | 1
247 | GENERATOR SERVICING | LAG, AJOSE ADEOGUN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-22 | 5 | 2024-11-22 | 0 | 2024-11-27 | 5 | 2024-11-27 | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 | 181700 | Completed | 2024-11-27 | 1
248 | GENERATOR TRIP OFF EVERY 30MUNITES | LAG, LEKKI PHASE 1 | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 150000 | Completed | 2024-11-22 | 1
249 | GENERATOR DUE FOR SERVICING | LAG, AJAH | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-25 | 2 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 | 2 | 2024-11-27 | 181700 | Completed | 2024-11-27 | 1
250 | GENERATOR BREAKDOWN | IMO, WETHERAL RD, OWERRI | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-11-25 | 15 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-12-10 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 | 202450 | Completed | 2024-12-10 | 1
251 | DIESE SPILLAGE | LAG, AWOLOWO | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-11-11 | 15 | 2024-11-13 | 2 | 2024-11-25 | 12 | 2024-11-25 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 | 1 | 2024-11-26 | 237160 | Completed | 2024-11-26 | 1
252 | Generator Service Request_.xlsx | IMO, IKENEGBU, OWERRI | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-28 | 4 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 4 | 2024-12-02 | 202450 | Completed | 2024-12-02 | 1
253 | GENERATOR SERVCING | EDO, SAPELE RD, BENIN | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-11-29 | 3 | 2024-11-29 | 0 | 2024-11-30 | 1 | 2024-11-30 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 2 | 2024-12-02 | 322450 | Completed | 2024-12-02 | 1
254 | SERVICING OF PPU UYO GENERATOR |  | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-29 | 3 | 2024-11-29 | 0 | 2024-11-30 | 1 | 2024-11-30 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 2 | 2024-12-02 |  | Completed | 2024-12-02 | 1
255 | SERVICING OF GENERATOR | AKWA IBOM, AKA RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-29 | 3 | 2024-11-29 | 0 | 2024-11-30 | 1 | 2024-11-30 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 2 | 2024-12-02 | 202450 | Completed | 2024-12-02 | 1
256 | AFIKPO road Generator Service Request.xlsx | EBONYI, AFIKPO, ABAKALIKI | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-28 | 4 | 2024-11-29 | 1 | 2024-11-30 | 1 | 2024-11-30 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 2 | 2024-12-02 | 202450 | Completed | 2024-12-02 | 1
257 | GENERATOR DUE FOR SERVICE AND CHANGE OF LIFT PUMP | LAG, OSOLOWAY | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-28 | 4 | 2024-11-29 | 1 | 2024-11-30 | 1 | 2024-11-30 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 2 | 2024-12-02 |  | Completed | 2024-12-02 | 1
258 | GENERATOR SERVICE | LAG, ONIRU | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-30 | 2 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 2 | 2024-12-02 | 114250 | Completed | 2024-12-02 | 1
259 | GENERATOR DUE FOR SERVICING |  | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-30 | 2 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 2 | 2024-12-02 |  | Completed | 2024-12-02 | 1
260 | STATE OF EMERGENCY: GENERATOR NOT COMING ON | LAG, MARINA | Others | Breakdown | MIDTECH | GENERATOR | GENERATOR | 2024-11-27 | 1 | 2024-11-27 | 0 | 2024-11-28 | 1 | 2024-11-28 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 193125 | Completed | 2024-11-28 | 1
261 | GENERATOR DUE FOR SERVICING | ILORIN, TAIWO RD | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-11-28 | 112 | 2024-11-28 | 0 |  | 112 | [9 empty] | Overdue
262 | Servicing Of Generator | IBADAN, MOKOLA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-11-14 | 5 | 2024-11-16 | 2 | 2024-11-17 | 1 | 2024-11-17 | 2024-11-17 | 0 | 2024-11-17 | 2024-11-17 | 2024-11-17 | 2 | 2024-11-19 | 130375 | Completed | 2024-11-19 | 1
263 | QUOTATION FOR COMPLETE OVERHAULING | ILORIN, ASA DAM | Corrective Action | Corrective | MIDTECH | GENERATOR | GENERATOR | 2024-11-05 | 17 | 2024-11-06 | 1 | 2024-11-06 | 0 | 2024-11-18 | 2024-11-19 | 1 | 2024-11-19 | 3 | 2024-11-22 | 0 | 2024-11-22 | 104267.5 | Completed | 2024-11-22 | 1
264 | STATE OF EMERGENCY: GENERATOR NOT COMING ON(Fuel in water, Marina) | LAG, MARINA | Others | Breakdown | DAMI FORTE | GENERATOR | GENERATOR | 2024-11-28 | 6 | 2024-11-29 | 1 | 2024-11-29 | 0 | 2024-11-29 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 5 | 2024-12-04 | 365500 | Completed | 2024-12-04 | 1
265 | GENERATOR BREAKDOWN | ILORIN, GRA | Others | Breakdown | MID TECH | GENERATOR | GENERATOR | 2024-11-17 | 7 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-17 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-17 | 7 | 2024-11-24 |  | Completed | 2024-11-24 | 1
266 | GENERATOR DUE FOR SERVICING | LAG, MAGODO | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-11-10 | 5 | 2024-11-10 | 0 | 2024-11-15 | 5 | 2024-11-15 | 2024-11-15 | 0 | 2024-11-15 | 0 | 2024-11-15 | 0 | 2024-11-15 | 37625 | Completed | 2024-11-15 | 1
267 | GENERATOR DUE FOR SERVICING | LAG, IKORODU | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-11-19 | 1 | 2024-11-20 | 1 | 2024-11-20 | 0 | 2024-11-20 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 193125 | Completed | 2024-11-20 | 1
268 | GENERATOR DUE FOR SERVICES | LAG, OKE-AFA | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-11-18 | 3 | 2024-11-18 | 0 | 2024-11-21 | 3 | 2024-11-21 | 2024-11-21 | 0 | 2024-11-21 | 0 | 2024-11-21 | 0 | 2024-11-21 | 208125 | Completed | 2024-11-21 | 1
269 | GENERATOR DRIPPING OIL | ILORIN, TAIWO RD | Others | Breakdown | MID TECH | GENERATOR | GENERATOR | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 |  | Completed | 2024-11-22 | 1
270 | GENERATOR DUE FOR SERVICING | OSUN, GBONGAN | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-11-24 | 116 | 2024-11-25 | 1 |  | 115 | [9 empty] | Overdue
271 | GENERATOR DUE FOR SERVICE. | IBADAN, MOKOLA | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-11-27 | -19 | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 | 2024-11-27 | 0 | 2024-11-28 | 1 | 2024-11-29 | -21 | 2024-11-08 | 242500 | Completed | 2024-11-08 | 1
272 | GENERATOR DUE FOR SERVICE | LAG, MARINA | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2024-11-27 | 1 | 2024-11-27 | 0 | 2024-11-28 | 1 | 2024-11-28 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 193125 | Completed | 2024-11-28 | 1
273 | BROKEN TAP AT COOK SECTION | LAG, BADORE | Wear & Tear | Breakdown | JOEL | TAP | PLUMBING | 2024-11-06 | 2 | 2024-11-07 | 1 | 2024-11-08 | 1 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 |  | Completed | 2024-11-08 | 1
274 | BROKEN WALL TILES IN THE STORE | LAG, DIYA STREET | Wear & Tear | Breakdown | ARIZMAYAN | WALL | BUILDING | 2024-11-11 | 32 | 2024-11-11 | 0 | 2024-11-26 | 15 | 2024-12-08 | 2024-12-10 | 2 | 2024-12-10 | 2 | 2024-12-12 | 1 | 2024-12-13 | 135000 | Completed | 2024-12-13 | 1
275 | FREEZER ROOM NOT COMING UP | LAG, MAGODO | Wear & Tear | Breakdown | TRIPPLE O | FREEZER ROOM | HVAC | 2024-11-01 | 17 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 17 | 2024-11-14 | 360125 | Completed | 2024-11-18 | 0
276 | DAMAGED PASTRY RACK | LAG, ABULE EGBA | Users Misuse | Breakdown | LAMB TECH | OTHERS | OTHERS | 2024-11-01 | 139 | 2024-11-01 | 0 | 2024-11-21 | 20 | 2024-11-21 |  | 119 | [6 empty] | Overdue
277 | LEAKING DIESEL PIPE | LAG, HEYDEN IPAJA | Wear & Tear | Breakdown | DAMI FOTE | GENERATOR | GENERATOR | 2024-11-01 | 139 | 2024-11-01 | 0 | 2024-11-02 | 1 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 121 |  |  | Overdue
278 | DAMAGED TAP | LAG, ABULE EGBA | Wear & Tear | Breakdown | PROPEAR JEFF | TAP | PLUMBING | 2024-11-01 | 32 | 2024-11-01 | 0 | 2024-11-02 | 1 | 2024-11-02 | 2024-11-02 | 0 | 2024-11-02 | 0 | 2024-11-02 | 31 | 2024-12-03 | 70412.5 | Completed | 2024-12-03 | 1
279 | CRACKED TILES IN THE STORES SIGNAGE | PH, ABACHA RD | Wear & Tear | Breakdown | GLUFFSCO | OTHERS | OTHERS | 2024-11-01 | 139 | 2024-11-01 | 0 | 2024-11-04 | 3 | 2024-11-04 |  | 136 | [6 empty] | Overdue
280 | FREEZER NOT WORKING | LAG, ALIMOSHO | Wear & Tear | Breakdown | DYNAMITE | FREEZER ROOM | HVAC | 2024-11-01 | 1 | 2024-11-01 | 0 | 2024-11-02 | 1 | 2024-11-02 | 2024-11-02 | 0 | 2024-11-02 | 0 | 2024-11-02 | 0 | 2024-11-02 | 134371 | Completed | 2024-11-02 | 1
281 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | LAG, OKOTA | Wear & Tear | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-12 | 128 | 2024-11-12 | 0 | 2024-11-21 | 9 | 2024-11-25 |  | 115 | [6 empty] | Overdue
282 | REPLACEMENT OF PRESSURE FRYER GASKET LID | LAG, HEYDEN IPAJA | Wear & Tear | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2024-11-02 | 8 | 2024-11-02 | 0 | 2024-11-08 | 6 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 2 | 2024-11-10 | 231000 | Completed | 2024-11-10 | 1
283 | GENERATOR DUE FOR SERVICE | LAG, OKOTA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-11-04 | 3 | 2024-11-04 | 0 | 2024-11-07 | 3 | 2024-11-07 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 193125 | Completed | 2024-11-07 | 1
284 | GENERATOR SERVICING | PPU Ajah | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR
285 | GENERATOR DUE FOR SERVICING | LAG, OMOLE | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-11-07 | 2 | 2024-11-07 | 0 | 2024-11-08 | 1 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 1 | 2024-11-08 | 193125 | Completed | 2024-11-09 | 0
286 | BLOWN OUTDOOR FAN FOR FREEZER ROOM | LAG, AJAH | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-11-04 | 11 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 2024-11-05 | 1 | 2024-11-05 | 0 | 2024-11-05 | 10 | 2024-11-15 | 350000 | Completed | 2024-11-15 | 1
287 | FIXING OF PEELED TABLES AND THE LEGS OF THE DIRTY CHAIRS | OSUN, GBONGAN | Wear & Tear | Breakdown | REVELATION | CUSTOMER TABLE | FURNITURE | 2024-11-07 | 133 | 2024-11-07 | 0 | 2024-11-26 | 19 | [9 empty] | Overdue
288 | FAULTY COOK AREA TAP | LAG, ABULE EGBA | Wear & Tear | Breakdown | PROPEAR JEFF | TAP | PLUMBING | 2024-11-01 | 32 | 2024-11-01 | 0 | 2024-11-02 | 1 | 2024-11-02 | 2024-11-02 | 0 | 2024-11-02 | 0 | 2024-11-02 | 31 | 2024-12-03 | 70412.5 | Completed | 2024-12-03 | 1
289 | AWOLOWO 1 MAINTENANCE ISSUES | LAG, AWOLOWO | Wear & Tear | Breakdown | MATOLAD | CUSTOMER TABLE | FURNITURE | 2024-11-05 | 2 | 2024-11-05 | 0 | 2024-11-06 | 1 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 1 | 2024-11-07 | 220000 | Completed | 2024-11-07 | 1
290 | Washing Of FOH facade wall tiles and roller shutter | LAG, OSOLOWAY | Routine Servicing | Preventive | PENTECOSTAL | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-11-02 | 10 | 2024-11-02 | 0 | 2024-11-11 | 9 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 1 | 2024-11-12 | 224675 | Completed | 2024-11-12 | 1
291 | BROKEN TILES AT CK VERANDAH AND WALKWAY | PPU Ilupeju | Others | Breakdown | ACORN | WALL | BUILDING | 2024-10-29 | 17 | 2024-11-01 | 3 | 2024-11-03 | 2 | 2024-11-03 | 2024-11-08 | 5 | 2024-11-09 | 0 | 2024-11-09 | 6 | 2024-11-15 | 1050000 | Completed | 2024-11-15 | 1
292 | BACK YARD SECURITY LIGHT IS FAULTY | LAG, FREEDOMWAY | Wear & Tear | Breakdown | ISMAIL | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-11-01 | 48 | 2024-11-01 | 0 | 2024-11-19 | 18 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 30 | 2024-11-19 |  | Completed | 2024-12-19 | 0
293 | CORRODED WALLS IN DRY STORE, MANAGERS OFFICE AND BACK OF HOUSE | LAG, OMOLE | Wear & Tear | Breakdown | ARIZMAYAN | WALL | BUILDING | 2024-11-05 | 15 | 2024-11-05 | 0 | 2024-11-08 | 3 | 2024-11-09 | 2024-11-10 | 1 | 2024-11-11 | 1 | 2024-11-12 | 8 | 2024-11-20 | 300000 | Completed | 2024-11-20 | 1
294 | Damage sink | LAG, MOBIL OGBA | Wear & Tear | Breakdown | PROEQUIP | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-02 | 3 | 2024-11-02 | 0 | 2024-11-02 | 0 | 2024-11-03 | 2024-11-03 | 0 | 2024-11-03 | 0 | 2024-11-03 | 2 | 2024-11-05 | 132250 | Completed | 2024-11-05 | 1
295 | FAULTY ICE CREAM MACHINE | LAG, OPEBI | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-02 | 3 | 2024-11-02 | 0 | 2024-11-04 | 2 | 2024-12-04 | 2024-12-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 1 | 2024-11-05 |  | Completed | 2024-11-05 | 1
296 | FAULTY ICE CREAM MACHINE | IBADAN, CHALLENGE | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-01 | 2 | 2024-11-01 | 0 | 2024-11-02 | 1 | 2024-11-02 | 2024-11-02 | 0 | 2024-11-02 | 0 | 2024-11-02 | 1 | 2024-11-03 |  | Completed | 2024-11-03 | 1
297 | FAULTY ICE CREAM MACHINE | PH, IWOFE | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-01 | 5 | 2024-11-03 | 2 | 2024-11-05 | 2 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 1 | 2024-11-06 | 1059364.66 | Completed | 2024-11-06 | 1
298 | FAULTY ICE CREAM MACHINE | AKWA IBOM, IKOT EKPENE RD | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-04 | 2 | 2024-11-04 | 0 | 2024-11-05 | 1 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 1 | 2024-11-06 |  | Completed | 2024-11-06 | 1
299 | FAULTY ICE CREAM MACHINE[SPACEMAN] | AKWA IBOM, NWANIBA | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-01 | 5 | 2024-11-04 | 3 | 2024-11-05 | 1 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 1 | 2024-11-06 |  | Completed | 2024-11-06 | 1
300 | FAULTY ICE CREAM MACHINE | LAG, AKOWONJO | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-06 | 36 | 2024-11-06 | 0 | 2024-11-11 | 5 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 1 | 2024-11-12 | 30 | 2024-12-12 | 590603.37 | Completed | 2024-12-12 | 1
301 | FAULTY ICE CREAM MACHINE SCRAPPER BLADE | PH, OMOKU | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-06 | 7 | 2024-11-07 | 1 | 2024-11-11 | 4 | 2024-11-11 | 2024-12-11 | 30 | 2024-11-11 | 1 | 2024-11-12 | 1 | 2024-11-13 |  | Completed | 2024-11-13 | 1
302 | FAULTY ICE CREAM MACHINE | LAG, VGC | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-18 | 2 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 1 | 2024-11-19 | 1 | 2024-11-20 |  | Completed | 2024-11-20 | 1
303 | FAULTY ICE CREAM MACHINE | LAG, DOMINO E-CENTRE | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-21 | 32 | 2024-11-21 | 0 | 2024-11-21 | 0 | 2024-11-22 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 31 | 2024-11-22 | 168154.92 | Completed | 2024-12-23 | 0
304 | FAULTY ICE CREAM MACHINE | LAG, NNPC ALAPERE | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-21 | 32 | 2024-11-21 | 0 | 2024-11-22 | 1 | 2024-11-22 | 2024-11-22 | 0 | 2024-11-22 | 1 | 2024-11-23 | 30 | 2024-12-23 |  | Completed | 2024-12-23 | 1
305 | FAULTY ICE CREAM MACHINE | LAG, ONIRU | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-24 | 1 | 2024-11-24 | 0 | 2024-11-25 | 1 | 2024-11-25 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 |  | Completed | 2024-11-25 | 1
306 | FAULTY ICE CREAM MACHINE | IBADAN, IDI-APE (IWO RD) | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-25 | 18 | 2024-11-25 | 0 | 2024-11-26 | 1 | 2024-12-03 | 2024-12-03 | 0 | 2024-12-09 | 0 | 2024-12-09 | 4 | 2024-12-09 | 42571.51 | Completed | 2024-12-13 | 0
307 | DEAD BULB IN STORE SIGNAGE | LAG, JIBOWU | Wear & Tear | Breakdown | ARIZMANYA | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-11-03 | 137 | 2024-11-04 | 1 | 2024-11-10 | 6 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-11 | 129 |  |  |  |  | Overdue
308 | Damaged letter signage | LAG, EJIGBO | Wear & Tear | Breakdown | ARIZMANYA | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-11-06 | 134 | 2024-11-06 | 0 | 2024-11-10 | 4 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-11 | 21 | 2024-12-02 | 108 |  | 380000 | Overdue
309 | RUSTED DRY STORE RACK, FREEZER ROOM DOOR, CHILLER RACK AND OPS ALERT HOLDER | LAG, ILUPEJU | Wear & Tear | Breakdown | ARIZMANYA | OTHERS | OTHERS | 2024-11-04 | 21 | 2024-11-04 | 0 | 2024-11-10 | 6 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-11 | 1 | 2024-11-12 | 13 | 2024-11-25 | 250000 | Completed | 2024-11-25 | 1
310 | RUST STAIR CASE HANDLE | LAG, OSOLOWAY | Wear & Tear | Breakdown | ARIZMANYA | OTHERS | OTHERS | 2024-11-04 | 136 | 2024-11-04 | 0 | 2024-11-10 | 6 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-11 | 129 |  |  |  | 150000 | Overdue
311 | OPEN ROOF AT THE GENERATOR HOUSE | LAG, OPEBI | Others | Breakdown | ARIZMANYA | ROOF | BUILDING | 2024-11-04 | 13 | 2024-11-04 | 0 | 2024-11-10 | 6 | 2024-11-10 | 2024-11-11 | 1 | 2024-11-11 | 0 | 2024-11-11 | 6 | 2024-11-17 | 150000 | Completed | 2024-11-17 | 1
312 | BROKEN / CRACKRED WALL TILES | LAG, ONIRU | Others | Breakdown | ARIZMANYA | WALL | BUILDING | 2024-11-05 | 135 | 2024-11-05 | 0 | 2024-11-10 | 5 | [8 empty] | 280000 | Overdue
313 | REQUEST TO LEVEL CAR PARK ENTRANCE | LAG, ONIRU | Corrective Action | Corrective | PENTECOSTAL | OTHERS | OTHERS | 2024-11-11 | 16 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-12 | 2024-11-13 | 1 | 2024-11-14 | 12 | 2024-11-26 | 1 | 2024-11-27 | 170000 | Completed | 2024-11-27 | 1
314 | Supply and installation of visitor toilet door at Chicken Republic NNPC Alapere | LAG, NNPC ALAPERE | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-11-01 | 26 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-13 | 2024-11-14 | 1 | 2024-11-14 | 0 | 2024-11-14 | 13 | 2024-11-27 | 330000 | Completed | 2024-11-27 | 1
315 | FREEZER ROOM LEAKING WATER & PEELED TILES | OSUN, GBONGAN | Wear & Tear | Breakdown | DEACONESS TAIWO | FREEZER ROOM | HVAC | 2024-11-03 | 137 | 2024-11-04 | 1 | 2024-11-13 | 9 | 2024-11-14 |  | 126 | [5 empty] | 750000 | Overdue
316 | FALLEN AIR CURTAIN | ABIA, OGBOR HILLS | Wear & Tear | Breakdown | EKNOR | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2024-11-30 | 110 | 2024-12-01 | 1 | 2024-12-15 | 14 | 2024-12-16 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 94 |  | 268255.5 | Overdue
317 | RAT MENACE AT CR ENTOURAGE MALL | LAG, ENTOURAGE MALL | Others | Breakdown | VENYS | OTHERS | OTHERS | 2024-11-06 | 134 | 2024-11-06 | 0 | 2024-11-09 | 3 | 2024-11-12 | 2024-11-19 | 7 | 2024-11-19 | 0 | 2024-11-19 | 121 |  | 150000 | Overdue
318 | REQUEST FOR THE DEMOLITION OF LOBBY PARTITION | LAG, MARINA | Others | Breakdown | ACORN | WALL | BUILDING | 2024-11-13 | 15 | 2024-11-14 | 1 | 2024-11-15 | 1 | 2024-11-15 | 2024-11-15 | 0 | 2024-11-16 | 9 | 2024-11-25 | 3 | 2024-11-28 | 155552.5 | Completed | 2024-11-28 | 1
38 | FREEZER ROOM AND COLD ROOM NOT ATTAINING TEMPERATURE | OSUN, AYETORO | Routine Servicing | Preventive | TONAOGUNS | FREEZER ROOM | HVAC | 2024-11-06 | 134 | 2024-11-07 | 1 | 2024-11-16 | 9 | 2024-11-16 | 2024-11-16 | 0 | [5 empty] | 520000 | Overdue
320 | FREEZER ROOM NOT WORKING | ILORIN, TAIWO RD | Wear & Tear | Breakdown | TONAOGUNS | FREEZER ROOM | HVAC | 2024-11-09 | 131 | 2024-11-09 | 0 | 2024-11-11 | 2 | 2024-11-11 | 2024-11-18 | 7 | 2024-11-18 | 122 |  |  |  | 390000 | Overdue
321 | FREEZER ROOM NOT WORKING | OGUN, OKE-ILEWO | Wear & Tear | Breakdown | DYNAMITE | FREEZER ROOM | HVAC | 2024-11-04 | 6 | 2024-11-04 | 0 | 2024-11-07 | 3 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 |  | Completed | 2024-11-10 | 1
322 | FREEZER ROOM NOT WORKING | LAG, AJAH | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-11-04 | 11 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 2024-11-05 | 1 | 2024-11-05 | 0 | 2024-11-05 | 10 | 2024-11-15 | 350000 | Completed | 2024-11-15 | 1
323 | AWKA ROAD FREEZER ROOM NOT WORKING | ANAMBRA, AWKA RD, ONITSHA | Routine Servicing | Preventive | MOFEEN | FREEZER ROOM | HVAC | 2024-11-09 | 131 | 2024-11-10 | 1 | 2024-11-12 | 2 | 2024-11-12 | 2024-11-12 | 0 | [5 empty] | 98000 | Overdue
324 | FREEZER ROOM NOT WORKING. | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-11-14 | 1 | 2024-11-14 | 0 | 2024-11-15 | 1 | 2024-11-15 | 2024-11-15 | 0 | 2024-11-15 | 0 | 2024-11-15 | 0 | 2024-11-15 | 123125 | Completed | 2024-11-15 | 1
325 | FREEZER ROOM NOT WORKING | OGUN, OKE-ILEWO | Wear & Tear | Breakdown | DYNAMITE | FREEZER ROOM | HVAC | 2024-11-14 | 4 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 |  | Completed | 2024-11-18 | 1
326 | PEALED EATING AREA WALL | LAG, HEYDEN IPAJA | Wear & Tear | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-11-12 | 128 | 2024-11-12 | 0 | 2024-11-17 | 5 | 2024-11-17 | 2024-11-18 | 1 | 2024-11-18 | 122 |  |  |  | 320000 | Overdue
327 | FADED PYLON | LAG, IKORODU | Wear & Tear | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-11-12 | 10 | 2024-11-12 | 0 | 2024-11-17 | 5 | 2024-11-17 | 2024-11-18 | 1 | 2024-11-18 | 1 | 2024-11-19 | 3 | 2024-11-22 | 190000 | Completed | 2024-11-22 | 1
328 | EVACUATION AND EXCAVATION OF SEWAGE | LAG, FESTAC | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 350000 | Completed | 2024-11-18 | 1
329 | WATER DRIPPING FROM THE MALE STAFF REST ROOM. | LAG, ALIMOSHO | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-11-13 | 127 | 2024-11-14 | 1 | 2024-11-16 | 2 | 2024-11-16 | 2024-11-18 | 2 | 2024-11-18 | 122 |  |  |  |  | Overdue
330 | DIRTY STORE ENTRANCE TILES AND COCK HEAD SIGNAGE | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-11-01 | 139 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 2024-11-18 | 17 | 2024-11-18 | 122 |  |  |  | 185000 | Overdue
331 | REQUEST FOR PROFESSIONAL CLEANER TO ERADICATE ALGAE IN THE STORE PREMISES | LAG, AWOLOWO 2 | Corrective Action | Corrective | PENTECOSTAL | WALL | BUILDING | 2024-11-06 | 134 | 2024-11-06 | 0 | 2024-11-07 | 1 | 2024-11-07 | 2024-11-18 | 11 | 2024-11-18 | 122 |  |  |  |  | Overdue
332 | Roller shutter key broken |  | Users Misuse | Breakdown | VENYS | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-11-07 | 133 | 2024-11-07 | 0 | 2024-11-19 | 12 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 121 |  |  |  | 87000 | Overdue
333 | NEW INVERTER NEEDED | ILORIN, TAIWO RD | Wear & Tear | Breakdown | NISTECH | INVERTER SYSTEM | INVERTER | 2024-11-04 | 49 | 2024-11-04 | 0 | 2024-11-07 | 3 | 2024-11-07 | 2024-11-19 | 12 | 2024-11-19 | 28 | 2024-12-17 | 6 | 2024-12-19 | 1032000 | Completed | 2024-12-23 | 0
334 | SIGNAGE ILLUMINATION AND BROKEN SIGNAGE | LAG, SKYMALL | Wear & Tear | Breakdown | ARIZMANYA | OTHERS | OTHERS | 2024-11-04 | 136 | 2024-11-04 | 0 | 2024-11-20 | 16 | 2024-11-20 | 2024-11-21 | 1 | 2024-11-21 | 119 |  |  |  |  | Overdue
335 | COL ROOM NOT WORKING | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-11-06 | 19 | 2024-11-06 | 0 | 2024-11-20 | 14 | 2024-11-20 | 2024-11-23 | 3 | 2024-11-23 | 2 | 2024-11-25 | 0 | 2024-11-25 | 111437.5 | Completed | 2024-11-25 | 1
336 | COLD ROOM NOT WORKING | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-11-23 | 117 | 2024-11-25 | 2 | 2024-11-25 | 0 | [9 empty] | Overdue
337 | BLOCKED DRAINAGE | LAG, ABULE EGBA | Others | Breakdown | PENTECOSTAL | DRAIN COVER | BUILDING | 2024-11-19 | 5 | 2024-11-22 | 3 | 2024-11-22 | 0 | 2024-11-22 | 2024-11-23 | 1 | 2024-11-23 | 1 | 2024-11-24 | 0 | 2024-11-24 | 2024-11-24 | Completed | 2024-11-24 | 1
338 | BLOCKED DRAINAGE AT THE BACK OF HOUSE WASH AREA | LAG, OPEBI | Others | Breakdown | PENTECOSTAL | DRAIN COVER | BUILDING | 2024-11-03 | 2 | 2024-11-03 | 0 | 2024-11-05 | 2 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 108775 | Completed | 2024-11-05 | 1
340 | BLOCKED DRAINAGE | LAG, OSOLOWAY | Others | Breakdown | OLUWATOSIN OLATUNDE | DRAIN COVER | BUILDING | 2024-11-07 | 1 | 2024-11-08 | 1 | 2024-11-08 | 0 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 |  | Completed | 2024-11-08 | 1
341 | BLOCKED DRAINAGE | LAG, FREEDOMWAY | Others | Breakdown | JOEL OMOTOSHO | DRAIN COVER | BUILDING | 2024-11-26 | 0 | 2024-11-26 | 0 | 2024-11-26 | 0 | 2024-11-26 | 2024-11-26 | 0 | 2024-11-26 | 0 | 2024-11-26 | 0 | 2024-11-26 |  | Completed | 2024-11-26 | 1
342 | CRACKED WALL IN THE CUSTOMER RESTROOM | LAG, ABULE EGBA | Wear & Tear | Breakdown | PENTECOSTAL | WALL | BUILDING | 2024-11-05 | 19 | 2024-11-05 | 0 | 2024-11-21 | 16 | 2024-11-21 | 2024-11-23 | 2 | 2024-11-23 | 1 | 2024-11-24 | 0 | 2024-11-24 | 86000 | Completed | 2024-11-24 | 1
343 | DAMAGE TO ALUMINUM BOARD AT THE FOH | LAG, ABULE EGBA | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-11-13 | 127 | 2024-11-13 | 0 | 2024-11-21 | 8 | 2024-11-21 | 2024-11-23 | 2 | 2024-11-23 | 117 |  |  |  |  | Overdue
344 | LEAKING AERATION TANK, SAND AND CARBON MEDIA - CR IKOT EKPENE | AKWA IBOM, IKOT EKPENE RD | Wear & Tear | Breakdown | SAPAT | AERATION TANK | WTP | 2024-11-11 | 37 | 2024-11-11 | 0 | 2024-11-18 | 7 | 2024-11-18 | 2024-11-25 | 7 | 2024-11-25 | 0 | 2024-11-25 | 23 | 2024-12-18 | 600000 | Completed | 2024-12-18 | 1
345 | EVACUATION OF SEPTIC TANK | LAG, NNPC ALAPERE | Others | Breakdown | CHRIS OWOLABI | SEPTIC TANK | EVACUATION | 2024-11-02 | 138 | 2024-11-02 | 0 | 2024-11-02 | 0 | 2024-11-02 | 2024-11-02 | 0 | 2024-11-02 | 0 | 2024-11-02 | 138 | 2024-11-02 |  | Overdue
346 | COLD ROOM IS NOT ATTAINING TEMPERATURE | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-11-19 | 121 | 2024-11-19 | 0 | 2024-11-25 | 6 | 2024-11-25 | 2024-11-25 | 0 | 2024-11-25 | 115 |  |  |  | 250000 | Overdue
347 | COLD ROOM IS NOT ATTAINING TEMPERATURE | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-11-25 | 115 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 | 2024-11-25 | 0 | 2024-11-25 | 115 |  |  |  | 850000 | Overdue
348 | Urgent maintenance issues at Cr awolowo2 kitchen | LAG, AWOLOWO 2 | Others | Breakdown | ACORN | P.O.P | BUILDING | 2024-11-18 | 122 | 2024-11-19 | 1 | 2024-11-25 | 6 | 2024-11-25 | 2024-11-25 | 0 | 2024-11-25 | 115 |  |  |  | 250000 | Overdue
349 | BAD DOOR AT WASTE BIN AREA | LAG, BADORE | Wear & Tear | Breakdown | FULL TURN | WASTE BIN HOUSE | BUILDING | 2024-11-18 | 18 | 2024-11-18 | 0 | 2024-11-20 | 2 | 2024-11-20 | 2024-11-28 | 8 | 2024-11-28 | 1 | 2024-11-29 | 7 | 2024-12-06 | 226309 | Completed | 2024-12-06 | 1
350 | ENVIRONMENTAL ISSUE AFFECTING THE NEIGHBORING SCHOOL | OGUN, SOKENU | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-11-21 | 119 | 2024-11-21 | 0 | 2024-11-22 | 1 | 2024-11-28 | 2024-11-28 | 0 | 2024-11-28 | 1 | 2024-11-29 | 111 |  | 950000 | Overdue
351 | REQUEST FOR EXTRACTOR BLADES | LAG, OGUDU | Wear & Tear | Breakdown |  |  |  | 2024-11-07 | 133 | 2024-11-09 | 2 | 2024-11-11 | 2 | 2024-11-25 | 2024-11-29 | 4 | 2024-11-29 | 111 |  |  |  |  | Overdue
352 | FAULTY FREEZER ROOM & Coldroom | IBADAN, AKOBO | Routine Servicing | Preventive | TONAOGUNS | FREEZER ROOM | HVAC | 2024-11-02 | 6 | 2024-11-02 | 0 | 2024-11-02 | 0 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 3 | 2024-11-08 | 680000 | Completed | 2024-11-08 | 1
353 | FAULTY FREEZER ROOM & Coldroom | IBADAN, AKOBO | Routine Servicing | Preventive | TONAOGUNS | FREEZER ROOM | HVAC | 2024-11-08 | 23 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-11 | 2024-12-04 | 23 | 2024-12-04 | 1 | 2024-12-05 | -4 | 2024-12-01 | 510000 | Completed | 2024-12-01 | 1
355 | BROKEN INTERLOCK AT THE CARPARK | LAG, OKOTA | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-11-25 | 17 | 2024-11-26 | 1 | 2024-11-26 | 0 | 2024-11-26 | 2024-12-04 | 8 | 2024-12-04 | 0 | 2024-12-04 | 8 | 2024-12-12 | 200000 | Completed | 2024-12-12 | 1
356 | REQUEST TO FIX BARRICADE POLES IN FRONT OF THE KIOSK- PX AJOSE | LAG, AJOSE ADEOGUN | Corrective Action | Corrective | PENTECOSTAL | OTHERS | OTHERS | 2024-11-29 | 12 | 2024-11-29 | 0 | 2024-11-30 | 1 | 2024-11-30 | 2024-12-04 | 4 | 2024-12-04 | 0 | 2024-12-04 | 7 | 2024-12-11 | 150000 | Completed | 2024-12-11 | 1
357 | GAS BURNER SERVICING | LAG, FREEDOMWAY | Routine Servicing | Preventive | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2024-11-29 | 7 | 2024-11-29 | 0 | 2024-12-02 | 3 | 2024-12-02 | 2024-12-04 | 2 | 2024-12-04 | 0 | 2024-12-04 | 2 | 2024-12-06 | 235000 | Completed | 2024-12-06 | 1
358 | FAT TRAP NOT WORKING | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | ZEBRA G3 | GREASE TRAP | GREASE_TRAP | 2024-11-21 | 22 | 2024-11-21 | 0 | 2024-12-02 | 11 | 2024-12-02 | 2024-12-04 | 2 | 2024-12-04 | 0 | 2024-12-04 | 9 | 2024-12-13 | 420000 | Completed | 2024-12-13 | 1
359 | LEAKING MEDIA TANK | ILORIN, GRA | Others | Breakdown | PROEQUIP | GROUND WATER TANK | WTP | 2024-11-19 | 23 | 2024-11-19 | 0 | 2024-11-25 | 6 | 2024-11-26 | 2024-12-04 | 8 | 2024-12-04 | 0 | 2024-12-04 | 8 | 2024-12-12 | 650000 | Completed | 2024-12-12 | 1
360 | LEAVING SILVER TANK | ILORIN, OFFA GARAGE | Others | Breakdown | PROEQUIP | AERATION TANK | WTP | 2024-11-18 | 36 | 2024-11-18 | 0 | 2024-11-19 | 1 | 2024-11-19 | 2024-12-04 | 15 | 2024-12-04 | 5 | 2024-12-09 | 15 | 2024-12-24 | 1700000 | Completed | 2024-12-24 | 1
361 | EXTRACTOR AIR VENT NOT WORKING | LAG, NNPC ALAPERE | Wear & Tear | Breakdown | ABBEY | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2024-11-11 | 43 | 2024-11-11 | 0 | 2024-11-14 | 3 | 2024-12-02 | 2024-12-04 | 2 | 2024-12-04 | 0 | 2024-12-04 | 20 | 2024-12-24 | 360000 | Completed | 2024-12-24 | 1
362 | FAULTY FREEZER-ROOM FAN BLADE ( CR LIMCA RD0 | ANAMBRA, LIMCA RD, ONITSHA | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-11-07 | 7 | 2024-11-07 | 0 | 2024-11-12 | 5 | 2024-11-14 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 170000 | Completed | 2024-11-14 | 1
363 | FAULTY FREEZER ROOM- OPOLO | BAYELSA, OPOLO | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-11-12 | 17 | 2024-11-13 | 1 | 2024-11-29 | 16 | 2024-11-29 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 98000 | Completed | 2024-11-29 | 1
364 | FAULTY FREEZER ROOM SELF-OPENER | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-11-18 | 10 | 2024-11-18 | 0 | 2024-11-19 | 1 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 9 | 2024-11-28 | 63625 | Completed | 2024-11-28 | 1
365 | FAULTY FREEZER ROOM | BAYELSA, YENAGOA | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 130000 | Completed | 2024-11-18 | 1
366 | FAULTY FREEZER ROOM | BAYELSA, YENAGOA | Wear & Tear | Breakdown | ECS | FREEZER ROOM | HVAC | 2024-11-28 | 112 | 2024-11-28 | 0 | 2024-12-05 | 7 | [9 empty] | Overdue
367 | FAULTY FREEZER ROOM | LAG, IKOTUN | Wear & Tear | Breakdown | THIO & PARTNER | FREEZER ROOM | HVAC | 2024-11-28 | 12 | 2024-11-28 | 0 | 2024-12-04 | 6 | 2024-12-04 | 2024-12-04 | 0 | 2024-12-04 | 0 | 2024-12-04 | 6 | 2024-12-10 | 152625 | Completed | 2024-12-10 | 1
368 | AC DUE FOR SEVICING | ILORIN, MM WAY | Routine Servicing | Preventive | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-11-09 | 37 | 2024-11-10 | 1 | 2024-12-02 | 22 | 2024-12-02 | 2024-12-07 | 5 | 2024-12-07 | 0 | 2024-12-07 | 9 | 2024-12-16 | 410000 | Completed | 2024-12-16 | 1
369 | LOBBY FUNITURE AND CASHIER COUNTER NOT IN GOOD CONDITION | DELTA, ISOKO RD | Wear & Tear | Breakdown | FULLTURN | CASHIER COUNTER | BUILDING | 2024-11-21 | 27 | 2024-11-21 | 0 | 2024-11-26 | 5 | 2024-11-26 | 2024-12-10 | 14 | 2024-12-10 | 1 | 2024-12-11 | 7 | 2024-12-18 | 185000 | Completed | 2024-12-18 | 1
370 | FALLEN AIR VENT | ABIA, OGBOR HILLS | Wear & Tear | Breakdown | EK NOR | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2024-11-30 | 23 | 2024-12-01 | 1 | 2024-12-05 | 4 | 2024-12-16 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 7 | 2024-12-23 | 383255.5 | Completed | 2024-12-23 | 1
371 | FAULTY AIR CURTAIN AT THE BOH | AKWA IBOM, ORON RD | Wear & Tear | Breakdown | EK NOR | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2024-11-19 | 34 | 2024-11-20 | 1 | 2024-11-21 | 1 | 2024-12-16 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 7 | 2024-12-23 | 344755.5 | Completed | 2024-12-23 | 1
372 | WOBBLING WATER TANK STAND | LAG, AGUNGI | Wear & Tear | Breakdown | MODEL | GROUND WATER TANK | WTP | 2024-11-27 | 113 | 2024-11-27 | 0 | 2024-12-11 | 14 | 2024-12-22 | 2024-12-22 | 0 | [5 empty] | 2500000 | Overdue
373 | Repainting of lobby tables and cash point tables | AKWA IBOM, NWANIBA | Wear & Tear | Breakdown | FULL TURN | OTHERS | OTHERS
374 | FAULTY TAP HEAD FOR MALE AND FEMALE RESTROOM | LAG, FREEDOMWAY | Wear & Tear | Breakdown | PRO-EQUIP | TAP | PLUMBING | 2024-11-28 | 112 | 2024-11-28 | 0 | 2024-12-02 | 4 | [9 empty] | Overdue
375 | LEAKAGE IN COOKING GAS BURNER | LAG, MARINA | Wear & Tear | Breakdown | JOEL | GAS CYLINDER | GAS | 2024-11-01 | 1 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 1 | 2024-11-02 |  | Completed | 2024-11-02 | 1
376 | FAULTY CUSTOMER RESTROOM DOOR | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-11-11 | 2 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-12 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 1 | 2024-11-13 |  | Completed | 2024-11-13 | 1
377 | FAULTY CUSTOMER RESTROOM DOOR | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-11-20 | 3 | 2024-11-20 | 0 | 2024-11-21 | 1 | 2024-11-22 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 1 | 2024-11-23 |  | Completed | 2024-11-23 | 1
378 | FAULTY CUSTOMER RESTROOM DOOR | LAG, IRE-AKARI | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-11-19 | 21 | 2024-11-20 | 1 | 2024-11-26 | 6 | 2024-12-09 | 2024-12-09 | 0 | 2024-12-09 | 0 | 2024-12-09 | 1 | 2024-12-10 | 190000 | Completed | 2024-12-10 | 1
379 | ELECTRICAL ISSUE IN THE STORE | LAG, FESTAC | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-11-20 | -17 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | -17 | 2024-11-20 |  | Completed | 2024-11-03 | 1
380 | Lobby ACs not cooling | ENUGU, CHIME AVENUE | Wear & Tear | Breakdown | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-11-02 | 1 | 2024-11-02 | 0 | 2024-11-02 | 0 | 2024-11-02 | 2024-11-02 | 0 | 2024-11-02 | 1 | 2024-11-03 | 0 | 2024-11-03 | 540000 | Completed | 2024-11-03 | 1
381 | CONSTRUCTION OF SLAB FOR OUTSIDE DRAINAGE | LAG, ALIMOSHO | Others | Breakdown | PENTECOSTAL | SLAB | BUILDING | 2024-11-02 | 138 | 2024-11-02 | 0 |  | 138 | [9 empty] | Overdue
382 | FAULTY CUSTOMERS RESTROOM DOOR | LAG, IKOTUN | Users Misuse | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-11-24 | 1 | 2024-11-24 | 0 | 2024-11-24 | 0 | 2024-11-24 | 2024-11-24 | 0 | 2024-11-24 | 0 | 2024-11-24 | 1 | 2024-11-25 |  | Completed | 2024-11-25 | 1
383 | REQUEST FOR LED LIGHTS | LAG, IDIMU | Electrical Surge | Breakdown | RANEX4WARD | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-11-13 | 2 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 2 | 2024-11-15 | 172430 | Completed | 2024-11-15 | 1
384 | LOBBY TV NOT SHOWING | LAG, ETERNA LEKKI | Electrical Surge | Breakdown | ACORN | TELEVISION | AUDIOVISUAL | 2024-11-01 | 3 | 2024-11-01 | 0 | 2024-11-03 | 2 | 2024-11-03 | 2024-11-03 | 0 | 2024-11-03 | 1 | 2024-11-04 | 0 | 2024-11-04 | 21500 | Completed | 2024-11-04 | 1
385 | FREEZER, AMD CHEST FREEZER NOT ATTANNING TEMPERATURE | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | G.B BOYEJO | CHEST FREEZER | HVAC | 2024-11-01 | 139 | 2024-11-03 | 2 |  | 137 | [9 empty] | Overdue
386 | FAULTY CABINET | LAG, IKORODU | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-05 | 3 | 2024-11-06 | 1 | 2024-11-08 | 2 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 130075 | Completed | 2024-11-08 | 1
387 | FAULTY CABINET | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-07 | 6 | 2024-11-07 | 0 | 2024-11-13 | 6 | 2024-11-13 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 135987.5 | Completed | 2024-11-13 | 1
388 | FAULTY CABINET LAMPHOLDER | LAG, BODE THOMAS | Wear & Tear | Breakdown | TIMILEHIN | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-12 | 1 | 2024-11-13 | 1 | 2024-11-13 | 0 | 2024-11-13 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 0 | Completed | 2024-11-13 | 1
389 | FAULTY CABINET BULB AND CUSTOMERS REST ROOM BULB | LAG, IPAJA RD | Electrical Surge | Breakdown | TAYO | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-19 | 121 | 2024-11-19 | 0 |  | 121 | [9 empty] | Overdue
390 | FAULTY CABINET LAMP HOLDER | LAG, SKYMALL | Electrical Surge | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-25 | 115 | 2024-11-25 | 0 |  | 115 | [9 empty] | Overdue
391 | FAULTY CABINET | LAG, OBA AKRAN | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-25 | 115 | 2024-11-25 | 0 |  | 115 | [9 empty] | Overdue
392 | FAULTY CABINET LAMP HOLDER | LAG, IRE-AKARI | Wear & Tear | Breakdown | FRIDAY | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-25 | 115 | 2024-11-25 | 0 | 2024-11-27 | 2 | [9 empty] | Overdue
393 | FAULTY CABINET LAMP HOLDER | LAG, IRE-AKARI | Wear & Tear | Breakdown | EMMANUEL | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 |  | Completed | 2024-11-27 | 1
394 | LOUD SOUND AT WATER TREATMENT AREA | LAG, JIBOWU | Wear & Tear | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2024-11-03 | 8 | 2024-11-03 | 0 | 2024-11-11 | 8 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 476767.5 | Completed | 2024-11-11 | 1
395 | ELECTRICITY SUPPLY NOT SUFFICIENT | LAG, AWOLOWO 2 | Electrical Surge | Breakdown | GBATMO | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-11-02 | 2 | 2024-11-02 | 0 | 2024-11-04 | 2 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 |  | Completed | 2024-11-04 | 1
396 | POWER SUPPLY | ILORIN, TAIWO RD | Electrical Surge | Breakdown | IFEONU | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-11-06 | 2 | 2024-11-06 | 0 | 2024-11-07 | 1 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 |  | Completed | 2024-11-08 | 1
397 | WASTE WATER EVACUATION | OGUN, HEYDEN IBAFO | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-11-04 | 136 | 2024-11-05 | 1 |  | 135 | [9 empty] | Overdue
398 | FILLED SEPTIC TANK | LAG, IDI-IROKO RD | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION
399 | cabinet dead bulb light | LAG, AKOWONJO | Wear & Tear | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-03 | 14 | 2024-11-03 | 0 | 2024-11-17 | 14 | 2024-11-17 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-17 | 24187 | Completed | 2024-11-17 | 1
400 | REQUEST FOR WARMER GASKET | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2024-11-03 | 39 | 2024-11-03 | 0 | 2024-11-18 | 15 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 24 | 2024-12-12 | 146200 | Completed | 2024-12-12 | 1
401 | px akowonjo celling dead bulb light | LAG, AKOWONJO | Wear & Tear | Breakdown | FRIDAY | DROPPING LIGHT | ELECTRICAL | 2024-11-03 | 4 | 2024-11-03 | 0 | 2024-11-07 | 4 | 2024-11-07 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 |  | Completed | 2024-11-07 | 1
402 | FAULTY MOBILE WARMER DOOR GASKET. LIMCA ROAD | ANAMBRA, LIMCA RD, ONITSHA | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2024-11-03 | 137 | 2024-11-03 | 0 | 2024-11-04 | 1 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 132 |  | 115025 | Overdue
403 | CABINET BULB COVER | IBADAN, OJOO | Users Misuse | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-03 | 72 | 2024-11-03 | 0 | 2024-12-22 | 49 | 2024-12-22 | 2024-12-22 | 0 | 2024-12-22 | 0 | 2024-12-22 | 23 | 2024-12-22 | 308146.6 | Completed | 2025-01-14 | 0
404 | POLARITY ISSUE AT ENTOURAGE MALL | LAG, ENTOURAGE MALL | Electrical Surge | Breakdown | ISMAIL | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-11-03 | 137 | 2024-11-03 | 0 |  | 137 | [9 empty] | Overdue
405 | BURNT CHEST FREEZER CABLE | LAG, AWOLOWO 2 | Electrical Surge | Breakdown | ISMAIL | CHEST FREEZER | HVAC | 2024-11-03 | 1 | 2024-11-03 | 0 | 2024-11-04 | 1 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 |  | Completed | 2024-11-04 | 1
406 | BURNT BULB IN THE OFFICE | LAG, IDI-IROKO RD | Electrical Surge | Breakdown | TAYO | DROPPING LIGHT | ELECTRICAL | 2024-11-03 | 17 | 2024-11-03 | 0 | 2024-11-11 | 8 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 9 | 2024-11-20 | 726875 | Completed | 2024-11-20 | 1
407 | BROKEN HAND SINK WASH | OSUN, GBONGAN | Others | Breakdown | REVELATION | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-03 | 137 | 2024-11-03 | 0 |  | 137 | [9 empty] | Overdue
408 | OVER GROWN TREE INTRUDING THE COMPOUND | LAG, JOEL OGUNNAIKE | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-11-05 | 9 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 2024-11-12 | 7 | 2024-11-12 | 0 | 2024-11-12 | 2 | 2024-11-14 | 79120 | Completed | 2024-11-14 | 1
409 | DIESEL TANK PUMP LEAKAGE. | LAG, MOBIL OGBA | Wear & Tear | Breakdown | DELIGHTSOME | GENERATOR | GENERATOR | 2024-11-07 | 5 | 2024-11-07 | 0 | 2024-11-11 | 4 | 2024-11-12 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 |  | Completed | 2024-11-12 | 1
410 | CR AWOLOWO 1 PENDING MAINTAINANCE ISSUES | LAG, AWOLOWO | Wear & Tear | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-11-03 | 1 | 2024-11-03 | 0 | 2024-11-03 | 0 | 2024-11-03 | 2024-11-03 | 0 | 2024-11-03 | 0 | 2024-11-03 | 1 | 2024-11-04 |  | Completed | 2024-11-04 | 1
411 | FAULTY ROTISSERIE MACHINE | LAG, OSOLOWAY | Wear & Tear | Breakdown | HEFHEM | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-11-03 | 4 | 2024-11-03 | 0 | 2024-11-04 | 1 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 3 | 2024-11-07 |  | Completed | 2024-11-07 | 1
412 | FAULTY ROTISSERIE MACHINE | LAG, IDIMU | Wear & Tear | Breakdown | HEFHEM | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-11-08 | 3 | 2024-11-09 | 1 | 2024-11-11 | 2 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 |  | Completed | 2024-11-11 | 1
413 | FAULTY LOBBY AC | LAG, MMA2 | Wear & Tear | Breakdown | G.B BOYEJO | 5HP STANDING AC UNIT 1 | HVAC | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 164000 | Completed | 2024-11-04 | 1
414 | Lobby Ac | LAG, AWOLOWO | Wear & Tear | Breakdown | FOLLTEC | 5HP STANDING AC UNIT 1 | HVAC | 2024-11-05 | 135 | 2024-11-05 | 0 | 2024-11-06 | 1 | [9 empty] | Overdue
415 | NEPA NOT WORKING WITH LOBBY AC | LAG, TEJUOSHO | Electrical Surge | Breakdown | TIMILEHIN | 5HP STANDING AC UNIT 1 | HVAC | 2024-11-07 | 133 | 2024-11-07 | 0 |  | 133 | [9 empty] | Overdue
416 | LOBBY AC NOT FUNCTIONING WELL | LAG, AJAH | Wear & Tear | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC
417 | Faulty Roof Above Industrial Breaker | LAG, VGC | Wear & Tear | Breakdown | MATOLAD | CEILING BOARD | BUILDING | 2024-11-20 | 120 | 2024-11-20 | 0 | 2024-11-21 | 1 | [9 empty] | Overdue
418 | FREEZER ROOM NOT ATTAINING TEMPERATURE | ABIA, AZIKIWE RD, UMUAHIA | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-11-14 | 126 | 2024-11-14 | 0 | 2024-11-15 | 1 | [9 empty] | Overdue
419 | COLD ROOM NOT ATTAINING TEMPERATURE | PH, ABACHA RD | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-11-19 | 121 | 2024-11-19 | 0 |  | 121 | [9 empty] | Overdue
420 | Cold room not attaining temperature | PH, OYIGBO | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2024-11-24 | 116 | 2024-11-24 | 0 |  | 116 | [9 empty] | Overdue
421 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | THIO & PARTNERS | COLD ROOM UNIT | HVAC | 2024-11-25 | 14 | 2024-11-25 | 0 | 2024-12-09 | 14 | 2024-12-09 | 2024-12-09 | 0 | 2024-12-09 | 0 | 2024-12-09 | 0 | 2024-12-09 | 141500 | Completed | 2024-12-09 | 1
422 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-11-17 | 39 | 2024-11-18 | 1 | 2024-12-26 | 38 | 2024-12-26 | 2024-12-26 | 0 | 2024-12-26 | 0 | 2024-12-26 | 0 | 2024-12-26 |  | Completed | 2024-12-26 | 1
423 | STORE BLACK OUT | LAG, GBAGADA | Electrical Surge | Breakdown | TIMILEHIN | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 |  | Completed | 2024-11-14 | 1
424 | DEAD BULB IN THE CABINET | LAG, AWOLOWO | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-05 | 7 | 2024-11-05 | 0 | 2024-11-12 | 7 | 2024-11-12 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 39237.5 | Completed | 2024-11-12 | 1
425 | DEAD BULB IN THE CABINET | LAG, ABULE EGBA | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-05 | 135 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 135 | 2024-11-05 | 33325 | Overdue
426 | DEAD BULB IN THE CABINET | LAG, TEJUOSHO | Wear & Tear | Breakdown | TIMILEHIN | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-06 | 134 | 2024-11-06 | 0 |  | 134 | [9 empty] | Overdue
427 | DEAD BULB IN THE CABINET | LAG, VGC | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-06 | 134 | 2024-11-06 | 0 |  | 134 | [9 empty] | Overdue
428 | DEAD BULB IN THE CABINET | LAG, IKORODU | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-25 | 115 | 2024-11-25 | 0 |  | 115 | [9 empty] | Overdue
429 | FAULTY ROLLER SHUTTER | LAG, MAGODO | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-11-08 | 52 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 41 | 2024-12-30 | 225965 | Completed | 2024-12-30 | 1
430 | FAULTY ROLLER SHUTTER REMOTE | LAG, ALIMOSHO | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-11-10 | 42 | 2024-11-10 | 0 | 2024-11-11 | 1 | 2024-12-19 | 2024-12-19 | 0 | 2024-12-20 | 2 | 2024-12-22 | 0 | 2024-12-22 | 76970 | Completed | 2024-12-22 | 1
431 | BAD CAR PARK- ZIK AVENUE AWKA | ANAMBRA, ZIK AVENUE, AWKA | Others | Breakdown | FULL TURN | OTHERS | OTHERS | 2024-11-17 | 123 | 2024-11-18 | 1 | 2025-01-09 | 52 | 2025-01-09 | 2025-01-10 | 1 | [6 empty] | Overdue
432 | GENERATOR SERVICING | LAG, MOBIL OGBA | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-11-07 | 5 | 2024-11-07 | 0 | 2024-11-12 | 5 | 2024-11-12 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 241176.25 | Completed | 2024-11-12 | 1
433 | GENERATOR SERVICING | ILORIN, GRA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-11-10 | 14 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 14 | 2024-11-24 | 85000 | Completed | 2024-11-24 | 1
434 | GENERATOR SERVICING | IBADAN, BODIJA | Routine Servicing | Preventive | SYMINERTIAS | GENERATOR | GENERATOR | 2024-11-11 | 1 | 2024-11-11 | 0 | 2024-11-12 | 1 | 2024-11-12 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 263437.5 | Completed | 2024-11-12 | 1
435 | GENERATOR SERVICING | IBADAN, OJOO | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-11-13 | 1 | 2024-11-13 | 0 | 2024-11-14 | 1 | 2024-11-14 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 301000 | Completed | 2024-11-14 | 1
436 | REQUEST FOR GENERATOR SERVICING | ABIA, AZIKIWE RD, UMUAHIA | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2024-11-16 | 3 | 2024-11-16 | 0 | 2024-11-18 | 2 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 1 | 2024-11-19 | 247250 | Completed | 2024-11-19 | 1
437 | GENERATOR SERVICING | AKWA IBOM, EKET-ORON RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-11-17 | 2 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-17 | 2024-11-17 | 0 | 2024-11-17 | 0 | 2024-11-17 | 2 | 2024-11-19 | 100000 | Completed | 2024-11-19 | 1
438 | GENERATOR SERVICING | BAYELSA, OPOLO | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 217000 | Completed | 2024-11-22 | 1
439 | FAULTY BULB HOLDER IN THE CABINET. | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | JOEL | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-01 | 3 | 2024-11-02 | 1 | 2024-11-04 | 2 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 |  | Completed | 2024-11-04 | 1
440 | BROKEN FRYER SINC TAP | LAG, LEKKI PHASE 1 | Users Misuse | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-01 | 3 | 2024-11-03 | 2 | 2024-11-04 | 1 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 |  | Completed | 2024-11-04 | 1
441 | SINK LEAKING OUT WATER | LAG, ETERNA LEKKI | Users Misuse | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-03 | 1 | 2024-11-03 | 0 | 2024-11-04 | 1 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 |  | Completed | 2024-11-04 | 1
442 | BLOCK KITCHEN SINK | LAG, LEKKI PHASE 1 | Users Misuse | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 |  | Completed | 2024-11-04 | 1
443 | FAULTY TAP | LAG, AJOSE ADEOGUN | Users Misuse | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-04 | 1 | 2024-11-04 | 0 | 2024-11-05 | 1 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 |  | Completed | 2024-11-05 | 1
444 | LEAKING PIPE AT FRYER'S SECTION | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-04 | 1 | 2024-11-04 | 0 | 2024-11-05 | 1 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 |  | Completed | 2024-11-05 | 1
445 | MALE REST ROOM LEAKING OUT WATER | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-04 | 1 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 2024-11-05 | 1 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 |  | Completed | 2024-11-05 | 1
446 | CHANGE OF FRYER TAP HEADS | LAG, FREEDOMWAY | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-04 | 1 | 2024-11-04 | 0 | 2024-11-05 | 1 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 |  | Completed | 2024-11-05 | 1
447 | FAULTY STAFF ROOM SINK | LAG, FREEDOMWAY | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-04 | 1 | 2024-11-04 | 0 | 2024-11-05 | 1 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 |  | Completed | 2024-11-05 | 1
448 | Urgent need to check on proffer and buns rounder | PPU Oniru | Wear & Tear | Breakdown | JOEL | TAP | PLUMBING | 2024-11-04 | 136 | 2024-11-04 | 0 | 2024-11-05 | 1 | [9 empty] | Overdue
449 | FAULTY DRAINAGE BLOWER MACHINE | LAG, FREEDOMWAY | Wear & Tear | Breakdown | JOEL | TAP | PLUMBING | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 |  | Completed | 2024-11-05 | 1
450 | FRYER SECTION WATER HEATER PIPE LEAKING | LAG, AGUNGI | Wear & Tear | Breakdown | JOEL | TAP | PLUMBING | 2024-11-05 | 1 | 2024-11-05 | 0 | 2024-11-06 | 1 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 |  | Completed | 2024-11-06 | 1
451 | WATER LEAKAGE IN COOK WASHING SINK | LAG, AGUNGI | Wear & Tear | Breakdown | JOEL | TAP | PLUMBING | 2024-11-04 | 2 | 2024-11-04 | 0 | 2024-11-06 | 2 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 |  | Completed | 2024-11-06 | 1
452 | NON-AVALABILITY OF WATER IN STORE. | LAG, MARINA | Others | Breakdown | JOEL | TAP | PLUMBING | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 |  | Completed | 2024-11-06 | 1
453 | REPLACEMENT OF FEMALE RESTROOM TAP KNOB | LAG, AWOLOWO | Others | Breakdown | JOEL | TAP | PLUMBING | 2024-11-06 | 1 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 1 | 2024-11-07 |  | Completed | 2024-11-07 | 1
454 | FAT TRAP MACHINE NOT WORKING | LAG, AWOLOWO | Others | Breakdown | JOEL | GREASE TRAP | GREASE_TRAP | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 |  | Completed | 2024-11-07 | 1
455 | NO LIGHT IN THE FREEZER ROOM. | LAG, VGC | Others | Breakdown | JOEL | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-11-04 | 4 | 2024-11-04 | 0 | 2024-11-08 | 4 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 |  | Completed | 2024-11-08 | 1
456 | TOP HEAD LEAKING OUT WATER | LAG, ETERNA LEKKI | Others | Breakdown | PROOEQUIP | TAP | PLUMBING | 2024-11-10 | 4 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 4 | 2024-11-14 |  | Completed | 2024-11-14 | 1
457 | WATER NOT RUNNING INTO THE STORE | LAG, MARINA | Others | Breakdown | JOEL | OTHERS | OTHERS | 2024-11-09 | 1 | 2024-11-09 | 0 | 2024-11-10 | 1 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 |  | Completed | 2024-11-10 | 1
458 | Urgent need to connect gas burner Oniru PPU | PPU Oniru | Wear & Tear | Breakdown | JOEL | COOKING BURNER | KITCHEN_EQUIPMENT | 2024-11-07 | 4 | 2024-11-08 | 1 | 2024-11-11 | 3 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 |  | Completed | 2024-11-11 | 1
459 | BOREHOLE MACHING NOT WORKING | LAG, AWOLOWO | Wear & Tear | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-11-11 | 1 | 2024-11-11 | 0 | 2024-11-12 | 1 | 2024-11-12 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 232200 | Completed | 2024-11-12 | 1
460 | NO RUNNING WATER | LAG, AWOLOWO | Wear & Tear | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 0 | 2024-11-07 | 144318.75 | Completed | 2024-11-07 | 1
461 | NO RUNNING WATER | LAG, AJOSE ADEOGUN | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS
462 | BAD WRC | LAG, ETERNA LEKKI | Others | Breakdown | JOEL | OTHERS | OTHERS | 2024-11-12 | 1 | 2024-11-13 | 1 | 2024-11-13 | 0 | 2024-11-13 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 |  | Completed | 2024-11-13 | 1
463 | FRYER HOT WATER TAP IS NOT WORKING | LAG, BADORE | Wear & Tear | Breakdown | PROEQUIP | WATER HEATER | PLUMBING | 2024-11-15 | 125 | 2024-11-15 | 0 | 2024-11-20 | 5 | [9 empty] | Overdue
464 | FLOODED BOH | LAG, AJAH | Wear & Tear | Breakdown | JOEL | GREASE TRAP | GREASE_TRAP | 2024-11-14 | 1 | 2024-11-14 | 0 | 2024-11-15 | 1 | 2024-11-15 | 2024-11-15 | 0 | 2024-11-15 | 0 | 2024-11-15 | 0 | 2024-11-15 |  | Completed | 2024-11-15 | 1
465 | MALE TOLIET LIGHT SENSOR IS NOT WORK | LAG, BADORE | Wear & Tear | Breakdown | ADEREMI KAZEEM | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-11-15 | 4 | 2024-11-15 | 0 | 2024-11-19 | 4 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 |  | Completed | 2024-11-19 | 1
466 | AC GAS LEAKAGE | LAG, ONIRU | Wear & Tear | Breakdown | FOLLTEC | 5HP STANDING AC UNIT 2 | HVAC | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 250000 | Completed | 2024-11-18 | 1
467 | GAS LEAKAGE | LAG, ONIRU | Wear & Tear | Breakdown | JOEL | GAS HOSE & SUNDRIES | GAS | 2024-11-15 | 3 | 2024-11-15 | 0 | 2024-11-18 | 3 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 |  | Completed | 2024-11-18 | 1
468 | LEAKING KITCHEN SINK/ BLOCKAGE AT BOH | LAG, VGC | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-17 | 2 | 2024-11-18 | 1 | 2024-11-19 | 1 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 |  | Completed | 2024-11-19 | 1
469 | UNAVAILABILTY OF WATER IN THE STORE | LAG, ONIRU | Users Misuse | Breakdown | JOEL | TAP | PLUMBING | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 |  | Completed | 2024-11-19 | 1
470 | LINKING PIPE | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | JOEL | OTHERS | OTHERS | 2024-11-19 | 1 | 2024-11-19 | 0 | 2024-11-20 | 1 | 2024-11-20 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 |  | Completed | 2024-11-20 | 1
471 | LEAKING COOK SINK | LAG, FREEDOMWAY | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-19 | 3 | 2024-11-19 | 0 | 2024-11-20 | 1 | 2024-11-20 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 2 | 2024-11-22 |  | Completed | 2024-11-22 | 1
472 | BAD DOOR HANDLE. | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-11-04 | 14 | 2024-11-04 | 0 | 2024-11-13 | 9 | 2024-11-13 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 5 | 2024-11-18 | 30500 | Completed | 2024-11-18 | 1
473 | BROKEN SHATTER PROOF GLASS IN THE CABINET | LAG, MMA2 | Wear & Tear | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-11-06 | 14 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 2024-11-06 | 0 | 2024-11-06 | 0 | 2024-11-06 | 14 | 2024-11-20 | 95000 | Completed | 2024-11-20 | 1
474 | Broken Aluco Board | LAG, ILUPEJU | Wear & Tear | Breakdown | TAIDAV | OTHERS | OTHERS
475 | SEWAGE WATER PIPE BLOCKAGE-FOOD SAFETY AND ENVIRONMENTAL POLLUTION AT AJAH | PPU Ajah | Wear & Tear | Breakdown | JOEL | OTHERS | OTHERS | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 | 0 | 2024-11-20 |  | Completed | 2024-11-20 | 1
476 | blocked fat track | LAG, TOTAL LEKKI | Others | Breakdown | JOEL | GREASE TRAP | GREASE_TRAP | 2024-11-20 | 1 | 2024-11-20 | 0 | 2024-11-21 | 1 | 2024-11-21 | 2024-11-21 | 0 | 2024-11-21 | 0 | 2024-11-21 | 0 | 2024-11-21 |  | Completed | 2024-11-21 | 1
477 | FAULTY WATER TAP | LAG, VGC | Wear & Tear | Breakdown | JOEL | TAP | PLUMBING | 2024-11-15 | 125 | 2024-11-15 | 0 | 2024-11-21 | 6 | 2024-11-21 | 2024-11-21 | 0 | 2024-11-21 | 0 | 2024-11-21 | 119 | 2024-11-21 |  | Overdue
478 | BLOCK FEMALE TOILET CHAMBER | LAG, AWOLOWO 2 | Others | Breakdown | JOEL | CHAMBER | BUILDING | 2024-11-21 | 119 | 2024-11-21 | 0 |  | 119 | [9 empty] | Overdue
479 | FAULTY DOWNSTAIRS HAND DRYER | LAG, BADORE | Wear & Tear | Breakdown | JOEL | OTHERS | OTHERS | 2024-11-18 | 7 | 2024-11-18 | 0 | 2024-11-25 | 7 | 2024-11-25 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 | 0 | 2024-11-25 |  | Completed | 2024-11-25 | 1
480 | LEAKING KITCHING SINK | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-23 | 3 | 2024-11-24 | 1 | 2024-11-26 | 2 | 2024-11-26 | 2024-11-26 | 0 | 2024-11-26 | 0 | 2024-11-26 | 0 | 2024-11-26 |  | Completed | 2024-11-26 | 1
481 | FAULTY FEMALE AND MALE CUSTOMER REST ROOM FLUSHERS NOT WORKING | LAG, BADORE | Wear & Tear | Breakdown | JOEL | OTHERS | OTHERS | 2024-11-27 | 1 | 2024-11-27 | 0 | 2024-11-28 | 1 | 2024-11-28 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 |  | Completed | 2024-11-28 | 1
482 | BROKEN TOLIET CLOSET | LAG, BADORE | Others | Breakdown | PRO-EQUIP | OTHERS | OTHERS | 2024-11-06 | 22 | 2024-11-06 | 0 | 2024-11-28 | 22 | 2024-11-28 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 |  | Completed | 2024-11-28 | 1
483 | LEAKING SINK. | LAG, AGUNGI | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-27 | 1 | 2024-11-27 | 0 | 2024-11-28 | 1 | 2024-11-28 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 |  | Completed | 2024-11-28 | 1
484 | REPORT OF DAILY HYGIENE WALKTHROUGH AND CLOSURE ACTION PLAN FOR OPEN OPPORTUNITIES FROM PPU AJAH | PPU Ajah | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2024-11-20 | 8 | 2024-11-20 | 0 | 2024-11-28 | 8 | 2024-11-28 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 | 0 | 2024-11-28 |  | Completed | 2024-11-28 | 1
485 | REPORT OF DAILY HYGIENE WALKTHROUGH AND CLOSURE ACTION PLAN FOR OPEN OPPORTUNITIES FROM PPU AJAH | PPU Ajah | Wear & Tear | Breakdown | ADEREMI KAZEEM | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-11-20 | 22 | 2024-11-20 | 0 | 2024-12-12 | 22 | 2024-12-12 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 |  | Completed | 2024-12-12 | 1
486 | WATER NOT RUNNING INTO THE STORE. | LAG, MARINA | Others | Breakdown | JOEL | TAP | PLUMBING | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-11-11 |  | Completed | 2024-11-11 | 1
487 | FAULTY PUMPING MACHINE | LAG, IKOTUN | Wear & Tear | Breakdown | PROPEARJEFF | SUBMERSIBLE PUMP | WTP | 2024-11-18 | 122 | 2024-11-18 | 0 |  | 122 | [9 empty] | Overdue
488 | FREEZER ROOM GAS LEAKAGE | LAG, ONIRU | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-11-11 | 129 | 2024-11-11 | 0 | 2024-11-11 | 0 | [9 empty] | Overdue
489 | GAS LEAKAGE | LAG, MOBIL OGBA | Wear & Tear | Breakdown | BERRADE | GAS CYLINDER | GAS | 2024-11-22 | 118 | 2024-11-22 | 0 |  | 118 | [9 empty] | Overdue
490 | GAS LEAKAGE | LAG, DIYA STREET | Wear & Tear | Breakdown | BERRADE | GAS CYLINDER | GAS | 2024-11-23 | 9 | 2024-11-23 | 0 | 2024-11-24 | 1 | 2024-11-24 | 2024-11-25 | 1 | 2024-11-25 | 1 | 2024-11-26 | 6 | 2024-12-02 | 123000 | Completed | 2024-12-02 | 1
491 | DEAD INSECTLOCUTOR BULBS | LAG, SKYMALL | Wear & Tear | Breakdown | ADEREMI KAZEEM | INSECT KILLER LOBBY 1 | ELECTRICAL | 2024-11-05 | 13 | 2024-11-05 | 0 | 2024-11-18 | 13 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 |  | Completed | 2024-11-18 | 1
492 | REPOSITIONING OF INSECTOCUTOR | LAG, ETERNA LEKKI | Corrective Action | Corrective | ADEREMI KAZEEM | INSECT KILLER LOBBY 1 | ELECTRICAL | 2024-11-20 | 10 | 2024-11-20 | 0 | 2024-11-30 | 10 | 2024-11-30 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 |  | Completed | 2024-11-30 | 1
493 | REPOSITIONING OF INSECTOCUTOR | LAG, AGUNGI | Corrective Action | Corrective | ADEREMI KAZEEM | INSECT KILLER LOBBY 1 | ELECTRICAL | 2024-11-14 | 9 | 2024-11-14 | 0 | 2024-11-23 | 9 | 2024-11-23 | 2024-11-23 | 0 | 2024-11-23 | 0 | 2024-11-23 | 0 | 2024-11-23 |  | Completed | 2024-11-23 | 1
494 | REPOSITIONING OF INSECTOCUTOR | LAG, AJAH | Corrective Action | Corrective | ADEREMI KAZEEM | INSECT KILLER LOBBY 1 | ELECTRICAL | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 |  | Completed | 2024-11-29 | 1
495 | REQUEST FOR LED BULB | LAG, AGUNGI | Wear & Tear | Breakdown | ADEREMI KAZEEM | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-11-28 | 2 | 2024-11-29 | 1 | 2024-11-30 | 1 | 2024-11-30 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 | 0 | 2024-11-30 |  | Completed | 2024-11-30 | 1
496 | FAULTY INSECUTOR | LAG, ONIRU | Wear & Tear | Breakdown | ADEREMI KAZEEM | INSECT KILLER LOBBY 2 | ELECTRICAL | 2024-11-29 | 5 | 2024-11-29 | 0 | 2024-12-04 | 5 | 2024-12-04 | 2024-12-04 | 0 | 2024-12-04 | 0 | 2024-12-04 | 0 | 2024-12-04 |  | Completed | 2024-12-04 | 1
497 | REQUEST FOR MOTOR STARTER | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-11-26 | 1 | 2024-11-26 | 0 | 2024-11-27 | 1 | 2024-11-27 | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 | 0 | 2024-11-27 |  | Completed | 2024-11-27 | 1
498 | FAULTY LAMPHOLDER IN THE CABINET | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-11-06 | 4 | 2024-11-06 | 0 | 2024-11-10 | 4 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 |  | Completed | 2024-11-10 | 1
499 | fluorescent bulb and starter | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | ISMAIL | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-11-06 | 4 | 2024-11-06 | 0 | 2024-11-10 | 4 | 2024-11-10 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 | 0 | 2024-11-10 |  | Completed | 2024-11-10 | 1
500 | FAULTY COLLECTRAMATIC FUSE | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | ISMAIL | COLLECTRAMATIC OIL PUMP MACHINE | KITCHEN_EQUIPMENT | 2024-11-09 | 131 | 2024-11-10 | 1 | 2024-12-13 | 33 | 2024-12-13 | 2025-01-10 | 28 | 2025-01-10 | 10 | 2025-01-20 | 59 | 2025-01-24 | 580500 | Overdue
501 | SEVERAL OPEN SOCKETS IN THE STORE | LAG, AWOLOWO | Wear & Tear | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-11-11 | 129 | 2024-11-11 | 0 | 2024-11-11 | 0 | 2024-12-05 | 2024-12-05 | 0 | 2024-12-05 | 105 |  |  |  |  | Overdue
502 | FAULTY INDUSTRIAL SOCKET FOR CHIPS & 6-HEAD MACHINE | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-11-11 | 1 | 2024-11-12 | 1 | 2024-11-12 | 0 | 2024-11-12 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 | 0 | 2024-11-12 |  | Completed | 2024-11-12 | 1
503 | OPEN SOCKET | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-11-03 | 16 | 2024-11-04 | 1 | 2024-11-19 | 15 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 |  | Completed | 2024-11-19 | 1
504 | EXPOSED WIRE INSIDE CHEST FREEZER/OPEN SOCKET AT BOH | LAG, VGC | Wear & Tear | Breakdown | ADEREMI KAZEEM | CHEST FREEZER | HVAC | 2024-11-06 | 134 | 2024-11-06 | 0 |  | 134 | [9 empty] | Overdue
505 | OPEN SOCKET IN THE STORE | OGUN, HEYDEN IBAFO | Others | Breakdown | MOSES O | OTHERS | OTHERS | 2024-11-12 | 1 | 2024-11-12 | 0 | 2024-11-13 | 1 | 2024-11-13 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 |  | Completed | 2024-11-13 | 1
506 | OPEN SOCKET | LAG, MARINA | Wear & Tear | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-11-15 | 3 | 2024-11-15 | 0 | 2024-11-18 | 3 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 |  | Completed | 2024-11-18 | 1
507 | OPEN SOCKET AT BACK OF CABINET | LAG, VGC | Wear & Tear | Breakdown | ADEREMI KAZEEM | OTHERS | OTHERS | 2024-11-18 | 1 | 2024-11-19 | 1 | 2024-11-19 | 0 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 |  | Completed | 2024-11-19 | 1
508 | EXPOSED WIRE,FUSED LED AND OPEN SOCKET | LAG, OKOTA | Wear & Tear | Breakdown | FRIDAY | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-11-25 | 115 | 2024-11-25 | 0 |  | #VALUE! | [9 empty] | Overdue
509 | GENERATOR DUE FOR SERVICING | PH, OYIGBO | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-11-03 | 137 | 2024-11-03 | 0 |  | 137 | [9 empty] | Overdue
510 | ICE CREAM MACHINE NOT FREEZING | LAG, OMOLE | Wear & Tear | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-04 | 136 | 2024-11-04 | 0 | 2024-11-05 | 1 | [9 empty] | Overdue
511 | CR GWARINPA 2 ICE CREAM MACHINE NOT FREEZING | ABUJA, GWARIMPA 2 | Wear & Tear | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-11-19 | 20 | 2024-11-21 | 2 | 2024-11-22 | 1 | 2024-11-22 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 17 | 2024-12-09 | 1376420 | Completed | 2024-12-09 | 1
512 | FREEZER ROOM FREEZING FLOOR AND PIPE. Temperature not attained | IBADAN, RING-ROAD | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-11-03 | 4 | 2024-11-03 | 0 | 2024-11-03 | 0 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-06 | 0 | 2024-11-06 | 1 | 2024-11-07 |  | Completed | 2024-11-07 | 1
513 | FAULTY LIGHT IN ROTISSERIES MACHINE | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-11-03 | 12 | 2024-11-03 | 0 | 2024-11-13 | 10 | 2024-11-13 | 2024-11-13 | 0 | 2024-11-14 | 0 | 2024-11-14 | 1 | 2024-11-15 | 337550 | Completed | 2024-11-15 | 1
514 | SYNAGE AND PYLON ARE TERRIBLY DIRTY | OSUN, GBONGAN | Users Misuse | Breakdown | DEFAVOURS | OTHERS | OTHERS | 2024-11-03 | 4 | 2024-11-03 | 0 | 2024-11-03 | 0 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-06 | 0 | 2024-11-06 | 1 | 2024-11-07 |  | Completed | 2024-11-07 | 1
515 | FREEZER ROOM NOT ATTAINING TEMPRATURE | LAG, ABULE EGBA | Wear & Tear | Breakdown | DYNAMITE | FREEZER ROOM | HVAC | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 0 | 2024-11-22 | 368725 | Completed | 2024-11-22 | 1
516 | FREEZER ROOM AND COLD ROOM NOT ATTAINING TEMPERATURE | LAG, AKOWONJO | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-10-06 | 40 | 2024-11-06 | 31 | 2024-11-09 | 3 | 2024-11-09 | 2024-11-09 | 0 | 2024-11-09 | 1 | 2024-11-10 | 5 | 2024-11-15 | 156125 | Completed | 2024-11-15 | 1
517 | FREEZER ROOM AND COLD ROOM NOT ATTAINING TEMPERATURE | ABIA, OGBOR HILLS | Wear & Tear | Breakdown | MOFFEEN | FREEZER ROOM | HVAC | 2024-11-13 | 127 | 2024-11-13 | 0 |  | 127 | [9 empty] | Overdue
518 | FREEZER ROOM AND COLD ROOM NOT ATTAINING TEMPERATURE | LAG, OBA AKRAN | Wear & Tear | Breakdown | BCE | FREEZER ROOM | HVAC | 2024-11-08 | 10 | 2024-11-08 | 0 | 2024-11-18 | 10 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 89225 | Completed | 2024-11-18 | 1
519 | FEMALE CHANGING ROOM DOOR FAUTLY | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-11-03 | 4 | 2024-11-05 | 2 | 2024-11-05 | 0 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-06 | 0 | 2024-11-06 | 1 | 2024-11-07 | 70000 | Completed | 2024-11-07 | 1
520 | INVERTER NOT WORKING | EDO, UGBOWO, BENIN | Wear & Tear | Breakdown | PET OJO 4 STAR | INVERTER SYSTEM | INVERTER | 2024-11-03 | 8 | 2024-11-03 | 0 | 2024-11-03 | 0 | 2024-11-03 | 2024-11-03 | 0 | 2024-11-03 | 0 | 2024-11-03 | 8 | 2024-11-11 | 622000 | Completed | 2024-11-11 | 1
521 | SEWAGE EVACUATION | LAG, EJIGBO | Wear & Tear | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-11-10 | 3 | 2024-11-10 | 0 | 2024-11-13 | 3 | 2024-11-13 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 | 0 | 2024-11-13 |  | Completed | 2024-11-13 | 1
522 | DEAD INSECT KILLER FLUORESCENT | LAG, MMA2 | Wear & Tear | Breakdown | TIMILEHIN | INSECT KILLER BOH | ELECTRICAL | 2024-11-29 | 1 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 2024-11-29 | 0 | 2024-11-29 | 0 | 2024-11-29 | 1 | 2024-11-30 |  | Completed | 2024-11-30 | 1
523 | Damage POP Ceiling | LAG, TEJUOSHO | Wear & Tear | Breakdown | ARIZMAYAN | CEILING BOARD | BUILDING | 2024-11-11 | 45 | 2024-11-11 | 0 | 2025-01-27 | 77 | 2024-12-26 | 2024-12-26 | 0 | 2024-12-26 | 0 | 2024-12-26 | 0 | 2024-12-26 |  | Completed | 2024-12-26 | 1
524 | SLUDGE EVACUATION | DELTA, EFFURUN | Corrective Action | Corrective |  |  |  | 2024-11-25 | 115 | 2024-11-25 | 0 |  | 115 | [9 empty] | Overdue
525 | BURNT CABINET LAMP HOLDERS AND DEAD CABINET BULBS | LAG, MMA2 | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-11-04 | 136 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-05 | 2024-11-05 | 0 | 2024-11-05 | 0 | 2024-11-05 | 135 | 2024-11-05 |  | Overdue
526 | REPAIR OF LOBBY AC AND OTHERS | IBADAN, MOKOLA | Routine Servicing | Preventive | TONAOGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-11-27 | 113 | 2024-11-27 | 0 | 2025-01-06 | 40 | 2025-01-07 | 2025-01-07 | 0 | 2025-01-07 | 72 |  |  |  | 650000 | Overdue
527 | FAULTY WATER HEATER | ILORIN, OFFA GARAGE | Others | Breakdown | PROEQUIP | WATER HEATER | PLUMBING | 2024-11-18 | 122 | 2024-11-18 | 0 | 2024-11-18 | 0 | 2024-11-18 | 2024-11-19 | 1 | 2024-11-19 | 2 | 2024-11-21 | 119 |  | 262250 | Overdue
528 | FAULTY A.C IN THE STORE | ABIA, FACTORY RD, ABA | Routine Servicing | Preventive | MOFEEN | 5HP STANDING AC UNIT 4 | HVAC | 2024-11-19 | 121 | 2024-11-19 | 0 | 2025-01-25 | 67 | 2025-01-25 |  | 54 | [6 empty] | Overdue
529 | faulty fan | LAG, MOBIL OGBA | Wear & Tear | Breakdown | MOSES | WALL FAN | HVAC | 2024-11-06 | 134 | 2024-11-06 | 0 | 2024-11-06 | 0 | [9 empty] | Overdue
530 | FAULTY FAN IN FEMALE CHANGING ROOM | LAG, OGUNLANA DRIVE | Wear & Tear | Breakdown | TIMILEHIN | WALL FAN | HVAC | 2024-11-07 | 67 | 2024-11-08 | 1 | 2024-11-08 | 0 | 2024-11-08 | 2024-11-08 | 0 | 2024-11-08 | 0 | 2024-11-08 | 66 | 2025-01-13 | 28000 | Completed | 2025-01-13 | 1
531 | STATUS UPDATE: NAFDAC GHP INSPECTION AT CR IDI-IROKO | LAG, IDI-IROKO RD | Others | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-11-16 | 124 | 2024-11-16 | 0 | 2024-11-16 | 0 | [9 empty] | Overdue
532 | FAULTY CHIPS FRYER MACHINE | LAG, BADORE | Wear & Tear | Breakdown | ECS | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-11-13 | 127 | 2024-11-13 | 0 | 2024-11-18 | 5 | 2024-11-18 | 2024-11-18 | 0 | 2024-11-18 | 4 | 2024-11-22 | 118 |  | 90250 | Overdue
533 | FAULTY CHIPS FRYER | LAG, FREEDOMWAY | Wear & Tear | Breakdown | ISMAIL | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-11-15 | 4 | 2024-11-15 | 0 | 2024-11-19 | 4 | 2024-11-19 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 | 0 | 2024-11-19 |  | Completed | 2024-11-19 | 1
534 | FAULTY SWING DOOR | OGUN, HEYDEN IBAFO | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-11-12 | 3 | 2024-11-13 | 1 | 2024-11-13 | 0 | 2024-11-14 | 2024-11-14 | 0 | 2024-11-14 | 0 | 2024-11-14 | 1 | 2024-11-15 | 75000 | Completed | 2024-11-15 | 1
535 | FAULTY SWING DOOR | LAG, OMOLE | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-11-04 | 1 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 2024-11-04 | 0 | 2024-11-04 | 0 | 2024-11-04 | 1 | 2024-11-05 |  | Completed | 2024-11-05 | 1
536 | Remodeling of Freedom way Car Park | LAG, FREEDOMWAY | Others | Breakdown | ARIZMANYA | OTHERS | OTHERS | 2024-11-20 | 120 | 2024-11-20 | 0 | 2024-12-24 | 34 | 2024-12-24 | 2025-01-02 | 9 | 2025-01-02 | 1 | 2025-01-03 | 76 |  |  | Overdue
537 | FAULTY CONNECTING PIPE IN FEMALE CUSTOMER REST ROOM
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
Formulas:
Days Since Request = IF([Request Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Request Date],TODAY()-[Request Date]))
Days Delayed by Helpdesk = IF([Date Shared by Helpdesk]<>"",[Date Shared by Helpdesk]-[Request Date],IF([Request Date]="","",TODAY()-[Request Date]))
Days Delayed by Vendor/Technician = IF(M6<>"",M6-[Date Shared by Helpdesk],IF([Date Shared by Helpdesk]="","",TODAY()-[Date Shared by Helpdesk]))
Days Since Negotiation Request = TODAY() - [Date Negotiated]
Days Since Negotiation Request = IF([Date Negotiated]<>"",[Date Negotiated]-[Date Sent for Negotiation],IF([Date Sent for Negotiation]="","",TODAY()-[Date Sent for Negotiation]))
Days Since Approval Request = IF([Approved Date]<>"",[Approved Date]-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval Request = IF([Approved Date]<>"",[Approved Date]-[Approved Date, row above],IF([Approved Date, row above]="","",TODAY()-[Approved Date, row above]))
Days Since Approval = IF([Approved Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Approved Date],TODAY()-[Approved Date]))
Status = IF([Request Date]="","",IF([Actual delivery date]<>"","Completed",IF(TODAY()<[Expected Delivery Date],"Planned",IF(TODAY()=[Expected Delivery Date],"Due","Overdue"))))
Note on AA6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vendor gave feedback thaat part is not available on 18 of Jan
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR SANGOTEDO
Note on C45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR SANGOTEDO
Note on C60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CHOP BOX OPEBI
Note on C66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IBADAN IWOROAD
Note on C80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PPU MOKOLA IBADAN
Note on G99: Inioluwa Okeowo: MIXER
Note on C105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PPU OKIGWE
Note on C137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CHOP BOX AGUNYI
Note on G139: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SAFE ROOM DOOR
Note on G161: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MALE AND FEMALE STAFF CHANGING ROOM
Note on C170: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IBADAN IWO ROAD
Note on C172: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR IYANA IYESI
Note on C185: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR IYANA IYESI
Note on C190: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR TAKIE ROAD
Note on C192: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR WAREHOUSE PH-DC
Note on G211: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: POTATO PEELER
Note on C225: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PPU MM WAY ILORIN
Note on C226: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR IBADAN IWO ROAD
Note on C241: Inioluwa Okeowo: PPU
Note on C251: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PPU UYO
Note on C256: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IYANA IYESI
Note on C273: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX ABULE EGBA
Note on C278: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX OKOTA
Note on C329: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX FAGBA
Note on C339: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX
Note on C344: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CB
Note on C363: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PPU
Note on C386: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX
Note on C391: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX

## DECMBER
Legend
Completed on time
Completed late
S/N | ACTION/TASK | Store | Reason for Breakdown | Maintenance Category | Responsible | Specific Equipment | Category | Request Date | Days Since Request | Date Shared by Helpdesk | Days Delayed by Helpdesk | Date Attended/Checked by Vendor/Technician | Days Delayed by Vendor/Technician | Date Sent for Negotiation | Date Negotiated | Days Since Negotiation Request | Date Approval Requested | Days Since Approval Request | Approved Date | Days Since Approval | Expected Delivery Date | Cost | Status | Actual delivery date | Compliance check | Insert Comment
1 | DETACHED DOOR HINGES IN CHIPS FRYER | PH, DOX RD | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-12-01 | 109 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 2024-12-01 | 109 | 2024-12-01 | 109 |  |  |  |  | Overdue
2 | STORE REPAIRS | IMO, OKIGWE | Electrical Surge | Breakdown | RANEX | OTHERS | OTHERS | 2024-12-04 | 106 | 2024-12-04 | 0 | 2024-12-04 | 0 | 2024-12-04 | 2024-12-04 | 0 | 2024-12-04 | 0 | 2024-12-04 | 106 |  | 96750 | Overdue
3 | STORE REPAIRS | IMO, OKIGWE | Others | Breakdown | DEACONESS | OTHERS | OTHERS | 2024-12-04 | 106 | 2024-12-04 | 0 | 2024-12-04 | 0 | [9 empty] | Overdue
4 | PIE EXPRESS OKE AFA MELTING CABINET CABLE | LAG, OKE-AFA | Electrical Surge | Breakdown | EMMAUEL | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-02 | 108 | 2024-12-02 | 0 | 2024-12-04 | 2 | [9 empty] | Overdue
5 | GENERATOR SERVICING | BAYELSA, TOMBIA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-03 | 107 | 2024-12-03 | 0 | 2024-12-03 | 0 | [9 empty] | Overdue
6 | GENERATOR SERVICING | PH, IWOFE | Routine Servicing | Preventive | CHRISTAIN | GENERATOR | GENERATOR | 2024-12-03 | 2 | 2024-12-04 | 1 | 2024-12-04 | 0 | 2024-12-04 | 2024-12-05 | 1 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 | 199750 | Completed | 2024-12-05 | 1
7 | REQUEST FOR GENERATOR SERVICING (CR LIMCA RD) | ANAMBRA, LIMCA RD, ONITSHA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-03 | 7 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-10 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 |  | Completed | 2024-12-10 | 1
8 | GENERATOR SERVICING | IBADAN, BODIJA | Routine Servicing | Preventive | SYMINETIAS | GENERATOR | GENERATOR | 2024-12-02 | 11 | 2024-12-02 | 0 | 2024-12-02 | 0 | 2024-12-07 | 2024-12-10 | 3 | 2024-12-10 | 2 | 2024-12-12 | 1 | 2024-12-13 | 413437.5 | Completed | 2024-12-13 | 1
9 | SERVICING OF GAS BURNER/ GAS LEAKAGE AT SOCKET JOINT | LAG, EKORO | Routine Servicing | Preventive | BERRADE | GAS CYLINDER | GAS | 2024-12-03 | 107 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-04 | 2024-12-04 | 0 | 2024-12-04 | 0 | 2024-12-04 | 106 |  | 115250 | Overdue
10 | FAULTY COLD ROOM | AKWA IBOM, ORON RD | Wear & Tear | Breakdown | MOFFEEN | COLD ROOM UNIT | HVAC | 2024-12-01 | 109 | 2024-12-02 | 1 | 2024-12-03 | 1 | 2024-12-04 | 2024-12-04 | 0 | 2024-12-04 | 106 |  |  |  | 300000 | Overdue
12 | GAS LEAKAGE | LAG, OBA AKRAN | Routine Servicing | Preventive | BERRADE | GAS CYLINDER | GAS | 2024-12-03 | 107 | 2024-12-03 | 0 | 2024-12-04 | 1 | 2024-12-04 | 2024-12-04 | 0 | 2024-12-04 | 0 | 2024-12-04 | 106 |  | 104000 | Overdue
13 | GAS LEAKAGE |  | Routine Servicing | Preventive | BERRADE | GAS CYLINDER | GAS | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-03 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-03 | 90000 | Completed | 2024-12-03 | 1
14 | FAULTY GAS REGULATOR | IBADAN, RING-ROAD | Routine Servicing | Preventive | BERRADE | GAS CYLINDER | GAS | 2024-11-30 | 110 | 2024-12-01 | 1 | 2024-12-01 | 0 | 2024-12-02 | 2024-12-02 | 0 | 2024-12-02 | 0 | 2024-12-02 | 108 | 2024-12-04 | 240000 | Overdue
15 | INSECT ELECTROCUTOR BULB BAD | LAG, BODE THOMAS | Wear & Tear | Breakdown | TIMILEHIN | INSECT KILLER LOBBY 1 | ELECTRICAL | 2024-12-02 | 2 | 2024-12-02 | 0 | 2024-12-04 | 2 | 2024-12-04 | 2024-12-04 | 0 | 2024-12-04 | 0 | 2024-12-04 | 0 | 2024-12-04 |  | Completed | 2024-12-04 | 1
16 | AC SERVICING - AWKA ROAD | ANAMBRA, AWKA RD, ONITSHA | Routine Servicing | Preventive | MOFFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-12-04 | 106 | 2024-12-04 | 0 |  | 106 | [9 empty] | Overdue
17 | FAULTY WALL SOCKETS IN THE KITCHEN | LAG, OMOLE | Others | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-12-04 | 2 | 2024-12-04 | 0 | 2024-12-04 | 0 | 2024-12-06 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 |  | Completed | 2024-12-06 | 1
18 | REQUEST FOR CABINET BULB | LAG, AWOLOWO 2 | Electrical Surge | Breakdown | RANEX | OTHERS | OTHERS | 2024-12-05 | 1 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-06 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 |  | Completed | 2024-12-06 | 1
19 | FAULTY ROLLER SHUTTER | LAG, AJOSE ADEOGUN | Routine Servicing | Preventive | PENTICOSTAL | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-12-05 | 1 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 | 2024-12-05 | 0 | 2024-12-05 | 1 | 2024-12-06 | 0 | 2024-12-06 | 139965 | Completed | 2024-12-06 | 1
20 | REQUEST FOR LED LIGHT | IBADAN, RING-ROAD | Electrical Surge | Breakdown | RANEX | OTHERS | OTHERS | 2024-12-04 | 3 | 2024-12-04 | 0 | 2024-12-04 | 0 | 2024-12-05 | 2024-12-05 | 0 | 2024-12-05 | 1 | 2024-12-06 | 1 | 2024-12-07 | 48375 | Completed | 2024-12-07 | 1
21 | REQUEST FOR LED LIGHT,MOTOR STARTER AND SOCKET | IBADAN, VENTURA MALL | Electrical Surge | Breakdown | RANEX | OTHERS | OTHERS
22 | FAULTY WARMER HANDLE | LAG, LEKKI PHASE 1 | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-12-03 | 107 | 2024-12-03 | 0 | 2024-12-06 | 3 | 2024-12-06 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 | 104 |  | 152650 | Overdue
23 | DEAD INSECTROCUTOR BULBS | LAG, DIYA STREET | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 |  | Completed | 2024-12-06 | 1
24 | Septic tank flll up | LAG, MOBIL OGBA | Others | Breakdown | PENTICOSTAL | SEPTIC TANK | EVACUATION | 2024-12-05 | 1 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 | 1 | 2024-12-06 | 240000 | Completed | 2024-12-06 | 1
25 | PX OGUDU CABINET NOT ATTAINING TEMPERATURE | LAG, OGUDU | Others | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-12-04 | 2 | 2024-12-04 | 0 | 2024-12-04 | 0 | 2024-12-06 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 |  | Completed | 2024-12-06 | 1
26 | CRITICAL WATER ISSUES | ILORIN, MM WAY | Corrective Action | Corrective | PROEQUIP | WATER TREATMENT PLANT BLD | BUILDING | 2024-12-03 | 107 | 2024-12-05 | 2 | 2024-12-06 | 1 | 2024-12-06 | 2024-12-06 | 0 | 2024-12-07 | 0 | 2024-12-07 | 103 |  | 600000 | Overdue
28 | FAULTY FREEZER ROOM BULB | OGUN, HEYDEN IBAFO | Routine Servicing | Preventive | MOSES | FREEZER ROOM | HVAC | 2024-12-06 | 6 | 2024-12-06 | 0 | 2024-12-12 | 6 | 2024-12-12 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 |  | Completed | 2024-12-12 | 1
29 | FAULTY KETTLE | LAG, OBA AKRAN | Users Misuse | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-12-06 | 104 | 2024-12-06 | 0 |  | 104 | [9 empty] | Overdue
30 | Faulty Cabinet lamp holders | LAG, OSOLOWAY | Others | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-12-03 | 2 | 2024-12-03 | 0 | 2024-12-05 | 2 | 2024-12-05 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 |  | Completed | 2024-12-05 | 1
31 | FAULTY CABINET LAMP HOLDERS | LAG, ONIRU | Others | Breakdown | KITCHTEC | OTHERS | OTHERS | 2024-12-06 | 104 | 2024-12-06 | 0 |  | 104 | [9 empty] | Overdue
32 | FAULTY CHIPS FRYER |  | Users Misuse | Breakdown | HEFHEM | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-12-06 | 104 | 2024-12-06 | 0 |  | 104 | [9 empty] | Overdue
33 | FAULTY CHIPS FRYER | LAG, AJOSE ADEOGUN | Users Misuse | Breakdown | KITCHTEC | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-12-05 | 105 | 2024-12-05 | 0 |  | 105 | [9 empty] | Overdue
34 | FAULTY CHIPS FRYER COMPARTMENT | LAG, AWOLOWO 2 | Users Misuse | Breakdown | BCE | OTHERS | OTHERS | 2024-12-03 | 107 | 2024-12-03 | 0 |  | 107 | [9 empty] | Overdue
35 | CABINET NOT ATTAINING TEMPERATURE | LAG, AKOWONJO | Others | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-06 | 104 | 2024-12-06 | 0 | 2024-12-06 | 0 | [9 empty] | Overdue
36 | PX OGUDU CABINET NOT ATTAINING TEMPERATURE | LAG, OGUDU | Others | Breakdown | TIMILEHIN | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-04 | 2 | 2024-12-04 | 0 | 2024-12-05 | 1 | 2024-12-06 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 |  | Completed | 2024-12-06 | 1
37 | PLANTING OF FLOWER AT FLOWER BED | OSUN, AYETORO | Corrective Action | Corrective | DEFAVOURS | OTHERS | OTHERS | 2024-12-05 | 4 | 2024-12-05 | 0 | 2024-12-06 | 1 | 2024-12-06 | 2024-12-06 | 0 | 2024-12-06 | 104 |  |  | 2024-12-09 | 603075 | Completed | 2024-12-09 | 1
38 | FAULTY INSECTICUTOR BULB | LAG, IRE-AKARI | Electrical Surge | Breakdown | EMMANUEL | INSECT KILLER BOH | ELECTRICAL | 2024-12-06 | 104 | 2024-12-06 | 0 | 2024-12-06 | 0 | [9 empty] | Overdue
39 | LEAKING GAS AND SLOW BURNING BURNERS | LAG, BADORE | Corrective Action | Corrective | BERRADE | GAS CYLINDER | GAS | 2024-12-05 | 5 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-06 | 2024-12-06 | 0 | 2024-12-09 | 0 | 2024-12-09 | 1 | 2024-12-10 | 270000 | Completed | 2024-12-10 | 1
40 | FREEZER ROOM BREAKDOWN | LAG, OGUDU | Routine Servicing | Preventive | DETONA | FREEZER ROOM | HVAC | 2024-12-07 | 103 | 2024-12-07 | 0 |  | 103 | [9 empty] | Overdue
41 | FAULTY INVERTER AT ADEOLA ODEKU |  | Corrective Action | Corrective | CURRENT | INVERTER BATTERIES | INVERTER | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 | 0 | [7 empty] | 2024-12-05 | 556762.5 | Completed | 2024-12-05 | 1
42 | STORE GENERATOR DUE FOR SERVICING | PH, TRANS AMADI | Routine Servicing | Preventive |  | GENERATOR | GENERATOR | 2024-12-07 | 103 | 2024-12-07 | 0 |  | 103 | [9 empty] | Overdue
43 | FAULTY WARMER | LAG, ALIMOSHO | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-12-06 | 104 | 2024-12-06 | 0 |  | 104 | [9 empty] | Overdue
44 | FAULTY WARMER | LAG, TEJUOSHO | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-12-02 | 108 | 2024-12-02 | 0 |  | 108 | [9 empty] | Overdue
45 | BROKEN STORE ENTRANCE | OSUN, GBONGAN | Wear & Tear | Breakdown | DEFAVOURS | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-12-06 | 1 | 2024-12-06 | 0 | 2024-12-07 | 1 | 2024-12-07 | 2024-12-09 | #REF! | 2024-12-09 | 0 | 2024-12-09 | -2 | 2024-12-07 | 471000 | Completed | 2024-12-07 | 1
46 | REQUEST FOR COLLECTOR GASKET FOR 6 HEAD MACHINE | OYO, OWODE | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-12-07 | 103 | 2024-12-07 | 0 | 2024-12-07 | 0 | [9 empty] | Overdue
47 | FAULTY CUSTOMER REST ROOM DOOR |  | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-12-06 | 104 | 2024-12-07 | 1 |  | 103 | [9 empty] | Overdue
48 | FAULTY CUSTOMER REST ROOM DOOR LOCK. | LAG, TEJUOSHO | Wear & Tear | Breakdown |  | OTHERS | OTHERS | 2024-12-07 | 1 | 2024-12-07 | 0 | 2024-12-08 | 1 | [7 empty] | 2024-12-08 |  | Completed | 2024-12-08 | 1
49 | FAULTY CUSTOMER REST ROOM DOOR LOCK. | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-12-03 | 107 | 2024-12-03 | 0 |  | 107 | [9 empty] | Overdue
50 | Urgent need for re- painting PPU Mokola |  | Wear & Tear | Breakdown | DEFAVOURS | PAINTING | BUILDING | 2024-12-06 | 104 | 2024-12-06 | 0 | 2024-12-07 | 1 | 2024-12-07 |  | 103 | [6 empty] | Overdue
51 | FAULTY TOASTER | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2024-12-07 | 103 | 2024-12-07 | 0 |  | 103 | [9 empty] | Overdue
52 | DEAD BULBS AT BOH |  | Electrical Surge | Breakdown | ADEREMI | INSECT KILLER BOH | ELECTRICAL | 2024-12-07 | 5 | 2024-12-07 | 0 | 2024-12-12 | 5 | 2024-12-12 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 |  | Completed | 2024-12-12 | 1
53 | Faulty generator fuel pump. | IBADAN, CHALLENGE | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-12-07 | 103 | 2024-12-07 | 0 |  | 103 | [9 empty] | Overdue
54 | GAS LEAKAGE | LAG, IRE-AKARI | Corrective Action | Corrective | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-12-07 | 103 | 2024-12-07 | 0 | 2024-12-07 | 0 | [9 empty] | Overdue
55 | DAILY EQJUIPMENT STATUS | PPU Ajah | Others | Breakdown | ACORN | OTHERS | OTHERS | 2024-12-04 | 106 | 2024-12-04 | 0 | 2024-12-05 | 1 | 2024-12-18 |  | 92 | [5 empty] | 999750 | Overdue
56 | DAILY EQJUIPMENT STATUS | PPU Ajah | Others | Breakdown | BCE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2024-12-04 | 106 | 2024-12-04 | 0 |  | 106 | [9 empty] | Overdue
57 | DAILY EQJUIPMENT STATUS | PPU Ajah | Others | Breakdown | TONA OGUNS | OTHERS | OTHERS | 2024-12-04 | 9 | 2024-12-04 | 0 | 2024-12-08 | 4 | 2024-12-08 | 2024-12-09 | 1 | 2024-12-09 | 0 | 2024-12-09 | 4 | 2024-12-13 | 365000 | Completed | 2024-12-13 | 1
58 | FAULTY TAP HEAD AT FRYER SECTION | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | PROEQUIP | TAP | PLUMBING | 2024-12-03 | 16 | 2024-12-03 | 0 | 2024-12-11 | 8 | [7 empty] | 2024-12-19 |  | Completed | 2024-12-19 | 1
59 | FAULTY ROTESSERIE MACHINE | PH, OMOKU | Wear & Tear | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-12-05 | 105 | 2024-12-05 | 0 |  | 105 | [9 empty] | Overdue
60 | Faulty under bar chiller | LAG, DOMINO E-CENTRE | Wear & Tear | Breakdown | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-12-06 | 104 | 2024-12-06 | 0 |  | 104 | [9 empty] | Overdue
61 | GENERATOR BATERRY NOT WORKING | LAG, HEYDEN ALAPERE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-06 | 104 | 2024-12-06 | 0 | 2024-12-06 | 0 | [9 empty] | Overdue
62 | FAULTY CABBAGE SHREDDER | LAG, OSOLOWAY | Wear & Tear | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-12-07 | 103 | 2024-12-07 | 0 | 2024-12-07 | 0 | [9 empty] | Overdue
63 | GENERATOR DUE FOR SERVICING | LAG, GBAGADA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-05 | 105 | 2024-12-05 | 0 | 2024-12-05 | 0 | [9 empty] | Overdue
64 | GENERATOR DUE FOR SERVICING | DELTA, EFFURUN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-04 | 106 | 2024-12-04 | 0 | 2024-12-05 | 1 | [9 empty] | Overdue
65 | GENERATOR DUE FOR SERVICING - CR AWKA ROAD, ONITSHA. | ANAMBRA, AWKA RD, ONITSHA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-02 | 108 | 2024-12-02 | 0 | 2024-12-03 | 1 | [9 empty] | Overdue
66 | GENERATOR DUE FOR SERVICING | LAG, LEKKI PHASE 1 | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-06 | 104 | 2024-12-06 | 0 | 2024-12-06 | 0 | [9 empty] | Overdue
67 | GENERATOR DUE FOR SERVICING | LAG, IRE-AKARI | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-12-05 | 105 | 2024-12-05 | 0 |  | 105 | [9 empty] | Overdue
68 | GENERATOR DUE FOR SERVICING | LAG, ILUPEJU | Routine Servicing | Preventive | DELIGHT | GENERATOR | GENERATOR | 2024-12-04 | 106 | 2024-12-04 | 0 |  | 106 | [9 empty] | Overdue
69 | FILLED SEPTIC TANK | LAG, IDI-IROKO RD | Corrective Action | Corrective | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-12-01 | 109 | 2024-12-02 | 1 |  | 108 | [9 empty] | Overdue
70 | EVACUATION OF FILLED SEPTIC TANK | LAG, IPAJA RD | Corrective Action | Corrective | MOONLIGHT | SEPTIC TANK | EVACUATION |  | #VALUE! | 2024-12-04 | #VALUE! |  | 106 | [9 empty] | Overdue
71 | FUALTY CUSTOMERS REST ROOM AC | LAG, GBAGADA | Routine Servicing | Preventive | THIO & PARTNERS | 5HP STANDING AC UNIT 1 | HVAC | 2024-12-08 | 0 | 2024-12-08 | 0 | 2024-12-08 | 0 | 2024-12-08 | 2024-12-08 | 0 | 2024-12-08 | 0 | 2024-12-08 | 0 | 2024-12-08 |  | Completed | 2024-12-08 | 1
72 | WATER LEAKAGE FROM PIPE CONNECTED TO UNOX MACHINE | LAG, AWOLOWO | Wear & Tear | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-12-05 | 105 | 2024-12-05 | 0 | 2024-12-10 | 5 | [9 empty] | Overdue
73 | BAD DOUBLE FACE CHILLER | LAG, AWOLOWO | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2024-12-05 | 105 | 2024-12-05 | 0 |  | 105 | [9 empty] | Overdue
74 | FAULTY LOBBY AC | LAG, FREEDOMWAY | Routine Servicing | Preventive | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-12-06 | 104 | 2024-12-06 | 0 |  | 104 | [9 empty] | Overdue
75 | COLLECTROMATTRIC MACHINE FAULTY | LAG, FREEDOMWAY | Wear & Tear | Breakdown | BCE | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2024-12-06 | 104 | 2024-12-06 | 0 |  | 104 | [9 empty] | Overdue
76 | FAULTY PASTRY MIXER | ENUGU, CHIME AVENUE | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2024-12-01 | 109 | 2024-12-01 | 0 | 2024-12-07 | 6 | [9 empty] | Overdue
77 | REQUEST FOR SOAP DISPENSER | IBADAN, MOKOLA | Others | Breakdown | PRO-EQUIP | OTHERS | OTHERS | 2024-12-06 | 104 | 2024-12-06 | 0 |  | 104 | [9 empty] | Overdue
78 | COOK SINK IS FAULTY | LAG, FREEDOMWAY | Others | Breakdown | JOEL OMOTOSHO | KITCHEN WASH HAND SINK | PLUMBING | 2024-12-09 | 101 | 2024-12-09 | 0 |  | 101 | [9 empty] | Overdue
79 | CR AJOSE PENDING MAINTENANCE ISSUE_.xlsx | LAG, AJOSE ADEOGUN | Others | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-12-09 | 101 | 2024-12-09 | 0 | 2024-12-09 | 0 | [9 empty] | Overdue
80 | WARMER MAKING NOISE | LAG, AJAH | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2024-12-06 | 104 | 2024-12-06 | 0 | 2024-12-06 | 0 |  |  | #VALUE! | [6 empty] | Overdue
81 | DAILY EQJUIPMENT STATUS | PPU Ajah | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-12-04 | 106 | 2024-12-04 | 0 | 2024-12-08 | 4 | 2024-12-08 | 2024-12-09 | 1 | [6 empty] | Overdue
82 | FAULTY GENERATOR ( OVERSPEED) | IBADAN, AKOBO | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-12-02 | 108 | 2024-12-02 | 0 | 2024-12-02 | 0 | [9 empty] | Overdue
83 | GENERATOR SERVICE REQUEST - CR NSUKKA | ENUGU, NSUKKA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-02 | 108 | 2024-12-02 | 0 |  | 108 | [9 empty] | Overdue
84 | FAULTY GENERATOR BATTERY - CR NSUKKA | ENUGU, NSUKKA | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-12-03 | 8 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-03 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-03 | 8 | 2024-12-11 | 185000 | Completed | 2024-12-11 | 1
85 | WATERWORKS Generator Service Request (004) (002).xlsx | EBONYI, WATERWORKS, ABAKALIKI | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-04 | 106 | 2024-12-04 | 0 |  | 106 | [9 empty] | Overdue
86 | MAINTENANCE REQUEST | EDO, RAHMAT PARK, BENIN | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-12-04 | 106 | 2024-12-04 | 0 | 2024-12-04 | 0 | [9 empty] | Overdue
87 | GENERATOR SERVICING | BAYELSA, OPOLO | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-12-06 | 104 | 2024-12-06 | 0 |  | 104 | [9 empty] | Overdue
88 | FREEZER ROOM NOT COMING UP | IMO, WETHERAL RD, OWERRI | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-12-02 | 4 | 2024-12-06 | 4 | 2024-12-06 | 0 | 2024-12-06 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 |  | Completed | 2024-12-06 | 1
89 | GENERATOR DUE FOR SERVICING | IBADAN, IDI-APE (IWO RD) | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-08 | 102 | 2024-12-08 | 0 | 2024-12-09 | 1 | [9 empty] | Overdue
90 | FREEZER ROOM NOT COMING UP | IMO, WETHERAL RD, OWERRI | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-12-09 | 101 | 2024-12-09 | 0 | 2024-12-16 | 7 | [9 empty] | Overdue
91 | LOW ENGINE OIL | LAG, OGUNLANA DRIVE | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-12-09 | 1 | 2024-12-09 | 0 | 2024-12-09 | 0 | 2024-12-09 | 2024-12-09 | 0 | 2024-12-09 | 0 | 2024-12-09 | 1 | 2024-12-09 |  | Completed | 2024-12-10 | 0
92 | GENERATOR DUE FOR SERVICING | DELTA, ISOKO RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-10 | 100 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 | 100 |  |  | Overdue
93 | GENERATOR DUE FOR SERVICING | IBADAN, AKOBO | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-10 | 100 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 | 100 |  |  | Overdue
94 | GENERATOR DUE FOR 1ST SERVICE | LAG, DIYA STREET | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-10 | 1 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 | 1 | 2024-12-11 |  | Completed | 2024-12-11 | 1
95 | GENERATOR BATTERY NOT WORKING | LAG, HEYDEN ALAPERE | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-12-07 | 103 | 2024-12-07 | 0 |  | 103 | [9 empty] | Overdue
96 | GENERATOR SERVICE | EDO, UGBOWO, BENIN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-06 | 104 | 2024-12-06 | 0 | 2024-12-06 | 0 | [9 empty] | Overdue
97 | BAD GENRATOR RADIATOR | ANAMBRA, ZIK AVENUE, AWKA | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-12-10 | 100 | 2024-12-10 | 0 | 2024-12-11 | 1 | [9 empty] | Overdue
98 | GENSET SERVICING | BAYELSA, TOMBIA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-11 | 2 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 | 2 | 2024-12-13 | 202450 | Completed | 2024-12-13 | 1
99 | GENERATOR BREAKDOWN | EDO, SAPELE RD, BENIN | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 |  | Completed | 2024-12-11 | 1
100 | GENERATOR BREAKDOWN | LAG, OBA AKRAN | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-12-12 | 98 | 2024-12-12 | 0 | 2024-12-12 | 0 | [9 empty] | Overdue
101 | GENERATOR NOT STARTING | LAG, AKOWONJO | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-12-12 | 98 | 2024-12-12 | 0 | 2024-12-12 | 0 | [9 empty] | Overdue
102 | GENERATOR SERVICING | LAG, AJOSE ADEOGUN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-13 | 97 | 2024-12-13 | 0 | 2024-12-13 | 0 |  |  |  |  | #REF! |  | #REF! |  |  | Overdue
103 | GENERATOR DUE FOR SERVICE | ILORIN, OFFA GARAGE | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-12-03 | 107 | 2024-12-03 | 0 |  | 107 | [9 empty] | Overdue
104 | GENERATOR DUE FOR SERVICING | ILORIN, OLOFAWAY | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-12-03 | 107 | 2024-12-03 | 0 |  | 107 | [9 empty] | Overdue
105 | LOBBY AC NOT COOLING | PH, TRANS AMADI | Routine Servicing | Preventive | CHRISTAIN | 5HP STANDING AC UNIT 1 | HVAC | 2024-12-15 | 95 | 2024-12-15 | 0 |  | 95 | [9 empty] | Overdue
106 | NO RUNNING WATER IN THE STORE | LAG, AWOLOWO | Corrective Action | Corrective | JOEL | TAP | PLUMBING | 2024-12-15 | 0 | 2024-12-15 | 0 | 2024-12-15 | 0 | 2024-12-15 | 2024-12-15 | 0 | 2024-12-15 | 0 | 2024-12-15 | 0 | 2024-12-15 |  | Completed | 2024-12-15 | 1
107 | DEAD INSECTOCUTOR BULBS | LAG, IKOTUN | Electrical Surge | Breakdown | EMMANUEL | OTHERS | OTHERS | 2024-12-15 | 95 | 2024-12-15 | 0 |  | 95 | [9 empty] | Overdue
108 | DEAD SECURITY BULB |  | Electrical Surge | Breakdown | EMMANUEL | OTHERS | OTHERS | 2024-12-11 | 4 | 2024-12-12 | 1 | 2024-12-15 | 3 | 2024-12-15 | 2024-12-15 | 0 | 2024-12-15 | 0 | 2024-12-15 | 0 | 2024-12-15 |  | Completed | 2024-12-15 | 1
109 | BROKEN TAP PIPE AT COOK SECTION | LAG, OGUNLANA DRIVE | Wear & Tear | Breakdown | OLUWATOSIN | TAP | PLUMBING | 2024-12-15 | 95 | 2024-12-15 | 0 |  | 95 | [9 empty] | Overdue
110 | FULTY INVERTER | LAG, ETERNA LEKKI | Others | Breakdown | DALEMATRIX | INVERTER DB | ELECTRICAL | 2024-12-11 | 99 | 2024-12-12 | 1 | 2024-12-13 | 1 | [9 empty] | Overdue
111 | GENERATOR SERVICES | EDO, SILUKO | Routine Servicing | Preventive |  | GENERATOR | GENERATOR | 2024-12-15 | 3 | 2024-12-15 | 0 | 2024-12-16 | 1 | 2024-12-16 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 2 | 2024-12-18 |  | Completed | 2024-12-18 | 1
112 | SEPTIC TANK FILL | LAG, JIBOWU | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-12-15 | 95 | 2024-12-15 | 0 | 2024-12-15 | 0 | [9 empty] | Overdue
113 | LOBBY AC'S NOT WORKING | PH, ONNE RD, GRA | Routine Servicing | Preventive | MOFFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-12-15 | 95 | 2024-12-15 | 0 |  | 95 | [9 empty] | Overdue
114 | LOBBY AC NOT WORKING | PH, ABACHA RD | Routine Servicing | Preventive | MOFFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2024-12-10 | 100 | 2024-12-10 | 0 |  | 100 | [9 empty] | Overdue
115 | OPEN WALL | LAG, IDIMU | Wear & Tear | Breakdown | PROPEAR | WALL | BUILDING | 2024-12-14 | 96 | 2024-12-15 | 1 |  | 95 | [9 empty] | Overdue
116 | OPEN WALL | Central Kitchen | Wear & Tear | Breakdown | ARIZMAYAN | WALL | BUILDING | 2024-12-15 | 95 | 2024-12-15 | 0 | 2024-12-15 | 0 | [9 empty] | Overdue
117 | BENT SIGNAGE | LAG, IDIMU | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-12-15 | 95 | 2024-12-15 | 0 | 2024-12-15 | 0 | [9 empty] | Overdue
118 | RUSTED PEELED PYLON AND SIGNAGE |  | Wear & Tear | Breakdown | JOWYN | OTHERS | OTHERS | 2024-12-14 | 96 | 2024-12-15 | 1 |  | 95 | [9 empty] | Overdue
119 | CUSTOMER BLOCKED TOILET | LAG, FREEDOMWAY | Corrective Action | Corrective | JOEL | OTHERS | OTHERS | 2024-12-13 | 97 | 2024-12-15 | 2 |  | 95 | [9 empty] | Overdue
120 | LOBBY AC NOT WORKUNG EFFECTIVELY | LAG, ETERNA LEKKI | Routine Servicing | Preventive | TONAOGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-12-14 | 96 | 2024-12-15 | 1 | 2024-12-28 | 13 | 2025-01-06 | 2025-01-07 | 1 | [6 empty] | Overdue
121 | WOBBLING TABLES | LAG, OGUDU | Corrective Action | Corrective | MATOLAD | CUSTOMER TABLE | FURNITURE | 2024-12-14 | 96 | 2024-12-15 | 1 |  | 95 | [9 empty] | Overdue
122 | DAAMAGED LOBBY DOOR |  | Wear & Tear | Breakdown | TAIDAV | OTHERS | OTHERS | 2024-12-15 | 95 | 2024-12-15 | 0 |  | 95 | [9 empty] | Overdue
123 | REPLACEMENT OF FAULTY STORE TV | LAG, JIBOWU | Wear & Tear | Breakdown | ACORN | TELEVISION | AUDIOVISUAL | 2024-12-15 | 95 | 2024-12-15 | 0 |  | 95 | [9 empty] | Overdue
124 | FOH GLASS DOOR ABOUT TO FALL | IBADAN, VENTURA MALL | Corrective Action | Corrective | DEFAVOURS | OTHERS | OTHERS | 2024-12-10 | 4 | 2024-12-10 | 0 | 2024-12-14 | 4 | 2024-12-14 | 2024-12-14 | 0 | 2024-12-15 | 0 | 2024-12-15 | -1 | 2024-12-14 | 148000 | Completed | 2024-12-14 | 1
125 | DEAD BULB AT PRODUCTION AREA AND BOH | LAG, OPEBI | Electrical Surge | Breakdown | FRIDAY | OTHERS | OTHERS | 2024-12-14 | 96 | 2024-12-15 | 1 |  | 95 | [9 empty] | Overdue
126 | REPAIR OF CONCRETE SLABS & CAR PARK | ILORIN, GRA | Wear & Tear | Breakdown | DEFAFOURS | OTHERS | OTHERS | 2024-12-09 | 101 | 2024-12-10 | 1 | 2024-12-13 | 3 | 2024-12-15 |  | 95 | [6 empty] | Overdue
127 | LEAKING SINK AT COOK WASHING AREA | LAG, OPEBI | Wear & Tear | Breakdown | ADEREMI | KITCHEN WASH HAND SINK | PLUMBING | 2024-12-14 | 96 | 2024-12-15 | 1 |  | 95 | [9 empty] | Overdue
128 | SEPTIC TANK EVACUATION | LAG, ALIMOSHO | Corrective Action | Corrective | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-12-14 | 4 | 2024-12-15 | 1 | 2024-12-16 | 1 | 2024-12-16 | 2024-12-16 | 0 | 2024-12-17 | 0 | 2024-12-17 | 1 | 2024-12-18 | 218977.5 | Completed | 2024-12-18 | 1
129 | SEPTIC TANK EVACUATION | LAG, IKORODU | Corrective Action | Corrective | MOONLIGHT
130 | FAULTY ICE CREAM MACHINE | ABUJA, KUBWA | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-12-01 | 109 | 2024-12-01 | 0 | 2024-12-13 | 12 | 2024-12-13 | 2024-12-13 | 0 | 2024-12-13 | 0 | 2024-12-13 | 97 |  |  | Overdue
131 | FAULTY ICE CREAM MACHINE | PH, GRA BIRABI | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-12-03 | 107 | 2024-12-04 | 1 | 2024-12-13 | 9 | 2024-12-13 | 2024-12-13 | 0 | 2024-12-13 | 97 |  |  |  |  | Overdue
132 | FAULTY ICE CREAM MACHINE | LAG, OKE-AFA | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-12-08 | 102 | 2024-12-08 | 0 | 2024-12-09 | 1 | 2024-12-09 | 2024-12-09 | 0 | 2024-12-09 | 1 | 2024-12-10 | 100 |  | 277229.67 | Overdue
133 | FAULTY ICE-CREAM MACHINE { TAYLOR MACHINE} | LAG, ILUPEJU | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-12-14 | 96 | 2024-12-15 | 1 |  | 95 | [9 empty] | Overdue
134 | FREEZER ROOM NOT WORKING | LAG, HEYDEN IPAJA | Wear & Tear | Breakdown | THIO& PARTNER | FREEZER ROOM | HVAC | 2024-12-11 | 99 | 2024-12-11 | 0 | 2024-12-17 | 6 | 2024-12-17 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 93 |  |  | Overdue
135 | FREEZER ROOM NOT WORKING | LAG, DIYA STREET | Wear & Tear | Breakdown | THIO& PARTNER | FREEZER ROOM | HVAC | 2024-12-15 | 2 | 2024-12-15 | 0 | 2024-12-17 | 2 | 2024-12-17 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 |  | Completed | 2024-12-17 | 1
136 | Cold room not working | PH, GRA BIRABI | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2024-12-07 | 103 | 2024-12-07 | 0 |  | 103 | [9 empty] | Overdue
137 | LEAKING SINK AT COOK WASHING AREA | LAG, OPEBI | Wear & Tear | Breakdown | ADEREMI WAHAB | KITCHEN WASH HAND SINK | PLUMBING | 2024-12-14 | 3 | 2024-12-15 | 1 | 2024-12-15 | 0 | 2024-12-15 | 2024-12-15 | 0 | 2024-12-15 | 0 | 2024-12-15 | 2 | 2024-12-17 |  | Completed | 2024-12-17 | 1
138 | BROKEN BOREHOLE PIPE | LAG, OGUDU | Wear & Tear | Breakdown | ADEREMI WAHAB | OTHERS | OTHERS | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 |  | Completed | 2024-12-17 | 1
139 | FAULTY FREEZER ROOM & Coldroom | IBADAN, AKOBO | Routine Servicing | Preventive | TONAOGUNS | FREEZER ROOM | HVAC | 2024-12-02 | 5 | 2024-12-02 | 0 | 2024-12-02 | 0 | 2024-12-02 | 2024-12-02 | 0 | 2024-12-02 | 0 | 2024-12-02 | 5 | 2024-12-07 | 92500 | Completed | 2024-12-07 | 1
140 | REQUEST FOR GAS BURNER SERVICING AND CHANGING OF BAD BURNER CONTROL. | LAG, ALIMOSHO | Routine Servicing | Preventive | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2024-12-02 | 108 | 2024-12-02 | 0 | 2024-12-03 | 1 | 2024-12-03 | 2024-12-03 | 0 | 2024-12-03 | 107 |  |  |  | 90150 | Overdue
141 | FAULTY FREEZER ROOM | LAG, IPAJA RD | Wear & Tear | Breakdown | TRIPPLE O | FREEZER ROOM | HVAC | 2024-12-03 | 6 | 2024-12-03 | 0 | 2024-12-04 | 1 | 2024-12-05 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 | 4 | 2024-12-09 | 491000 | Completed | 2024-12-09 | 1
142 | FAULTY FREEZER ROOM-YENAGOA | BAYELSA, YENAGOA | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-12-05 | 105 | 2024-12-05 |  |  | 105 | [9 empty] | Overdue
143 | FAULTY FREEZER ROOM DOOR HINGES | LAG, SKYMALL | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-12-05 | 105 | 2024-12-05 | 0 |  | 105 | [9 empty] | Overdue
144 | FAULTY FREEZER ROOM DOOR | LAG, IRE-AKARI | Wear & Tear | Breakdown | THIO & PARTNER | FREEZER ROOM | HVAC | 2024-12-06 | 104 | 2024-12-06 | 0 |  | 104 | [9 empty] | Overdue
145 | FAULTY FREEZER ROOM LIGHT | LAG, IRE-AKARI | Wear & Tear | Breakdown | FRIDAY | FREEZER ROOM | HVAC | 2024-12-10 | 100 | 2024-12-10 | 0 |  | 100 | [9 empty] | Overdue
146 | FAULTY FREEZER ROOM DOOR HANDLE | PPU Ajah | Others | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-12-13 | 97 | 2024-12-13 | 0 | 2024-12-19 | 6 | 2025-02-09 | 2025-02-09 | 0 | 2025-02-09 | 2 | 2025-02-11 | 37 |  | 160000 | Overdue
147 | FAULTY FREEZER ROOM BULB | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | ISMAIL | FREEZER ROOM | HVAC | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 |  | Completed | 2024-12-16 | 1
148 | FAULTY FREEZER ROOM AND COLD ROOM | BAYELSA, OPOLO | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-12-17 | 93 | 2024-12-17 | 0 |  | 93 | [9 empty] | Overdue
149 | FAULTY FREEZER ROOM DOOR | LAG, BADORE | Wear & Tear | Breakdown | ECS | FREEZER ROOM | HVAC | 2024-12-17 | 93 | 2024-12-17 | 0 |  | 93 | [9 empty] | Overdue
150 | MAINTENANCE ISSUES PICK DURING OSC | LAG, MAGODO | Others | Breakdown | PENTECOATAL | OTHERS | OTHERS | 2024-12-04 | 106 | 2024-12-04 | 0 | 2024-12-07 | 3 | 2024-12-07 | 2024-12-09 | 2 | [5 empty] | 900000 | Overdue
151 | COLLAPSING CEILING | ABIA, OGBOR HILLS | Wear & Tear | Breakdown | FULLTURN | CEILING BOARD | BUILDING | 2024-12-01 | 109 | 2024-12-01 | 0 | 2024-12-17 | 16 | 2024-12-17 | 2024-12-18 | 1 | 2024-12-18 | 92 |  |  |  | 276000 | Overdue
152 | DAMAGED CEELING AT C.R OKIGWE ROAD OWERRI | IMO, OKIGWE | Wear & Tear | Breakdown | FULLTURN | CEILING BOARD | BUILDING | 2024-12-13 | 97 | 2024-12-13 | 0 | 2024-12-18 | 5 | 2024-12-18 | 2024-12-18 | 0 | 2024-12-18 | 92 |  |  |  | 180000 | Overdue
153 | NEED FOR INVERTER FOR PPU PH, UYO, TOMBIA AND OWERRI |  | Others | Breakdown | PETOJA | INVERTER DB | ELECTRICAL | 2024-12-07 | 103 | 2024-12-08 | 1 | 2024-12-17 | 9 | 2024-12-18 | 2024-12-18 | 0 | [5 empty] | 3100000 | Overdue
154 | CHIPS FRYER NOT MELTING | IBADAN, RING-ROAD | Wear & Tear | Breakdown | KITCHTEC | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-12-12 | 98 | 2024-12-13 | 1 | 2024-12-18 | 5 | 2024-12-18 | 2024-12-18 | 0 | 2024-12-18 | 0 | 2024-12-18 | 92 |  |  | Overdue
155 | BROKEN SEWAGE PIPE | LAG, NNPC ALAPERE | Wear & Tear | Breakdown | PROEQUIP | OTHERS | OTHERS | 2024-12-16 | 94 | 2024-12-16 | 0 | 2024-12-18 | 2 | [9 empty] | Overdue
156 | UPRIGHT TANK DUE FOR WASHINING | LAG, FREEDOMWAY | Corrective Action | Corrective | JOEL | OVERHEAD WATER TANK | WTP | 2024-12-10 | 8 | 2024-12-10 | 0 | 2024-12-11 | 1 | [7 empty] | 2024-12-18 |  | Completed | 2024-12-18 | 1
157 | ICE CREAM MACHINE NOT COMING UP (SPACEMAN) | LAG, MAGODO | Routine Servicing | Preventive | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-12-14 | 96 | 2024-12-14 | 0 | 2024-12-17 | 3 | 2024-12-18 | 2024-12-18 | 0 | 2024-12-18 | 0 | 2024-12-18 | 92 |  | 408765.26 | Overdue
158 | EVACUATION OF SEPTIC TANK AND FAT TRAP | LAG, OKE-AFA | Corrective Action | Corrective | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-12-18 | 92 | 2024-12-18 | 0 |  | 92 | [9 empty] | Overdue
159 | FAULTY AC - CUSTOMER RESTROOM AND DRY STORE | OGUN, OKE-ILEWO | Routine Servicing | Preventive | ADEGBENRO | 5HP STANDING AC UNIT 4 | HVAC | 2024-12-18 | 59 | 2024-12-18 | 0 | 2025-02-15 | 59 | [7 empty] | 2025-02-15 |  | Completed | 2025-02-15 | 1
160 | 4 DEAD BULB IN THE CABINET | LAG, AWOLOWO | Electrical Surge | Breakdown |  |  |  | 2024-12-18 | 92 |  | 92 | [11 empty] | Overdue
161 | WASTE EVACUATION IN SEPTIC TANK | LAG, ALIMOSHO | Corrective Action | Corrective | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2024-12-14 | 4 | 2024-12-14 | 0 | 2024-12-17 | 3 | 2024-12-17 | 2024-12-18 | 1 | 2024-12-18 | 0 | 2024-12-18 | 0 | 2024-12-18 | 102125 | Completed | 2024-12-18 | 1
162 | BLOCKRD DRAINAGE | LAG, ONIRU | Corrective Action | Corrective | JOEL | OTHERS | OTHERS | 2024-12-17 | 1 | 2024-12-17 | 0 | 2024-12-18 | 1 | 2024-12-18 | 2024-12-18 | 0 | 2024-12-18 | 0 | 2024-12-18 | 0 | 2024-12-18 |  | Completed | 2024-12-18 | 1
163 | STORE AUDIT REPORT (19.12.24) | LAG, IDIMU | Wear & Tear | Breakdown | FRIDAY | UPRIGHT UNDERBAR MACHINE | HVAC | 2024-12-22 | 88 | 2024-12-23 | 1 |  | 87 | [9 empty] | Overdue
164 | GENERATOR BREAKDOWN | PH, RUMUOLA | Wear & Tear | Breakdown | PAGISEL | GENERATOR | GENERATOR | 2024-12-10 | 100 | 2024-12-10 | 0 | 2024-12-12 | 2 | 2024-12-16 | 2024-12-18 | 2 | 2024-12-23 | 0 | 2024-12-23 | 87 |  |  | Overdue
165 | 6 DEAD BULBS IN THE LOBBY | LAG, AWOLOWO | Electrical Surge | Breakdown | ISMAIL | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-12-18 | 92 | 2024-12-19 | 1 |  | 91 | [9 empty] | Overdue
166 | CRACKED FLOOR AND WALL TILES AROUND THE STORE | LAG, AWOLOWO | Wear & Tear | Breakdown | ACORN | WALL | BUILDING | 2024-12-18 | 92 | 2024-12-23 | 5 |  | 87 | [9 empty] | Overdue
167 | FAULTY ICE CREAM MACHINE | LAG, ONIRU | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-12-22 | 88 | 2024-12-22 | 0 |  | 88 | [9 empty] | Overdue
168 | INCOMPLET 3 PHASE OF ELECTRICITY SUPPLY | LAG, MOBIL OGBA | Electrical Surge | Breakdown | GBATMO | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-12-21 | 89 | 2024-12-21 | 0 |  | 89 | [9 empty] | Overdue
169 | OFFENCING GAS SMELL AT THE CONNECTION OF THE GAS | LAG, MAGODO | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-12-19 | 91 | 2024-12-19 | 0 | 2024-12-21 | 2 | 2024-12-21 | 2024-12-23 | 2 | [6 empty] | Overdue
170 | ALL COLD ROOM CHAMBERS AT PPU ONIRU NOT WORKING | PPU Oniru | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-12-23 | 87 | 2024-12-23 | 0 |  | 87 | [9 empty] | Overdue
171 | LOBBY AC NOT COOLING | LAG, AGUNGI | Routine Servicing | Preventive | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-12-24 | 86 | 2024-12-24 | 0 | 2024-12-25 | 1 | [9 empty] | Overdue
172 | REQUEST FOR 3 AIR VENTS | OSUN, AYETORO | Others | Breakdown | RANEX4WARD | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2024-12-26 | 84 | 2024-12-26 | 0 | 2024-12-26 | 0 | 2024-12-26 | 2024-12-26 | 0 | 2024-12-26 | 0 | 2024-12-26 | 84 | 2024-12-27 |  | Overdue
173 | 3 LOBBY AC DRIPPING WATER | LAG, AWOLOWO | Wear & Tear | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-12-23 | 87 | 2024-12-23 | 0 |  | 87 | [9 empty] | Overdue
174 | REPLACEMENT OF INSECT KILLER WITH BULBS. | LAG, MARINA | Electrical Surge | Breakdown | ISMAIL | INSECT KILLER BOH | ELECTRICAL | 2024-12-16 | 94 | 2024-12-16 | 0 |  | 94 | [9 empty] | Overdue
175 | TIMER SWITCH NOT FUNCTIONING | LAG, FREEDOMWAY | Wear & Tear | Breakdown | PRO-EQUIP | FILTRATION VESSEL 1 | WTP
176 | LEAKING FILTER TANK | LAG, FREEDOMWAY
177 | CR RUMUOLA GENERATOR BREAKDOWN | PH, RUMUOLA | Wear & Tear | Breakdown
178 | GENERATOR NOT CARRYING LOAD | ILORIN, GRA | Others | Breakdown | MIDTECH | GENERATOR | GENERATOR | 2024-12-20 | 90 | 2024-12-20 | 0 | 2024-12-27 | 7 | [9 empty] | Overdue
179 | GREASE TRAP NOT WORKING EFFECTIVELY | OGUN, OKE-ILEWO | Wear & Tear | Breakdown | PENTECOSTAL | GREASE TRAP | GREASE_TRAP | 2024-12-07 | 103 | 2024-12-07 | 0 | 2024-12-10 | 3 | 2024-12-10 |  | 100 | [5 empty] | 615000 | Overdue
180 | LEAKING AERATION TANK | EDO, SAKPOMBA | Wear & Tear | Breakdown | PRO-EQUIP | AERATION TANK | WTP | 2024-12-04 | 106 | 2024-12-04 | 0 |  | 106 | [9 empty] | Overdue
181 | BAD FLUSHER IN THE CUSTOMER RESTROOM | LAG, OBA AKRAN | Wear & Tear | Breakdown | PROPEARJEFF | SPLIT UNIT TOILET | HVAC | 2024-12-18 | 92 | 2024-12-18 | 0 | 2024-12-18 | 0 | [9 empty] | Overdue
182 | REQUEST FOR GENERATOR SERVICING + REPLAMNENT NEW TURBO CHARGER AT - CR-AZIKIWE RD, 10 AZIKIWE ROAD, UMUAHIA, ABIA - STATE | ABIA, AZIKIWE RD, UMUAHIA | Routine Servicing | Preventive | KB | GENERATOR | GENERATOR | 2024-12-14 | 96 | 2024-12-15 | 1 | 2024-12-15 | 0 | 2024-12-15 | 2024-12-15 | 0 | 2024-12-15 | 1 | 2024-12-16 | 94 |  | 1026625 | Overdue
183 | REQUEST FOR GENERATOR SERVICING + REPLAMNENT NEW TURBO CHARGER AT - CR-AZIKIWE RD, 10 AZIKIWE ROAD, UMUAHIA, ABIA - STATE | ABIA, AZIKIWE RD, UMUAHIA | Corrective Action | Corrective | KB | GENERATOR | GENERATOR | 2024-12-14 | 96 | 2024-12-15 | 1 | 2024-12-27 | 12 | 2024-12-27 | 2024-12-27 | 0 | 2024-12-27 | 0 | 2024-12-27 | 83 |  | 166625 | Overdue
184 | FAULTY WARMER AND TOASTER SOCKET | LAG, BODE THOMAS | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2024-12-27 | 83 | 2024-12-27 | 0 |  | 83 | [9 empty] | Overdue
185 | FAULTY WARMER | EDO, AIRPORT RD, BENIN | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-12-09 | 101 | 2024-12-09 | 0 | 2024-12-19 | 10 | 2025-01-09 | 2025-01-09 | 0 | 2025-03-09 | 11 |  |  |  |  | Overdue
186 | FAULTY WARMER | ABIA, OGBOR HILLS | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-12-21 | 89 | 2024-12-21 | 0 | 2024-12-21 | 0 | 2024-12-24 | 2024-12-24 | 0 | 2024-12-24 | 0 | 2024-12-24 | 86 |  | 581575 | Overdue
187 | FAULTY WARMER | LAG, IDIMU | Others | Breakdown | BCE | OTHERS | OTHERS | 2024-12-27 | 83 | 2024-12-27 | 0 | 2024-12-27 | 0 | [8 empty] | 215000 | Overdue
188 | A/C OUTDOOR UNIT BURLARY AND DRAINAGE COVER | LAG, ILUPEJU | Others | Breakdown | MODEL | OTHERS | OTHERS | 2024-12-27 | 83 | 2024-12-27 | 0 | 2024-12-27 | 0 | 2024-12-27 |  | 83 | [6 empty] | Overdue
189 | REPLACEMENT OF UNDER COUNTER QUEUE TABLE | LAG, OKOTA | Corrective Action | Corrective | MATOLAD | PRODUCTION TABLE | FURNITURE | 2024-12-25 | 85 | 2024-12-25 | 0 | 2024-12-25 | 0 | [9 empty] | Overdue
190 | AC DUE FOR SERVICE | ILORIN, MM WAY | Routine Servicing | Preventive | TONAOGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2024-12-22 | 5 | 2024-12-22 | 0 | 2024-12-24 | 2 | [7 empty] | 2024-12-27 |  | Completed | 2024-12-27 | 1
191 | REQUEST FOR LED LIGHT - CR OJOO | IBADAN, OJOO | Electrical Surge | Breakdown | RANEX | OTHERS | OTHERS | 2024-12-18 | 4 | 2024-12-18 | 0 | 2024-12-18 | 0 | 2024-12-18 | 2024-12-18 | 0 | 2024-12-18 | 92 |  |  | 2024-12-22 | 48375 | Completed | 2024-12-22 | 1
192 | REQUEST FOR LED LIGHT | OSUN, AYETORO | Electrical Surge | Breakdown | RANEX | OTHERS | OTHERS | 2024-12-17 | 7 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 7 | 2024-12-24 | 147275 | Completed | 2024-12-24 | 1
193 | FAULTY ROLLER SHUTTER | AKWA IBOM, IKOT EKPENE RD | Corrective Action | Corrective | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-12-05 | 22 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-12 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 | 15 | 2024-12-27 | 87720 | Completed | 2024-12-27 | 1
194 | FAULTY ROLLER SHUTTER | LAG, GBAGADA | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-12-24 | 86 | 2024-12-24 | 0 | 2024-12-24 | 0 | 2025-01-07 | 2025-01-07 | 0 | 2025-01-07 | 0 | 2025-01-07 | 72 |  | 135209.61 | Overdue
195 | FAULTY ROLLER SHORTER REMOTE | LAG, ALIMOSHO | Users Misuse | Breakdown | BASSCOMM | OTHERS | OTHERS | 2024-12-19 | 91 | 2024-12-19 | 0 | 2024-12-19 | 0 | 2024-12-20 | 2024-12-20 | 0 | 2024-12-20 | 2 | 2024-12-22 | 88 |  |  | Overdue
196 | FAULTY ROLLER SHUTTER | LAG, OGUDU | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-12-06 | 18 | 2024-12-06 | 0 | 2024-12-10 | 4 | 2024-12-17 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 7 | 2024-12-24 | 138880.48 | Completed | 2024-12-24 | 1
197 | FAULTY ROLLER SHUTTER | LAG, OKOTA | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-12-20 | 90 | 2024-12-20 | 0 | 2024-12-21 | 1 | 2024-12-21 | 2024-12-21 | 0 | 2024-12-21 | 0 | 2024-12-21 | 89 |  | 193500 | Overdue
198 | Faulty standing chiller Oniru PPU | PPU Oniru | Routine Servicing | Preventive | BCE | NBC CHILLER | HVAC | 2024-12-27 | 83 | 2024-12-27 | 0 |  | 83 | [9 empty] | Overdue
199 | FAULTY BURNER | LAG, IKORODU | Corrective Action | Corrective | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2024-12-22 | 88 | 2024-12-22 | 0 | 2024-12-27 | 5 | 2024-12-27 |  | 83 | [6 empty] | Overdue
200 | SEWAGE EVACUATION | LAG, ETERNA LEKKI | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-12-23 | 87 | 2024-12-23 | 0 | 2024-12-23 | 0 | [9 empty] | Overdue
201 | LOBBY AC NOT WORKING | LAG, TEJUOSHO | Routine Servicing | Preventive | GB | 5HP STANDING AC UNIT 1 | HVAC | 2024-12-26 | 84 | 2024-12-26 | 0 | 2024-12-27 | 1 | 2024-12-27 |  | 83 | [6 empty] | Overdue
202 | FAULTY CABINET BULB | LAG, GBAGADA | Wear & Tear | Breakdown | TIMILEHIN | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-02 | 1 | 2024-12-02 | 0 | 2024-12-03 | 1 | 2024-12-03 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-03 |  | Completed | 2024-12-03 | 1
203 | Faulty Cabinet lamp holders | LAG, OSOLOWAY | Wear & Tear | Breakdown | TIMILEHIN | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-03 | 2 | 2024-12-03 | 0 | 2024-12-05 | 2 | 2024-12-05 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 |  | Completed | 2024-12-05 | 1
204 | CABINET LAMP HOLDER | LAG, AWOLOWO | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-04 | 3 | 2024-12-04 | 0 | 2024-12-07 | 3 | 2024-12-07 | 2024-12-07 | 0 | 2024-12-07 | 0 | 2024-12-07 | 0 | 2024-12-07 |  | Completed | 2024-12-07 | 1
205 | FAULTY CABINET | LAG, IKOTUN | Wear & Tear | Breakdown | EMMANUEL | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-16 | 3 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 3 | 2024-12-19 |  | Completed | 2024-12-19 | 1
206 | FAULTY CABINET | LAG, IDIMU | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-23 | 87 | 2024-12-23 | 0 |  | 87 | [9 empty] | Overdue
207 | FAULTY CABINET FLAP | LAG, AGUNGI | Wear & Tear | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-22 | 2 | 2024-12-22 | 0 | 2024-12-22 | 0 | 2024-12-22 | 2024-12-22 | 0 | 2024-12-22 | 0 | 2024-12-22 | 2 | 2024-12-24 |  | Completed | 2024-12-24 | 1
208 | FAULTY CABINET | AKWA IBOM, IKOT EKPENE RD | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-28 | 82 | 2024-12-28 | 0 | 2024-12-28 | 0 | 2024-12-31 | 2024-12-31 | 0 | 2024-12-31 | 0 | 2024-12-31 | 79 | 2025-01-01 |  | Overdue
209 | FAULTY CHIPS COMPARTMENT | ENUGU, CHIME AVENUE | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-01 | 109 | 2024-12-01 | 0 |  | 109 | [9 empty] | Overdue
210 | FILLED SEPTIC TANK | LAG, IDI-IROKO RD | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-12-14 | 96 | 2024-12-14 | 0 |  | 96 | [9 empty] | Overdue
211 | EVACUATION OF FILLED SEPTIC TANK | LAG, IPAJA RD | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-12-17 | 93 | 2024-12-17 | 0 |  | 93 | [9 empty] | Overdue
212 | FILLED SEPTIC TANK |  | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-12-22 | 3 | 2024-12-22 | 0 | 2024-12-24 | 2 | 2024-12-24 | 2024-12-25 | 1 | 2024-12-25 | 0 | 2024-12-25 | 0 | 2024-12-25 |  | Completed | 2024-12-25 | 1
213 | FILLED SEPTIC TANK | LAG, IDI-IROKO RD | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-12-27 | 83 | 2024-12-27 | 0 |  | 83 | [9 empty] | Overdue
214 | PIE EXPRESS OKE AFA MELTING CABINET CABLE | LAG, OKE-AFA | Electrical Surge | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-05 | 105 | 2024-12-05 | 0 | 2025-01-08 | 34 | 2025-01-09 | 2025-01-09 | 0 | 2025-01-09 | 70 |  |  |  |  | Overdue
215 | FREEZER NOT FROZEN | LAG, MARINA | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-12-10 | 100 | 2024-12-11 | 1 | 2024-12-12 | 1 | 2024-12-16 | 2024-12-17 | 1 | 2024-12-17 | 0 | 2024-12-17 | 93 |  | 195000 | Overdue
216 | FREEZER NOT ATTAINING TEMPERATURE | ABIA, ADAZI RD | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-12-08 | 102 | 2024-12-09 | 1 |  | 101 | [9 empty] | Overdue
217 | OPEN CEILING IN MANAGER OFFICE | LAG, VGC | Wear & Tear | Breakdown | MATOLAD | CEILING BOARD | BUILDING | 2024-12-13 | 97 | 2024-12-13 | 0 | 2025-01-09 | 27 | [9 empty] | Overdue
218 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, VGC | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-12-28 | 82 | 2024-12-29 | 1 | 2025-01-02 | 4 | 2025-01-08 | 2025-01-27 | 19 | 2025-01-27 | 12 | 2025-02-08 | 40 |  | 446000 | Overdue
219 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-12-30 | 4 | 2024-12-31 | 1 | 2025-01-03 | 3 | 2025-01-03 | 2025-01-03 | 0 | 2025-01-03 | 0 | 2025-01-03 | 0 | 2025-01-03 |  | Completed | 2025-01-03 | 1
220 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, OGUNLANA DRIVE | Wear & Tear | Breakdown | BB COMMERCIAL | COLD ROOM UNIT | HVAC | 2024-12-29 | 2 | 2024-12-29 | 0 | 2024-12-31 | 2 | 2024-12-31 | 2024-12-31 | 0 | 2024-12-31 | 0 | 2024-12-31 | 0 | 2024-12-31 |  | Completed | 2024-12-31 | 1
221 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | THIO & PARTNERS | COLD ROOM UNIT | HVAC | 2024-12-28 | 82 | 2024-12-29 | 1 |  | 81 | [9 empty] | Overdue
222 | COLD ROOM NOT ATTAINING TEMPERATURE | AKWA IBOM, AKA RD | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2024-12-22 | 88 | 2024-12-22 | 0 |  | 88 | [9 empty] | Overdue
223 | FREEZER ROOM AND COLD ROOM NOT ATTAINING TEMPERATURE | OSUN, AYETORO | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2024-12-17 | 93 | 2024-12-17 | 0 | 2024-12-18 | 1 | [9 empty] | Overdue
224 | COLD ROOM NOT ATTAINING TEMPERATURE | PH, TRANS AMADI | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-12-12 | 98 | 2024-12-12 | 0 |  | 98 | [9 empty] | Overdue
225 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, SKYMALL | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2024-12-01 | 109 | 2024-12-01 | 0 | 2024-12-02 | 1 | [9 empty] | Overdue
226 | COLD ROOM NOT ATTAINING TEMPERATURE | PH, WOJI | Wear & Tear | Breakdown
227 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, IKOTUN | Wear & Tear | Breakdown | THIO & PARTNER | COLD ROOM UNIT | HVAC | 2024-12-04 | 106 | 2024-12-04 | 0 | 2024-12-06 | 2 | [9 empty] | Overdue
228 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, IRE-AKARI | Wear & Tear | Breakdown | THIO & PARTNER | COLD ROOM UNIT | HVAC | 2024-12-05 | 105 | 2024-12-05 | 0 |  | 105 | [9 empty] | Overdue
229 | FREEZER ROOM AND COLD ROOM NOT ATTAINING TEMPERATURE | PH, GRA BIRABI | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2024-12-09 | 101 | 2024-12-10 | 1 |  | 100 | [9 empty] | Overdue
230 | COLD ROOM NOT ATTAINING TEMPERATURE | CALABAR, NDIDEM | Wear & Tear | Breakdown | BCE | COLD ROOM UNIT | HVAC | 2024-12-10 | 100 | 2024-12-10 | 0 |  | 100 | [9 empty] | Overdue
231 | GENERATOR SERVICING | ABIA, ADAZI RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-16 | 2 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 2 | 2024-12-18 |  | Completed | 2024-12-18 | 1
232 | SERVICING OF GENERATOR | LAG, OGUNLANA DRIVE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-17 | 1 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 1 | 2024-12-18 |  | Completed | 2024-12-18 | 1
233 | RADIATOR TREATMENT | LAG, OBA AKRAN | Corrective Action | Corrective | GAMMA | GENERATOR | GENERATOR | 2024-12-17 | 1 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 1 | 2024-12-18 |  | Completed | 2024-12-18 | 1
234 | GENERATOR BREAKDOWN | LAG, ONIRU | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-12-19 | 91 | 2024-12-19 | 0 | 2024-12-19 | 0 | 2024-12-22 | 2024-12-22 | 0 | 2024-12-22 | 0 | 2024-12-22 | 88 | 2024-12-22 | 150000 | Overdue
235 | LEAKING WATER SEPARATOR | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-12-19 | 91 | 2024-12-19 | 0 | 2024-12-19 | 0 | [9 empty] | Overdue
236 | GENERATOR RADIATOR TREATMENT AND FIXING OF LIFT PUMP | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-12-19 | 1 | 2024-12-19 | 0 | 2024-12-19 | 0 | 2024-12-19 | 2024-12-19 | 0 | 2024-12-19 | 0 | 2024-12-19 | 1 | 2024-12-20 |  | Completed | 2024-12-20 | 1
237 | GENERATOR DUE FOR SERIVICING | LAG, BADORE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-20 | 90 | 2024-12-20 | 0 | 2024-12-20 | 0 | [9 empty] | Overdue
238 | FAULTY GENERATOR BATTERY | LAG, AKOWONJO | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-12-21 | 89 | 2024-12-21 | 0 |  | 89 | [9 empty] | Overdue
239 | GENERATOR DUE FOR SERVICING | LAG, GBAGADA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-21 | 89 | 2024-12-21 | 0 | 2024-12-22 | 1 | [9 empty] | Overdue
240 | ABA-OWERRI ROAD GENERATOR DSE (DISPLAY PANEL BOARD) | ABIA, ABA-OWERRI RD | Corrective Action | Corrective | GAMMA | GENERATOR | GENERATOR | 2024-12-10 | 100 | 2024-12-11 | 1 | 2024-12-21 | 10 | 2024-12-21 | 2024-12-21 | 0 | 2024-12-21 | 89 |  |  |  |  | Overdue
241 | GENERATOR DUE FOR SERVICING |  | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-22 | 0 | 2024-12-22 | 0 | 2024-12-22 | 0 | 2024-12-22 | 2024-12-22 | 0 | 2024-12-22 | 0 | 2024-12-22 | 0 | 2024-12-22 |  | Completed | 2024-12-22 | 1
242 | STORE BLACK OUT | LAG, GBAGADA | Electrical Surge | Breakdown | TIMILEHIN | MAIN ELECTRICAL PANEL | ELECTRICAL
243 | PX BARIGA FAULTY INVERTER |  | Wear & Tear | Breakdown | CURRENT DATA | INVERTER SYSTEM | INVERTER | 2024-12-16 | 94 | 2024-12-16 | 0 |  | 94 | [9 empty] | Overdue
244 | GENERATOR DUE FOR SERVICE | LAG, VGC | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-12-02 | 108 | 2024-12-02 | 0 |  | 108 | [9 empty] | Overdue
245 | GENERATOR DUE FOR SERVICE | LAG, ETERNA LEKKI | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-12-16 | 94 | 2024-12-16 | 0 |  | 94 | [9 empty] | Overdue
246 | GENERATOR DUE FOR SERVICE | LAG, OKOTA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-12-19 | 91 | 2024-12-19 | 0 |  | 91 | [9 empty] | Overdue
247 | GENERATOR DUE FOR SERVICE | LAG, TEJUOSHO | Routine Servicing | Preventive | GENERATOR WH | GENERATOR | GENERATOR | 2024-12-21 | 3 | 2024-12-21 | 0 | 2024-12-21 | 0 | 2024-12-21 | 2024-12-21 | 0 | 2024-12-21 | 0 | 2024-12-21 | 3 | 2024-12-24 | 215000 | Completed | 2024-12-24 | 1
248 | GENERATOR DUE FOR SERVICE | ILORIN, OFFA GARAGE | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-12-24 | 86 | 2024-12-24 | 0 |  | 86 | [9 empty] | Overdue
249 | GENERATOR DUE FOR SERVICE | LAG, JOEL OGUNNAIKE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-30 | 80 | 2024-12-30 | 0 |  | 80 | [9 empty] | Overdue
250 | GENERATOR DUE FOR SERVICE | LAG, VGC | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-12-30 | 80 | 2024-12-30 | 0 |  | 80 | [9 empty] | Overdue
251 | GASKET ELECTROMATIC MACHINE RUBBER NEEDED | LAG, FREEDOMWAY | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-12-31 | 79 | 2024-12-31 | 0 |  | 79 | [9 empty] | Overdue
252 | BURNT COLDROOM ELECTRICAL SWITCH BOX | ANAMBRA, ZIK AVENUE, AWKA | Electrical Surge | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2024-12-28 | 11 | 2024-12-28 | 0 | 2025-01-08 | 11 | 2025-01-08 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 |  | Completed | 2025-01-08 | 1
253 | FAULTY ROLLER SHUTTER | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | EKNOR | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-12-31 | 79 | 2024-12-31 | 0 |  | 79 | [9 empty] | Overdue
254 | Faulty Roller shutter door | ABUJA, AREA 8 | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-12-16 | 15 | 2024-12-26 | 10 | 2024-12-27 | 1 | 2024-12-30 | 2024-12-30 | 0 | 2024-12-30 | 0 | 2024-12-30 | 1 | 2024-12-31 | 133476.92 | Completed | 2024-12-31 | 1
255 | FAULTY ROLLER SHUTTER | AKWA IBOM, IKOT EKPENE RD | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-12-05 | 21 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-09 | 2024-12-09 | 0 | 2024-12-12 | 0 | 2024-12-12 | 14 | 2024-12-26 |  | Completed | 2024-12-26 | 1
256 | FAULTY ROLLER SHUTTER | IMO, IKENEGBU, OWERRI | Wear & Tear | Breakdown | OUTSOURCED | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-12-19 | 91 | 2024-12-19 | 0 |  | 91 | [9 empty] | Overdue
257 | COLD ROOM NOT WORKING. | PPU Kaduna | Wear & Tear | Breakdown | NGUTAN | COLD ROOM UNIT | HVAC | 2024-12-28 | 3 | 2024-12-29 | 1 | 2024-12-31 | 2 | 2024-12-31 | 2024-12-31 | 0 | 2024-12-31 | 0 | 2024-12-31 | 0 | 2024-12-31 |  | Completed | 2024-12-31 | 1
258 | WATER LEAKAGE FROM PIPE CONNECTED TO UNOX MACHINE | LAG, AWOLOWO | Wear & Tear | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2024-12-05 | 105 | 2024-12-05 | 0 | 2024-12-11 | 6 | 2024-12-11 | 2024-12-11 | 0 | 2024-12-13 | 4 | 2024-12-17 | 93 | 2025-01-09 |  | Overdue
259 | FAULTY KITCHEN TAP AND CHANGING ROOM TAP | LAG, OKE-AFA | Wear & Tear | Breakdown | PROPEARJEFF | TAP | PLUMBING | 2024-12-17 | 93 | 2024-12-17 | 0 |  | 93 | [9 empty] | Overdue
260 | CAR PARK AREA REVAMPING | BAYELSA, YENAGOA | Wear & Tear | Breakdown | DEACONESS TAIWO | OTHERS | OTHERS | 2024-12-28 | 82 | 2024-12-28 | 0 | 2025-01-09 | 12 | 2025-01-09 |  | 70 | [6 empty] | Overdue
261 | GENERATOR SERVICING | BAYELSA, YENAGOA | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-12-04 | 106 | 2024-12-04 | 0 |  | 106 | [9 empty] | Overdue
262 | GENERATOR SERVICING | PH AGGREY | Routine Servicing | Preventive | PROPARATECH | GENERATOR | GENERATOR | 2024-12-08 | 102 | 2024-12-12 | 4 |  | 98 | [9 empty] | Overdue
263 | GENERATOR SERVICING - CR OJOO | IBADAN, OJOO | Routine Servicing | Preventive | GENERATOR WH | GENERATOR | GENERATOR | 2024-12-10 | 100 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 | 100 |  |  | Overdue
264 | GENERATOR SERVICING. | PH, RUMUOLA | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-12-10 | 100 | 2024-12-10 | 0 |  | 100 | [9 empty] | Overdue
265 | REQUEST FOR GENERATOR SERVICING | ABIA, AZIKIWE RD, UMUAHIA | Routine Servicing | Preventive | GENERATOR WH | GENERATOR | GENERATOR | 2024-12-14 | 16 | 2024-12-15 | 1 | 2024-12-19 | 4 | 2024-12-19 | 2024-12-19 | 0 | 2024-12-19 | 0 | 2024-12-19 | 11 | 2024-12-30 |  | Completed | 2024-12-30 | 1
266 | GENERATOR SERVICING | IBADAN, BODIJA | Wear & Tear | Breakdown | SYMINERTIAS | GENERATOR | GENERATOR | 2024-12-13 | 4 | 2024-12-13 | 0 | 2024-12-17 | 4 | 2024-12-17 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 |  | Completed | 2024-12-17 | 1
267 | REQUEST FOR GENERATOR SERVICING | PH, ABACHA RD | Routine Servicing | Preventive | GLUFFSCO | GENERATOR | GENERATOR | 2024-12-23 | 87 | 2024-12-23 | 0 |  | 87 | [9 empty] | Overdue
268 | GENERATOR SERVICING | PH, ONNE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-23 | 2 | 2024-12-23 | 0 | 2024-12-23 | 0 | 2024-12-23 | 2024-12-23 | 0 | 2024-12-23 | 0 | 2024-12-23 | 2 | 2024-12-25 |  | Completed | 2024-12-25 | 1
269 | Generator Servicing | IBADAN, MOKOLA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-12-24 | 7 | 2024-12-24 | 0 | 2024-12-24 | 0 | 2024-12-24 | 2024-12-24 | 0 | 2024-12-24 | 0 | 2024-12-24 | 7 | 2024-12-31 |  | Completed | 2024-12-31 | 1
270 | GENERATOR SERVICING | BAYELSA, YENAGOA | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-12-26 | 84 | 2024-12-26 | 0 |  | 84 | [9 empty] | Overdue
271 | GENERATOR SERVICING | IMO, WETHERAL RD, OWERRI | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-29 | 1 | 2024-12-29 | 0 | 2024-12-29 | 0 | 2024-12-29 | 2024-12-29 | 0 | 2024-12-29 | 0 | 2024-12-29 | 1 | 2024-12-30 |  | Completed | 2024-12-30 | 1
272 | GENERATOR SERVICING | OYO, OWODE | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2024-12-27 | 2 | 2024-12-27 | 0 | 2024-12-27 | 0 | 2024-12-27 | 2024-12-27 | 0 | 2024-12-27 | 0 | 2024-12-27 | 2 | 2024-12-29 | 334647.5 | Completed | 2024-12-29 | 1
273 | GENERATOR SERVICING | ABIA, OGBOR HILLS | Routine Servicing | Preventive | GENERATOR WH | GENERATOR | GENERATOR | 2024-12-30 | 80 | 2024-12-30 | 0 |  | 80 | [9 empty] | Overdue
274 | GENERATOR SERVICING | IBADAN, BODIJA | Routine Servicing | Preventive | SYMINERTIAS | GENERATOR | GENERATOR | 2024-12-31 | 79 | 2024-12-31 | 0 |  | 79 | [9 empty] | Overdue
275 | GENERATOR SERVICING | BAYELSA, OPOLO | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2024-12-31 | 79 | 2024-12-31 | 0 |  | 79 | [9 empty] | Overdue
276 | REQUEST FOR GENERATOR SERVICING (CR LIMCA RD) | ANAMBRA, LIMCA RD, ONITSHA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-04 | 75 |  | 75 | [11 empty] | Overdue
277 | VEGETABLE SHREDDER NOT WORKING | OGUN, OKE-ILEWO | Corrective Action | Corrective | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-12-27 | 15 | 2024-12-27 | 0 |  | 83 | [7 empty] | 2025-01-11 |  | Completed | 2025-01-11 | 1
278 | NO RUNNING WATER | LAG, AJOSE ADEOGUN | Others | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-12-04 | 2 | 2024-12-04 | 0 | 2024-12-06 | 2 | 2024-12-06 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 | 0 | 2024-12-06 |  | Completed | 2024-12-06 | 1
279 | LEAKING SINK AND BAD TAPS | LAG, MOBIL OGBA | Users Misuse | Breakdown | PRO-EQUIP | KITCHEN WASH HAND SINK | PLUMBING | 2024-12-11 | 6 | 2024-12-11 | 0 | 2024-12-17 | 6 | 2024-12-17 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 |  | Completed | 2024-12-17 | 1
280 | WATER LEAKAGE IN MALE CUSTOMER RESTROOM | LAG, AWOLOWO | Wear & Tear | Breakdown | JOEL | TAP | PLUMBING | 2024-12-02 | 108 | 2024-12-02 | 0 | 2024-12-04 | 2 | [9 empty] | Overdue
281 | FAULTY LOBBY FEMALE RESTROOM FLUSHER | LAG, IKORODU | Users Misuse | Breakdown | JOEL | OTHERS | OTHERS | 2024-12-03 | 4 | 2024-12-03 | 0 | 2024-12-07 | 4 | 2024-12-07 | 2024-12-07 | 0 | 2024-12-07 | 0 | 2024-12-07 | 0 | 2024-12-07 |  | Completed | 2024-12-07 | 1
282 | DAILY EQJUIPMENT STATUS | LAG, AJAH | Users Misuse | Breakdown | JOEL | TAP | PLUMBING | 2024-12-07 | 3 | 2024-12-10 | 3 | 2024-12-12 | 2 | 2024-12-10 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 |  | Completed | 2024-12-10 | 1
283 | WATER NOT RUNNING | LAG, MARINA | Others | Breakdown | JOEL | TAP | PLUMBING | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 |  | Completed | 2024-12-11 | 1
284 | FAULTY GAS BURNER. | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | JOEL | COOKING BURNER | KITCHEN_EQUIPMENT | 2024-12-10 | 32 | 2024-12-10 | 0 | 2024-12-12 | 2 | 2024-12-12 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 | 30 | 2025-01-11 |  | Completed | 2025-01-11 | 1
285 | [23 empty] | 45633 | #REF!
286 | FAULTY PUMPING MACHINE | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | PROPEARJEFF | SUBMERSIBLE PUMP | WTP | 2024-12-12 | 98 | 2024-12-12 | 0 | 2024-12-12 | 0 | [9 empty] | Overdue
287 | FAULTY PUMPING MACHINE | OGUN, HEYDEN IBAFO | Wear & Tear | Breakdown | PRO-EQUIP | SUBMERSIBLE PUMP | WTP | 2024-12-26 | 84 | 2024-12-26 | 0 |  | 84 | [9 empty] | Overdue
288 | BROKEN PIPE (GP TANK) | LAG, AWOLOWO | Users Misuse | Breakdown | JOEL | GROUND WATER TANK | WTP | 2024-12-12 | 1 | 2024-12-12 | 0 | 2024-12-13 | 1 | 2024-12-13 | 2024-12-13 | 0 | 2024-12-13 | 0 | 2024-12-13 | 0 | 2024-12-13 |  | Completed | 2024-12-13 | 1
289 | REQUEST FOR K-ROD | LAG, MARINA | Others | Breakdown | PRO-EQUIP | OTHERS | OTHERS | 2024-12-18 | 1 | 2024-12-18 | 0 | 2024-12-19 | 1 | 2024-12-19 | 2024-12-19 | 0 | 2024-12-19 | 0 | 2024-12-19 | 0 | 2024-12-19 |  | Completed | 2024-12-19 | 1
290 | GAS LEAKAGE FROM THE BURNER | LAG, AJAH | Wear & Tear | Breakdown | JOEL | GAS HOSE & SUNDRIES | GAS | 2024-12-13 | 3 | 2024-12-13 | 0 | 2024-12-16 | 3 | 2024-12-16 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 |  | Completed | 2024-12-16 | 1
291 | FAULTY GREASE TRAP | LAG, SKYMALL | Others | Breakdown | JOEL | GREASE TRAP | GREASE_TRAP | 2024-12-17 | 2 | 2024-12-17 | 0 | 2024-12-19 | 2 | 2024-12-19 | 2024-12-19 | 0 | 2024-12-19 | 0 | 2024-12-19 | 0 | 2024-12-19 |  | Completed | 2024-12-19 | 1
292 | HOT WATER NOT WITHIN TEMPERATURE RANGE | LAG, AWOLOWO | Others | Breakdown | JOEL | WATER HEATER | PLUMBING | 2024-12-18 | 2 | 2024-12-18 | 0 | 2024-12-20 | 2 | 2024-12-20 | 2024-12-20 | 0 | 2024-12-20 | 0 | 2024-12-20 | 0 | 2024-12-20 |  | Completed | 2024-12-20 | 1
293 | FAULTY DRAINAGE BLOCKED | LAG, FREEDOMWAY | Others | Breakdown | JOEL | OTHERS | OTHERS | 2024-12-19 | 4 | 2024-12-19 | 0 | 2024-12-23 | 4 | 2024-12-23 | 2024-12-23 | 0 | 2024-12-23 | 0 | 2024-12-23 | 0 | 2024-12-23 |  | Completed | 2024-12-23 | 1
294 | MALE RESTROOM WC NOT FLUSHING | LAG, AJOSE ADEOGUN | Users Misuse | Breakdown | JOEL | OTHERS | OTHERS | 2024-12-26 | 1 | 2024-12-26 | 0 | 2024-12-27 | 1 | 2024-12-27 | 2024-12-27 | 0 | 2024-12-27 | 0 | 2024-12-27 | 0 | 2024-12-27 |  | Completed | 2024-12-27 | 1
295 | LEAKING FAT TRAP PIPE | LAG, AWOLOWO | Others | Breakdown | JOEL | GREASE TRAP | GREASE_TRAP | 2024-12-26 | 4 | 2024-12-26 | 0 | 2024-12-30 | 4 | 2024-12-30 | 2024-12-30 | 0 | 2024-12-30 | 0 | 2024-12-30 | 0 | 2024-12-30 |  | Completed | 2024-12-30 | 1
296 | FAULTY COOK SINK | LAG, FREEDOMWAY | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2024-12-29 | 2 | 2024-12-29 | 0 | 2024-12-31 | 2 | 2024-12-31 | 2024-12-31 | 0 | 2024-12-31 | 0 | 2024-12-31 | 0 | 2024-12-31 |  | Completed | 2024-12-31 | 1
297 | GAS LEAKAGE . | LAG, ABULE EGBA | Wear & Tear | Breakdown | PRO-EQUIP | GAS HOSE & SUNDRIES | GAS | 2024-12-09 | 101 | 2024-12-10 | 1 |  | 100 | [9 empty] | Overdue
298 | GAS LEAKAGE IN THE STORE | LAG, MMA2 | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-12-11 | 4 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 | 2024-12-12 | 1 | 2024-12-13 | 0 | 2024-12-13 | 2 | 2024-12-15 | 320000 | Completed | 2024-12-15 | 1
299 | GAS LEAKAGE | LAG, IRE-AKARI | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2024-12-07 | 103 | 2024-12-07 | 0 | 2024-12-23 | 16 | 2024-12-23 | 2024-12-31 | 8 | 2024-12-31 | 0 | 2024-12-31 | 79 |  | 230000 | Overdue
300 | GAS LEAKAGE IN THE COLDROOM | LAG, FESTAC | Wear & Tear | Breakdown | BERRADE | COLD ROOM UNIT | HVAC | 2024-12-24 | 86 | 2024-12-24 | 0 | 2024-12-24 | 0 | 2025-01-02 | 2025-01-03 | 1 | 2025-01-03 | 7 | 2025-01-10 | 69 |  | 77501 | Overdue
301 | FAULTY CUSTOMER REST ROOM FLUSHER | LAG, NNPC ALAPERE | Users Misuse | Breakdown | ADEREMI WAHAB | OTHERS | OTHERS | 2024-12-10 | 100 | 2024-12-10 | 0 |  | 100 | [9 empty] | Overdue
302 | FAULTY CUSTOMER'S REST ROOM DOORS AND FAULTY MANAGER'S DOOR HANDLE | LAG, IPAJA RD | Users Misuse | Breakdown | MATOLAD | OTHERS | OTHERS | 2024-12-09 | 101 | 2024-12-10 | 1 | 2024-12-12 | 2 | [9 empty] | Overdue
303 | FAULTY CUSTOMER REST ROOM | LAG, IRE-AKARI | Users Misuse | Breakdown | OLUWATOSIN | OTHERS | OTHERS | 2024-12-11 | 99 | 2024-12-11 | 0 |  | 99 | [9 empty] | Overdue
304 | FAULTY INSECUTOR | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | MOSES O | INSECT KILLER BOH | ELECTRICAL | 2024-12-13 | 3 | 2024-12-13 | 0 | 2024-12-16 | 3 | 2024-12-16 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 |  | Completed | 2024-12-16 | 1
305 | PX IDIMU FAULTY INSECUTOR BULB. | LAG, IDIMU | Wear & Tear | Breakdown | FRIDAY | INSECT KILLER LOBBY 1 | ELECTRICAL | 2024-12-14 | 3 | 2024-12-14 | 0 | 2024-12-17 | 3 | 2024-12-17 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 |  | Completed | 2024-12-17 | 1
306 | FAULTY UP LOBBY LIGHT | LAG, BADORE | Wear & Tear | Breakdown | ADEREMI KAZEEM | DROPPING LIGHT | ELECTRICAL | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 |  | Completed | 2024-12-05 | 1
307 | STORE AUDIT (04.12.24) | LAG, VGC | Wear & Tear | Breakdown | ADEREMI KAZEEM | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-12-04 | 106 | 2024-12-05 | 1 |  | 105 | [9 empty] | Overdue
308 | STORE AUDIT (04.12.24) | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | PRO-EQUIP | OTHERS | OTHERS | 2024-12-05 | 105 | 2024-12-05 | 0 |  | 105 | [9 empty] | Overdue
309 | REPLACEMEMT OF EXTRACTOR LAMPHOLDER AND BLOWN BULB | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | ISMAIL | 18W ROUND LIGHT FITTING | ELECTRICAL | 2024-12-09 | 2 | 2024-12-10 | 1 | 2024-12-11 | 1 | 2024-12-11 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 |  | Completed | 2024-12-11 | 1
310 | REQUEST FOR MOTOR STARTER | LAG, AJAH | Wear & Tear | Breakdown | ADEREMI KAZEEM | OTHERS | OTHERS | 2024-12-09 | 2 | 2024-12-10 | 1 | 2024-12-11 | 1 | 2024-12-11 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 |  | Completed | 2024-12-11 | 1
311 | BURNT SOCKET | LAG, AGUNGI | Wear & Tear | Breakdown | ADEREMI KAZEEM | OTHERS | OTHERS | 2024-12-08 | 4 | 2024-12-08 | 0 | 2024-12-12 | 4 | 2024-12-12 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 |  | Completed | 2024-12-12 | 1
312 | BURNT INVERTER SOCKET | LAG, SKYMALL | Wear & Tear | Breakdown | DALEMATRIX | INVERTER SYSTEM | INVERTER | 2024-12-12 | 7 | 2024-12-12 | 0 | 2024-12-19 | 7 | 2024-12-19 | 2024-12-19 | 0 | 2024-12-19 | 0 | 2024-12-19 | 0 | 2024-12-19 |  | Completed | 2024-12-19 | 1
313 | ALMOST BURNT ELECTRICITY METER CABLES | LAG, SKYMALL | Electrical Surge | Breakdown | ADEREMI KEZEEM | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-12-10 | 11 | 2024-12-10 | 0 | 2024-12-21 | 11 | 2024-12-21 | 2024-12-21 | 0 | 2024-12-21 | 0 | 2024-12-21 | 0 | 2024-12-21 |  | Completed | 2024-12-21 | 1
314 | Electric Spark in the Store | LAG, VGC | Electrical Surge | Breakdown | GBATMO | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-12-25 | 8 | 2024-12-26 | 1 | 2024-12-26 | 0 | 2024-12-26 | 2024-12-26 | 0 | 2024-12-26 | 0 | 2024-12-26 | 7 | 2025-01-02 |  | Completed | 2025-01-02 | 1
315 | FAULTY FRYER SOCKET AND 4 HEAD FRYER MACHINE | LAG, BADORE | Wear & Tear | Breakdown | ADEREMI KEZEEM | OTHERS | OTHERS | 2024-12-25 | 2 | 2024-12-26 | 1 | 2024-12-27 | 1 | 2024-12-27 | 2024-12-27 | 0 | 2024-12-27 | 0 | 2024-12-27 | 0 | 2024-12-27 |  | Completed | 2024-12-27 | 1
316 | ICE CREAM MACHINE NOT FREEZING | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-12-05 | 105 | 2024-12-05 | 0 | 2024-12-17 | 12 | 2024-12-17 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 93 |  |  | Overdue
317 | FREEZER ROOM NOT WORKING | DELTA, ISOKO RD | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2024-12-25 | 85 | 2024-12-26 | 1 |  | 84 | [9 empty] | Overdue
318 | FAULTY BOH INSERCUTOR BULB | LAG, IKEJA MALL | Wear & Tear | Breakdown | TIMILEHIN | INSECT KILLER LOBBY 1 | ELECTRICAL | 2024-12-06 | 5 | 2024-12-06 | 0 | 2024-12-11 | 5 | 2024-12-11 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 | 0 | 2024-12-11 |  | Completed | 2024-12-11 | 1
319 | FREEZER ROOM NOT ATTAINING TEMPRATURE | LAG, ABULE EGBA | Wear & Tear | Breakdown | DYNAMITE | FREEZER ROOM | HVAC
320 | COLDROOM NOT WORKING EFFECTIVELY | LAG, MOBIL OGBA | Wear & Tear | Breakdown | TRIPPLE O | COLD ROOM UNIT | HVAC | 2024-12-28 | 155 | 2024-12-28 | 0 | 2025-01-06 | 9 | 2025-01-06 | 2025-01-06 | 0 | 2025-01-06 | 0 | 2025-01-06 | 146 | 2025-06-01 |  | Completed | 2025-06-01 | 1
321 | SEWAGE EVACUATION. | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-12-01 | 2 | 2024-12-01 | 0 | 2024-12-03 | 2 | 2024-12-03 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-03 | 0 | 2024-12-03 |  | Completed | 2024-12-03 | 1
322 | SEWAGE EVACUATION. | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-12-07 | 0 | 2024-12-07 | 0 | 2024-12-07 | 0 | 2024-12-07 | 2024-12-07 | 0 | 2024-12-07 | 0 | 2024-12-07 | 0 | 2024-12-07 |  | Completed | 2024-12-07 | 1
323 | SEWAGE EVACUATION | LAG, EJIGBO | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-12-10 | 2 | 2024-12-10 | 0 | 2024-12-12 | 2 | 2024-12-12 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 |  | Completed | 2024-12-12 | 1
324 | SEWAGE EVACUATION. | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 | 0 | 2024-12-12 |  | Completed | 2024-12-12 | 1
325 | SEWAGE EVACUATION. | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 |  | Completed | 2024-12-17 | 1
326 | SEWAGE EVACUATION | LAG, EJIGBO | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 | 0 | 2024-12-17 |  | Completed | 2024-12-17 | 1
327 | SEWAGE EVACUATION. | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2024-12-22 | 0 | 2024-12-22 | 0 | 2024-12-22 | 0 | 2024-12-22 | 2024-12-22 | 0 | 2024-12-22 | 0 | 2024-12-22 | 0 | 2024-12-22 |  | Completed | 2024-12-22 | 1
328 | SEWAGE EVACUATION | LAG, FREEDOMWAY | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-01-06 | 3 | 2025-01-09 | 3 | 2025-01-09 | 0 | 2025-01-09 | 2025-01-09 | 0 | 2025-01-09 | 0 | 2025-01-09 | 0 | 2025-01-09 |  | Completed | 2025-01-09 | 1
329 | GENERATOR DUE FOR SERVICING | ILORIN, TAIWO RD | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2024-12-31 | 2 | 2024-12-31 | 0 | 2024-12-31 | 0 | 2024-12-31 | 2024-12-31 | 0 | 2024-12-31 | 0 | 2024-12-31 | 2 | 2025-01-02 |  | Completed | 2025-01-02 | 1
330 | LOW ENGINE OIL | LAG, OBA AKRAN | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2024-12-26 | 84 | 2024-12-26 | 0 | 2025-01-15 | 20 | 2025-01-15 |  | 64 | [6 empty] | Overdue
331 | FAULTY COLD ROOM | LAG, MARINA | Routine Servicing | Preventive | TONAOGUNS | COLD ROOM UNIT | HVAC | 2024-12-26 | 84 | 2024-12-27 | 1 | 2024-12-27 | 0 | 2025-01-03 | 2025-01-08 | 5 | 2025-01-08 | 0 | 2025-01-08 | 71 |  | 1681000 | Overdue
332 | REPLACEMENT OF AERATION TANK | LAG, AJOSE ADEOGUN | Corrective Action | Corrective | PROPEAR | AERATION TANK | WTP | 2024-12-12 | 98 | 2024-12-12 | 0 | 2024-12-16 | 4 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 49 |  |  |  | 2100000 | Overdue
333 | ORDER CONNECT SIGNAGE REQUEST | LAG, TEJUOSHO | Others | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-12-26 | 84 | 2024-12-26 | 0 | 2024-12-26 | 0 | 2025-02-03 |  | 45 | [5 empty] | 111500 | Overdue
334 | RUSTED COLD ROOM WALL | LAG, AWOLOWO | Wear & Tear | Breakdown |  | COLD ROOM UNIT | HVAC | 2024-12-24 | 86 |  | 86 | [11 empty] | Overdue
335 | DEAD INSECT KILLER FLUORESCENT | LAG, MMA2 | Wear & Tear | Breakdown | TIMILEHIN | INSECT KILLER BOH | ELECTRICAL | 2024-12-25 | 1 | 2024-12-26 | 1 | 2024-12-26 | 0 | 2024-12-26 | 2024-12-26 | 0 | 2024-12-26 | 0 | 2024-12-26 | 0 | 2024-12-26 |  | Completed | 2024-12-26 | 1
336 | PAINTING OF OFFFICE | LAG, AGUNGI | Wear & Tear | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2024-12-18 | 92 | 2024-12-18 | 0 |  | 92 | [9 empty] | Overdue
337 | PEST WORK OUTCOME | Central Kitchen | Others | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2024-12-06 | 104 | 2024-12-06 | 0 | 2025-01-28 | 53 | 2025-02-04 |  | 44 | [6 empty] | Overdue
338 | BROKEN TILE AT CARPARK | LAG, OBA AKRAN | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2024-12-19 | 91 | 2024-12-19 | 0 | 2024-12-20 | 1 | 2024-12-20 | 2024-12-23 | 3 | 2024-12-23 | 33 | 2025-01-25 | 54 |  | 170000 | Overdue
339 | FAULTY SHREDDING MACHINE |  | Wear & Tear | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2024-12-10 | 100 | 2024-12-12 | 2 | 2024-12-19 | 7 | 2024-12-19 | 2024-12-19 | 0 | 2024-12-19 | 0 | 2024-12-19 | 91 |  | 159100 | Overdue
340 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | LAG, MMA2 | Wear & Tear | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 |  | Completed | 2024-12-16 | 1
341 | DISPLAY CABINET NOT ATTAINING TEMPERATURE |  | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-20 | 90 | 2024-12-20 | 0 | 2024-12-21 | 1 | 2025-01-08 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 | 71 |  | 296625 | Overdue
342 | FREEZER ROOM NOT ATTAINING TEMPERATURE | CALABAR, NDIDEM | Routine Servicing | Preventive | BCE | FREEZER ROOM | HVAC | 2024-12-16 | 0 | 2024-12-16 | 0 | 2024-12-16 | 0 | [7 empty] | 2024-12-16 |  | Completed | 2024-12-16 | 1
343 | WATER TREATMENT SERVICING | BAYELSA, TOMBIA | Routine Servicing | Preventive | PRO-EQUIPTECH | WATER TREATMENT PLANT BLD | BUILDING | 2024-12-30 | 80 | 2024-12-30 | 0 | 2025-01-17 | 18 | 2025-01-17 | 2025-02-10 | 24 | [5 empty] | 885000 | Overdue
344 | WATER TREATMENT SERVICING | BAYELSA, OPOLO | Routine Servicing | Preventive | PRO-EQUIPTECH | WATER TREATMENT PLANT BLD | BUILDING | 2024-12-30 | 80 | 2024-12-30 | 0 | 2025-01-17 | 18 | 2025-01-17 | 2025-02-10 | 24 | [5 empty] | 900000 | Overdue
345 | WATER TREATMENT SERVICING |  | Routine Servicing | Preventive | PRO-EQUIPTECH | WATER TREATMENT PLANT BLD | BUILDING | 2024-12-30 | 80 | 2024-12-30 | 0 | 2025-01-17 | 18 | 2025-01-17 | 2025-02-10 | 24 | [5 empty] | 1150000 | Overdue
346 | AWKA ROAD UNDER GROUND SUMO NOT PUMPING | ANAMBRA, AWKA RD, ONITSHA | Wear & Tear | Breakdown | PRO-EQUIPTECH | SUBMERSIBLE PUMP | WTP | 2024-12-12 | 98 | 2024-12-12 | 0 | 2025-01-19 | 38 | [9 empty] | Overdue
347 | FAULTY INSECT INSECTOCUTOR BULB/ DEAD LED BULB | LAG, FREEDOMWAY | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-12-24 | 12 | 2024-12-25 | 1 | 2025-01-05 | 11 | 2025-01-05 | 2025-01-05 | 0 | 2025-01-05 | 0 | 2025-01-05 | 0 | 2025-01-05 |  | Completed | 2025-01-05 | 1
348 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | ABIA, ABA-OWERRI RD | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2024-12-20 | 19 | 2024-12-20 | 0 | 2024-12-21 | 1 | 2025-01-08 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 | 463325 | Completed | 2025-01-08 | 1
349 | DEAD INSECTICUTOR BULB IN THE LOBBY | LAG, AKOWONJO | Electrical Surge | Breakdown | EMMANUEL | OTHERS | OTHERS | 2024-12-03 | 65 | 2024-12-03 | 0 | 2024-12-05 | 2 | 2025-01-06 | 2025-01-06 | 0 | 2025-01-06 | 31 | 2025-02-06 | 0 | 2025-02-06 |  | Completed | 2025-02-06 | 1
350 | DEAD INSECTICUTOR | LAG, AJOSE ADEOGUN | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2024-12-09 | 1 | 2024-12-09 | 0 | 2024-12-12 | 3 | 2024-12-09 | 2024-12-10 | 1 | 2024-12-10 | 0 | 2024-12-10 | 0 | 2024-12-10 |  | Completed | 2024-12-10 | 1
351 | BROKEN WALL AND FLOOR TILES IN THE LOBBY,KITCHEN, LOBBY ENTRANCE AND DISCOLOURED FLOOR TILES IN THE LOBBY | LAG, IDI-IROKO RD | Wear & Tear | Breakdown | PENTECOSTAL | WALL | BUILDING | 2024-12-30 | 80 | 2024-12-30 | 0 | 2025-01-20 | 21 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 45 |  |  |  |  | Overdue
352 | FAULTY/NOISY ROTISSERIE MACHINE | LAG, ALIMOSHO | Wear & Tear | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2024-12-30 | 80 | 2024-12-30 | 0 | 2025-03-19 | 79 | 2025-03-19 | 2025-03-19 | 0 | 2025-03-19 | 1 |  |  |  |  | Overdue
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
Formulas:
Days Since Request = IF([Request Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Request Date],TODAY()-[Request Date]))
Days Since Request = IF([Request Date]="","",IF(#REF!<>"",#REF!-[Request Date],TODAY()-[Request Date]))
Days Delayed by Helpdesk = IF([Date Shared by Helpdesk]<>"",[Date Shared by Helpdesk]-[Request Date],IF([Request Date]="","",TODAY()-[Request Date]))
Days Delayed by Vendor/Technician = IF(M6<>"",M6-[Date Shared by Helpdesk],IF([Date Shared by Helpdesk]="","",TODAY()-[Date Shared by Helpdesk]))
Days Since Negotiation Request = TODAY() - [Date Negotiated]
Days Since Negotiation Request = IF([Date Negotiated]<>"",[Date Negotiated]-[Date Sent for Negotiation],IF([Date Sent for Negotiation]="","",TODAY()-[Date Sent for Negotiation]))
Days Since Approval Request = IF([Approved Date]<>"",[Approved Date]-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval Request = IF(#REF!<>"",#REF!-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval = IF([Approved Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Approved Date],TODAY()-[Approved Date]))
Days Since Approval = IF(#REF!="","",IF([Actual delivery date]<>"",[Actual delivery date]-#REF!,TODAY()-#REF!))
Status = IF([Request Date]="","",IF([Actual delivery date]<>"","Completed",IF(TODAY()<[Expected Delivery Date],"Planned",IF(TODAY()=[Expected Delivery Date],"Due","Overdue"))))
Status = IF([Request Date]="","",IF(#REF!<>"","Completed",IF(TODAY()<[Expected Delivery Date],"Planned",IF(TODAY()=[Expected Delivery Date],"Due","Overdue"))))
Note on AA6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vendor gave feedback thaat part is not available on 18 of Jan
Note on C111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR EGBE ROAD
Note on C121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR ABA OWERRI RD
Note on C125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR SANGOTEDO
Note on C139: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ppu
Note on C150: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MPU
Note on C158: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR ALAPERE
Note on C181: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ppu
Note on C200: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX
Note on C209: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX
Note on C215: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IYANA IYESI
Note on C244: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IYANA IYESI
Note on C246: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX BARIGA
Note on C342: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: EGBE ROAD
Note on C344: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR ABA OWERRI RD
Note on C348: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR KPANSHIA

## JANUARY
Legend
Completed on time
Completed late
S/N | ACTION/TASK | Store | Reason for Breakdown | Maintenance Category | Responsible | Specific Equipment | Category | Request Date | Days Since Request | Date Shared by Helpdesk | Days Delayed by Helpdesk | Date Attended/Checked by Vendor/Technician | Days Delayed by Vendor/Technician | Date Sent for Negotiation | Date Negotiated | Days Since Negotiation Request | Date Approval Requested | Days Since Approval Request | Approved Date | Days Since Approval | Expected Delivery Date | Cost | Status | Actual delivery date | Compliance check | Insert Comment
1 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, MMA2 | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-01-06 | 73 | 2025-01-06 | 0 |  | 73 |  |  | 45736 | [6 empty] | Overdue
2 | INSTALLATION OF NEW AC | LAG, ABULE EGBA | Others | Breakdown
3 | BLACK OUT | LAG, ABULE EGBA | Electrical Surge | Breakdown | TAYO | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-01-08 | 6 | 2025-01-08 | 0 | 2025-01-14 | 6 | 2025-01-14 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 |  | Completed | 2025-01-14 | 1
4 | Air Condition's In CK | LAG, ILUPEJU | Routine Servicing | Preventive | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-09 | 70 | 2025-01-09 | 0 |  | 70 | [9 empty] | Overdue
5 | BROKEN CABINET GLASS. | LAG, LEKKI PHASE 1 | Users Misuse | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-09 | 70 | 2025-01-09 | 0 |  | 70 | [9 empty] | Overdue
6 | FAULTY OFFICE AND DRY STORE A.C | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | G.B BOYEJO | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-07 | 72 | 2025-01-08 | 1 | 2025-01-09 | 1 | [9 empty] | Overdue
7 | GENERATOR DUE FOR SERVICE | LAG, DIYA STREET | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-05 | 1 | 2025-01-05 | 0 | 2025-01-05 | 0 | 2025-01-05 | 2025-01-05 | 0 | 2025-01-05 | 0 | 2025-01-05 | 1 | 2025-01-06 |  | Completed | 2025-01-06 | 1
8 | GENERATOR DUE FOR SERVICE | LAG, OKOTA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-05 | 74 | 2025-01-05 | 0 |  | 74 | [9 empty] | Overdue
9 | GENERATOR DUE FOR SERVICE | LAG, FESTAC | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-06 | 3 | 2025-01-06 | 0 | 2025-01-09 | 3 | 2025-01-09 | 2025-01-09 | 0 | 2025-01-09 | 0 | 2025-01-09 | 0 | 2025-01-09 |  | Completed | 2025-01-09 | 1
10 | GENERATOR DUE FOR SERVICE | DELTA, ISOKO RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-08 | 71 | 2025-01-08 | 0 | 2025-01-08 | 0 | [9 empty] | Overdue
12 | FALLING ROOF AT THE DESPATCH CORRIDOR/BESIDE THE FREEZER ROOM
13 | FAULTY DRY STORE AC | PPU Ajah | Wear & Tear | Breakdown
14 | DEAD BULB IN THE CABINET | LAG, AWOLOWO | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-08 | 71 | 2025-01-08 | 0 |  | 71 | [9 empty] | Overdue
15 | FAULTY MALE CHANGING ROOM FAN | LAG, FESTAC | Wear & Tear | Breakdown | TIMILEHIN | WALL FAN | HVAC | 2025-01-09 | 70 | 2025-01-09 | 0 |  | 70 | [9 empty] | Overdue
16 | PRESSURE FRYER NOT ATTAINING TEMPERATURE |  | Wear & Tear | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-01-09 | 70 | 2025-01-09 | 0 |  | 70 | [9 empty] | Overdue
17 | REPAINTING OF CAR PARK, GENERATOR AREA AND INSIDE THE STORE | LAG, FESTAC | Wear & Tear | Breakdown | WESTERN DESIGN | WALL | BUILDING | 2025-01-09 | 70 | 2025-01-09 | 0 |  | 70 | [9 empty] | Overdue
18 | FAULTY LOBBY AC | LAG, GBAGADA | Wear & Tear | Breakdown | THIO & PARTNERS | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-09 | 70 | 2025-01-09 | 0 |  | 70 | [9 empty] | Overdue
19 | EVACUATION OF SEPTIC TANK | LAG, AWOLOWO 2 | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-01-09 | 70 | 2025-01-09 | 0 |  | 70 | [9 empty] | Overdue
20 | Freezer room interior fan is bad | DELTA, EFFURUN | Wear & Tear | Breakdown | ECS | FREEZER ROOM | HVAC | 2025-01-08 | 71 | 2025-01-08 | 0 | 2025-01-09 | 1 | [9 empty] | Overdue
21 | FAULTY KITCHEN TAP. | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2025-01-09 | 70 | 2025-01-09 | 0 |  | 70 | [9 empty] | Overdue
22 | FAULTY FOUR HEAD MACHINE SPRING | LAG, FESTAC | Wear & Tear | Breakdown | KITCHTECH | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-01-09 | 70 | 2025-01-09 | 0 |  | 70 | [9 empty] | Overdue
23 | FAULTY MAGNETIC LOCK | LAG, ILUPEJU | Wear & Tear | Breakdown | ITC | OTHERS | OTHERS | 2025-01-09 | 70 | 2025-01-09 | 0 |  | 70 | [9 empty] | Overdue
24 | FAULTY OFFICE AND DRY STORE A.C | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | G.B BOYEJO | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-08 | 71 | 2025-01-09 | 1 | 2025-01-09 | 0 | [9 empty] | Overdue
25 | FAULTY ROLLER SHUTTER | LAG, IRE-AKARI | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-01-03 | 76 | 2025-01-03 | 0 | 2025-01-08 | 5 | 2025-01-08 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 | 71 |  | 73100 | Overdue
26 | FAULTY ROLLER SHUTTER | EDO, SAPELE RD, BENIN | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-01-07 | 72 | 2025-01-07 | 0 | 2025-01-07 | 0 | [9 empty] | Overdue
28 | FAULTY ROLLER SHUTTER | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | EKNOR | ENTRANCE ROLLER SHUTTER | SECURITY | 2024-12-31 | 79 |  | 79 | [11 empty] | Overdue
29 | GENERATOR SERVICING | LAG, JIBOWU | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-08 | 71 | 2025-01-08 | 0 | 2025-01-09 | 1 | [9 empty] | Overdue
30 | REQUEST FOR COLLECTOR GASKET | PH, ABA | Others | Breakdown | BCE | PRESURE FRYER 2 | KITCHEN_EQUIPMENT | 2025-01-09 | 70 | 2025-01-09 | 0 | 2025-01-09 | 0 | [9 empty] | Overdue
31 | Request for Collector Gasket | DELTA, EFFURUN | Others | Breakdown | BCE | PRESURE FRYER 2 | KITCHEN_EQUIPMENT | 2025-01-07 | 72 | 2025-01-07 | 0 | 2025-01-07 | 0 | [9 empty] | Overdue
32 | DEMOLISHING OF BIN HOUSE | IBADAN, BODIJA | Others | Breakdown | REVELATION | WASTE BIN HOUSE | BUILDING | 2025-01-08 | 71 | 2025-01-08 | 0 | 2025-01-10 | 2 | 2025-01-13 | 2025-01-16 | 3 | 2025-01-16 | 19 | 2025-02-04 | 44 |  | 900000 | Overdue
33 | COLD ROOM NOT WORKING. | IBADAN, RING-ROAD | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-01-05 | 11 | 2025-01-05 | 0 | 2025-01-08 | 3 | 2025-01-12 | 2025-01-13 | 1 | 2025-01-15 | 1 | 2025-01-16 | 0 | 2025-01-16 | 160000 | Completed | 2025-01-16 | 1
34 | FAULTY ICE CREAM MACHINE | EDO, SILUKO | Wear & Tear | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-01-04 | 75 | 2025-01-04 | 0 | 2025-01-09 | 5 | [9 empty] | Overdue
35 | FAULTY ICE CREAM MACHINE | LAG, BADORE | Wear & Tear | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-01-08 | 71 | 2025-01-08 | 0 | 2025-01-14 | 6 | [9 empty] | Overdue
36 | Faulty Ice Cream Machine & Shaky Tables | BENUE, OLD OTUKPO | Wear & Tear | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-01-02 | 77 | 2025-01-07 | 5 | 2025-01-08 | 1 | 2025-02-20 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 | 28 | 2025-03-03 |  | Overdue
37 | FAUTY BIG DOUGHNUT FRAYER | PPU Kaduna | Wear & Tear | Breakdown | OLANIYI | OTHERS | OTHERS | 2025-01-08 | 1 | 2025-01-08 | 0 | 2025-01-09 | 1 | 2025-01-09 | 2025-01-09 | 0 | 2025-01-09 | 0 | 2025-01-09 | 0 | 2025-01-09 |  | Completed | 2025-01-09 | 1
38 | FAULTY KITCHEN TAP. | LAG, LEKKI PHASE 1 | Others | Breakdown | PRO EQUIP | TAP | PLUMBING | 2025-01-09 | 1 | 2025-01-09 | 0 | 2025-01-10 | 1 | 2025-01-10 | 2025-01-10 | 0 | 2025-01-10 | 0 | 2025-01-10 | 0 | 2025-01-10 |  | Completed | 2025-01-10 | 1
39 | REQUEST FOR 5 HORSEPOWER EVAPORATOR FOR A.C | LAG, AWOLOWO 2 | Others | Breakdown | TAYO | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-09 | 70 | 2025-01-09 | 0 |  | 70 | [9 empty] | Overdue
40 | EQUIPMENT STATUS REPORT | PPU Ilupeju | Others | Breakdown | PROPEARJEFF | HAND DRYER TOILET | ELECTRICAL | 2025-01-08 | 71 | 2025-01-08 | 0 | 2025-01-09 | 1 | [9 empty] | Overdue
41 | STORE RENOVATION | PH, RUMUBIAKANI | Wear & Tear | Breakdown | DEACONESS TAIWO | OTHERS | OTHERS | 2025-01-07 | 72 | 2025-01-07 | 0 | 2025-01-10 | 3 | [9 empty] | Overdue
42 | TAYLOR LUBE REQUISITION | EBONYI, AFIKPO, ABAKALIKI | Others | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-01-07 | 72 | 2025-01-07 | 0 |  | 72 | [9 empty] | Overdue
43 | TOASTER NOT WORKING | ABIA, AZIKIWE RD, UMUAHIA | Wear & Tear | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2025-01-09 | 70 | 2025-01-09 | 0 |  | 70 | [9 empty] | Overdue
44 | GENERATOR SERVICING REQUEST | ANAMBRA, ZIK AVENUE, AWKA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-01 | 78 | 2025-01-01 | 0 | 2025-01-02 | 1 | [9 empty] | Overdue
45 | GENERATOR SERVICING. | ABIA, FACTORY RD, ABA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-02 | 77 | 2025-01-02 | 0 | 2025-01-03 | 1 |  |  | #REF! | [6 empty] | Overdue
46 | REQUEST FOR GENERATOR SERVICING (CR LIMCA RD) | ANAMBRA, LIMCA RD, ONITSHA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-04 | 75 | 2025-01-04 | 0 | 2025-01-04 | 0 | [9 empty] | Overdue
47 | REQUEST FOR GENERATOR SERVICING | AKWA IBOM, ORON RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-05 | 74 | 2025-01-05 | 0 | 2025-01-05 | 0 | [9 empty] | Overdue
48 | REQUEST FOR GENERATOR SERVICING - CR NSUKKA | ENUGU, NSUKKA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-05 | 74 | 2025-01-05 | 0 |  | 74 | [9 empty] | Overdue
49 | LED LIGHTS REQUEST | OSUN, GBONGAN | Electrical Surge | Breakdown | RANEX | OTHERS | OTHERS | 2025-01-10 | 69 | 2025-01-10 | 0 | 2025-01-11 | 1 | 2025-01-11 | 2025-01-11 | 0 | 2025-01-11 | 0 | 2025-01-11 | 68 |  | 116100 | Overdue
50 | REQUEST FOR STORE PAINTING | LAG, OKE-AFA | Wear & Tear | Breakdown | GENEROUS | PAINTING | BUILDING | 2025-01-02 | 77 | 2025-01-02 | 0 | 2025-01-06 | 4 | 2025-01-10 | 2025-01-11 | 1 | 2025-01-11 | 68 |  |  |  | 700000 | Overdue
51 | QUOTATION FOR REPAIR OF LOBBY SWINGING DOORS AND PRODUCTION SWINGING DOOR AT CHICKEN REPUBLIC, NSUKA, ENUGU. | ENUGU, NSUKKA | OTHERS | Breakdown | FULLTURN | OTHERS | OTHERS | 2025-01-10 | 69 | 2025-01-10 | 0 | 2025-01-10 | 0 | 2025-01-10 | 2025-01-10 | 0 | 2025-01-11 | 68 |  |  |  | 24 | Overdue
52 | NO RUNNING WATER IN MALE AND FEMALE REST ROOM AND BROKEN TOILETS PIPE. | LAG, MARINA | Users Misuse | Breakdown | JOEL | TAP | PLUMBING | 2025-01-10 | 3 | 2025-01-10 | 0 | 2025-01-13 | 3 | 2025-01-13 | 2025-01-13 | 0 | 2025-01-13 | 0 | 2025-01-13 | 0 | 2025-01-13 |  | Completed | 2025-01-13 | 1
53 | FAULTY CUSTOMER RESTROOM | LAG, MARINA | Users Misuse | Breakdown
54 | LEAKING AERATION TANK | LAG, IKOTUN | Wear & Tear | Breakdown | PROPEARJEFF | AERATION TANK | WTP | 2025-01-07 | 72 | 2025-01-07 | 0 | 2025-01-16 | 9 | 2025-01-30 | 2025-01-30 | 0 | [5 empty] | 2100000 | Overdue
55 | FAULTY CHEST FREEZER HINGES | LAG, OPEBI | Wear & Tear | Breakdown | G.B BOYEJO | CHEST FREEZER | HVAC | 2025-01-14 | 2 | 2025-01-14 | 0 | 2025-01-16 | 2 | 2025-01-16 | 2025-01-16 | 0 | 2025-01-16 | 0 | 2025-01-16 | 0 | 2025-01-16 |  | Completed | 2025-01-16 | 1
56 | FAULTY WARMER LOCK | LAG, OPEBI | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-01-08 | 8 | 2025-01-08 | 0 | 2025-01-13 | 5 | 2025-01-13 | 2025-01-13 | 0 | 2025-01-13 | 1 | 2025-01-14 | 2 | 2025-01-16 |  | Completed | 2025-01-16 | 1
57 | WATER NOT RUNNING IN THE STORE | LAG, AWOLOWO | Others | Breakdown | JOEL | TAP | PLUMBING | 2025-01-03 | 0 | 2025-01-03 | 0 | 2025-01-03 | 0 | 2025-01-03 | 2025-01-03 | 0 | 2025-01-03 | 0 | 2025-01-03 | 0 | 2025-01-03 |  | Completed | 2025-01-03 | 1
58 | FAULTY GAS BURNER | LAG, OGUNLANA DRIVE | Wear & Tear | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-01-02 | 77 | 2025-01-02 | 0 | 2025-01-06 | 4 | 2025-01-06 | 2025-01-07 | 1 | [6 empty] | Overdue
59 | FAULTY GREASE TRAP PIPE | LAG, TEJUOSHO | Users Misuse | Breakdown | PRO-EQUIP | TAP | PLUMBING | 2025-01-13 | 66 | 2025-01-16 | 3 |  | 63 | [9 empty] | Overdue
60 | FAULTY COOK SINK | LAG, NNPC ALAPERE | Wear & Tear | Breakdown | ADEREMI WAHAB | KITCHEN WASH HAND SINK | PLUMBING | 2025-01-06 | 1 | 2025-01-06 | 0 | 2025-01-07 | 1 | 2025-01-07 | 2025-01-07 | 0 | 2025-01-07 | 0 | 2025-01-07 | 0 | 2025-01-07 |  | Completed | 2025-01-07 | 1
61 | RAMSHCAKLE WATER TAP (2) | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | JOEL | TAP | PLUMBING | 2025-01-05 | 1 | 2025-01-05 | 0 | 2025-01-06 | 1 | 2025-01-06 | 2025-01-06 | 0 | 2025-01-06 | 0 | 2025-01-06 | 0 | 2025-01-06 |  | Completed | 2025-01-06 | 1
62 | LEAKING GAS | LAG, AJAH | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-01-06 | 1 | 2025-01-06 | 0 | 2025-01-06 | 0 | 2025-01-06 | 2025-01-06 | 0 | 2025-01-06 | 0 | 2025-01-06 | 1 | 2025-01-07 |  | Completed | 2025-01-07 | 1
63 | UNAVAILABILITY OF HOT WATER | LAG, ONIRU | Wear & Tear | Breakdown | JOEL | WATER HEATER | PLUMBING | 2025-01-06 | 2 | 2025-01-06 | 0 | 2025-01-08 | 2 | 2025-01-08 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 |  | Completed | 2025-01-08 | 1
64 | GAS LEAKAGE | LAG, MARINA | Wear & Tear | Breakdown | JOEL | GAS HOSE & SUNDRIES | GAS | 2025-01-07 | 1 | 2025-01-07 | 0 | 2025-01-08 | 1 | 2025-01-08 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 |  | Completed | 2025-01-08 | 1
65 | SERIOUS GAS LEAKAGE | LAG, ONIRU | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-01-09 | 0 | 2025-01-09 | 0 | 2025-01-09 | 0 | 2025-01-09 | 2025-01-09 | 0 | 2025-01-09 | 0 | 2025-01-09 | 0 | 2025-01-09 |  | Completed | 2025-01-09 | 1
66 | GAS LEAKAGE | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | JOEL | GAS HOSE & SUNDRIES | GAS | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 |  | Completed | 2025-01-14 | 1
67 | GAS LEAKAGE FROM UNOX OVEN | LAG, DIYA STREET | Wear & Tear | Breakdown | PRO-EQUIP | OTHERS | OTHERS | 2025-01-14 | 13 | 2025-01-14 | 0 | 2025-01-14 | 0 | [7 empty] | 2025-01-27 |  | Completed | 2025-01-27 | 1
68 | BLOCKED WASHING ZINC AND FAULTY BULB | LAG, ONIRU | Others | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2025-01-07 | 1 | 2025-01-07 | 0 | 2025-01-08 | 1 | 2025-01-08 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 |  | Completed | 2025-01-08 | 1
69 | LEAKING FRYER ZINC TAP | LAG, TOTAL LEKKI | Users Misuse | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 |  | Completed | 2025-01-14 | 1
70 | DIRECT DIESEL TANK CONNECTION WITH THE GENERATOR | LAG, TOTAL LEKKI | Others | Breakdown | DAMI FOTE | GENERATOR | GENERATOR | 2025-01-12 | 2 | 2025-01-12 | 0 | 2025-01-14 | 2 | 2025-01-14 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 |  | 2025-01-14 |  | Completed | 2025-01-14 | 1
71 | NO RUNNING WATER IN MALE AND FEMALE REST ROOM AND BROKEN TOILETS PIPE. | LAG, MARINA | Others | Breakdown | JOEL | TAP | PLUMBING | 2025-01-10 | 4 | 2025-01-10 | 0 | 2025-01-14 | 4 | 2025-01-14 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 |  | Completed | 2025-01-14 | 1
72 | BROKEN FILTER CANDLE GLASS | LAG, LEKKI PHASE 1 | Others | Breakdown | JOEL | FILTRATION VESSEL 1 | WTP | 2025-01-13 | 2 | 2025-01-15 | 2 | 2025-01-15 | 0 | 2025-01-15 | 2025-01-15 | 0 | 2025-01-15 | 0 | 2025-01-15 | 0 | 2025-01-15 |  | Completed | 2025-01-15 | 1
73 | FAULTY CUSTOMER REST ROOM | LAG, AJOSE ADEOGUN | Users Misuse | Breakdown | JOEL | OTHERS | OTHERS | 2025-01-14 | 1 | 2025-01-14 | 0 | 2025-01-15 | 1 | 2025-01-15 | 2025-01-15 | 0 | 2025-01-15 | 0 | 2025-01-15 | 0 | 2025-01-15 |  | Completed | 2025-01-15 | 1
74 | GENERATOR SERVICING | OYO, OWODE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-19 | 60 | 2025-01-19 | 0 |  | 60 | [9 empty] | Overdue
75 | GENERATOR SERVICING - CR OJOO | IBADAN, OJOO | Routine Servicing | Preventive | KB | GENERATOR | GENERATOR | 2025-01-13 | 66 | 2025-01-13 | 0 | 2025-01-13 | 0 | 2025-01-13 | 2025-01-13 | 0 | 2025-01-13 | 5 | 2025-01-18 | 61 |  | 252625 | Overdue
76 | GENERATOR SERVICING | BAYELSA, YENAGOA | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2025-01-18 | 61 | 2025-01-18 | 0 | 2025-01-18 | 0 | [9 empty] | Overdue
77 | GENERATOR SERVICING AND SHORTAGE OF OIL | IMO, OKIGWE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-16 | 63 | 2025-01-16 | 0 | 2025-01-16 | 0 | 2025-02-04 |  | 44 | [6 empty] | Overdue
78 | GENERATOR SERVICING | LAG, BODE THOMAS | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-16 | 63 | 2025-01-16 | 0 |  | 63 | [9 empty] | Overdue
79 | Decayed Skirting Board | LAG, OMOLE | Wear & Tear | Breakdown | PENTICOSTAL | OTHERS | OTHERS | 2025-01-18 | 61 | 2025-01-19 | 1 | 2025-01-19 | 0 | 2025-01-19 |  | 60 | [6 empty] | Overdue
80 | SHOCKING EQUIPMENTS IN STORE |  | Electrical Surge | Breakdown | ADEREMI | OTHERS | OTHERS | 2025-01-07 | 12 | 2025-01-07 | 0 | 2025-01-08 | 1 | 2025-01-08 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 | 11 | 2025-01-19 |  | Completed | 2025-01-19 | 1
81 | WEED AT THE ROOF TOP OF STORE BUILDING | LAG, AJAH | Corrective Action | Corrective | PENTICOSTAL | OTHERS | OTHERS | 2025-01-12 | 67 | 2025-01-12 | 0 | 2025-01-19 | 7 | 2025-01-19 |  | 60 | [6 empty] | Overdue
82 | BROKEN WASH AREA TILES | LAG, JIBOWU | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-01-17 | 62 | 2025-01-17 | 0 | 2025-01-19 | 2 | [9 empty] | Overdue
83 | DAMAGED GREASE TRAP BASKET | LAG, OPEBI | Wear & Tear | Breakdown | ZEBRA | GREASE TRAP | GREASE_TRAP | 2025-01-17 | 62 | 2025-01-17 | 0 | 2025-01-18 | 1 | 2025-01-19 | 2025-01-19 | 0 | 2025-01-19 | 60 |  |  |  |  | Overdue
84 | DIESEL MAIN TANK LEAKING AND WASHING | LAG, TEJUOSHO | Wear & Tear | Breakdown |  | OTHERS | OTHERS | 2025-01-14 | 65 | 2025-01-14 | 0 |  | 65 | [9 empty] | Overdue
85 | CORRODED WALLS IN DRY STORE, MANAGERS OFFICE AND BACK OF HOUSE | LAG, OMOLE | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-01-19 | 60 | 2025-01-19 | 0 | 2025-01-19 | 0 | 2025-01-19 | 2025-01-19 | 0 | 2025-01-19 | 0 | 2025-01-19 | 60 |  | 300000 | Overdue
86 | PX IGANDO CABINET ISSUES |  | Wear & Tear | Breakdown | HEFHEM | OTHERS | OTHERS | 2025-01-13 | 2 | 2025-01-13 | 0 | 2025-01-13 | 0 | [7 empty] | 2025-01-15 |  | Completed | 2025-01-15 | 1
87 | GENERATOR DUE FOR | LAG, IPAJA RD | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-19 | 60 | 2025-01-19 | 0 |  | 60 | [9 empty] | Overdue
88 | GENERATOR DUE FOR SERVICING | LAG, ILUPEJU | Routine Servicing | Preventive | DELIGHT | GENERATOR | GENERATOR | 2025-01-18 | 61 | 2025-01-19 | 1 |  | 60 | [9 empty] | Overdue
89 | GENERATOR DUE FOR SERVICE | LAG, OGUDU | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-18 | 61 | 2025-01-18 | 0 | 2025-01-18 | 0 | [9 empty] | Overdue
90 | GENERATOR DUE FOR SERVICING | LAG, IKORODU | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-18 | 61 | 2025-01-18 | 0 |  | 61 | [9 empty] | Overdue
91 | GENERATOR DUE FOR SERVIVCING | LAG, ISAWO-IKORODU | Routine Servicing | Preventive | DELIGHT | GENERATOR | GENERATOR | 2025-01-17 | 62 | 2025-01-17 | 0 | 2025-01-17 | 0 | [9 empty] | Overdue
92 | GENERATOR DUE FOR SERVICING - OPEBI | LAG, OPEBI | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-15 | 1 | 2025-01-15 | 0 | 2025-01-16 | 1 | 2025-01-16 | 2025-01-16 | 0 | 2025-01-16 | 0 | 2025-01-16 | 0 | 2025-01-16 |  | Completed | 2025-01-16 | 1
93 | OPEN WARMER SWITCH. | LAG, JOEL OGUNNAIKE | Users Misuse | Breakdown | TIMILEHIN | UPRIGHT WARMER MACHINE | HVAC | 2025-01-19 | 60 | 2025-01-19 | 0 | 2025-01-19 | 0 | [9 empty] | Overdue
94 | FAULTY WARMER GASKET | LAG, IRE-AKARI | Others | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-01-13 | 66 | 2025-01-13 | 0 | 2025-01-13 | 0 | 2025-01-13 | 2025-01-13 | 0 | 2025-01-13 | 6 | 2025-01-19 | 60 |  | 108575 | Overdue
95 | LEAKING FRYER SINK |  | Wear & Tear | Breakdown | ADEREMI | KITCHEN WASH HAND SINK | PLUMBING | 2025-01-17 | 62 | 2025-01-17 | 0 | 2025-01-19 | 2 | [9 empty] | Overdue
96 | REQUEST FOR INDUTRIAL BOX AND OTHER ITEM | PPU Ilupeju | Others | Breakdown | ADEREMI | OTHERS | OTHERS | 2025-01-16 | 63 | 2025-01-16 | 0 | 2025-01-18 | 2 | [9 empty] | Overdue
97 | SEWAGE EVACUATION | LAG, TOTAL LEKKI | Routine Servicing | Preventive | BERRADE | SEPTIC TANK | EVACUATION | 2025-01-19 | 60 | 2025-01-19 | 0 |  | 60 | [9 empty] | Overdue
98 | FAULTY FEMALE CHANGING ROOM WALL HANGER. | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-01-18 | 61 | 2025-01-19 | 1 | 2025-01-19 | 0 | [9 empty] | Overdue
99 | PX IGANDO FADED SIGNAGE |  | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-01-13 | 66 | 2025-01-13 | 0 | 2025-01-13 | 0 | 2025-01-19 |  | 60 | [6 empty] | Overdue
100 | WATER HEATER NOT WORKING | LAG, MOBIL OGBA | Electrical Surge | Breakdown | Proequiptech | WATER HEATER | PLUMBING | 2025-01-14 | 7 | 2025-01-15 | 1 | 2025-01-15 | 0 | 2025-01-19 | 2025-01-21 | 2 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 | 120000 | Completed | 2025-01-21 | 1
101 | Cold room and freezer room not attaining temperature | EBONYI, WATERWORKS, ABAKALIKI | Routine Servicing | Preventive | MOFEEN | OTHERS | OTHERS | 2025-01-18 | 61 | 2025-01-18 | 0 |  | 61 | [9 empty] | Overdue
102 | FREEZER ROOM NOT ATTAINING TEMPERATURE | IBADAN, BODIJA | Routine Servicing | Preventive | TONAOGUNS | COLD ROOM UNIT | HVAC | 2025-01-07 | 9 | 2025-01-07 | 0 | 2025-01-12 | 5 | 2025-01-12 | 2025-01-13 | 1 | 2025-01-15 | #REF! | 2025-01-18 | #REF! | 2025-01-16 | 195500 | Completed | 2025-01-16 | 1
103 | COLD ROOM AND FREEZER ROOM NOT ATTAINING TEMPERATURE | EDO, AIRPORT RD, BENIN | Routine Servicing | Preventive | ECS | OTHERS | OTHERS | 2025-01-14 | 65 | 2025-01-14 | 0 | 2025-01-16 | 2 | 2025-01-16 | 2025-01-17 | 1 | 2025-01-17 | 61 |  |  |  |  | Overdue
104 | FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, TOTAL LEKKI | Routine Servicing | Preventive | TONA OGUNS | FREEZER ROOM | HVAC | 2025-01-12 | 67 | 2025-01-12 | 0 | 2025-01-12 | 0 | 2025-01-13 | 2025-01-14 | 1 | 2025-01-14 | 65 |  |  |  | 300000 | Overdue
105 | FAULTY INSECUTOR | LAG, IRE-AKARI | Wear & Tear | Breakdown | FRIDAY | INSECT KILLER LOBBY 1 | ELECTRICAL | 2025-01-05 | 74 | 2025-01-05 | 0 |  | 74 | [9 empty] | Overdue
106 | FAULTY INSECUTOR AND CABINETS BULBS | LAG, BADORE | Wear & Tear | Breakdown | FRIDAY | INSECT KILLER LOBBY 1 | ELECTRICAL | 2025-01-15 | 64 | 2025-01-15 | 0 |  | 64 | [9 empty] | Overdue
107 | BURNT SOCKET | LAG, BODE THOMAS | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-01-12 | 67 | 2025-01-12 | 0 |  | 67 | [9 empty] | Overdue
108 | Electric Spark in the Store. | LAG, VGC | Electrical Surge | Breakdown | ADEREMI KAZEEM | MAIN ELECTRICAL PANEL | ELECTRICAL | 2024-12-22 | 88 | 2024-12-22 | 0 |  | 88 | [9 empty] | Overdue
109 | EXTRACTOR NOT WORKING | ABIA, OGBOR HILLS | Wear & Tear | Breakdown | SEASON BENDAN | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2025-01-20 | 59 | 2025-01-20 | 0 |  | 59 | [9 empty] | Overdue
110 | DEAD BULBS IN CABINET | LAG, AJAH | Wear & Tear | Breakdown | ADEREMI KAZEEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-12 | 2 | 2025-01-12 | 0 | 2025-01-14 | 2 | 2025-01-14 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 |  | Completed | 2025-01-14 | 1
111 | BAD FEMALE CUSTOMERS' RESTROOM LIGHT | LAG, BADORE | Wear & Tear | Breakdown | ADEREMI KAZEEM | 18W ROUND LIGHT FITTING | ELECTRICAL | 2025-01-15 | 64 | 2025-01-15 | 0 |  | 64 | [9 empty] | Overdue
112 | FAULTY GENERATOR BREAKER | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | ADEREMI KAZEEM | OTHERS | OTHERS | 2025-01-16 | 1 | 2025-01-16 | 0 | 2025-01-17 | 1 | 2025-01-17 | 2025-01-17 | 0 | 2025-01-17 | 0 | 2025-01-17 | 0 | 2025-01-17 |  | Completed | 2025-01-17 | 1
113 | ROLLER SHIRTER NOT WORKIN | LAG, MAGODO | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-01-18 | 61 | 2025-01-18 | 0 | 2025-01-20 | 2 | [9 empty] | Overdue
114 | WASHING OF FACADE AND PYLON | LAG, IKORODU | Others | Breakdown | PENTICOSTAL | OTHERS | OTHERS | 2025-01-15 | 64 | 2025-01-15 | 0 | 2025-01-16 | 1 | 2025-01-16 | 2025-01-16 | 0 | 2025-01-16 | 4 | 2025-01-20 | 59 |  |  | Overdue
115 | WASHING OF FACADE AND PYLON | LAG, OGUDU | Electrical Surge | Breakdown | BONDSGATE | OTHERS | OTHERS | 2025-01-20 | 59 | 2025-01-20 | 0 |  | 59 | [9 empty] | Overdue
116 | BLOCKED DRAINAGE | LAG, ONIRU | Corrective Action | Corrective | ZEBRA | OTHERS | OTHERS | 2025-01-09 | 12 | 2025-01-09 | 0 | 2025-01-16 | 7 | 2025-01-16 | 2025-01-16 | 0 | 2025-01-16 | 0 | 2025-01-16 | 5 | 2025-01-21 | 220000 | Completed | 2025-01-21 | 1
117 | BLOCKED DRAINAGE | LAG, DIYA STREET | Corrective Action | Corrective | PENTICOSTAL | SEPTIC TANK | EVACUATION | 2025-01-06 | 1 | 2025-01-06 | 0 | 2025-01-06 | 0 | 2025-01-06 | 2025-01-06 | 0 | 2025-01-06 | 0 | 2025-01-06 | 1 | 2025-01-07 | 286810 | Completed | 2025-01-07 | 1
118 | BLOCKED DRAINAGE IN THE MALE STAFF CHANGING ROOM | LAG, OGUNLANA DRIVE | Corrective Action | Corrective | OLUWATOSIN | OTHERS | OTHERS | 2025-01-19 | 1 | 2025-01-19 | 0 | 2025-01-20 | 1 | 2025-01-20 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 |  | Completed | 2025-01-20 | 1
119 | PEELING SIGNAGE | LAG, BODE THOMAS | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-01-08 | 71 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-17 | 2025-01-20 | 3 | 2025-01-20 | 0 | 2025-01-20 | 59 |  | 66000 | Overdue
120 | ICE CREAM MACHINE NOT FREEZING | ABUJA, DAWAKI | Routine Servicing | Preventive | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-01-12 | 67 | 2025-01-12 | 0 | 2025-01-13 | 1 | [9 empty] | Overdue
121 | CR OMOLE ICE CREAM MACHINE NOT FREEZING | LAG, OMOLE | Routine Servicing | Preventive | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-01-10 | 69 | 2025-01-10 | 0 |  | 69 | [9 empty] | Overdue
122 | ICE CREAM MACHINE NOT FREEZING | ABUJA, DAWAKI | Wear & Tear | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-01-12 | 67 | 2025-01-13 | 1 | 2025-01-13 | 0 | [9 empty] | Overdue
123 | CR OMOLE ICE CREAM MACHINE NOT FREEZING | LAG, OMOLE | Wear & Tear | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-01-10 | 5 | 2025-01-10 | 0 | 2025-01-13 | 3 | 2025-01-13 | 2025-01-13 | 0 | 2025-01-13 | 0 | 2025-01-13 | 2 | 2025-01-15 |  | Completed | 2025-01-15 | 1
124 | ROLLER SHIRTER NOT WORKIN | LAG, MAGODO | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-01-18 | 48 | 2025-01-18 | 0 | 2025-01-20 | 2 | 2025-01-22 | 2025-01-22 | 0 | 2025-01-22 | 42 | 2025-03-05 | 2 | 2025-03-07 | 270000 | Completed | 2025-03-07 | 1
125 | LIST OF MAINTAINANCE ISSUE IN THE STORE | LAG, NNPC ALAPERE | Wear & Tear | Breakdown | ACORN | OTHERS | OTHERS | 2025-01-20 | 59 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-22 |  | 57 | [6 empty] | Overdue
126 | FREEZER ROOM NOT WORKING | LAG, OBA AKRAN | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2025-01-06 | 73 | 2025-01-06 | 0 |  | 73 | [9 empty] | Overdue
127 | FREEZER ROOM NOT WORKING | OGUN, OKE-ILEWO | Wear & Tear | Breakdown | DYNAMITE | FREEZER ROOM | HVAC | 2025-01-14 | 65 | 2025-01-14 | 0 |  | 65 | [9 empty] | Overdue
128 | freezer room not working | LAG, OBA AKRAN | Wear & Tear | Breakdown | BCE | FREEZER ROOM | HVAC | 2025-01-15 | 64 | 2025-01-15 | 0 | 2025-01-15 | 0 | [9 empty] | Overdue
129 | FREEZER ROOM NOT WORKING | LAG, OGUDU | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2025-01-16 | 63 | 2025-01-16 | 0 | 2025-01-20 | 4 | 2025-01-22 |  | 57 | [6 empty] | Overdue
130 | FREEZER ROOM NOT ATTAINING TEMPRATURE | PH, DOX RD | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2025-01-04 | 75 | 2025-01-04 | 0 |  | 75 | [9 empty] | Overdue
131 | FREEZER ROOM NOT ATTAINING TEMPRATURE. | LAG, ALIMOSHO | Wear & Tear | Breakdown | DYNAMITE | FREEZER ROOM | HVAC | 2025-01-09 | 70 | 2025-01-09 | 0 | 2025-01-21 | 12 | 2025-01-21 | 2025-01-22 | 1 | 2025-01-22 | 57 |  |  |  | 387100 | Overdue
132 | TECHNICAL ISSSUES IN THE STORE | LAG, LATEEF JAKANDE | Wear & Tear | Breakdown | MOSES O | OTHERS | OTHERS | 2025-01-21 | 1 | 2025-01-21 | 0 | 2025-01-22 | 1 | 2025-01-22 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 |  | Completed | 2025-01-22 | 1
133 | BROKEN PIPE AT WATER TREATMENT PLAN | LAG, FREEDOMWAY | Users Misuse | Breakdown | JOEL | OTHERS | OTHERS | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 |  | Completed | 2025-01-20 | 1
134 | cabinet bulb lamp holder | LAG, MOBIL OGBA | Wear & Tear | Breakdown | MOSES O | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 |  | Completed | 2025-01-21 | 1
135 | CEILING DROP DOWN | LAG, OMOLE | Wear & Tear | Breakdown | MATOLAD | ROOF | BUILDING | 2025-01-21 | 58 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-22 | 2025-01-22 | 0 | 2025-01-22 | 57 |  |  |  | 100000 | Overdue
136 | FAULTY CHANGING ROOM DOOR HANDLE BOTH MALE AND FEMALE ( TWO EACH ) | LAG, MARINA | Users Misuse | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-01-17 | 62 | 2025-01-17 | 0 |  | 62 | [9 empty] | Overdue
137 | FAULTY CHANGING ROOM DOOR HANDLE | OGUN, HEYDEN IBAFO | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-01-22 | 57 | 2025-01-22 | 0 |  | 57 | [9 empty] | Overdue
138 | THE INVERTER BREAKER CRITICALLY FAULTY | LAG, IKEJA MALL | Wear & Tear | Breakdown | TIMILEHIN | INVERTER SYSTEM | INVERTER | 2025-01-21 | 58 | 2025-01-22 | 1 |  | 57 | [9 empty] | Overdue
139 | COLD ROOM NOT WORKING | PH, UST | Wear & Tear | Breakdown
140 | COLD ROOM NOT WORKING | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-01-21 | 58 | 2025-01-21 | 0 |  | 58 | [9 empty] | Overdue
141 | FAULTY LOBBY LIGHT,SOCKET AND DRINKAGE LIGHT | LAG, OKOTA | Wear & Tear | Breakdown | FRIDAY | OTHERS | OTHERS | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 |  | Completed | 2025-01-22 | 1
142 | BROKEN TILES IN THE STORE | LAG, OKE-AFA | Others | Breakdown | VENYS | OTHERS | OTHERS | 2025-01-02 | 77 | 2025-01-02 |  | 2025-01-03 | 1 | 2025-01-03 | 2025-01-22 | 19 | [6 empty] | Overdue
143 | BROKEN TILES IN THE STORE | LAG, MMA2 | Others | Breakdown | ACORN | OTHERS | OTHERS | 2025-01-06 | 73 | 2025-01-14 | 8 | 2025-01-15 | 1 | 2025-02-03 |  | 45 | [6 empty] | Overdue
144 | SEWAGE EVACUATION | LAG, ETERNA LEKKI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-01-02 | 0 | 2025-01-02 | 0 | 2025-01-02 | 0 | 2025-01-02 | 2025-01-02 | 0 | 2025-01-02 | 0 | 2025-01-02 | 0 | 2025-01-02 |  | Completed | 2025-01-02 | 1
145 | SEWAGE EVACUATION. | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-01-03 | 0 | 2025-01-03 | 0 | 2025-01-03 | 0 | 2025-01-03 | 2025-01-03 | 0 | 2025-01-03 | 0 | 2025-01-03 | 0 | 2025-01-03 |  | Completed | 2025-01-03 | 1
146 | SEWAGE EVACUATION | LAG, FREEDOMWAY | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-01-06 | 3 | 2025-01-09 | 3 | 2025-01-09 | 0 | 2025-01-09 | 2025-01-09 | 0 | 2025-01-09 | 0 | 2025-01-09 | 0 | 2025-01-09 |  | Completed | 2025-01-09 | 1
147 | SEWAGE EVACUATION | LAG, TOTAL LEKKI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-01-12 | 0 | 2025-01-12 | 0 | 2025-01-12 | 0 | 2025-01-12 | 2025-01-12 | 0 | 2025-01-12 | 0 | 2025-01-12 | 0 | 2025-01-12 |  | Completed | 2025-01-12 | 1
148 | SEWAGE EVACUATION | LAG, ONIRU | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 |  | Completed | 2025-01-22 | 1
149 | GENERATOR BREAK DOWN | EDO, RAHMAT PARK, BENIN | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-01-21 | 58 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-22 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 | 57 | 2025-01-27 |  | Overdue
150 | WASHING OF PHYLON LIGHT AND FOH TILES | LAG, OKE-AFA | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-20 | 59 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-22 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 | 57 |  |  | Overdue
151 | FREEZER ROOM SELF LOCK | PH, ABA | Wear & Tear | Breakdown |  | FREEZER ROOM | HVAC | 2025-01-23 | 56 |  | 56 | [11 empty] | Overdue
152 | FAULTY CHIPS DUMP. | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | BCE | CHIPS DUMP | KITCHEN_EQUIPMENT | 2025-01-19 | 60 | 2025-01-19 | 0 | 2025-01-23 | 4 | [9 empty] | Overdue
153 | Generator is due servicing need urgent attention | DELTA, EFFURUN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2024-12-28 | 82 | 2024-12-28 | 0 | 2024-12-28 | 0 | [9 empty] | Overdue
154 | GENERATOR DUE FOR SERVICING | ILORIN, MM WAY | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-11 | 68 | 2025-01-11 | 0 |  | 68 | [9 empty] | Overdue
155 | GENERATOR DUE FOR SERVICING | LAG, ABULE EGBA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-09 | 3 | 2025-01-10 | 1 | 2025-01-10 | 0 | 2025-01-12 | 2025-01-12 | 0 | 2025-01-12 | 0 | 2025-01-12 | 0 | 2025-01-12 |  | Completed | 2025-01-12 | 1
156 | GENERATOR DUE FOR SERVICING | LAG, GBAGADA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-12 | 67 | 2025-01-12 | 0 | 2025-01-13 | 1 | 2025-01-13 | 2025-01-13 | 0 | 2025-01-13 | 0 | 2025-01-13 | 66 |  |  | Overdue
157 | GENERATOR SERVICING | IBADAN, BODIJA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-08 | 71 | 2025-01-08 | 0 |  | 71 | [9 empty] | Overdue
158 | Generator need servicing | DELTA, SAPELE-WARRI RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-03 | 3 | 2025-01-03 | 0 | 2025-01-03 | 0 | 2025-01-03 | 2025-01-03 | 0 | 2025-01-03 | 0 | 2025-01-03 | 3 | 2025-01-06 |  | Completed | 2025-01-06 | 1
159 | Generator need servicing | DELTA, SAPELE-WARRI RD | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-12 | 0 | 2025-01-12 | 0 | 2025-01-12 | 0 | 2025-01-12 | 2025-01-12 | 0 | 2025-01-12 | 0 | 2025-01-12 | 0 | 2025-01-12 |  | Completed | 2025-01-12 | 1
160 | GENERATOR DUE FOR SERVICING: TURBO CHARGER | ILORIN, TAIWO RD | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-10 | 2 | 2025-01-10 | 0 | 2025-01-10 | 0 | 2025-01-11 | 2025-01-11 | 0 | 2025-01-11 | 1 | 2025-01-12 | 0 | 2025-01-12 |  | Completed | 2025-01-12 | 1
161 | GENERATOR DUE FOR SERVICING | LAG, NNPC ALAPERE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-13 | 66 | 2025-01-13 | 0 | 2025-01-14 | 1 | [9 empty] | Overdue
162 | FAULTY GNERATOR | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | DELIGHTSOME | GENERATOR | GENERATOR | 2025-01-03 | 76 | 2025-01-03 | 0 | 2025-01-03 | 0 | 2025-01-03 | 2025-01-03 | 0 | 2025-01-03 | 76 |  |  |  |  | Overdue
163 | REQUEST FOR RADIATOR WASHING AND CHANGE OF AIR FILTER FOR GENERATOR - CR NSUKKA | ENUGU, NSUKKA | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-01-13 | 66 | 2025-01-13 | 0 |  | 66 | [9 empty] | Overdue
164 | GENERATOR SERVICING - CR OJOO, IBADAN, OYO STATE | IBADAN, OJOO | Routine Servicing | Preventive | GENERATOR WH | GENERATOR | GENERATOR | 2025-01-13 | 66 | 2025-01-13 | 0 | 2025-01-13 | 0 | 2025-01-13 | 2025-01-13 | 0 | 2025-01-13 | 66 |  |  |  |  | Overdue
165 | GENERATOR SERVICING | LAG, AJOSE ADEOGUN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-14 | 65 | 2025-01-14 | 0 |  | 65 | [9 empty] | Overdue
166 | GENERATOR DUE FOR SERVICING | PH, UST | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-12 | 67 | 2025-01-15 | 3 |  | 64 | [9 empty] | Overdue
167 | GENERATOR DUE FOR SERVICING - OPEBI | LAG, OPEBI | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-15 | 64 | 2025-01-15 | 0 | 2025-01-15 | 0 | [9 empty] | Overdue
168 | GENERATOR DUE FOR SERVICING | LAG, EKORO | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2025-01-15 | 64 | 2025-01-15 | 0 | 2025-01-17 | 2 | [9 empty] | Overdue
169 | FAULTY CABINET LAMP HOLDER | OGUN, HEYDEN IBAFO | Electrical Surge | Breakdown | MOSES | OTHERS | OTHERS | 2025-01-07 | 1 | 2025-01-07 | 0 | 2025-01-07 | 0 | 2025-01-08 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-08 |  | Completed | 2025-01-08 | 1
170 | SERVICING OF WATER TREATMENT PLANT | BAYELSA, OPOLO | Routine Servicing | Preventive | PRO-EQUIPTECH | WATER TREATMENT PLANT BLD | BUILDING | 2025-01-03 | 76 | 2025-01-03 | 0 | 2025-01-17 | 14 | 2025-01-17 | 2025-01-23 | 6 | 2025-01-25 | 54 |  |  |  | 1400000 | Overdue
171 | SERVICING OF WATER TREATMENT PLANT | BAYELSA, TOMBIA | Routine Servicing | Preventive | PRO-EQUIPTECH | WATER TREATMENT PLANT BLD | BUILDING | 2025-01-02 | 77 | 2025-01-02 | 0 | 2025-01-17 | 15 | 2025-01-17 | 2025-01-23 | 6 | 2025-01-25 | 54 |  |  |  | 1400000 | Overdue
172 | FAULTY ROLLER SHUTTER | LAG, OMOLE | Others | Breakdown | Basscomm | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-01-24 | 55 |  | 55 | [11 empty] | Overdue
173 | UPRIGHT CHILLER(UNDERBAR) NOT WORKING | EDO, UGBOWO, BENIN | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2025-01-07 | 72 | 2025-01-07 | 0 | 2025-01-08 | 1 | [9 empty] | Overdue
174 | BROKEN WASH AREA TILES | LAG, ILUPEJU | Wear & Tear | Breakdown | ACORN | OTHERS | OTHERS | 2025-01-19 | 60 | 2025-01-19 | 0 | 2025-01-20 | 1 | 2025-01-23 | 2025-01-23 | 0 | 2025-01-27 | 0 | 2025-01-27 | 52 |  | 356700 | Overdue
175 | LEAKAGE FROM ONE OF THE PUMPING MACHINES | LAG, TEJUOSHO | Wear & Tear | Breakdown | PROQUIP TECH | OTHERS | OTHERS | 2025-01-13 | 66 | 2025-01-13 | 0 | 2025-01-13 | 0 | [9 empty] | Overdue
176 | FAULTY A/C IN CUSTOMER RESTROOM | LAG, ILUPEJU | Wear & Tear | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-17 | 62 | 2025-01-27 | 10 | 2025-01-27 | 0 | [9 empty] | Overdue
177 | DAMAGED FREEZER ROOM HANDLE | ABIA, ABA-OWERRI RD | Wear & Tear | Breakdown | MOFFEEN | FREEZER ROOM | HVAC | 2025-01-24 | 55 | 2025-01-25 | 1 | 2025-01-26 | 1 | [9 empty] | Overdue
178 | Damage POP Ceiling | LAG, TEJUOSHO | Wear & Tear | Breakdown | ARIZMAYAN | P.O.P | BUILDING | 2025-01-27 | 52 | 2025-01-27 | 0 | 2025-01-27 | 0 | [9 empty] | Overdue
179 | FAULTY DISPLAY CABINET | ANAMBRA, LIMCA RD, ONITSHA | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-24 | 55 | 2025-01-24 | 0 | 2025-01-25 | 1 | [9 empty] | Overdue
180 | LOW CURRENT OF PHCN LIGHT | LAG, IRE-AKARI | Electrical Surge | Breakdown | GBATMO | OTHERS | OTHERS | 2025-01-26 | 53 | 2025-01-27 | 1 | 2025-01-28 | 1 | 2025-01-30 | 2025-02-05 | 6 | 2025-02-05 | 2 | 2025-02-07 | 41 |  |  | Overdue
181 | FAULTY CHIPS MACHINE TAP | LAG, FESTAC | Wear & Tear | Breakdown | BCE | CHIPS DUMP | KITCHEN_EQUIPMENT | 2025-01-27 | 52 |  | 52 | [11 empty] | Overdue
182 | EXTRACTOR NOT WORKING EFFECTIVELY | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | SEASONED BENDAN | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2025-01-25 | 2 | 2025-01-25 | 0 | 2025-01-27 | 2 | 2025-01-27 | 2025-01-27 | 0 | 2025-01-27 | 0 | 2025-01-27 | 0 | 2025-01-27 |  | Completed | 2025-01-27 | 1
183 | CHEST FREEZER NOT ATTAINING TEMPERATURE | LAG, AWOLOWO | Wear & Tear | Breakdown | BOYEJO | CHEST FREEZER | HVAC | 2025-01-26 | 53 | 2025-01-27 | 1 |  | 52 | [9 empty] | Overdue
184 | CHEST FREEZER NOT ATTAINING TEMPERATURE | OGUN, OKE-ILEWO | Wear & Tear | Breakdown | BOYEJO | CHEST FREEZER | HVAC | 2025-01-23 | 56 | 2025-01-23 | 0 | 2025-01-23 | 0 | [9 empty] | Overdue
185 | CHEST FREEZER NOT ATTAINING TEMPERATURE | LAG, IKORODU | Wear & Tear | Breakdown | BOYEJO | CHEST FREEZER | HVAC | 2025-01-17 | 62 |  | 62 | [11 empty] | Overdue
186 | CHEST FREEZER NOT ATTAINING TEMPERATURE | LAG, IPAJA RD | Wear & Tear | Breakdown | BOYEJO | CHEST FREEZER | HVAC | 2025-01-05 | 74 | 2025-01-05 | 0 |  | 74 | [9 empty] | Overdue
187 | CHEST FREEZER NOT ATTAINING TEMPERATURE | LAG, MMA2 | Wear & Tear | Breakdown | BOYEJO | CHEST FREEZER | HVAC | 2025-01-16 | 63 | 2025-01-16 | 0 |  | 63 | [9 empty] | Overdue
188 | FAULTY LED BULB | LAG, AKOWONJO | Wear & Tear | Breakdown | FRIDAY | OTHERS | OTHERS | 2025-01-27 | 8 | 2025-01-27 | 0 | 2025-02-04 | 8 | 2025-02-04 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 |  | Completed | 2025-02-04 | 1
189 | DOORS WITH NO HANDLE AND LOCK | LAG, ISAWO-IKORODU | Wear & Tear | Breakdown | Matolad | OTHERS | OTHERS | 2025-01-21 | 58 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-25 | 2025-01-27 | 2 | 2025-01-27 | 0 | 2025-01-27 | 52 |  | 300000 | Overdue
190 | FAULTY GAS BURNER | Central Kitchen | Wear & Tear | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2025-01-06 | 1 | 2025-01-06 | 0 | 2025-01-06 | 0 | 2025-01-06 | 2025-01-06 | 0 | 2025-01-06 | 1 | 2025-01-07 | 0 | 2025-01-07 | 80000 | Completed | 2025-01-07 | 1
191 | FAULTY LOBBY A.C | LAG, IKORODU | Routine Servicing | Preventive | TONAOGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-17 | 62 | 2025-01-17 | 0 | 2025-01-21 | 4 | 2025-01-24 | 2025-01-27 | 3 | 2025-01-27 | 0 | 2025-01-27 | 52 |  | 750000 | Overdue
192 | FAULTY GAS BOILER | Central Kitchen | Wear & Tear | Breakdown | AKANS | OTHERS | OTHERS | 2025-01-10 | 69 | 2025-01-13 | 3 | 2025-01-13 | 0 | [9 empty] | Overdue
193 | LEAKING DISESEL PIPE IN CR OMOLE | LAG, OMOLE | Wear & Tear | Breakdown | MOSAB | OTHERS | OTHERS | 2025-01-24 | 55 | 2025-01-24 | 0 | 2025-01-27 | 3 | [9 empty] | Overdue
194 | FADED SIGNAGE | LAG, ALIMOSHO | Wear & Tear | Breakdown | EDIDIONG | OTHERS | OTHERS | 2025-01-03 | 76 | 2025-01-03 | 0 | 2025-01-03 | 0 | [9 empty] | Overdue
195 | FADED PYLON | LAG, IRE-AKARI | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-01-14 | 13 | 2025-01-15 | 1 | 2025-01-15 | 0 | 2025-01-21 | 2025-01-24 | 3 | 2025-01-24 | 0 | 2025-01-24 | 3 | 2025-01-27 | 162250 | Completed | 2025-01-27 | 1
196 | BROKEN SIGNAGE |  | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-01-13 | 11 | 2025-01-13 | 0 | 2025-01-16 | 3 | 2025-01-21 | 2025-01-22 | 1 | 2025-01-22 | 0 | 2025-01-22 | 2 | 2025-01-24 | 42750 | Completed | 2025-01-24 | 1
197 | GENERATOR AND AC SERVICING + STEAM WASH RADIATOR + ENGINE FAN BELT | IMO, OKIGWE | Routine Servicing | Preventive | KB | GENERATOR | GENERATOR | 2025-01-25 | 54 | 2025-01-25 | 0 | 2025-01-27 | 2 | 2025-01-27 |  | 52 | [6 empty] | Overdue
198 | PEELING SIGNAGE | LAG, BODE THOMAS | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-01-08 | 14 | 2025-01-08 | 0 | 2025-01-08 | 0 | 2025-01-17 | 2025-01-20 | 3 | 2025-01-20 | 0 | 2025-01-20 | 2 | 2025-01-22 | 66125 | Completed | 2025-01-22 | 1
199 | HOLE N THE CEILING IN THE DRY STORE | LAG, IDI-IROKO RD | Wear & Tear | Breakdown | MATOLAD | CEILING BOARD | BUILDING | 2025-01-27 | 8 | 2025-01-27 | 0 | 2025-02-03 | 7 | [7 empty] | 2025-02-04 |  | Completed | 2025-02-04 | 1
200 | BROKEN OIL TANK MACHINE SWITCH | LAG, ILUPEJU | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2025-01-06 | 73 | 2025-01-06 | 0 | 2025-01-17 | 11 | [9 empty] | Overdue
201 | SIGNAGE LIGHT NOT WORKING |  | Electrical Surge | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-01-16 | 8 | 2025-01-16 | 0 | 2025-01-16 | 0 | 2025-01-21 | 2025-01-22 | 1 | 2025-01-22 | 0 | 2025-01-22 | 2 | 2025-01-24 | 40750 | Completed | 2025-01-24 | 1
202 | BROKEN WASH AREA TILES | LAG, ILUPEJU | Wear & Tear | Breakdown | ACORN | OTHERS | OTHERS | 2025-01-17 | 62 | 2025-01-17 | 0 |  | 62 | [9 empty] | Overdue
203 | Faulty bulb and old broken cabinet shelf | LAG, ILUPEJU | Wear & Tear | Breakdown | FULLTURN | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-29 | 50 | 2025-01-29 | 0 | 2025-01-29 | 0 | [9 empty] | Overdue
204 | Faulty bulb and old broken cabinet shelf | LAG, ILUPEJU | Wear & Tear | Breakdown | KOLA | OTHERS | OTHERS | 2025-01-14 | 15 | 2025-01-14 | 0 | 2025-01-15 | 1 | 2025-01-29 | 2025-01-29 | 0 | 2025-01-29 | 0 | 2025-01-29 | 0 | 2025-01-29 |  | Completed | 2025-01-29 | 1
205 | GENERATOR DUE FOR SERVICING | OSUN, AYETORO | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-01 | 78 | 2025-01-01 | 0 |  | 78 | [9 empty] | Overdue
206 | SPOILT LOBBY ENTRANCE DOOR. | EBONYI, AFIKPO, ABAKALIKI | Wear & Tear | Breakdown | FULLTURN | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-01-24 | 6 | 2025-01-25 | 1 | 2025-01-28 | 3 | 2025-01-28 | 2025-01-28 | 0 | 2025-01-28 | 2 | 2025-01-30 | 0 | 2025-01-30 | 144050 | Completed | 2025-01-30 | 1
207 | FAULTY EXTRACTOR AT BOH | LAG, BADORE | Wear & Tear | Breakdown | SEASONED | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2025-01-05 | 74 | 2025-01-05 | 0 |  | 74 | [9 empty] | Overdue
208 | ROLLER SUTTER NOT FUNCTIONING | ANAMBRA, ZIK AVENUE, AWKA | Wear & Tear | Breakdown | Basscomm | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-01-29 | 50 | 2025-01-30 | 1 | 2025-01-30 | 0 | [9 empty] | Overdue
209 | DIESEL LEAKAGE. | LAG, JOEL OGUNNAIKE | Corrective Action | Corrective | GAMMA | OTHERS | OTHERS | 2025-01-30 | 49 | 2025-01-30 | 0 | 2025-01-30 | 0 | [9 empty] | Overdue
210 | DIESEL LEAKAGE | EDO, AIRPORT RD, BENIN | Corrective Action | Corrective | PRO-EQUIPTECH | OTHERS | OTHERS | 2025-01-12 | 67 | 2025-01-12 | 0 | 2025-01-27 | 15 | [9 empty] | Overdue
211 | DETACHED FREEZER ROOM DOOR HANDLE | LAG, IDI-IROKO RD | Wear & Tear | Breakdown | DYNAMITE | FREEZER ROOM | HVAC | 2025-01-10 | 69 | 2025-01-10 | 0 | 2025-01-10 | 0 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 49 |  | 325000 | Overdue
212 | FAULTY COLD ROOM | PPU Ilupeju | Wear & Tear | Breakdown | BCE | COLD ROOM UNIT | HVAC | 2025-01-25 | 54 | 2025-01-25 | 0 | 2025-01-26 | 1 | [9 empty] | Overdue
213 | SERVICE OF ENTRANCE DOORS | LAG, MARINA | Routine Servicing | Preventive | TAIDAV | OTHERS | OTHERS | 2025-01-30 | 49 | 2025-01-30 | 0 |  | 49 | [9 empty] | Overdue
214 | BROKEN WATER TREATMENT FILTER | LAG, MAGODO | Wear & Tear | Breakdown | ADEREMI | WATER TREATMENT PLANT BLD | BUILDING | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 |  | Completed | 2025-01-30 | 1
215 | BROKEN TILES IN THE FREEZER ROOM FLOOR AND FRYER SINK AREA | LAG, BODE THOMAS | Wear & Tear | Breakdown | Arizmayan | OTHERS | OTHERS | 2025-01-16 | 63 | 2025-01-16 | 0 | 2025-01-16 | 0 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 49 |  | 280000 | Overdue
216 | NON-AVAILABILITY OF WATER IN STORE | LAG, MARINA | Corrective Action | Corrective | JOEL | OTHERS | OTHERS | 2025-01-20 | 1 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-21 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 |  | Completed | 2025-01-21 | 1
217 | AC SERVICING | ABIA, OGBOR HILLS | Routine Servicing | Preventive | MOFFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-02 | 77 | 2025-01-02 | 0 | 2025-01-29 | 27 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 36 |  |  | Overdue
218 | REQUEST FOR AC SERVICING | LAG, OMOLE | Routine Servicing | Preventive | TONAOGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-21 | 58 | 2025-01-21 | 0 | 2025-01-26 | 5 | [9 empty] | Overdue
219 | AC SERVICING | AKWA IBOM, EKET-ORON RD | Routine Servicing | Preventive | MOFFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-20 | 59 | 2025-01-20 | 0 | 2025-02-08 | 19 | [9 empty] | Overdue
220 | AC SERVICING | LAG, JIBOWU | Routine Servicing | Preventive | FOLLTECH | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-04 | 75 | 2025-01-04 | 0 | 2025-01-04 | 0 | [9 empty] | Overdue
221 | REQUEST FOR COLLECTOR GASKET AND WINSTON PUMP POWER CORD (FOR PRESSURE FRYERS) | ABIA, AZIKIWE RD, UMUAHIA | Others | Breakdown | BCE | DIRECT POWER DB | ELECTRICAL | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 |  | Completed | 2025-01-30 | 1
222 | BURNT LOBBY's AC" CABLES | LAG, MARINA | Electrical Surge | Breakdown | FOLLTECC | OTHERS | OTHERS | 2025-01-30 | 49 | 2025-01-30 | 0 | 2025-01-30 | 0 | [9 empty] | Overdue
223 | FAULTY ROLLER SHUTTER | LAG, OBA AKRAN | Wear & Tear | Breakdown | PENTECOSTAL | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-01-29 | 1 | 2025-01-29 | 0 | 2025-01-29 | 0 | 2025-01-29 | 2025-01-29 | 0 | 2025-01-29 | 1 | 2025-01-30 | 0 | 2025-01-30 | 110000 | Completed | 2025-01-30 | 1
224 | OPENED HOLES IN WALLS AND CEILING | LAG, BADORE | Wear & Tear | Breakdown | FULLTURN | WALL | BUILDING | 2025-01-15 | 64 | 2025-01-15 | 0 | 2025-01-29 | 14 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 49 |  | 79550 | Overdue
225 | BAD WARMER HANDLE | PH, ABACHA RD | Users Misuse | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-01-05 | 25 | 2025-01-05 | 0 | 2025-01-29 | 24 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 118250 | Completed | 2025-01-30 | 1
226 | BROKEN WALLS &FLOORS | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | ARIZMAYAN | WALL | BUILDING | 2025-01-30 | 49 | 2025-01-30 | 0 | 2025-01-30 | 0 | [9 empty] | Overdue
227 | GENERATOR DUE FOR SERVICE | LAG, FESTAC | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-25 | 54 | 2025-01-25 | 0 | 2025-01-30 | 5 | [9 empty] | Overdue
228 | GENERATOR DUE FOR SERVICE | IBADAN, MOKOLA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-26 | 53 | 2025-01-26 | 0 |  | 53 | [9 empty] | Overdue
229 | BURNT INSECTICUTOR AND WALL SOCKET | LAG, OMOLE | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 |  | Completed | 2025-01-30 | 1
230 | CABINET DRIP WATER | LAG, FREEDOMWAY | Wear & Tear | Breakdown | JOEL | OTHERS | OTHERS | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 |  | Completed | 2025-01-20 | 1
231 | CABINET DRIP WATER | LAG, FREEDOMWAY | Wear & Tear | Breakdown | JOEL | OTHERS | OTHERS | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 |  | Completed | 2025-01-30 | 1
232 | ROTISERIE MACHINE NOT WORKING | LAG, LEKKI PHASE 1 | OTHERS | Breakdown | KITCHTEC | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 |  | Completed | 2025-01-30 | 1
233 | Plumbing issues @MMA2 | LAG, MMA2 | Corrective Action | Corrective | PROPEAR | OTHERS | OTHERS | 2025-01-29 | 50 | 2025-01-29 | 0 | 2025-01-30 | 1 | [9 empty] | Overdue
234 | BLOCK DRAINAGE AT THE BIN AREA | LAG, FREEDOMWAY | Corrective Action | Corrective | JOEL | OTHERS | OTHERS | 2025-01-28 | 2 | 2025-01-28 | 0 | 2025-01-30 | 2 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 |  | Completed | 2025-01-30 | 1
235 | Faulty bulb and old broken cabinet shelf | LAG, ILUPEJU | Wear & Tear | Breakdown |  | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-14 | 65 | 2025-01-14 | 0 | 2025-01-29 | 15 | 2025-01-29 | 2025-01-30 | 1 | 2025-01-30 | 49 |  |  |  | 101049.98 | Overdue
236 | Faulty bulb and old broken cabinet shelf | LAG, ILUPEJU | Electrical Surge | Breakdown | KOLA | OTHERS | OTHERS | 2025-01-14 | 15 | 2025-01-14 | 0 | 2025-01-15 | 1 | 2025-01-29 | 2025-01-29 | 0 | 2025-01-29 | 0 | 2025-01-29 | 0 | 2025-01-29 |  | Completed | 2025-01-29 | 1
237 | FUALTY FRYER SINK | LAG, FREEDOMWAY | Wear & Tear | Breakdown | JOEL | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 |  | Completed | 2025-01-30 | 1
238 | FAULTY COLD ROOM | IBADAN, AKOBO | Wear & Tear | Breakdown | TONAOGUNS | COLD ROOM UNIT | HVAC | 2025-01-25 | 54 | 2025-01-26 | 1 |  | 53 | [9 empty] | Overdue
239 | CORRODED FREEZER ROOM DOOR | LAG, AGUNGI | Wear & Tear | Breakdown | TONAOGUNS | FREEZER ROOM | HVAC | 2025-01-06 | 73 | 2025-01-06 | 0 | 2025-01-08 | 2 | 2025-01-08 |  | 71 | [6 empty] | Overdue
240 | REPAIR OF LEAKING ROOF FOR PX OPOLO | BAYELSA, OPOLO | Wear & Tear | Breakdown | DT CONSULT | ROOF | BUILDING | 2025-01-30 | 49 | 2025-01-31 | 1 | 2025-01-31 | 0 | 2025-02-01 | 2025-02-01 | 0 | 2025-02-01 | 0 | 2025-02-01 | 47 |  |  | Overdue
241 | FAULTY UNDER BAR CHILLER | LAG, IRE-AKARI | Wear & Tear | Breakdown | G.B BOYEJO | NBC CHILLER | HVAC | 2025-01-28 | 51 | 2025-01-28 | 0 |  | 51 | [9 empty] | Overdue
242 | FAULTY PIPE AT FRYER'S SINK | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2025-01-30 | 5 | 2025-01-31 | 1 | 2025-02-04 | 4 | 2025-02-04 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 |  | Completed | 2025-02-04 | 1
243 | FAULTY SOCKET REPAIR | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | ISMAIL | OTHERS | OTHERS
244 | Door handle for PX ogunnaike | LAG, JOEL OGUNNAIKE | Users Misuse | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-29 | 6 | 2025-01-29 | 0 | 2025-01-30 | 1 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-31 | 1 | 2025-02-01 | 3 | 2025-02-04 | 66012.65 | Completed | 2025-02-04 | 1
245 | REPAINTING OF STORES LOBBY AND SURROUNDINGs | LAG, BODE THOMAS | Wear & Tear | Breakdown | GENEROUS | PAINTING | BUILDING | 2025-01-30 | 49 | 2025-01-30 | 0 | 2025-01-31 | 1 | 2025-01-31 | 2025-02-01 | 1 | 2025-02-01 | 47 |  |  |  | 1100000 | Overdue
246 | FAULTY WARMER | AKWA IBOM, ABAK RD | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-01-02 | 77 | 2025-01-02 | 0 | 2025-01-06 | 4 | 2025-01-06 | 2025-01-06 | 0 | 2025-01-06 | 10 | 2025-01-16 | 63 |  |  | Overdue
247 | FAULTY WARMER | AKWA IBOM, ABAK RD | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-01-17 | 62 | 2025-01-17 | 0 | 2025-01-17 | 0 | 2025-01-17 | 2025-01-17 | 0 | 2025-01-17 | 18 | 2025-02-04 | 44 |  |  | Overdue
248 | GENERATOR DUE FOR SERVICING | ILORIN, TAIWO RD | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-01-31 | 48 | 2025-02-01 | 1 |  | 47 | [9 empty] | Overdue
249 | Faulting generator | LAG, ISAWO-IKORODU | Wear & Tear | Breakdown | DELIGHTSOME | GENERATOR | GENERATOR | 2025-01-31 | 10 | 2025-02-01 | 1 | 2025-02-01 | 0 | 2025-02-01 | 2025-02-01 | 0 | 2025-02-01 | 0 | 2025-02-01 | 9 | 2025-02-10 |  | Completed | 2025-02-10 | 1
250 | BROKEN CABINET GLASS | LAG, FESTAC | Users Misuse | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-23 | 56 | 2025-01-23 | 0 |  | 56 | [9 empty] | Overdue
251 | PAINTING | LAG, TEJUOSHO | Wear & Tear | Breakdown | WESTERN DESIGN | WALL | BUILDING | 2025-01-31 | 48 | 2025-01-31 | 0 | 2025-01-31 | 0 | 2025-01-31 | 2025-02-01 | 1 | 2025-02-01 | 47 |  |  |  | 550000 | Overdue
252 | REPAINTING OF STORES LOBBY AND SURROUNDINGs | LAG, BODE THOMAS | Wear & Tear | Breakdown | WESTERN DESIGN | WALL | BUILDING | 2025-01-30 | 49 | 2025-01-30 | 0 | 2025-01-31 | 1 | 2025-01-31 | 2025-02-01 | 1 | [5 empty] | 1100000 | Overdue
253 | Cold room and freezer room not attaining temperature | EBONYI, WATERWORKS, ABAKALIKI | Wear & Tear | Breakdown | MOFFEEN | COLD ROOM UNIT | HVAC | 2025-01-16 | 28 | 2025-01-17 | 1 | 2025-02-05 | 19 | 2025-02-05 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 8 | 2025-02-13 |  | Completed | 2025-02-13 | 1
254 | PPU mixer not functioning | EBONYI, WATERWORKS, ABAKALIKI | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2025-01-31 | 48 | 2025-01-31 | 0 |  | 48 | [9 empty] | Overdue
255 | FAULTY AIR VENT IN CUSTOMER'S REST ROOM | LAG, IPAJA RD | Wear & Tear | Breakdown | ABBEY | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2025-01-31 | 48 | 2025-02-01 | 1 |  | 47 | [9 empty] | Overdue
256 | REQUEST FOR REPLACEMENT OF STORE ELECTRICITY METER | LAG, OGUDU | Others | Breakdown | EO IKEDC | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-01-20 | 36 | 2025-01-20 | 0 | 2025-02-05 | 16 | 2025-02-05 | 2025-02-05 | 0 | 2025-02-05 | 1 | 2025-02-06 | 19 | 2025-02-25 | 250000 | Completed | 2025-02-25 | 1
257 | COLDROOM AND FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, OKOTA | Wear & Tear | Breakdown | TRIPPLE O | COLD ROOM UNIT | HVAC | 2025-01-14 | 65 | 2025-01-14 | 0 | 2025-02-01 | 18 | 2025-02-28 | 2025-03-10 | 10 | 2025-03-10 | 2 | 2025-03-12 | 8 | 2025-02-09 | 180500 | Overdue
258 | Daily Equipment Status (air curtain update) | PPU Oniru | Wear & Tear | Breakdown | EKNOR | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2025-01-29 | 50 | 2025-01-29 | 0 | 2025-02-02 | 4 | [9 empty] | Overdue
259 | Daily Equipment Status (air curtain update) | PPU Oniru | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-01-29 | 50 | 2025-01-29 | 0 |  | 50 | [9 empty] | Overdue
260 | CABINET NOT ATTAINING TEMPERATURE | LAG, OKOTA | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-13 | 66 | 2025-01-14 | 1 |  | 65 | [9 empty] | Overdue
261 | DAMAGED COMPARTMENT PART | LAG, OKOTA | Wear & Tear | Breakdown | MATOLAD
262 | INVERTER NOT WORKING | OGUN, OKE-ILEWO | Wear & Tear | Breakdown | NISTECH | INVERTER SYSTEM | INVERTER | 2025-01-30 | 49 | 2025-01-31 | 1 | 2025-02-05 | 5 | 2025-02-07 | 2025-02-07 | 0 | 2025-02-07 | 41 |  |  |  |  | Overdue
263 | freezer room not working | LAG, OBA AKRAN | Wear & Tear | Breakdown | BCE | FREEZER ROOM | HVAC | 2025-01-28 | 51 | 2025-01-28 | 0 |  | 51 | [9 empty] | Overdue
264 | FULTY SEWAGE PUMP | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | JOEL | SEPTIC TANK | EVACUATION | 2025-01-30 | 49 | 2025-01-30 | 0 |  | 49 | [9 empty] | Overdue
265 | BAD WATER TREATMENT NET | LAG, FESTAC | Wear & Tear | Breakdown | TAIDAV | OTHERS | OTHERS | 2025-01-11 | 68 | 2025-01-11 | 0 | 2025-02-02 | 22 | 2025-02-02 | 2025-02-02 | 0 | 2025-02-02 | 0 | 2025-02-02 | 46 | 2025-02-04 |  | Overdue
266 | GENERATOR SERVICING | LAG, MOBIL OGBA | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2025-01-31 | 48 | 2025-02-02 | 2 |  | 46 | [9 empty] | Overdue
267 | DEAD BULB IN THE OFFICE | ABUJA, KARU | Wear & Tear | Breakdown |  | OTHERS | OTHERS | 2025-01-27 | 52 | 2025-02-02 | 6 |  | 46 | [9 empty] | Overdue
268 | EVACUATION OF SEPTIC TANK | ILORIN, MM WAY | Others | Breakdown | REVELATION | SEPTIC TANK | EVACUATION | 2025-01-20 | 59 | 2025-01-20 | 0 | 2025-02-02 | 13 | 2025-02-02 | 2025-02-03 | 1 | 2025-02-03 | 45 |  |  |  | 503900 | Overdue
269 | UNDERGROUND LINKAGE IN THE DRY STORE | LAG, AJOSE ADEOGUN | Others | Breakdown | ACORN | OTHERS | OTHERS | 2025-01-31 | 48 | 2025-01-31 | 0 | 2025-01-31 | 0 | [9 empty] | Overdue
270 | RODENT ACTIVITIES - ROACHES & RAT | LAG, AJOSE ADEOGUN | Corrective Action | Corrective | PENTECOSTAL | OTHERS | OTHERS | 2025-01-17 | 62 | 2025-01-18 | 1 | 2025-01-29 | 11 | [9 empty] | Overdue
271 | FAULTY CUSTOMER RESTROOM A.C | LAG, AWOLOWO | Wear & Tear | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-22 | 57 | 2025-01-22 | 0 | 2025-01-23 | 1 | 2025-02-11 | 2025-02-17 | 6 | 2025-02-17 | 0 | 2025-02-17 | 31 |  | 290000 | Overdue
272 | CHEST FREEZER NOT ATTAINING TEMPERATURE | LAG, AWOLOWO | Wear & Tear | Breakdown | G.B BOYEJO | CHEST FREEZER | HVAC | 2025-01-26 | 53 | 2025-01-27 | 1 |  | 52 | [9 empty] | Overdue
273 | TORN BOH UPRIGHT CHILLER GASKET | LAG, AWOLOWO | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2025-01-11 | 68 | 2025-01-11 | 0 | 2025-01-29 | 18 | [9 empty] | Overdue
274 | FAULTY GREASE TRAP | LAG, AWOLOWO | Wear & Tear | Breakdown | ZEBRA G3 | GREASE TRAP | GREASE_TRAP | 2025-01-29 | 50 | 2025-01-29 | 0 | 2025-02-03 | 5 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 42 |  |  |  | 270000 | Overdue
275 | 1 LOBBY AC NOT WORKING | LAG, AWOLOWO | Wear & Tear | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-20 | 18 | 2025-01-21 | 1 | 2025-01-22 | 1 | 2025-01-22 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 | 16 | 2025-02-07 |  | Completed | 2025-02-07 | 1
276 | BROKEN DRAIN WHEEL CONTROL | LAG, AWOLOWO | Wear & Tear | Breakdown | KITCHTECH | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT | 2025-01-21 | 58 | 2025-02-03 | 13 |  | 45 | [9 empty] | Overdue
277 | UNDERGROUND LINKAGE IN THE DRY STORE | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | ACORN | SPLIT UNIT DRY STORE | HVAC | 2025-01-31 | 48 | 2025-01-31 | 0 | 2025-01-31 | 0 | 2025-02-04 |  | 44 | [6 empty] | Overdue
278 | EBUTE METTA CRACKING CABINET GLASS |  | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-03 | 45 | 2025-02-03 | 0 |  | 45 | [9 empty] | Overdue
279 | CABINET DRIP WATER | LAG, FREEDOMWAY | Wear & Tear | Breakdown | JOEL | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-01-30 |  | Completed | 2025-01-30 | 1
280 | FAULTY VEGETABLE CUTTER | LAG, JOEL OGUNNAIKE | Users Misuse | Breakdown | BCE | OTHERS | OTHERS | 2025-01-27 | 52 | 2025-01-28 | 1 |  | 51 | [9 empty] | Overdue
281 | RATIONALE MACHINE DISPLAYING EMERGENCY MODE | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2025-01-28 | 51 | 2025-01-28 | 0 |  | 51 | [9 empty] | Overdue
282 | FAULTY COOKING BURNER | LAG, TEJUOSHO | Wear & Tear | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-01-22 | 57 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 |  | 57 | 2025-01-22 | 57 |  |  |  | 107000 | Overdue
283 | LEAKAGE FROM ONE OF THE PUMPING MACHINES | LAG, TEJUOSHO | Wear & Tear | Breakdown | PRO-EQUIP | DOSING PUMP | WTP | 2025-01-13 | 66 | 2025-01-13 | 0 |  | 66 | [9 empty] | Overdue
284 | COLDROOM NOT ATTAINING TEMPERATURE | LAG, OKOTA | Wear & Tear | Breakdown | THIO | COLD ROOM UNIT | HVAC | 2025-01-14 | 65 | 2025-01-14 | 0 | 2025-02-01 | 18 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 45 |  |  |  | 1550000 | Overdue
285 | BLOCKED DRAINGE | LAG, OMOLE | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-19 | 60 | 2025-01-19 | 0 | 2025-01-27 | 8 | 2025-02-03 | 2025-02-03 | 0 | [5 empty] | 750000 | Overdue
286 | FAULTY CUSTOMERS' TOILET | LAG, OGUNLANA DRIVE | Others | Breakdown | OLUWATOSIN | OTHERS | OTHERS | 2025-01-28 | 6 | 2025-01-28 | 0 | 2025-02-03 | 6 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 |  | Completed | 2025-02-03 | 1
287 | FAULTY COLLETRAMATIC DRAINING MACHINE | LAG, MOBIL OGBA | Wear & Tear | Breakdown | BCE | COLLECTRAMATIC OIL PUMP MACHINE | KITCHEN_EQUIPMENT | 2025-01-29 | 50 | 2025-01-29 | 0 |  | 50 | [9 empty] | Overdue
288 | SERVICING OF ICE CREAM MACHINE | LAG, JIBOWU | Routine Servicing | Preventive | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-01-16 | 63 | 2025-01-16 | 0 |  | 63 | [9 empty] | Overdue
289 | LEAKING FRYER ZINC TAP | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | JOEL | TAP | PLUMBING | 2025-01-30 | 49 | 2025-01-30 | 0 |  | 49 | [9 empty] | Overdue
290 | OPEN SOCKET AND FAULTY LAMP HOLDER IN THE KITCHEN | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | ISMAIL | 18W ROUND LIGHT FITTING | ELECTRICAL | 2025-01-30 | 49 | 2025-01-30 | 0 |  | 49 | [9 empty] | Overdue
291 | LEAKAGE OF GAS FROM THE GAS GOVERNOR | LAG, JIBOWU | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-01-28 | 6 | 2025-01-28 | 0 | 2025-01-28 | 0 | 2025-01-28 | 2025-01-28 | 0 | 2025-01-28 | 1 | 2025-01-29 | 5 | 2025-02-03 | 52000 | Completed | 2025-02-03 | 1
292 | CRACKED WALL AT THE DRY STORE | LAG, AWOLOWO | Wear & Tear | Breakdown | ACORN | WALL | BUILDING | 2025-01-22 | 7 | 2025-01-22 | 0 | 2025-01-29 | 7 | 2025-01-29 | 2025-01-29 | 0 | 2025-01-29 | 0 | 2025-01-29 | 0 | 2025-01-29 |  | Completed | 2025-01-29 | 1
293 | OVEN DUE FOR SERVICING | LAG, ILUPEJU | Routine Servicing | Preventive | PRO KITCHEN | OTHERS | OTHERS
294 | ELECTRICAL SHOCK AT BACK OF HOUSE | LAG, MAGODO | Electrical Surge | Breakdown | BCE | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-01-28 | 51 | 2025-01-28 | 0 | 2025-02-03 | 6 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 45 |  |  | Overdue
295 | BROKEN WALL TILES IN THE LOBBY AND DISCOLOURED FLOOR TILES IN THE LOBBY | LAG, IDI-IROKO RD | Wear & Tear | Breakdown | PENTECOSTAL | WALL | BUILDING | 2025-01-30 | 49 | 2025-01-30 | 0 | 2025-01-30 | 0 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 45 |  |  |  | 180000 | Overdue
296 | FAULTY INSECTICUTOR | LAG, FESTAC | Wear & Tear | Breakdown | TIMILEHIN | INSECT KILLER BOH | ELECTRICAL | 2025-01-28 | 0 | 2025-01-28 | 0 | 2025-01-28 | 0 | 2025-01-28 | 2025-01-28 | 0 | 2025-01-28 | 0 | 2025-01-28 | 0 | 2025-01-28 |  | Completed | 2025-01-28 | 1
297 | FAULTY DISPLAY CABINET FLIP DOOR HOLDER | ABUJA, KARU | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-26 | 53 | 2025-02-04 | 9 |  | 44 | [9 empty] | Overdue
298 | REPLACEMENT OF SOAP DISPENSER | LAG, JIBOWU | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2025-01-17 | 62 | 2025-01-18 | 1 | 2025-01-18 | 0 | 2025-02-02 |  | 46 | [6 empty] | Overdue
299 | ICE MACHINE NOT WORKING | LAG, AWOLOWO | Wear & Tear | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-01-22 | 57 | 2025-01-22 | 0 |  | 57 | [9 empty] | Overdue
300 | FAULTY WARMER DOOR HANDLE | AKWA IBOM, EKET-ORON RD | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 | 135450 | Completed | 2025-01-20 | 1
301 | REPLACEMENT OF KITCHEN TAP HEAD. | KADUNA, YAKUBU GOWON | Users Misuse | Breakdown | OLANIJI OJO | TAP | PLUMBING | 2025-02-04 | 44 | 2025-02-04 | 0 |  | 44 | [9 empty] | Overdue
302 | FAULTY INSECTOCUTOR | LAG, OBA AKRAN | Wear & Tear | Breakdown | TIMILEHIN | INSECT KILLER LOBBY 1 | ELECTRICAL | 2025-01-27 | 11 | 2025-01-27 | 0 | 2025-02-04 | 8 | 2025-02-04 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 3 | 2025-02-07 |  | Completed | 2025-02-07 | 1
303 | INCONSISTENCY IN RUN HOUR | ANAMBRA, ZIK AVENUE, AWKA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-15 | 64 | 2025-02-03 | 19 | 2025-02-03 | 0 | [9 empty] | Overdue
304 | FAULTY KEY KNOB | LAG, DIYA STREET | Wear & Tear | Breakdown | PENTICOSTAL | OTHERS | OTHERS | 2025-01-17 | 62 | 2025-01-17 | 0 | 2025-01-31 | 14 | 2025-02-04 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 44 |  | 67212.5 | Overdue
305 | BAD WATER TREATMENT NET | LAG, FESTAC | Routine Servicing | Preventive | TAIDAV | WATER TREATMENT PLANT BLD | BUILDING | 2025-01-11 | 24 | 2025-01-11 | 0 | 2025-01-14 | 3 | 2025-01-14 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 | 21 | 2025-02-04 |  | Completed | 2025-02-04 | 1
306 | RUSTED MALE STAFF RESTROOM WINDOW BURGLARY | LAG, ILUPEJU | Wear & Tear | Breakdown | TAIDAV | OTHERS | OTHERS | 2025-01-17 | 62 | 2025-01-17 | 0 | 2025-02-04 | 18 | [9 empty] | Overdue
307 | REPLACEMENT OF KITCHEN TAP HEAD. | KADUNA, YAKUBU GOWON | Wear & Tear | Breakdown | OLANIYI | TAP | PLUMBING | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 |  | Completed | 2025-02-04 | 1
308 | REQUEST FOR STORE BLENDER | LAG, OKE-AFA | Users Misuse | Breakdown | FRIDAY | OTHERS | OTHERS | 2025-02-04 | 44 | 2025-02-04 | 0 | 2025-02-04 | 0 | [9 empty] | Overdue
309 | Dead BULB | LAG, CONOIL IKEJA | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-01-31 | 10 | 2025-02-04 | 4 | 2025-02-04 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 |  | Completed | 2025-02-10 | 1
310 | DEAD BULB IN THE STORE | LAG, GBAGADA | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-01-22 | 1 | 2025-01-22 | 0 | 2025-01-23 | 1 | 2025-01-23 | 2025-01-23 | 0 | 2025-01-23 | 0 | 2025-01-23 | 0 | 2025-01-23 |  | Completed | 2025-01-23 | 1
311 | DEAD BULB IN MALE CUSTOMER RESTROOM | LAG, AWOLOWO | Wear & Tear | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 | 0 | 2025-01-20 |  | Completed | 2025-01-20 | 1
312 | FAULTY FREEZER ROOM | AKWA IBOM, NWANIBA | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2025-01-31 | 48 | 2025-01-31 | 0 | 2025-02-04 | 4 | [9 empty] | Overdue
313 | LEAKAGE AT THE HAND WASH BASIN PIPE | LAG, TEJUOSHO | Wear & Tear | Breakdown | OLUWATOSIN | KITCHEN WASH HAND SINK | PLUMBING | 2025-01-25 | 10 | 2025-01-25 | 0 | 2025-02-04 | 10 | 2025-01-28 | 2025-02-04 | 7 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 |  | Completed | 2025-02-04 | 1
314 | BROKEN TILE | LAG, ISAWO-IKORODU | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-01-21 | 58 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-02-04 |  | 44 | [6 empty] | Overdue
315 | Temporary Store closure Lekki phase one | LAG, LEKKI PHASE 1 | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-01-04 | 75 | 2025-01-04 | 0 | 2025-01-04 | 0 | 2025-02-02 |  | 46 | [6 empty] | Overdue
316 | WARMER HANDLE | CALABAR, NDIDEM | Users Misuse | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-01-30 | 5 | 2025-01-31 | 1 | 2025-01-31 | 0 | 2025-01-31 | 2025-01-31 | 0 | 2025-01-31 | 0 | 2025-01-31 | 4 | 2025-02-04 | 141900 | Completed | 2025-02-04 | 1
317 | FAULTY INSECUTOR | LAG, IRE-AKARI | Wear & Tear | Breakdown | FRIDAY | INSECT KILLER BOH | ELECTRICAL | 2025-01-05 | 15 | 2025-01-05 | 0 | 2025-01-05 | 0 | [7 empty] | 2025-01-20 |  | Completed | 2025-01-20 | 1
318 | CABINET LIGHT NOT COMING UP | BAYELSA, YENAGOA | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-28 | 51 | 2025-01-28 | 0 | 2025-01-29 | 1 | 2025-01-29 | 2025-01-29 | 0 | 2025-01-29 | 50 |  |  |  |  | Overdue
319 | OPEN HOLES AND CRACK WALL TILE AT BOH AND FOH | LAG, LEKKI PHASE 1 | Others | Breakdown | PENTECOSTAL | WALL | BUILDING | 2025-01-31 | 48 | 2025-01-31 | 0 | 2025-02-05 | 5 | 2025-02-05 | 2025-02-07 | 2 | [6 empty] | Overdue
320 | FAULTY SECURITY LIGHTS IN THE STORE | LAG, IPAJA RD | Wear & Tear | Breakdown | TAYO | 18W ROUND LIGHT FITTING | ELECTRICAL | 2025-01-24 | 55 | 2025-01-24 | 0 | 2025-02-05 | 12 | 2025-02-05 |  | 43 | [6 empty] | Overdue
321 | FAULTY GAS BOILER AND BURNER | LAG, ILUPEJU | Wear & Tear | Breakdown | PROPEARJEFF | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-01-06 | 0 | 2025-01-06 | 0 | 2025-01-06 | 0 | 2025-01-06 | 2025-01-06 | 0 | 2025-01-06 | 0 | 2025-01-06 | 0 | 2025-01-06 |  | Completed | 2025-01-06 | 1
322 | FAULTY GAS BOILER AND BURNER | LAG, ILUPEJU | Wear & Tear | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2025-01-27 | 52 | 2025-01-27 | 0 | 2025-02-05 | 9 | [9 empty] | Overdue
323 | FAULTY FLAME GRILLED MACHINE | LAG, OSOLOWAY | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2025-01-11 | 68 | 2025-01-11 | 0 |  | 68 | [9 empty] | Overdue
324 | FAULTY SOCKET REPAIR | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-01-31 | 48 | 2025-01-31 | 0 |  | 48 | [9 empty] | Overdue
325 | Faulty Oil Pump for Collectromatic Machine | LAG, OSOLOWAY | Wear & Tear | Breakdown | BCE | COLLECTRAMATIC OIL PUMP MACHINE | KITCHEN_EQUIPMENT | 2025-01-16 | 63 | 2025-01-16 | 0 |  | 63 | [9 empty] | Overdue
326 | URGENT NEED FOR SERVICING OF ACs PPU ONIRU | PPU Oniru | Routine Servicing | Preventive | FOLLTEC | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-10 | 69 | 2025-01-10 | 0 | 2025-01-10 | 0 | 2025-01-16 | 2025-01-16 | 0 | 2025-01-16 | 0 | 2025-01-16 | 63 |  |  | Overdue
327 | UV LIGHT NOT WORKING | OSUN, GBONGAN | Wear & Tear | Breakdown | PRO-EQUIP | UV LIGHT | WTP | 2025-01-17 | 62 | 2025-01-17 | 0 | 2025-02-20 | 34 | [9 empty] | Overdue
328 | BOH CHILLER NOT WORKING | IBADAN, VENTURA MALL | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2025-01-08 | 71 | 2025-01-08 | 0 | 2025-02-07 | 30 | 2025-02-07 | 2025-02-07 | 0 | 2025-02-13 | 0 | 2025-02-13 | 35 |  |  | Overdue
329 | DIRTY PYLON LIGHT | LAG, FESTAC | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-27 | 52 | 2025-01-27 | 0 | 2025-01-27 | 0 | 2025-01-28 | 2025-01-29 | 1 | 2025-01-29 | 50 |  |  |  |  | Overdue
330 | POTHOLES IN STORE SURROUNDINGS | EDO, UGBOWO, BENIN | Others | Breakdown | FULL TURN | OTHERS | OTHERS | 2025-01-24 | 55 | 2025-01-25 | 1 | 2025-02-07 | 13 | 2025-02-07 | 2025-02-08 | 1 | [5 empty] | 950000 | Overdue
331 | Leakage of water from Wall to next company from ppu and staff changing | LAG, ONIRU | Others | Breakdown | ACORN | OTHERS | OTHERS | 2025-01-21 | 30 | 2025-01-21 | 0 | 2025-01-23 | 2 | 2025-01-23 | 2025-01-25 | 2 | 2025-02-16 | 1 | 2025-02-17 | 3 | 2025-02-20 | 280476 | Completed | 2025-02-20 | 1
332 | BROKEN TILES IN THE LOBBY | LAG, IRE-AKARI | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-08 | 71 | 2025-01-08 | 0 | 2025-02-04 | 27 | 2025-02-05 | 2025-02-07 | 2 | [6 empty] | Overdue
333 | PX BADORE BROKEN CABINET GLASS. | LAG, BADORE | Users Misuse | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-18 | 25 | 2025-01-18 | 0 | 2025-02-12 | 25 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 30637.5 | Completed | 2025-02-12 | 1
334 | FAULTY CABINET GAUGE | LAG, BADORE | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-31 | 48 | 2025-01-31 | 0 |  | 48 | [9 empty] | Overdue
335 | WOBBLING CUSTOMER TOILET SEAT | LAG, MAGODO | Users Misuse | Breakdown | ADEREMI WAHAB | OTHERS | OTHERS | 2025-01-22 | 57 | 2025-01-22 | 0 |  | 57 | [9 empty] | Overdue
336 | CHECKING OF GAS PIPES AS USAGE IS HIGH | LAG, AGUNGI | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-01-04 | 75 | 2025-01-04 | 0 | 2025-01-13 | 9 | 2025-01-14 | 2025-01-14 | 0 | 2025-01-16 | 63 |  |  |  |  | Overdue
337 | Broken water pipe | LAG, OMOLE | Users Misuse | Breakdown | ADEREMI WAHAB | TAP | PLUMBING | 2025-01-30 | 8 | 2025-01-30 | 0 | 2025-02-07 | 8 | 2025-02-07 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 |  | Completed | 2025-02-07 | 1
338 | FAULTY CHEMICAL DOSING PUMP AT HQ WATER TREATMENT PLANT | LAG, ILUPEJU | Wear & Tear | Breakdown | PRO-EQUIP | DOSING PUMP | WTP | 2025-01-15 | 64 | 2025-01-15 | 0 | 2025-01-15 | 0 | 2025-02-08 |  | 40 | [6 empty] | Overdue
339 | LOBBY AC NOT WORKUNG EFFECTIVELY | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 2 | HVAC | 2025-01-23 | 1 | 2025-01-23 | 0 | 2025-01-24 | 1 | 2025-01-24 | 2025-01-24 | 0 | 2025-01-24 | 0 | 2025-01-24 | 0 | 2025-01-24 |  | Completed | 2025-01-24 | 1
340 | CAR PARK FLOWER VASE (POTS) NEEDED IN THE STORE | LAG, IPAJA RD | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-23 | 56 | 2025-01-23 | 0 | 2025-02-03 | 11 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-07 | 41 |  |  |  |  | Overdue
341 | FAULTY PIE STORAGE RACK |  | Wear & Tear | Breakdown | TAYO | OTHERS | OTHERS | 2025-01-14 | 65 | 2025-01-14 | 0 |  | 65 | [9 empty] | Overdue
342 | Faulty Extractor Fan | IBADAN, MOKOLA | Wear & Tear | Breakdown | RANEX4WARD | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2025-01-03 | 17 | 2025-01-03 | 0 | 2025-02-03 | 31 | 2025-01-06 | 2025-01-08 | 2 | 2025-01-08 | 0 | 2025-01-08 | 12 | 2025-01-20 | 175000 | Completed | 2025-01-20 | 1
343 | FAULTY WARMER HANDLE | EDO, AIRPORT RD, BENIN | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-01-26 | 53 | 2025-01-26 | 0 | 2025-01-27 | 1 | 2025-01-27 | 2025-01-27 | 0 | [5 empty] | 118250 | Overdue
344 | REQUEST FOR INSECTICUTOR AND CABINET BULB | OGUN, OKE-ILEWO | Electrical Surge | Breakdown | RANEX | OTHERS | OTHERS | 2025-01-21 | 58 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-08 | 2025-02-08 | 31 | 2025-02-08 | 40 |  |  |  |  | Overdue
345 | REQUEST FOR INSECUTOR BULB | OGUN, FATGBEMS IBB WAY | Electrical Surge | Breakdown | RANEX | INSECT KILLER BOH | ELECTRICAL | 2025-01-22 | 57 | 2025-01-22 | 0 | 2025-01-23 | 1 | 2025-01-23 | 2025-01-23 | 0 | 2025-01-23 | 56 |  |  |  | 25800 | Overdue
346 | FAULTY LOBBY ENTRANCE DOOR | LAG, ABULE EGBA | Wear & Tear | Breakdown | TAIDAV | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-01-28 | 51 | 2025-01-28 | 0 |  | 51 | [9 empty] | Overdue
347 | FAULTY LOBBY ENTRANCE DOOR | LAG, OGUNLANA DRIVE | Wear & Tear | Breakdown | TAIDAV | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-01-19 | 60 | 2025-01-19 | 0 | 2025-01-21 | 2 | [9 empty] | Overdue
348 | BROKEN TILES AT THE LOBBY | LAG, OPEBI | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-03 | 13 | 2025-01-03 | 0 |  | 76 | [7 empty] | 2025-01-16 |  | Completed | 2025-01-16 | 1
349 | BROKEN TILES AT THE LOBBY | LAG, IKORODU | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-21 | 58 | 2025-01-21 | 0 | 2025-01-21 | 0 | [9 empty] | Overdue
350 | FAULTY CABINET GLASS | LAG, IKEJA MALL | Users Misuse | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-08 | 71 | 2025-01-08 | 0 | 2025-01-14 | 6 | [9 empty] | Overdue
351 | FAULTY HAND DRYER AND BURNT SUPPLY WIRE | LAG, OKE-AFA | Electrical Surge | Breakdown | FRIDAY | OTHERS | OTHERS | 2025-01-27 | 7 | 2025-01-27 | 0 | 2025-02-03 | 7 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 |  | Completed | 2025-02-03 | 1
352 | FAULTY HAND DRYER IN THE STAFF AREA |  | Users Misuse | Breakdown | MOSES | HAND DRYER LOBBY | ELECTRICAL | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 |  | Completed | 2025-01-21 | 1
353 | BROKEN TILES IN THE LOBBY | LAG, IRE-AKARI | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-08 | 71 | 2025-01-08 | 0 | 2025-02-05 | 28 | 2025-02-07 | 2025-02-07 | 0 | 2025-02-08 | 0 | 2025-02-08 | 40 |  | 350000 | Overdue
354 | BROKEN TILES IN THE LOBBY | LAG, OKE-AFA | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-02 | 77 | 2025-01-02 | 0 | 2025-02-05 | 34 | 2025-02-05 | 2025-02-07 | 2 | 2025-02-08 | 0 | 2025-02-08 | 40 |  | 250000 | Overdue
355 | FREEZER ROOM NOT ATTAINING TEMPERATURE | CALABAR, NDIDEM | Routine Servicing | Preventive | BCE | FREEZER ROOM | HVAC | 2025-01-01 | 78 | 2025-02-01 | 31 | 2025-02-02 | 1 | 2025-01-06 | 2025-01-06 | 0 | 2025-01-06 | 0 | 2025-01-06 | 73 |  | 1084675 | Overdue
356 | FREEZER ROOM NOT ATTAINING TEMPERATURE |  | Routine Servicing | Preventive | TONAOGUNS | FREEZER ROOM | HVAC | 2025-01-04 | 75 | 2025-01-04 | 0 | 2025-01-06 | 2 | 2025-01-06 | 2025-01-07 | 1 | 2025-01-07 | 72 |  |  |  |  | Overdue
357 | FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, MMA2 | Routine Servicing | Preventive | TONAOGUNS | FREEZER ROOM | HVAC | 2025-01-20 | 10 | 2025-01-20 | 0 |  | 59 | [7 empty] | 2025-01-30 |  | Completed | 2025-01-30 | 1
358 | CASHIERS COUNTER CHIPPED AND NEEDS REPAIRS | LAG, IPAJA RD | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-01-23 | 56 | 2025-01-23 | 0 | 2025-01-23 | 0 | [9 empty] | Overdue
359 | FAULTY FOOD WARMER HANDLE | LAG, MMA2 | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2025-01-06 | 73 | 2025-01-06 | 0 | 2025-01-14 | 8 | 2025-01-14 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 | 65 |  | 135450 | Overdue
360 | DEAD INSECTOCUTOR BULB | LAG, MOBIL OGBA | Electrical Surge | Breakdown | MOSES | OTHERS | OTHERS | 2025-01-26 | 1 | 2025-01-26 | 0 | 2025-01-27 | 1 | 2025-01-27 | 2025-01-27 | 0 | 2025-01-27 | 0 | 2025-01-27 | 0 | 2025-01-27 |  | Completed | 2025-01-27 | 1
361 | DEAD PYLON LIGHT. | LAG, ALIMOSHO | Electrical Surge | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-01-06 | 73 | 2025-01-06 | 0 | 2025-01-28 | 22 | 2025-01-29 | 2025-01-29 | 0 | 2025-01-30 | 49 |  |  |  | 140625 | Overdue
362 | SERVICING OF LOBBY AC AND COLD ROOM CONDESER | IBADAN, RING-ROAD | Routine Servicing | Preventive | TONAOGUNS | OTHERS | OTHERS | 2025-01-22 | 16 | 2025-01-22 | 0 | 2025-01-23 | 1 | [7 empty] | 2025-02-07 | 179750 | Completed | 2025-02-07 | 1
363 | EVAPORATOR REPLACEMENT FOR DRYSTORE AC | LAG, ENTOURAGE MALL | Routine Servicing | Preventive | TONAOGUNS | OTHERS | OTHERS | 2025-01-07 | 72 | 2025-01-07 | 0 | 2025-02-06 | 30 | 2025-02-06 |  | 42 | [6 empty] | Overdue
364 | OPEN SOCKET IN FRYER SECTION | LAG, AWOLOWO | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-01-20 | 1 | 2025-01-20 | 0 | 2025-01-21 | 1 | 2025-01-21 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 |  | Completed | 2025-01-21 | 1
365 | MENU INSERT BOARD | ILORIN, GRA | Wear & Tear | Breakdown | EDIDIONG | OTHERS | OTHERS | 2025-01-10 | 69 | 2025-01-10 | 0 | 2025-01-24 | 14 | [9 empty] | Overdue
366 | FAULTY CHIPS FRYER | LAG, MOBIL OGBA | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-01-27 | 52 | 2025-01-27 | 0 | 2025-01-30 | 3 | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 12 | 2025-02-11 | 37 |  | 377325 | Overdue
367 | FAULTY CHIPS FRYER | LAG, ONIRU | Wear & Tear | Breakdown | ADEREMI | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-01-20 | 1 | 2025-01-20 | 0 | 2025-01-21 | 1 | 2025-01-21 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 |  | Completed | 2025-01-21 | 1
368 | FAULTY CHIPS FRYER SWITCH | LAG, TEJUOSHO | Wear & Tear | Breakdown | TIMILEHIN | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-01-07 | 0 | 2025-01-07 | 0 | 2025-01-07 | 0 | 2025-01-07 | 2025-01-07 | 0 | 2025-01-07 | 0 | 2025-01-07 | 0 | 2025-01-07 |  | Completed | 2025-01-07 | 1
369 | FAULTY CHIPS FRYER SOCKET | LAG, BODE THOMAS | Wear & Tear | Breakdown | TIMILEHIN | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-01-04 | 0 | 2025-01-04 | 0 | 2025-01-04 | 0 | 2025-01-04 | 2025-01-04 | 0 | 2025-01-04 | 0 | 2025-01-04 | 0 | 2025-01-04 |  | Completed | 2025-01-04 | 1
370 | FAULTY CHIPS FRYER PLUG. | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | TIMILEHIN | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-01-02 | 0 | 2025-01-02 | 0 | 2025-01-02 | 0 | 2025-01-02 | 2025-01-02 | 0 | 2025-01-02 | 0 | 2025-01-02 | 0 | 2025-01-02 |  | Completed | 2025-01-02 | 1
371 | VEGETABLE SHREDDER NOT WORKING | PH, RUKPOKWU | Wear & Tear | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2025-01-17 | 62 | 2025-01-17 | 0 | 2025-01-17 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 38 |  |  | Overdue
372 | FAULTY LOBBY A/C | LAG, ALIMOSHO | Routine Servicing | Preventive | GB | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-23 | 56 | 2025-01-23 | 0 | 2025-02-10 | 18 | 2025-02-10 |  | 38 | [6 empty] | Overdue
373 | WATER TREATMENT SERVICING/FAULTY DOUSING PUMP | LAG, ALIMOSHO | Routine Servicing | Preventive |  | OTHERS | OTHERS | 2025-01-31 | 48 | 2025-01-31 | 0 | 2025-02-03 | 3 | [9 empty] | Overdue
374 | FAULTY SOAP DISPENSER AND BROKEN HAND DYER | LAG, BODE THOMAS | Users Misuse | Breakdown | PRO-EQUIP | HAND DRYER TOILET | ELECTRICAL | 2025-01-14 | 65 | 2025-01-14 | 0 | 2025-01-20 | 6 | [9 empty] | Overdue
375 | REQUISITION FOR NEW RACK at BODETHOMAS | LAG, BODE THOMAS | Wear & Tear | Breakdown | LAMBTECH | OTHERS | OTHERS
376 | PEELING AND RUSTY CABINET |  | Wear & Tear | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-16 | 63 | 2025-01-16 | 0 | 2025-01-27 | 11 | [9 empty] | Overdue
377 | WATER PIPE LEAKAGE | LAG, FESTAC | Wear & Tear | Breakdown | PROPEAR | OTHERS | OTHERS | 2025-01-13 | 66 | 2025-01-13 | 0 | 2025-01-22 | 9 | [9 empty] | Overdue
378 | BROKEN WALL IN THE STORE | LAG, OKE-AFA | Wear & Tear | Breakdown | PENTICOSTAL | WALL | BUILDING | 2025-01-14 | 65 | 2025-01-14 | 0 | 2025-01-14 | 0 | 2025-01-14 | 2025-01-16 | 2 | 2025-01-16 | 63 |  |  |  | 170000 | Overdue
379 | FAULTY DISPLAY CABINET LAMPHOLDERS | LAG, IDIMU | Electrical Surge | Breakdown | EMMANUEL | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-11 | 1 | [9 empty] | Overdue
380 | BROKEN WALL TILES IN LOBBY | LAG, IKOTUN | Wear & Tear | Breakdown | PENTECOSTAL | WALL | BUILDING | 2025-01-07 | 72 | 2025-01-07 | 0 | 2025-01-07 | 0 | [9 empty] | Overdue
381 | GENERATOR DUE FOR SERIVICING | LAG, BADORE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-01-18 | 61 | 2025-01-18 | 0 | 2025-01-18 | 0 | [9 empty] | Overdue
382 | Faulty BOH net door | LAG, OSOLOWAY | Wear & Tear | Breakdown | TAIDAV | INSECT KILLER BOH | ELECTRICAL | 2025-01-29 | 13 | 2025-01-29 | 0 | 2025-02-10 | 12 | 2025-02-11 |  | 37 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 |  | Completed | 2025-02-11 | 1
383 | BLOCKED DRAINAGE | LAG, ONIRU | Corrective Action | Corrective | ZEBRA | SEPTIC TANK | EVACUATION
384 | FAULTY ROLLER SHUTTER | OGUN, HEYDEN IBAFO | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-01-20 | 17 | 2025-01-20 | 0 | 2025-01-21 | 1 | [7 empty] | 2025-02-06 |  | Completed | 2025-02-06 | 1
385 | STORE IN NEED OF PAINTING THE FADED CEILING | LAG, IPAJA RD | Wear & Tear | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2025-01-23 | 56 | 2025-01-23 | 0 | 2025-02-11 | 19 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 36 |  |  |  | 550000 | Overdue
386 | open ceiling | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | MATOLAD | CEILING BOARD | BUILDING | 2025-01-29 | 50 | 2025-01-29 | 0 | 2025-02-12 | 14 | [9 empty] | Overdue
387 | DISPLAY CABINET AND UNDERBAR NOT ATTAINING TEMPERATURE | LAG, IKOTUN | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-30 | 49 | 2025-01-31 | 1 |  | 48 | [9 empty] | Overdue
388 | STORE SEALED BY LAGOS STATE WASTEWATER MANAGEMENT. | LAG, AJAH | Corrective Action | Corrective | ZEBRA | GREASE TRAP | GREASE_TRAP | 2025-01-22 | 57 | 2025-01-22 | 0 | 2025-01-22 | 0 | [9 empty] | Overdue
389 | STORE SEALED BY LAGOS STATE WASTEWATER MANAGEMENT. | PPU Ajah | Corrective Action | Corrective | ZEBRA | GREASE TRAP | GREASE_TRAP | 2025-01-22 | 57 | 2025-01-22 | 0 | 2025-01-22 | 0 | [9 empty] | Overdue
390 | MAINTENANCE ISSUES PICK DURING OSC | LAG, MAGODO | Others | Breakdown | GENEROUS | OTHERS | OTHERS | 2025-01-20 | 59 | 2025-01-20 | 0 | 2025-02-10 | 21 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 2 | 2025-02-12 | 36 |  | 200000 | Overdue
391 | FAULTY ROLLER SHUTTER | LAG, IKORODU | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-01-29 | 44 | 2025-01-29 | 0 | 2025-02-14 | 16 | 2025-02-14 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 | 28 | 2025-03-14 |  | Completed | 2025-03-14 | 1
392 | OPEN BODY OF KIOSK - EXTERIOR IMAGE CONCERN (REMINDER) | LAG, OBA AKRAN | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-18 | 61 | 2025-01-18 | 0 | 2025-02-14 | 27 | 2025-02-14 |  | 34 | [6 empty] | Overdue
393 | BROKEN TILES AND DISCOLOURED TILES IN THE STORE | LAG, IPAJA RD | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-23 | 56 | 2025-01-24 | 1 | 2025-02-14 | 21 | 2025-02-14 |  | 34 | [6 empty] | Overdue
394 | CR LUGBE FREEZER ROOM NOT ATTAINING TEMPERATURE | ABUJA, LUGBE | Routine Servicing | Preventive
395 | UNDERGROUND WATER LEAKAGE IN THE DRY STORE | LAG, AJOSE ADEOGUN | Corrective Action | Corrective | ACORN | OTHERS | OTHERS | 2025-01-31 | 48 | 2025-01-31 | 0 | 2025-01-31 | 0 | 2025-02-05 | 2025-02-17 | 12 | 2025-02-17 | 14 | 2025-03-03 | 17 | 2025-03-11 |  | Overdue
396 | FUALTY DISPLAY CABINET | IMO, IKENEGBU, OWERRI | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-28 | 6 | 2025-01-28 | 0 | 2025-01-28 | 0 | 2025-01-28 | 2025-01-28 | 0 | 2025-01-28 | 2 | 2025-01-30 | 4 | 2025-02-03 |  | Completed | 2025-02-03 | 1
397 | FAULTY FREEZER ROOM - CR OLOFA | ILORIN, OLOFAWAY | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2025-01-25 | 54 | 2025-01-25 | 0 | 2025-01-26 | 1 | 2025-01-26 | 2025-01-26 | 0 | 2025-01-26 | 29 | 2025-02-24 | 24 |  | 800000 | Overdue
398 | BROKEN DOOR HANDLE | LAG, AJAH | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-13 | 66 | 2025-01-13 | 0 | 2025-02-17 | 35 | 2025-02-17 |  | 31 | [6 empty] | Overdue
399 | BROKEN COLD ROOM HINGE | IBADAN, VENTURA MALL | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-01-23 | 25 | 2025-01-23 | 0 | 2025-01-25 | 2 | 2025-01-25 | 2025-01-25 | 0 | 2025-01-25 | 1 | 2025-01-26 | 22 | 2025-02-17 | 84750 | Completed | 2025-02-17 | 1
400 | FAULTY CABINET BULB AT PX FAGBA |  | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-23 | 11 | 2025-01-23 | 0 | 2025-02-03 | 11 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 16125 | Completed | 2025-02-03 | 1
401 | BROKEN DOOR HANDLE | LAG, AJAH | Users Misuse | Breakdown | PENTICOSTAL | OTHERS | OTHERS | 2025-01-13 | 38 | 2025-01-13 | 0 | 2025-02-17 | 35 | 2025-02-17 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | 3 | 2025-02-20 | 83905 | Completed | 2025-02-20 | 1
402 | DEAD INSECTICUTOR BULB IN THE LOBBY
403 | CRACKED WALL IN MANAGER OFFICE, DRY STORE | LAG, EKORO | Wear & Tear | Breakdown | PENTECOSTAL | WALL | BUILDING | 2025-01-06 | 73 | 2025-01-06 | 0 | 2025-01-14 | 8 | 2025-01-14 | 2025-01-16 | 2 | 2025-01-16 | 63 |  |  |  | 400000 | Overdue
404 | REFLOORING OF THE BOH | LAG, OGUNLANA DRIVE | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-20 | 59 | 2025-01-20 | 0 | 2025-02-13 | 24 | 2025-02-20 | 2025-02-21 | 1 | 2025-02-21 | 0 | 2025-02-21 | 27 |  | 700000 | Overdue
405 | REQUEST FOR STATUS UPDATE: ABULE-EGBA BIODIGESTER SET-UP | LAG, ABULE EGBA | Others | Breakdown | CHRIS OWOLABI | OTHERS | OTHERS | 2025-01-23 |  | 2025-01-23 |  | 2025-03-05 |  | 2025-03-05 |  | 15 | [6 empty] | Overdue
406 | DAILY EQUIPMENT STATUS | PPU Ajah | Others | Breakdown | PRO-EQUIP | TAP | PLUMBING
407 | BROKEN CABINET GLASS | LAG, IDIMU | Users Misuse | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-01-11 |  | 2025-01-11 |  | 2025-02-26 | [8 empty] | 2025-02-26 |  | Completed | 2025-02-26 | 1
408 | FAULTY FREEZER ROOM DOOR HANDLE | PPU Ajah | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC
409 | GENERATOR LEAKING DIESEL | PH, ABACHA RD | Wear & Tear | Breakdown | GLUFFSCO | GENERATOR | GENERATOR | 2025-02-18 |  | 2025-01-18 |  | 2025-02-18 |  | 2025-02-18 | 2025-02-18 | 0 | 2025-02-18 | 0 | 2025-02-18 | 0 | 2025-02-18 |  | Completed | 2025-02-18 | 1
410 | FAULTY ROLLER SHUTTER IN CR OMOLE | LAG, OMOLE | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-01-24 |  | 2025-01-25 |  | 2025-01-28 |  | 2025-01-30 | 2025-01-30 | 0 | 2025-01-30 | 37 | 2025-03-08 | 12 |  | 268535 | Overdue
411 | BOH WARMER FAULTY | IBADAN, VENTURA MALL | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-01-13 |  | 2025-01-13 |  | 2025-01-15 |  | 2025-01-15 | 2025-01-15 | 0 | 2025-01-15 | 5 | 2025-01-20 | 59 |  | 400975 | Overdue
412 | PAINTING OF PYLON LIGHT POLE/ STAFF CHANGING ROOM AND LOCKER | LAG, EKORO | Wear & Tear | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2025-01-06 | 73 | 2025-01-06 | 0 | 2025-01-06 | 0 | 2025-01-16 | 2025-01-16 | 0 | 2025-01-16 | 55 | 2025-03-12 | 8 |  | 220000 | Overdue
413 | FAULTY AC | LAG, MOBIL OGBA | Routine Servicing | Preventive | [10 empty] | 2025-01-23 | 45680 | [5 empty] | 155000
414 | RE: EVACUATION OF WASTE FROM THE GUTTER | LAG, ENTOURAGE MALL | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-01-28 | 51 | 2025-01-28 | 0 | 2025-01-28 | 0 | 2025-01-28 | 2025-01-29 | 1 | 2025-01-29 | 50 |  |  |  |  | Overdue
415 | EVACUATION AND EXCAVATION OF SEPTIC TANK | LAG, FESTAC | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-01-23 | 56 | 2025-01-23 | 0 | 2025-01-23 | 0 | 2025-01-23 | 2025-01-23 | 0 | 2025-01-23 | 1 | 2025-01-24 | 55 |  | 395000 | Overdue
416 | RE: EVACUATION OF SEPTIC TANK | LAG, OGUNLANA DRIVE | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-01-23 | 56 | 2025-01-23 | 0 | 2025-01-23 | 0 | [9 empty] | Overdue
417 | RE: EVACUATION OF SEPTIC TANK | LAG, OKOTA | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2025-01-21 | 58 | 2025-01-21 | 0 | 2025-01-22 | 1 | [9 empty] | Overdue
418 | RE: WASTE EVACUATION IN SEPTIC TANK | LAG, ALIMOSHO | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2025-01-15 | 64 | 2025-01-15 | 0 | 2025-01-16 | 1 | [9 empty] | Overdue
419 | Re: FAULTY HAND FLUSHER | LAG, AKOWONJO | Wear & Tear | Breakdown | PROPEAR | OTHERS | OTHERS | 2025-01-16 | 63 | 2025-01-16 | 0 | 2025-01-16 | 0 | [9 empty] | Overdue
420 | Re: FAULTY HAND WASH SINK TAP | LAG, FESTAC | Wear & Tear | Breakdown | PROPEAR | KITCHEN WASH HAND SINK | PLUMBING | 2025-01-09 | 70 | 2025-01-09 | 0 |  | 70 | [9 empty] | Overdue
421 | RE: Daily Equipment Status | LAG, ONIRU | Routine Servicing | Preventive | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-01-02 | 77 | 2025-01-02 | 0 | 2025-01-03 | 1 | 2025-01-03 | 2025-01-04 | 1 | [5 empty] | 340000 | Overdue
422 | RE: FAULTY FOOD WARMER | PH, RUKPOKWU | Routine Servicing | Preventive | BCE | OTHERS | OTHERS | 2025-01-02 | 5 | 2025-01-02 | 0 | 2025-01-02 | 0 | 2025-01-07 | 2025-01-07 | 0 | 2025-01-07 | 0 | 2025-01-07 | 0 | 2025-01-07 | 236500 | Completed | 2025-01-07 | 1
423 | Re: cracks on wall in office and dry store | DELTA, ISOKO RD | Wear & Tear | Breakdown | FULL TURN | WALL | BUILDING | 2025-01-26 | 53 | 2025-01-26 | 0 | 2025-01-29 | 3 | 2025-01-29 | 2025-03-14 | 44 | 2025-03-15 | 5 |  |  |  | 540900 | Overdue
424 | RE: HOT WATER NOT RUNNING IN THE STORE. | LAG, ALIMOSHO | Corrective Action | Corrective | PROPEAR | WATER HEATER | PLUMBING | 2025-01-21 | 2 | 2025-01-21 | 0 | 2025-01-22 | 1 | 2025-01-23 | 2025-01-23 | 0 | 2025-01-23 | 0 | 2025-01-23 | 0 | 2025-01-23 |  | Completed | 2025-01-23 | 1
425 | RE: NEPA POWER SUPPLY ISSUE | LAG, JIBOWU | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-01-22 | 1 | 2025-01-22 | 0 | 2025-01-23 | 1 | 2025-01-23 | 2025-01-23 | 0 | 2025-01-23 | 0 | 2025-01-23 | 0 | 2025-01-23 |  | Completed | 2025-01-23 | 1
426 | FREEZER ROOM NOT FREEZING | LAG, JIBOWU | Routine Servicing | Preventive | DYNAMITE | FREEZER ROOM | HVAC | 2025-01-24 | 55 | 2025-01-24 | 0 | 2025-02-03 | 10 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 45 |  |  |  | 1152000 | Overdue
427 | REQUEST OF SOAP AND SANITIZER DISPENSER | LAG, ISAWO-IKORODU | Others | Breakdown | PROPEAR | OTHERS | OTHERS | 2025-01-21 | 58 | 2025-01-21 | 0 | 2025-01-22 | 1 | [9 empty] | Overdue
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
Formulas:
Days Since Request = IF([Request Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Request Date],TODAY()-[Request Date]))
Days Delayed by Helpdesk = IF([Date Shared by Helpdesk]<>"",[Date Shared by Helpdesk]-[Request Date],IF([Request Date]="","",TODAY()-[Request Date]))
Days Delayed by Vendor/Technician = IF(M6<>"",M6-[Date Shared by Helpdesk],IF([Date Shared by Helpdesk]="","",TODAY()-[Date Shared by Helpdesk]))
Days Since Negotiation Request = TODAY() - [Date Negotiated]
Days Since Negotiation Request = IF([Date Negotiated]<>"",[Date Negotiated]-[Date Sent for Negotiation],IF([Date Sent for Negotiation]="","",TODAY()-[Date Sent for Negotiation]))
Days Since Approval Request = IF([Approved Date]<>"",[Approved Date]-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval Request = IF(#REF!<>"",#REF!-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval = IF([Approved Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Approved Date],TODAY()-[Approved Date]))
Days Since Approval = IF(#REF!="","",IF([Actual delivery date]<>"",[Actual delivery date]-#REF!,TODAY()-#REF!))
Status = IF([Request Date]="","",IF([Actual delivery date]<>"","Completed",IF(TODAY()<[Expected Delivery Date],"Planned",IF(TODAY()=[Expected Delivery Date],"Due","Overdue"))))
Note on AA6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vendor gave feedback thaat part is not available on 18 of Jan
Note on C20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR IYANA IYESI
Note on C47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HEYDEN EBUTE METTA
Note on C83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR SANGOTEDO
Note on C84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR SANGOTEDO
Note on C89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX IGANDO
Note on C98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR AGIDINGBI
Note on C102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX IGANDO
Note on C110: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: px
Note on C158: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR ALAPERE
Note on C181: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ppu
Note on C199: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PIE Express Agidingbi
Note on C200: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PPU
Note on C204: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pie Express Adeola Odeku
Note on C209: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX
Note on C263: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX
Note on C264: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX
Note on C281: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: EBUTE META
Note on C344: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX FAGBA
Note on C355: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR AGIDINGBI
Note on C359: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AGUNGI
Note on C379: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PIE EXPRESS AGIDINGBI
Note on C403: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX FAGBA

## FEBUARY
Legend
Completed on time
Completed late
S/N | ACTION/TASK | Store | Reason for Breakdown | Maintenance Category | Responsible | Specific Equipment | Category | Request Date | Days Since Request | Date Shared by Helpdesk | Days Delayed by Helpdesk | Date Attended/Checked by Vendor/Technician | Days Delayed by Vendor/Technician | Date Sent for Negotiation | Date Negotiated | Days Since Negotiation Request | Date Approval Requested | Days Since Approval Request | Approved Date | Days Since Approval | Expected Delivery Date | Cost | Status | Actual delivery date | Compliance check | Insert Comment
1 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, MMA2 | Wear & Tear | Breakdown | TONS OGUNS | COLD ROOM UNIT | HVAC | 2025-02-01 | 47 | 2025-02-01 | 0 |  | 47 |  |  | 45736 | [6 empty] | Overdue
2 | FAULTY RATIONAL MACHINE | LAG, IPAJA RD | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2025-02-01 | 47 | 2025-02-01 | 0 |  | 47 | [9 empty] | Overdue
3 | FAULTY DRYSTORE DOOR KNOB | LAG, MAGODO | Users Misuse | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-02-01 | 47 | 2025-02-01 | 0 |  | 47 | [9 empty] | Overdue
4 | GAS BURNER HOSE FAULTY | LAG, ISAWO-IKORODU | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-02-01 | 47 | 2025-02-01 | 0 | 2025-02-02 | 1 | 2025-02-02 |  | 46 | [6 empty] | Overdue
5 | EARTHEN NOT EFFECTIVE |  | Electrical Surge | Breakdown | GLOBAL POWER | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-02-01 | 47 | 2025-02-01 | 0 |  | 47 | [9 empty] | Overdue
6 | REQUEST FOR REPLACEMENT OF STORE ELECTRICITY METER | LAG, OGUDU | Others | Breakdown |  | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-02-01 | 47 | 2025-02-01 | 0 |  | 47 | [9 empty] | Overdue
7 | FAULTY VEGETABLE CUTTER , | LAG, MOBIL OGBA | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2025-02-02 | 46 | 2025-02-02 | 0 |  | 46 | [9 empty] | Overdue
8 | WATER NOT FLOWING | LAG, MOBIL OGBA | Others | Breakdown | PRO-EQUIP | WATER TREATMENT PLANT BLD | BUILDING | 2025-02-01 | 2 | 2025-02-02 | 1 | 2025-02-03 | 1 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 |  | Completed | 2025-02-03 | 1
9 | GENERATOR NOT COMING UP | LAG, OBA AKRAN | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-02 | 46 | 2025-02-02 | 0 |  | 46 | [9 empty] | Overdue
10 | DEAD PEST KILLER BULBS | ABUJA, KARU | Wear & Tear | Breakdown |  | OTHERS | OTHERS | 2025-02-02 | 46 | 2025-02-03 | 1 |  | 45 | [9 empty] | Overdue
12 | DEAD BULB IN THE OFFICE | ABUJA, KARU | Wear & Tear | Breakdown |  | OTHERS | OTHERS
13 | FILLED SEPTIC TANK | LAG, IDI-IROKO RD | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2025-02-02 | 46 | 2025-02-03 | 1 |  | 45 | [9 empty] | Overdue
14 | LAMPLIGHT BLINKING | LAG, IDIMU | Wear & Tear | Breakdown | FRIDAY | 18W ROUND LIGHT FITTING | ELECTRICAL | 2025-01-22 | 9 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 | 2025-01-22 | 0 | 2025-01-22 | 0 | 2025-01-22 | 9 | 2025-01-31 |  | Completed | 2025-01-31 | 1
15 | REQUEST FOR INDUSTRIAL HOSE GAS CONNECTION | LAG, IKORODU | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-02-02 | 46 | 2025-02-03 | 1 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 45 |  | 56875 | Overdue
16 | GAS LEAKAGE FROM UNOX PIPE JOINTS | LAG, BODE THOMAS | Wear & Tear | Breakdown | PRO-EQUIP | GAS HOSE & SUNDRIES | GAS | 2025-02-03 | 9 | 2025-02-03 | 0 | 2025-02-12 | 9 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 |  | Completed | 2025-02-12 | 1
17 | DIRTY CHICKEN REPUBLIC SIGNAGE AND CHICKEN HEAD | LAG, JOEL OGUNNAIKE | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-02-03 | 45 | 2025-02-03 | 0 |  | 45 | [9 empty] | Overdue
18 | EVACUATION & EXCAVATION OF WASTE WATER | LAG, LATEEF JAKANDE | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-04 | 1 | 2025-02-04 | 0 | 2025-02-04 | 44 |  | 280000 | Overdue
19 | DEAD INSECT KILLER FLUORESCENT | LAG, MMA2 | Wear & Tear | Breakdown | TIMILEHIN | INSECT KILLER BOH | ELECTRICAL | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 |  | Completed | 2025-02-03 | 1
20 | SEPTIC TANK EVACUATION | LAG, ETERNA LEKKI
21 | MOTOR STARTER & INSECT KILLER REQUEST | LAG, LATEEF JAKANDE | Others | Breakdown | MOSES | INSECT KILLER LOBBY 1 | ELECTRICAL | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 |  | Completed | 2025-02-03 | 1
22 | POLARITY ISSUE AND DISPLAY CABINET SHOCKING | LAG, OKOTA | Electrical Surge | Breakdown | FRIDAY | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 |  | Completed | 2025-02-03 | 1
23 | SWING DOOR | ABUJA, KARU | Wear & Tear | Breakdown |  | OTHERS | OTHERS | 2025-02-02 | 46 | 2025-02-03 | 1 |  | 45 | [9 empty] | Overdue
24 | GENERATOR VOLTAGE HIGH | LAG, BODE THOMAS | Electrical Surge | Breakdown | TIMILEHIN | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-02-03 | 1 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 1 | 2025-02-04 |  | Completed | 2025-02-04 | 1
25 | OVEN DUE FOR SERVICING | LAG, ILUPEJU | Routine Servicing | Preventive | PRO KITCHEN | OTHERS | OTHERS | 2025-02-03 | 45 | 2025-02-03 | 0 |  | 45 | [9 empty] | Overdue
26 | FAULTY ROLLER SHUTTER | LAG, AJAH | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-02-02 | 46 | 2025-02-02 | 0 | 2025-02-03 | 1 | [9 empty] | Overdue
28 | SERVICING OF GENERATOR | KADUNA, KACHIA RD | Routine Servicing | Preventive | CONCIRCLE | GENERATOR | GENERATOR | 2025-02-03 | 45 | 2025-02-03 | 0 |  | 45 | [9 empty] | Overdue
29 | FAULTY INSECTICUTOR | LAG, FESTAC | Wear & Tear | Breakdown | TIMILEHIN | INSECT KILLER BOH | ELECTRICAL | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 |  | Completed | 2025-02-03 | 1
30 | MAINTAINANCE ISSUES AT PPU HOTORO. | KANO, HOTORO | Others | Breakdown | THOMPSON | OTHERS | OTHERS | 2025-02-04 | 44 | 2025-02-04 | 0 |  | 44 | [9 empty] | Overdue
31 | FAULTY ROTISSERIE MACHINE | LAG, MMA2 | Wear & Tear | Breakdown | HEFFEM | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2025-02-04 | 1 | 2025-02-04 | 0 | 2025-02-05 | 1 | 2025-02-05 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 |  | Completed | 2025-02-05 | 1
32 | LEAKING TREATED WATER TANK | LAG, OGUDU | Users Misuse | Breakdown | PROPEARJEFF | GROUND WATER TANK | WTP | 2025-02-04 | 44 | 2025-02-04 | 0 | 2025-02-05 | 1 | [9 empty] | Overdue
33 | DRY STORE NOT ATTAINING MAXIMUM TEMPERATURE. | LAG, MARINA | Wear & Tear | Breakdown | FOLLTEC | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-04 | 44 | 2025-02-04 | 0 | 2025-02-07 | 3 | 2025-02-07 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 41 |  |  | Overdue
34 | REQUEST FOR MAINTENANCE MATERIAL | LAG, ONIRU | Others | Breakdown | ADEREMI KAZEEM | OTHERS | OTHERS | 2025-02-04 | 44 | 2025-02-04 | 0 |  | 44 | [9 empty] | Overdue
35 | FAULTY WARMER DOOR HANDLE | LAG, IDI-IROKO RD | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-04 | 1 | 2025-02-04 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 44 | 2025-02-08 | 151575 | Overdue
36 | FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, AGUNGI | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2025-02-04 | 44 | 2025-02-04 | 0 | 2025-02-04 | 0 | [9 empty] | Overdue
37 | GAS VALVE LEAKAGE | LAG, OKOTA | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-04 | 1 | 2025-02-04 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 44 |  | 275000 | Overdue
38 | REQUEST FOR ENGINE OIL | LAG, OGUNLANA DRIVE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-04 | 1 | [9 empty] | Overdue
39 | DIRTY CHICKEN REPUBLIC SIGNAGE ( REQUEST FOR EXTERNAL WASHER ) | LAG, OPEBI | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-02-02 | 46 | 2025-02-03 | 1 | 2025-02-04 | 1 | 2025-02-04 | 2025-02-07 | 3 | 2025-02-08 | 40 |  |  |  | 400000 | Overdue
40 | GAS LEAKAGE IN THE STORE | LAG, OPEBI | Wear & Tear | Breakdown | BERRADE | GAS CYLINDER | GAS | 2025-02-01 | 47 | 2025-02-01 | 0 | 2025-02-03 | 2 | 2025-02-04 | 2025-02-04 | 0 | 2025-02-04 | 44 |  |  |  | 77950 | Overdue
41 | DEAD BULB IN THE CABINET | LAG, OGUNLANA DRIVE | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-02-02 | 0 | 2025-02-02 | 0 | 2025-02-02 | 0 | 2025-02-02 | 2025-02-02 | 0 | 2025-02-02 | 0 | 2025-02-02 | 0 | 2025-02-02 |  | Completed | 2025-02-02 | 1
42 | DEAD BULB | LAG, MOBIL OGBA | Electrical Surge | Breakdown | MOSES | OTHERS | OTHERS | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 |  | Completed | 2025-02-03 | 1
43 | FAULTY GENERATOR DIESEL LEAK | LAG, ALIMOSHO | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-04 | 1 | [9 empty] | Overdue
44 | REPLACEMENT OF INSECUTOR BULB. | KADUNA, YAKUBU GOWON | Electrical Surge | Breakdown | OLANIYI | INSECT KILLER BOH | ELECTRICAL | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 |  | Completed | 2025-02-04 | 1
45 | GENERATOR DUE FOR SERVICE | LAG, TEJUOSHO | Others | Breakdown | KB | GENERATOR | GENERATOR | 2025-02-04 | 44 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 2025-02-04 | #REF! | 2025-02-04 | 0 | 2025-02-04 | 44 |  | 236500 | Overdue
46 | BROKEN HOT WATER TAP HEAD | LAG, FREEDOMWAY | Wear & Tear | Breakdown | JOEL | TAP | PLUMBING | 2025-02-03 | 1 | 2025-02-03 | 0 | 2025-02-04 | 1 | 2025-02-04 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 |  | 2025-02-04 |  | Completed | 2025-02-04 | 1
47 | CABINET LIGHT NOT WORKING |  | Electrical Surge | Breakdown | KITCHTEC | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
48 | FAULTY INSECUTOR | LAG, MOBIL OGBA | Wear & Tear | Breakdown | ISMAIL |  |  | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 |  | Completed | 2025-02-03 | 1
49 | GENERATOR DUE FOR SERVICING | ABUJA, KARU | Routine Servicing | Preventive | CONCIRCLE | GENERATOR | GENERATOR | 2025-01-26 | 33 | 2025-01-27 | 1 | 2025-01-27 | 0 | 2025-02-28 |  | 20 |  |  |  |  | 2025-02-28 |  | Completed | 2025-02-28 | 1
50 | REPAINTING OF FOH DUMPSTER | LAG, SKYMALL | Wear & Tear | Breakdown | MATOLAD | CHICKEN DUMP TROLLEY | FURNITURE | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
51 | BROKEN CUSTOMER TOILET COVER | LAG, OBA AKRAN | Users Misuse | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-05 | 2 | [9 empty] | Overdue
52 | BURNT SOCKET | LAG, AWOLOWO 2 | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-02-04 | 44 | 2025-02-04 | 0 |  | 44 | [9 empty] | Overdue
53 | REPAINTING OF FOH DUMPSTER |  | Wear & Tear | Breakdown | MATOLAD | PAINTING | BUILDING | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
54 | FREEZER ROOM AND COLD ROOM NOT ATTAINING TEMPERATURE | LAG, OMOLE | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2025-02-07 | 41 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-18 | 2025-02-25 | 7 | 2025-02-26 | 0 | 2025-02-26 | 22 |  | 130000 | Overdue
55 | DIRTY PYLON | LAG, OMOLE | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-07 | 4 | [9 empty] | Overdue
56 | BROKEN HINGS OF DISPLAY CABINET GLASS | LAG, LATEEF JAKANDE | Wear & Tear | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-04 | 44 | 2025-02-05 | 1 | 2025-02-07 | 2 | [9 empty] | Overdue
57 | POWER SURGE(BLOWN SUPPLY SOCKET) | LAG, OKOTA | Wear & Tear | Breakdown | FRIDAY | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-02-06 | 1 | 2025-02-06 | 0 | 2025-02-07 | 1 | 2025-02-07 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 |  | Completed | 2025-02-07 | 1
58 | CABINET NOT ATTAINTING TEMPERATURE | LAG, IRE-AKARI | Wear & Tear | Breakdown | HEFFEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-06 | 42 | 2025-02-06 | 0 | 2025-02-07 | 1 | [9 empty] | Overdue
59 | Leakage of water from Wall to next company from ppu and staff changing | LAG, ONIRU | Wear & Tear | Breakdown | ACORN | OTHERS | OTHERS | 2025-02-06 | 42 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 |  | 42 | [6 empty] | Overdue
60 | BROKEN TILES IN THE STORE | LAG, OKE-AFA | Users Misuse | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-02-04 | 44 | 2025-02-04 | 0 | 2025-02-05 | 1 | 2025-02-05 | 2025-02-07 | 2 | [6 empty] | Overdue
61 | UNAUTHORIZE PACKING OF CARS | LAG, AJAH | Others | Breakdown | ARIZMANYA | OTHERS | OTHERS | 2025-02-05 | 43 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-07 |  | 41 | [6 empty] | Overdue
62 | DEAD BULB IN PEST KILLER | LAG, AJAH | Wear & Tear | Breakdown | ADEREMI KAZEEM | INSECT KILLER LOBBY 1 | ELECTRICAL | 2025-02-07 | 5 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 5 | 2025-02-12 |  | Completed | 2025-02-12 | 1
63 | FAULTY FAN | LAG, AGUNGI | Wear & Tear | Breakdown | ADEREMI KAZEEM | WALL FAN | HVAC | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
64 | FAULTY WALL SOCKET | LAG, AGUNGI | Wear & Tear | Breakdown | ADEREMI KAZEEM | OTHERS | OTHERS | 2025-02-03 | 4 | 2025-02-03 | 0 | 2025-02-06 | 3 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 1 | 2025-02-07 |  | Completed | 2025-02-07 | 1
65 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, IKORODU | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-02-07 | 41 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 |  | 41 | [6 empty] | Overdue
66 | FAULTY PEST KILLER BULB |  | Wear & Tear | Breakdown | TIMILEHIN | INSECT KILLER LOBBY 2 | ELECTRICAL | 2025-02-05 | 2 | 2025-02-05 | 0 | 2025-02-07 | 2 | 2025-02-07 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 |  | Completed | 2025-02-07 | 1
67 | FAULTY WARMER LID SEAL | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
68 | EXTRACTOR NOT WORKING | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | SEASON BENDAN | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
69 | Daily Equipment Status | PPU Oniru | Routine Servicing | Preventive | DELIGHTSOME | GENERATOR | GENERATOR | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
70 | UNDERBAR FRIDGE NOT WORKING | LAG, OKOTA | Wear & Tear | Breakdown | G.B BOYEJO | NBC CHILLER | HVAC | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
71 | FAULTY INVERTER | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | DALEMATRIX | INVERTER SYSTEM | INVERTER | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
72 | COLD ROOM FREEZING | LAG, BADORE | Wear & Tear | Breakdown | ECS | COLD ROOM UNIT | HVAC | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
73 | CHIPPED LOBBY TABLE | LAG, ONIRU | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
74 | GENERATOR DUE FOR SERVICING | LAG, OMOLE | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-02-06 | 42 | 2025-02-06 | 0 | 2025-02-07 | 1 | [9 empty] | Overdue
75 | BROKEN KITCHEN SINK PIPE | LAG, BADORE | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
76 | REQUEST TO LINK DIESEL MAIN TANK DIRECTLY TO GENERATOR | LAG, EKORO | Wear & Tear | Breakdown | DELIGHTSOME | GENERATOR | GENERATOR | 2025-02-06 | 42 | 2025-02-06 | 0 | 2025-02-07 | 1 | [9 empty] | Overdue
77 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | LAG, OKOTA | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-07 | 3 | 2025-02-07 | 0 |  | 41 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 |  | Completed | 2025-02-10 | 1
78 | torn warmer lather | LAG, AKOWONJO | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-02-06 | 42 | 2025-02-06 | 0 | 2025-02-06 | 0 | [9 empty] | Overdue
79 | SERVICING OF LOBBY ACS. | LAG, MARINA | Routine Servicing | Preventive | FOLLTEC | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
80 | CUSTOMER RESTROOM NOT FLUSHING | LAG, AWOLOWO | Wear & Tear | Breakdown | JOEL | OTHERS | OTHERS | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 |  | Completed | 2025-02-07 | 1
81 | LOBBY AC NOT WORKUNG EFFECTIVELY | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 |  |  |  |  | 45693 | 2025-02-05 | 43 |  |  | Overdue
82 | GENERATOR BREAKDOWN | ABIA, OGBOR HILLS | Wear & Tear | Breakdown | generator werahouse | GENERATOR | GENERATOR | 2025-02-01 | 47 | 2025-02-01 | 0 | 2025-02-03 | 2 | 2025-02-05 | 2025-02-05 | 0 | 2025-02-05 | 43 |  |  |  |  | Overdue
83 | FREEZER ROON NOT ATTAINING TEMPERATURE, | PH, GRA BIRABI | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2025-02-02 | 46 | 2025-02-03 | 1 | 2025-02-04 | 1 | [9 empty] | Overdue
84 | ROPPING OF FREQUENCY | PH, IWOFE | Wear & Tear | Breakdown | PROPARATECH | GENERATOR | GENERATOR | 2025-02-02 | 46 | 2025-02-02 | 0 | 2025-02-02 | 0 | 2025-02-03 |  | 45 | [6 empty] | Overdue
85 | DEAD LIGHTS AND FADED SIGNAGE AND PYLON/ BROKEN SIGNAGE LETTER | IMO, WETHERAL RD, OWERRI | Wear & Tear | Breakdown | JOWNY | OTHERS | OTHERS | 2025-01-29 | 50 | 2025-01-29 | 0 |  | 50 | [9 empty] | Overdue
86 | FREEZER ROOM NOT FREEZING AND COLD ROOM NOT ATTAINING TEMPERATURE | ANAMBRA, ZIK AVENUE, AWKA | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2025-02-02 | 46 | 2025-02-02 | 0 | 2025-02-03 | 1 | [9 empty] | Overdue
87 | GENERATOR SERVICING / REPLACEMENT OF PUMP LIFT | DELTA, EFFURUN | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-02 | 46 | 2025-02-02 | 0 |  | 46 | [9 empty] | Overdue
88 | Lobby Ac's /Dry Store Ac's/ Office Ac not working | DELTA, EFFURUN | Wear & Tear | Breakdown | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-28 | 51 | 2025-01-28 | 0 |  | 51 | [9 empty] | Overdue
89 | BOH Door Handle not in good Condition | DELTA, EFFURUN | Users Misuse | Breakdown | FRANK | OTHERS | OTHERS | 2025-01-20 | 59 | 2025-01-20 | 0 |  | 59 |  |  |  |  | 45588 | 2024-10-23 | 148 |  |  | Overdue
90 | Bad WC Flusher in Customer/Staff Restroom | DELTA, EFFURUN | Wear & Tear | Breakdown | PROEQUITECH | WATER TREATMENT PLANT BLD | BUILDING | 2024-07-09 | 254 | 2024-07-09 | 0 | 2024-10-15 | 98 | 2024-10-15 | 2024-10-21 | 6 | 2024-10-21 | 105 | 2025-02-03 | 45 |  |  | Overdue
91 | REQUEST FOR GENERATOR SERVICING | ABIA, AZIKIWE RD, UMUAHIA | Wear & Tear | Breakdown | generator werahouse | GENERATOR | GENERATOR | 2025-02-02 | 46 | 2025-02-03 | 1 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 45 |  |  |  |  | Overdue
92 | AZIKIWE ROAD MAINTENANCE ISSUES | ABIA, AZIKIWE RD, UMUAHIA | Others | Breakdown | Leonard | OTHERS | OTHERS | 2025-01-21 | 58 | 2025-01-22 | 1 | 2025-01-22 | 0 | [9 empty] | Overdue
93 | AIR CONDITIONERS NOT FUNCTIONING | PH, DOX RD | Wear & Tear | Breakdown | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-03 | 45 | 2025-02-03 | 0 |  | 45 |  |  |  |  | 45693 | 2025-02-05 | 43 |  |  | Overdue
94 | INCONSISTENCY IN RUN HOUR | ANAMBRA, ZIK AVENUE, AWKA | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-01-15 | 64 | 2025-02-03 | 19 | 2025-02-03 | 0 | 2025-02-04 | 2025-02-04 | 0 | 2025-02-05 | 43 |  |  |  |  | Overdue
95 | BACK OF HOUSE CHILLER NOT ATTAINING TEMPERATURE | PH, DOX RD | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2025-02-03 | 45 | 2025-02-03 | 0 |  | 45 | [9 empty] | Overdue
96 | BAD TOASTER REGULATOR | IMO, WETHERAL RD, OWERRI | Wear & Tear | Breakdown | BCE | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2025-02-03 | 45 | 2025-02-03 | 0 |  | 45 | [9 empty] | Overdue
97 | GENERATOR SERVICING | IMO, WETHERAL RD, OWERRI | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-03 | 45 | 2025-02-03 | 0 |  | 45 |  |  |  |  | 45695 | 2025-02-07 | 41 |  |  | Overdue
98 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | PH, RUKPOKWU | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-05 | 2 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 42 |  |  |  |  | Overdue
99 | REPLACEMENT OF INSECUTOR | BAYELSA, OPOLO | Others | Breakdown | GLUFFSCO | OTHERS | OTHERS | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-03 | 0 | [9 empty] | Overdue
100 | DEAD SIGNAGE BULB | BAYELSA, OPOLO | Others | Breakdown | CHRISTIAN | OTHERS | OTHERS | 2025-02-03 | 45 | 2025-02-03 | 0 |  | 45 | [9 empty] | Overdue
101 | OFFICE AC DRIPPING WATER | PH, ONNE | Wear & Tear | Breakdown | INNOCENT | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-03 | 45 | 2025-02-03 | 0 |  | 45 | [9 empty] | Overdue
102 | BLOWN OUT INSECTOCUTOR BULB | DELTA, EFFURUN | Others | Breakdown | FRANK | OTHERS | OTHERS | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-03 | 0 |  |  |  |  | #REF! |  | #REF! |  |  | Overdue
103 | MALFUNCTIONING ROTISSERIE MACHINE | ANAMBRA, ZIK AVENUE, AWKA | Wear & Tear | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-03 | 0 |  |  |  |  | 45671 | 2025-01-14 | 65 |  |  | Overdue
104 | Quotation For Replacement of Ceiling and Roofing From Local Vendor at Cr Afikpo | EBONYI, AFIKPO, ABAKALIKI | Wear & Tear | Breakdown | DT CONSULT | P.O.P | BUILDING | 2025-01-05 | 74 | 2025-01-05 | 0 | 2025-01-09 | 4 | 2025-01-09 | 2025-01-11 | 2 | 2025-01-11 | 24 | 2025-02-04 | 44 |  |  | Overdue
105 | GENERATOR RUN HOUR NOT READING | EBONYI, AFIKPO, ABAKALIKI | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 45 |  |  |  |  | Overdue
106 | Shredding Machine not Coming Up | DELTA, EFFURUN | Wear & Tear | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-03 | 0 | [9 empty] | Overdue
107 | GENERATOR SERVICE REQUEST - CR NSUKKA | NASSARAWA, NYANYA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-04 | 1 | [9 empty] | Overdue
108 | REQUEST FOR GENERATOR SERVICING (CR LIMCA RD) | ANAMBRA, LIMCA RD, ONITSHA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-02-04 | 44 | 2025-02-04 | 0 |  | 44 | [9 empty] | Overdue
109 | FAULTY CABINET BULB | IMO, IKENEGBU, OWERRI | Wear & Tear | Breakdown | Leonard | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-04 | 44 | 2025-02-04 | 0 |  | 44 | [9 empty] | Overdue
110 | PENDING MAINTENANCE ISSUES- AFIKPO ROAD | EBONYI, AFIKPO, ABAKALIKI | Others | Breakdown | UCH | OTHERS | OTHERS | 2025-02-04 | 44 | 2025-02-04 | 0 |  | 44 |  |  |  |  | 45695 | 2025-02-07 | 41 |  |  | Overdue
111 | FAULTY ROTISSERIE MACHINE | PH, RUKPOKWU | Wear & Tear | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2025-02-04 | 44 | 2025-02-04 | 0 | 2025-02-07 | 3 | 2025-02-07 | 2025-02-07 | 0 | 2025-02-07 | 41 |  |  |  |  | Overdue
112 | SERVICING OF ICE CREAM MACHINE | PH, WOJI | Routine Servicing | Preventive | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-02-03 | 45 | 2025-02-04 | 1 |  | 44 | [9 empty] | Overdue
113 | GENERATOR NOT WORKING- CR OKIGWE | IMO, OKIGWE | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-04 | 44 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 2025-02-04 | 0 | [6 empty] | Overdue
114 | FAULTY SIGNAGE | AKWA IBOM, ORON RD | Wear & Tear | Breakdown | JOWNY | OTHERS | OTHERS | 2025-02-04 | 44 | 2025-02-04 | 0 |  | 44 | [9 empty] | Overdue
115 | FAULTY SIGNAGE | AKWA IBOM, NWANIBA | Wear & Tear | Breakdown | JOWNY | OTHERS | OTHERS | 2025-02-04 | 44 | 2025-02-04 | 0 |  | 44 | [9 empty] | Overdue
116 | Faulty A.C at Lobby at Cr Afikpo | EBONYI, AFIKPO, ABAKALIKI | Wear & Tear | Breakdown | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-04 | 44 | 2025-02-04 | 0 |  | 44 | [9 empty] | Overdue
117 | OVEN NOT WORKING | ABIA, AZIKIWE RD, UMUAHIA | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
118 | COLD ROOM NOT COMING UP | DELTA, EFFURUN | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2025-02-05 | 43 | 2025-02-05 | 0 | 2025-02-05 | 0 |  |  |  |  | 45693 | 2025-02-05 | 43 |  |  | Overdue
119 | OVEN NOT WORKING | ABIA, AZIKIWE RD, UMUAHIA | Wear & Tear | Breakdown | LEO | OTHERS | OTHERS | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 |  | Completed | 2025-02-05 | 1
120 | UNUSUAL SOUND FROM THE FOH CHILLER | ENUGU, POLO MALL | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2025-02-05 | 43 | 2025-02-05 | 0 | 2025-02-06 | 1 | [9 empty] | Overdue
121 | FAULTY COLD ROOM SELF LOCK | PH, GRA BIRABI | Wear & Tear | Breakdown | CHRISTIAN/MOFEEN | COLD ROOM UNIT | HVAC | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
122 | SERVICING OF A.C IN THE STORE | PH, WOJI | Routine Servicing | Preventive | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
123 | GENERATOR SERVICING | PH, ABACHA RD | Routine Servicing | Preventive | GLUFFSCO | GENERATOR | GENERATOR | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
124 | CUMMINS GENERATOR BREAKDOWN | BAYELSA, OPOLO | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2025-02-05 | 43 | 2025-02-05 | 0 | 2025-02-05 | 0 | [9 empty] | Overdue
125 | GENERATOR SERVICING. | PH, UST | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-02-06 | 42 | 2025-02-06 | 0 | 2025-02-06 | 0 |  |  |  |  | 45695 | 2025-02-07 | 41 |  |  | Overdue
126 | UNAVAILABILITY OF WATER | BAYELSA, TOMBIA | Wear & Tear | Breakdown | PRO-EQUIPTECH | WATER TREATMENT PLANT BLD | BUILDING | 2025-02-06 | 42 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-07 | 41 |  |  |  |  | Overdue
127 | REQUEST FOR AC SERVICING IN THE STORE | AKWA IBOM, IKOT EKPENE RD | Routine Servicing | Preventive | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
128 | LEAKING DIESEL LINE | PH AGGREY | Wear & Tear | Breakdown | KAZIM | OTHERS | OTHERS | 2025-02-05 | 43 | 2025-02-05 | 0 | 2025-02-05 | 0 | [9 empty] | Overdue
129 | FAULTY COLD ROOM | BAYELSA, YENAGOA | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2025-02-06 | 42 | 2025-02-06 | 0 |  | 42 | [9 empty] | Overdue
130 | FAULTY COLD ROOM | BAYELSA, TOMBIA | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2025-02-06 | 42 | 2025-02-06 | 0 |  | 42 | [9 empty] | Overdue
131 | BROKEN TILES IN PRODUCTION FLOOR AND WALL TILES |  | Wear & Tear | Breakdown | SUNDAY | WALL | BUILDING | 2025-02-06 | 42 | 2025-02-06 | 0 |  | 42 | [9 empty] | Overdue
132 | Painting of staff room, office, and dry store | EDO, SAPELE RD, BENIN | Wear & Tear | Breakdown | FRANK | PAINTING | BUILDING | 2025-02-06 | 42 | 2025-02-06 | 0 |  | 42 | [9 empty] | Overdue
133 | GENERATOR DUE FOR SERVICING - CR AWKA ROAD, ONITSHA | ANAMBRA, AWKA RD, ONITSHA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-02-06 | 42 | 2025-02-06 | 0 |  | 42 |  |  |  |  | 45695 | 2025-02-07 | 41 |  |  | Overdue
134 | Generator breakdown | AKWA IBOM, NWANIBA | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-06 | 42 | 2025-02-06 | 0 | 2025-02-07 | 1 | 2025-02-07 | 2025-02-07 | 0 | 2025-02-07 | 41 |  |  |  |  | Overdue
135 | Outstanding Maintenance issue on Generator | EBONYI, WATERWORKS, ABAKALIKI | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-06 | 42 | 2025-02-06 | 0 | 2025-02-07 | 1 | [9 empty] | Overdue
136 | GEN DUE FOR SERVICE - CR-NYANYA, NASARAWA STATE. | NASSARAWA, NYANYA | Routine Servicing | Preventive | GENERATOR WEARHOUSE | GENERATOR | GENERATOR | 2025-02-06 | 42 | 2025-02-06 | 0 | 2025-02-06 | 0 | [9 empty] | Overdue
137 | FAULTY DOZING PUMPS | PH, GRA BIRABI | Wear & Tear | Breakdown | SAPAT | WATER TREATMENT PLANT BLD | BUILDING | 2025-02-06 | 42 | 2025-02-06 | 0 |  | 42 | [9 empty] | Overdue
138 | ISSUES REQUIRING ATTENTION | IMO, OKIGWE | Others | Breakdown | JOWNY | OTHERS | OTHERS | 2025-02-06 | 42 | 2025-02-07 | 1 |  | 41 | [9 empty] | Overdue
139 | CABINET NOT WORKING | EDO, SAPELE RD, BENIN | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
140 | GENERATOR SERVICING | PH, ABA | Routine Servicing | Preventive | CHIRST/GAMMA | GENERATOR | GENERATOR | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 |  |  |  |  | 45663 | 2025-01-06 | 73 |  |  | Overdue
141 | CHIPS FRYER MACHINE NEEDS URGENT ATTENTION | PH, WOJI | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2024-12-21 | 89 | 2025-01-23 | 33 | 2024-12-24 | -30 | 2024-12-24 | 2024-12-24 | 0 | 2024-12-24 | 86 |  |  |  |  | Overdue
142 | COLD ROOM NOT ATTAINING TEMPERATURE - CR AWKA ROAD, ONITSHA | ANAMBRA, AWKA RD, ONITSHA | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
143 | CHIPS FRYER MACHINE NEEDS URGENT ATTENTION | PH, WOJI | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
144 | CABINET NOT WORKING | DELTA, SAPELE-WARRI RD | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
145 | GENERATOR DUE FOR SERVICING | ILORIN, TAIWO RD | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2025-01-31 | -30 | 2025-02-01 | 1 | 2025-02-02 | 1 | 2025-01-31 |  | 48 | [6 empty] | Completed | 2025-01-01 | 0
146 | GENERATOR DUE FOR SERVICE | LAG, IDI-IROKO RD | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2025-02-01 | 2 | 2025-02-03 | 2 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 |  | Completed | 2025-02-03 | 1
147 | FAULTY TAYLOR MACHINE | ILORIN, ASA DAM | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-02-03 | 45 | 2025-02-03 | 0 |  | 45 | 2025-02-03 |  | 45 | [6 empty] | Overdue
148 | INVERTER NOT WORKING | OGUN, OKE-ILEWO | Wear & Tear | Breakdown | NISTECH | INVERTER BATTERIES | INVERTER | 2025-02-03 | 2 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 |  | Completed | 2025-02-05 | 1
149 | FREEZER ROOM NOT ATTAINING TEMPERATURE | IBADAN, BODIJA | Routine Servicing | Preventive | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 |  | 45 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 |  | Completed | 2025-02-03 | 1
150 | AC DUE FOR SEVICING | ILORIN, MM WAY | Routine Servicing | Preventive | TONA OGUNS | 5HP STANDING AC UNIT 2 | HVAC | 2025-02-04 | 44 | 2025-02-04 | 0 |  | 44 |  | 2025-02-04 | 45692 | [6 empty] | Overdue
151 | REQUEST FOR LID GASKET
152 | GENERATOR DUE FOR SERVICING | ILORIN, OLOFAWAY | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2025-02-04 | 44 | 2025-02-04 | 0 |  | 44 | 2025-02-04 | 2025-02-04 | 0 | [6 empty] | Overdue
153 | GENERATOR DUE FOR SERVICING | OYO, OGBOMOSHO | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2025-02-04 | 44 | 2025-02-04 | 0 |  | 44 | [9 empty] | Overdue
154 | CABINET BULB REQUEST | IBADAN, CHALLENGE | Wear & Tear | Breakdown | KITCH TECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-04 | 44 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 2025-02-04 | 0 | [6 empty] | Overdue
155 | GENERATOR DUE FOR SERVICING | OYO, OGBOMOSHO | Routine Servicing | Preventive | GENERATOR WAREHOUSE | GENERATOR | GENERATOR | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 268750 | Completed | 2025-02-04 | 1
156 | GENERATOR SERVICING | IBADAN, BODIJA | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2025-02-04 | 44 | 2025-02-04 | 0 | 2025-02-05 | 1 | 2025-02-05 | 2025-02-05 | 0 | [6 empty] | Overdue
157 | INVERTER NOT WORKING | OGUN, OKE-ILEWO | Routine Servicing | Preventive | NISTECH | INVERTER BATTERIES | INVERTER | 2025-01-30 | 49 | 2025-01-31 | 1 | 2025-02-05 | 5 | 2025-02-12 |  | 36 | [6 empty] | Overdue
158 | TAYLOR ICE CREAM MACHINE INSPECTION REPORT | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2024-12-05 | 62 | 2024-12-05 | 0 | 2024-12-05 | 0 | 2024-12-05 | 2024-12-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 |  | Completed | 2025-02-05 | 1
159 | EQUIPMENT STATUS REPORT | PPU Ilupeju | Wear & Tear | Breakdown | MACADAMS | HAND DRYER LOBBY | ELECTRICAL | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | 2025-02-05 |  | 43 | [6 empty] | Overdue
160 | ICE CREAM MACHINE SERVICING | OYO, OWODE | Routine Servicing | Preventive | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
161 | FAULTY DOSING PUMP | IBADAN, AKOBO | Wear & Tear | Breakdown | PRO-EQUIPTECH | DOSING PUMP | WTP | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 |  | Completed | 2025-02-05 | 1
162 | FAULTY LIGHT BULB AND LOW CABINET TEMPERATURE | IBADAN, CHALLENGE | Wear & Tear | Breakdown | KITCH TECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
163 | REQUEST FOR LID GASKET | OYO, OWODE | Wear & Tear | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2025-02-05 | 43 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-06 |  | 42 | [6 empty] | Overdue
164 | FAULTY AC - CUSTOMER RESTROOM AND DRY STORE | OGUN, OKE-ILEWO | Wear & Tear | Breakdown | TONA OGUNS | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 |  | Completed | 2025-02-06 | 1
165 | Lobby Ac's /Dry Store Ac's/ Office Ac not working | DELTA, EFFURUN | Routine Servicing | Preventive | MOFFEEN | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 |  | Completed | 2025-02-06 | 1
166 | BROKEN TILES IN THE STORE | EDO, UGBOWO, BENIN | Wear & Tear | Breakdown | DT CONSULT | OTHERS | OTHERS | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 |  | Completed | 2025-02-06 | 1
167 | DOCUMENT WITH ISSUES | LAG, EJIGBO | Wear & Tear | Breakdown | ILUPEJU
168 | EXCESS FURNITURE AND BAD CHAIRS AT OMOLE ANNEX LAGOS; AND 1 RIM OF LETTER HEADED PAPERS | LAG, OMOLE | Wear & Tear | Breakdown | OMOLE | CUSTOMER CHAIR | FURNITURE | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 |  | Completed | 2025-02-06 | 1
169 | COLD ROOM NOT ATTAINING TEMPERATURE | IBADAN, VENTURA MALL | Routine Servicing | Preventive | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 |  | Completed | 2025-02-06 | 1
170 | COLD ROOM NOT ATTAINING TEMPERATURE | OYO, OGBOMOSHO | Routine Servicing | Preventive | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 0 |  |  |  | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 |  | Completed | 2025-02-07 | 1
171 | : INVERTER NOT WORKING | OGUN, OKE-ILEWO | Routine Servicing | Preventive | NISTECH | INVERTER SYSTEM | INVERTER | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-12 |  | 36 | 2025-02-12 | 36 |  |  | 2025-02-07 |  | Completed | 2025-02-07 | 1
172 | SERVICING OF GENERATOR | ILORIN, ASA DAM | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 |  | 41 | 2025-02-07 | 41 |  |  | 2025-02-07 |  | Completed | 2025-02-07 | 1
173 | 1 LOBBY AC NOT WORKING | LAG, AWOLOWO | Electrical Surge | Breakdown | ISMAIL | 5HP STANDING AC UNIT 2 | HVAC | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
174 | FAULTY ICE CREAM MACHINE. | LAG, MARINA | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-02-07 | 41 | 2025-02-07 | 0 |  | 41 | [9 empty] | Overdue
175 | PX DIYA FAULTY BULB IN CABINET AND FAULTY PASTRY RACK | LAG, DIYA STREET | Wear & Tear | Breakdown | tayo | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-03 | 45 | 2025-02-03 | 0 |  | 45 | [9 empty] | Overdue
176 | HAND DRYER NOT WORKING |  | Wear & Tear | Breakdown | JOEL | HAND DRYER LOBBY | ELECTRICAL | 2025-02-04 | 6 | 2025-02-04 | 0 | 2025-02-10 | 6 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 |  | Completed | 2025-02-10 | 1
177 | FAULTY HENNY PENNY PRESSURE FRYER | LAG, LATEEF JAKANDE | Routine Servicing | Preventive | HEFHEM | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-08 | 9 | 2025-02-08 | 0 | 2025-02-08 | 0 | 2025-02-17 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 |  | Completed | 2025-02-17 | 1
178 | GENERATOR DUE FOR SERVICING | LAG, ALIMOSHO | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-02-08 | 40 | 2025-02-08 | 0 | 2025-02-08 | 0 | [9 empty] | Overdue
179 | SAFETY ALEART | LAG, TEJUOSHO | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-02-08 | 5 | 2025-02-08 | 0 | 2025-02-08 | 0 | 2025-02-13 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 |  | Completed | 2025-02-13 | 1
180 | EXTRACTOR LED BULB | ABUJA, KARU | Wear & Tear | Breakdown | MOSES | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2025-02-08 | 40 | 2025-02-08 | 0 |  | 40 | [9 empty] | Overdue
181 | FAULTY WARMER | LAG, AGUNGI | Wear & Tear | Breakdown |  | UPRIGHT WARMER MACHINE | HVAC | 2025-02-08 | 40 |  | 40 | [11 empty] | Overdue
182 | ELECTRICAL SHOCK AT BACK OF HOUSE | LAG, MAGODO | Electrical Surge | Breakdown | KOLA | OTHERS | OTHERS | 2025-02-08 | 40 | 2025-02-08 | 0 |  | 40 | [9 empty] | Overdue
183 | LOBBY HAND DRYER FAULTY | LAG, BODE THOMAS | Wear & Tear | Breakdown | PROEQUIP | HAND DRYER LOBBY | ELECTRICAL | 2025-02-08 | 40 | 2025-02-08 | 0 |  | 40 | [9 empty] | Overdue
184 | GENERATOR DUE FOR SERVICE | LAG, OKOTA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-02-08 | 40 | 2025-02-08 | 0 | 2025-02-08 | 0 | [9 empty] | Overdue
185 | GENERATOR DUE FOR SERVICE | KANO, KATSINA RD | Routine Servicing | Preventive | SP ABAYOMI | GENERATOR | GENERATOR | 2025-02-01 | 0 | 2025-02-01 | 0 | 2025-02-01 | 0 | 2025-02-01 | 2025-02-01 | 0 | 2025-02-01 | 0 | 2025-02-01 | 0 | 2025-02-01 | 191875.8 | Completed | 2025-02-01 | 1
186 | FAULTY COLD ROOM AND DEAD BULB | LAG, AWOLOWO | Routine Servicing | Preventive | ISMAIL | OTHERS | OTHERS | 2025-02-08 | 0 | 2025-02-08 | 0 | 2025-02-08 | 0 | 2025-02-08 | 2025-02-08 | 0 | 2025-02-08 | 0 | 2025-02-08 | 0 | 2025-02-08 |  | Completed | 2025-02-08 | 1
187 | FAULTY COLD ROOM | LAG, ENTOURAGE MALL | Routine Servicing | Preventive | TONAOGUNS | COLD ROOM UNIT | HVAC | 2025-02-05 | 43 | 2025-02-06 | 1 | 2025-02-06 | 0 | 2025-02-06 | 2025-02-21 | 15 | 2025-02-21 | 0 | 2025-02-21 | 27 |  | 490000 | Overdue
188 | FAULTY BOH CHILLER | LAG, OMOLE | Routine Servicing | Preventive | BCE | NBC CHILLER | HVAC | 2025-02-04 | 44 | 2025-02-05 | 1 |  | 43 | [9 empty] | Overdue
189 | FAULTY WALL SOCKET |  | Electrical Surge | Breakdown | TAYO | OTHERS | OTHERS | 2025-02-07 | 41 | 2025-02-08 | 1 | 2025-02-08 | 0 | [9 empty] | Overdue
190 | FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, IPAJA RD | Routine Servicing | Preventive | DYNAMITE | FREEZER ROOM | HVAC | 2025-02-08 | 40 | 2025-02-08 | 0 | 2025-02-08 | 0 | [9 empty] | Overdue
191 | FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, MMA2 | Routine Servicing | Preventive | TONAOGUNS | FREEZER ROOM | HVAC | 2025-02-06 | 42 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-10 | 38 |  |  |  | 189000 | Overdue
192 | DEAD INSECTOCUTOR BULB | LAG, IKOTUN | Electrical Surge | Breakdown | EMMANUEL | OTHERS | OTHERS | 2025-02-07 | 41 | 2025-02-07 | 0 | 2025-02-07 | 0 | [9 empty] | Overdue
193 | FAULTY BOH SECURITY LIGHT | LAG, AKOWONJO | Electrical Surge | Breakdown | FRIDAY | OTHERS | OTHERS | 2025-02-08 | 40 | 2025-02-08 | 0 | 2025-02-09 | 1 | [9 empty] | Overdue
194 | FAULTY SANITIZER DISPENSER AT THE UP LOBBY | LAG, FREEDOMWAY | Users Misuse | Breakdown | JOEL | OTHERS | OTHERS | 2025-02-03 | 4 | 2025-02-03 | 0 | 2025-02-07 | 4 | 2025-02-07 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 |  | Completed | 2025-02-07 | 1
195 | DEAD BULB IN THE CABINET | LAG, OKOTA | Electrical Surge | Breakdown | KITCHTEC | OTHERS | OTHERS | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-10 | 0 | [9 empty] | Overdue
196 | GENERATOR NOT COMING UP | LAG, MAGODO | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-10 | 0 | [9 empty] | Overdue
197 | OPEN SOCKET AND LICKING ZINK |  | Electrical Surge | Breakdown | FRIDAY | OTHERS | OTHERS | 2025-02-10 | 7 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 7 | 2025-02-10 |  | Completed | 2025-02-17 | 0
198 | GENERATOR SERVICING | KADUNA, CONSTITUTION RD | Routine Servicing | Preventive | CONCIRCLE | GENERATOR | GENERATOR | 2025-02-05 | 5 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 |  | Completed | 2025-02-10 | 1
199 | GENERATOR SERVICING | KADUNA, AHMADU DELLO WAY | Routine Servicing | Preventive | CONCIRCLE | GENERATOR | GENERATOR | 2025-02-05 | 1 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 |  | Completed | 2025-02-06 | 1
200 | SEWAGE EVACUATION. | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
201 | AC NOT COOLING IN THE LOBBY | LAG, OGUDU | Wear & Tear | Breakdown | FOLLTEC | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
202 | FAULTY DRYSTORE AC | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | FOLLTEC | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
203 | LEAKING DRAINAGE PIPE IN THE KITCHEN | LAG, DIYA STREET | Wear & Tear | Breakdown | ADEREMI KAZEEM | KITCHEN WASH HAND SINK | PLUMBING | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 |  | Completed | 2025-02-10 | 1
204 | LEAKING COOK SINK | LAG, MOBIL OGBA | Wear & Tear | Breakdown | ADEREMI KAZEEM | KITCHEN WASH HAND SINK | PLUMBING | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
205 | Urgent septic tank evacuation | LAG, OSOLOWAY | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
206 | GENERATOR BREAKDOWN | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 |  | Completed | 2025-02-10 | 1
207 | FAULTY DISPLAY CABINET LAMPHOLDERS | LAG, IDIMU | Wear & Tear | Breakdown | EMMANUEL | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-10 | 3 | 2025-02-10 | 0 | 2025-02-11 | 1 | 2025-02-13 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 |  | Completed | 2025-02-13 | 1
208 | FAULTY TRANSFER PUMP MACHINE | LAG, IKOTUN | Wear & Tear | Breakdown | PROPEARJEFF | TRANSFER PUMP 1 | WTP | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
209 | Faulty BOH net door | LAG, OSOLOWAY | Wear & Tear | Breakdown | TAIDAV | OTHERS | OTHERS | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
210 | GENERATOR SMOKE SMOKING DISTURBING CLOSE TO US | LAG, AJAH | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
211 | PYLON PICTURE AT NIGHT | LAG, BADORE | Others | Breakdown | ARIZMANYA | OTHERS | OTHERS | 2025-02-09 | 39 | 2025-02-10 | 1 | 2025-02-10 | 0 | [9 empty] | Overdue
212 | DIRTY WATER AT OMOLE OFFICE | LAG, OMOLE | Others | Breakdown | ADEREMI WAHAB | FILTRATION VESSEL 1 | WTP | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
213 | FAULTY LOBBY TV | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | ACORN | TELEVISION | AUDIOVISUAL | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-13 | 3 | 2025-02-14 | 2025-02-14 | 0 | 2025-02-14 | 13 | 2025-02-27 | 21 |  | 360000 | Overdue
214 | GENERATOR DUE FOR SERVICE | LAG, ETERNA LEKKI | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
215 | RUSTY COLDROOM AND FREEZER ROOM DOOR | LAG, AKOWONJO | Wear & Tear | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
216 | FAULTY UPRIGHT CHILLER | LAG, MARINA | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
217 | FOOD WARMER NOT WORKING | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
218 | FAULTY WARMER | LAG, ILUPEJU | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
219 | DEAD BULBS IN THE CABINET | LAG, MOBIL OGBA | Wear & Tear | Breakdown | MOSES | 18W ROUND LIGHT FITTING | ELECTRICAL | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
220 | BAD CHEST FREEZER GASKET | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | G.B BOYEJO | CHEST FREEZER | HVAC | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
221 | CRITICAL FOOD SAFETY; COLD ROOM NOT ATTAINING TEMPERATURE | LAG AHMADU BELLO WAY | Wear & Tear | Breakdown | NGUTAN | COLD ROOM UNIT | HVAC | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-12 | 2 | 2025-03-11 | 2025-03-11 | 0 | 2025-03-11 | 9 |  |  |  |  | Overdue
222 | DRAINAGE ISSUE IN THE FRONT OF THE STORE | LAG, ABULE EGBA | Others | Breakdown | PENTECOSTAL | DRAIN COVER | BUILDING | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
223 | FAULTY HAND DRYER. | LAG AHMADU BELLO WAY | Others | Breakdown | OLANIYI OJO | HAND DRYER TOILET | ELECTRICAL | 2025-02-06 | 42 | 2025-02-10 | 4 |  | 38 | [9 empty] | Overdue
224 | PRESSURE FRYER STARTER FAULTY | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | ISMAIL | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
225 | PFI FOOD CONCEPT JIBOWU | LAG, JIBOWU | Others | Breakdown | JUSTFOOD | OTHERS | OTHERS | 2025-02-04 | 44 | 2025-02-04 | 0 | 2025-02-04 | 0 | 2025-02-04 | 2025-02-04 | 0 | 2025-02-04 | 6 | 2025-02-10 | 38 |  | 420255.96 | Overdue
226 | BROKEN MENU BOARD | LAG, MMA2 | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-11 | 1 | [9 empty] | Overdue
227 | DETACHED CABINET GLASS | LAG, AJOSE ADEOGUN | Users Misuse | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-05 | 43 | 2025-02-06 | 1 |  | 42 | [9 empty] | Overdue
228 | MAINTENANCE ISSUE AT AWOLOWO 1 | LAG, AWOLOWO | Wear & Tear | Breakdown |  | COLD ROOM UNIT | HVAC | 2025-02-11 | 37 | 2025-02-11 | 0 |  | 37 | [9 empty] | Overdue
229 | BROKEN TILES IN THE STORE | LAG, MMA2 | Others | Breakdown | ACORN | OTHERS | OTHERS | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-03 | 0 | [9 empty] | Overdue
230 | REPLACEMENT OF DISPLAY CABINET GLASS | LAG, OKE-AFA | Others | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-08 | 3 | 2025-02-08 | 0 | 2025-02-08 | 0 | 2025-02-08 | 2025-02-08 | 0 | 2025-02-08 | 0 | 2025-02-08 | 3 | 2025-02-11 |  | Completed | 2025-02-11 | 1
231 | GAS LEAKAGE | LAG, IKOTUN | Wear & Tear | Breakdown | BERRADE | GAS CYLINDER | GAS | 2025-02-11 | 37 | 2025-02-11 | 0 |  | 37 | [9 empty] | Overdue
232 | GAS LEAKAGE | LAG, ILUPEJU | Wear & Tear | Breakdown | BERRADE | GAS CYLINDER | GAS | 2025-02-09 | 39 | 2025-02-09 | 0 | 2025-02-10 | 1 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 38 |  |  |  |  | Overdue
233 | DISPLAY CABINET GLASS | LAG, AWOLOWO | Users Misuse | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-02 | 9 | 2025-02-02 | 0 | 2025-02-11 | 9 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 |  | Completed | 2025-02-11 | 1
234 | FAULTY SWING DOOR | LAG, OPEBI | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-02-11 | 37 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-11 | 37 |  |  |  | 75000 | Overdue
235 | HEAVY BACK FLOW | LAG, IKEJA MALL | Corrective Action | Corrective | ADEREMI | OTHERS | OTHERS | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 |  | Completed | 2025-02-11 | 1
236 | BLOCKED DRAINAGE | ABUJA, KARU | Corrective Action | Corrective | JPILLAR | OTHERS | OTHERS | 2025-02-06 | 15 | 2025-02-12 | 6 | 2025-02-21 | 9 | 2025-02-21 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 |  | Completed | 2025-02-21 | 1
237 | DEAD BULBS & INSECTROCUTOR | LAG, DIYA STREET | Wear & Tear | Breakdown | KOLA | INSECT KILLER LOBBY 1 | ELECTRICAL | 2025-02-10 | 1 | 2025-02-10 | 0 | 2025-02-11 | 1 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 |  | Completed | 2025-02-11 | 1
238 | FADED PYLON AND SIGNAGE | KADUNA, CONSTITUTION RD | Wear & Tear | Breakdown |  | OTHERS | OTHERS | 2025-02-06 | 42 | 2025-02-12 | 6 |  | 36 | [9 empty] | Overdue
239 | NO WATER IN THE STORE | KADUNA, CONSTITUTION RD | Others | Breakdown |  | SUBMERSIBLE PUMP | WTP | 2025-02-10 | 38 | 2025-02-12 | 2 |  | 36 | [9 empty] | Overdue
240 | BLOCKED DRAINAGE | KADUNA, CONSTITUTION RD | Others | Breakdown |  | OTHERS | OTHERS | 2025-02-11 | 37 | 2025-02-12 | 1 |  | 36 | [9 empty] | Overdue
241 | FAULTY PUMPING MACHINE AT WTP | KADUNA, AHMADU DELLO WAY | Wear & Tear | Breakdown | OLANIYI OJO | SUBMERSIBLE PUMP | WTP | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 |  | Completed | 2025-02-11 | 1
242 | FAULTY CHIPS FRYER | KADUNA, BARNAWA | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-11 | 1 | 2025-02-12 | 1 | 2025-02-12 | 0 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 |  | Completed | 2025-02-12 | 1
243 | FAUTY INSECUTOR {PEST KILLER} | LAG, OSOLOWAY | Wear & Tear | Breakdown | KOLA | INSECT KILLER BOH | ELECTRICAL | 2025-02-11 | 37 | 2025-02-11 | 0 |  | 37 | [9 empty] | Overdue
244 | COLD ROOM AND FREEZER ROOM NOT ATTAINING TEMPERATURE (PROBE) | LAG, ONIRU | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-02-11 | 37 | 2025-02-11 | 0 | 2025-02-12 | 1 | 2025-03-13 | 2025-03-13 | 0 | 2025-03-14 | 6 |  |  |  | 890000 | Overdue
245 | Dead Pest killer bulbs | ABUJA, KARU | Wear & Tear | Breakdown | ANDREW | INSECT KILLER BOH | ELECTRICAL | 2025-02-11 | 10 | 2025-02-12 | 1 | 2025-02-21 | 9 | 2025-02-21 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 |  | Completed | 2025-02-21 | 1
246 | Faulty Bulb In The Cold Room | LAG, OGUNLANA DRIVE | Wear & Tear | Breakdown | TIMILEHIN | 18W ROUND LIGHT FITTING | ELECTRICAL | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 |  | Completed | 2025-02-11 | 1
247 | EVACUATION AND EXCAVATION OF THE SEPTIC TANK | LAG, OKOTA | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-12 | 2 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 36 |  |  | Overdue
248 | FAULTY GREASE TRAP SYSTEM | LAG, AJOSE ADEOGUN | Others | Breakdown | ZEBRA G3 | GREASE TRAP | GREASE_TRAP | 2025-02-11 | 37 | 2025-02-11 | 0 | 2025-02-17 | 6 | 2025-02-17 | 2025-02-17 | 0 | 2025-02-17 | 28 | 2025-03-17 | 3 | 2025-03-13 | 300000 | Overdue
249 | FADED LOBBY FLOOR TILES | LAG, JOEL OGUNNAIKE | Others | Breakdown | ACORN | OTHERS | OTHERS | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-12 | 9 | 2025-02-12 |  | 36 | [6 empty] | Overdue
250 | RATIONAL NOT WORKING | ABUJA, AMINU KANO DT | Wear & Tear | Breakdown | BCE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2025-02-08 | 40 | 2025-02-10 | 2 | 2025-02-11 | 1 | [9 empty] | Overdue
251 | FAULTY WARMER. | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-02-11 | 37 | 2025-02-11 | 0 | 2025-02-12 | 1 | 2025-02-12 | 2025-02-12 | 0 | [6 empty] | Overdue
252 | FAULTY VEGETABLE CUTTER | LAG, OBA AKRAN | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2025-02-10 | 2 | 2025-02-10 | 0 | 2025-02-12 | 2 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 |  | Completed | 2025-02-12 | 1
253 | MAINTENACE RELATED ISSUE | LAG, AGUNGI | Wear & Tear | Breakdown | ACORN | OTHERS | OTHERS | 2025-02-05 | 43 | 2025-02-05 | 0 | 2025-02-06 | 1 | 2025-02-12 |  | 36 | [6 empty] | Overdue
254 | SPRAYING OF CASHIER CANTER | LAG, ONIRU | Wear & Tear | Breakdown | WESTERN DESIGNER | PAINTING | BUILDING | 2025-02-11 | 37 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-12 | 36 |  |  |  |  | Overdue
255 | FREEZER ROOM NOT ATTAINING TEMPERATURE | EDO, SILUKO | Wear & Tear | Breakdown | ECS | FREEZER ROOM | HVAC | 2025-02-12 | 36 | 2025-02-12 | 0 |  | 36 | [9 empty] | Overdue
256 | FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | THIO & PARTNERS | FREEZER ROOM | HVAC | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
257 | REPAINTING OF FOH DUMPSTER |  | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-02-05 | 43 | 2025-02-05 | 0 | 2025-02-06 | 1 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 6 | 2025-02-12 | 36 |  | 65000 | Overdue
258 | LOBBY SPEAKER | OGUN, HEYDEN IBAFO | Wear & Tear | Breakdown | ACORN | OTHERS | OTHERS | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-12 | 2 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 1 | 2025-02-13 | 35 |  | 262750 | Overdue
259 | FAULTY LOBBY TELEVISION | LAG, AGUNGI | Wear & Tear | Breakdown | ACORN | TELEVISION | AUDIOVISUAL | 2025-02-12 | 36 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-13 | 2025-02-28 | 15 | 2025-02-28 | 20 |  |  |  |  | Overdue
260 | FAULTY WARMER HANDLE | LAG, OMOLE | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-02-08 | 40 | 2025-02-08 | 0 | 2025-02-12 | 4 | 2025-02-13 | 2025-02-13 | 0 | 2025-02-13 | 35 |  |  |  |  | Overdue
261 | LOBBY'S AC NAKED WIRES | LAG, MARINA | Wear & Tear | Breakdown | FOLLTEC | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-12 | 36 | 2025-02-12 | 0 | 2025-02-19 | 7 | [9 empty] | Overdue
262 | DETTACHED CHIPS FRYER COVER | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
263 | FREEZING COLD ROOM | KADUNA, BARNAWA | Wear & Tear | Breakdown | SAMSON | COLD ROOM UNIT | HVAC | 2025-02-12 | 36 | 2025-02-13 | 1 |  | 35 | [9 empty] | Overdue
264 | Proposed space for Zone 6 freezer room relocation | ABUJA, OANDO ZONE 6 | Corrective Action | Corrective | DANTEM | FREEZER ROOM | HVAC | 2025-02-05 | 43 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 43 | 2025-02-17 |  | Overdue
265 | OVERFUL SEPTIC TANK | LAG, OSOLOWAY | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-02-13 | 35 | 2025-02-13 | 0 | 2025-02-13 | 0 | [9 empty] | Overdue
266 | UNEFFECTIVE LOBBY AC | LAG, ONIRU | Wear & Tear | Breakdown | FOLLTEC | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-11 | 37 | 2025-02-11 | 0 | 2025-02-12 | 1 | [9 empty] | Overdue
267 | PX BARIGA MAINTENANCE ISSUE |  | Wear & Tear | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-02-10 | 3 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 3 | 2025-02-13 | 584841 | Completed | 2025-02-13 | 1
268 | FAULTY COLD ROOM LOCK | LAG, AGUNGI | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-02-13 | 35 | 2025-02-13 | 0 |  | 35 | [9 empty] | Overdue
269 | FAULTY GAS BURNER | OGUN, HEYDEN IBAFO | Wear & Tear | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-12 | 36 | 2025-02-12 | 0 | 2025-02-13 | 1 | 2025-02-13 | 2025-02-13 | 0 | 2025-02-13 | 35 |  |  |  |  | Overdue
270 | FAULTY BOH CHILLER | LAG, ONIRU | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2025-02-13 | 35 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 | 35 |  | 462250 | Overdue
271 | CRITICAL FOOD SAFETY (FAULTY BOH CHILLER) | LAG AHMADU BELLO WAY | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
272 | REPLACEMENT OF DILAPIDATED CHEMICAL CUPBOARD | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | MATOLAD | CHEMICAL CUPBOARD | FURNITURE | 2025-02-13 | 35 | 2025-02-13 | 0 |  | 35 | [9 empty] | Overdue
273 | DEAD EXTRACTOR BULB AND COLD ROOM BULB | LAG, MMA2 | Wear & Tear | Breakdown | TIMILEHIN | 18W ROUND LIGHT FITTING | ELECTRICAL | 2025-02-12 | 1 | 2025-02-12 | 0 | 2025-02-13 | 1 | 2025-02-13 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 |  | Completed | 2025-02-13 | 1
274 | DEAD EXTRACTOR BULB. | LAG, ALIMOSHO | Wear & Tear | Breakdown | FRIDAY | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2025-02-06 | 7 | 2025-02-06 | 0 | 2025-02-13 | 7 | 2025-02-13 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 |  | Completed | 2025-02-13 | 1
275 | FREEZER ROOM NOT READING ON PROBE AND THERMOMETER | LAG, MAGODO | Wear & Tear | Breakdown | TRIPPLE O | FREEZER ROOM | HVAC | 2025-02-14 | 34 | 2025-02-14 | 0 |  | 34 | [9 empty] | Overdue
276 | FAULTY GENERATOR AT THE STORE | LAG, IPAJA RD | Wear & Tear | Breakdown | MIDTECH | GENERATOR | GENERATOR | 2025-02-14 | 34 | 2025-02-14 | 0 |  | 34 | [9 empty] | Overdue
277 | ROTISERIE MACHINE NOT ROLLING | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | KITCHTECH | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2025-02-14 | 34 | 2025-02-14 | 0 |  | 34 | [9 empty] | Overdue
278 | chips door detaches | LAG, TEJUOSHO | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-14 | 34 | 2025-02-14 | 0 |  | 34 | [9 empty] | Overdue
279 | FAULTY FOUR HEAD MACHINE | LAG, AWOLOWO | Wear & Tear | Breakdown | ISMAIL | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2025-02-14 | 34 | 2025-02-14 | 0 |  | 34 | [9 empty] | Overdue
280 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | THIO | COLD ROOM UNIT | HVAC | 2025-02-10 | 4 | 2025-02-10 | 0 | 2025-02-14 | 4 | 2025-02-14 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 |  | Completed | 2025-02-14 | 1
281 | ISSUES SIGHTED DURING OSC | LAG, BODE THOMAS | Wear & Tear | Breakdown | ACORN | OTHERS | OTHERS | 2025-02-14 | 34 | 2025-02-14 | 0 | 2025-02-14 | 0 | [9 empty] | Overdue
282 | LOBBY ACs NOT COOLING | LAG, DIYA STREET | Wear & Tear | Breakdown | THIO | 5HP STANDING AC UNIT 2 | HVAC | 2025-02-14 | 3 | 2025-02-14 | 0 | 2025-02-17 | 3 | 2025-02-17 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 |  | Completed | 2025-02-17 | 1
283 | FAULTY ROLLER SHUTTER | LAG, JIBOWU | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-02-14 | 18 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-17 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | 15 | 2025-03-04 | 146822.79 | Completed | 2025-03-04 | 1
284 | FAULTY CHIPS FRYER | LAG, BADORE | Wear & Tear | Breakdown | ECS | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-14 | 34 | 2025-02-14 | 0 |  | 34 | [9 empty] | Overdue
285 | CRACK WALL | LAG, ISAWO-IKORODU | Corrective Action | Corrective | ARIZMANYA | WALL | BUILDING | 2025-02-13 | 35 | 2025-02-14 | 1 | 2025-02-14 | 0 | [9 empty] | Overdue
286 | GENERATOR DUE FOR SERVICING | LAG, IRE-AKARI | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-02-14 | 34 | 2025-02-14 | 0 |  | 34 | [9 empty] | Overdue
287 | FAULTY HENNY PENNY PRESSURE FRYER | LAG, MARINA | Wear & Tear | Breakdown | KITCHTECH | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-14 | 3 | 2025-02-14 | 0 | 2025-02-17 | 3 | 2025-02-17 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | 196918.5 | Completed | 2025-02-17 | 1
288 | GAS PIPE LEAKAGE | LAG, AGUNGI | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-02-11 | 37 | 2025-02-11 | 0 | 2025-02-14 | 3 | 2025-02-14 |  | 34 | [6 empty] | Overdue
289 | FAULTY WARMER HANDLE. | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-02-14 | 34 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 | 2025-02-17 | 3 | 2025-02-17 | 31 |  |  |  |  | Overdue
290 | BROKEN CHAMBER | LAG, MAGODO | Wear & Tear | Breakdown | PENTECOSTAL | CHAMBER | BUILDING | 2025-02-14 | 34 | 2025-02-14 | 0 | 2025-02-15 | 1 | 2025-02-15 | 2025-02-15 | 0 | 2025-02-15 | 2 | 2025-02-17 | 31 |  | 64505 | Overdue
291 | DEAD BULB IN DISPLAY CABINET | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-14 | 3 | 2025-02-14 | 0 | 2025-02-17 | 3 | 2025-02-17 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | 102125 | Completed | 2025-02-17 | 1
292 | FAULTY RATIONAL | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | BCE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2025-02-13 | 35 | 2025-02-13 | 0 | 2025-02-14 | 1 | [9 empty] | Overdue
293 | FREEZER ROOM NOT ATTATAINING TEMPERATURE | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2025-02-12 | 36 | 2025-02-12 | 0 |  | 36 | [9 empty] | Overdue
294 | PAINTING OF TABLES IN THE LOBBY | LAG, BADORE | Wear & Tear | Breakdown | MATOLAD | CUSTOMER TABLE | FURNITURE | 2025-02-14 | 34 | 2025-02-14 | 0 | 2025-02-15 | 1 | 2025-02-17 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | 31 |  | 185000 | Overdue
295 | OFFENCING GAS SMELL AT THE CONNECTION OF THE GAS | LAG, MAGODO | Others | Breakdown | PROPEARJEFF | GAS CYLINDER | GAS | 2025-02-13 | 35 | 2025-02-13 | 0 | 2025-02-14 | 1 | [9 empty] | Overdue
296 | GENERATOR DUE FOR SERVICING | LAG, IKORODU | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-02-14 | 34 | 2025-02-14 | 0 | 2025-02-14 | 0 | [9 empty] | Overdue
297 | CABINET NOT ATTAINING TEMPERATURE | LAG, AKOWONJO | Wear & Tear | Breakdown | HEFFEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-11 | 3 | 2025-02-11 | 0 | 2025-02-14 | 3 | 2025-02-14 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 |  | Completed | 2025-02-14 | 1
298 | FAULTY HAND WASH TAP | LAG, CONOIL IKEJA | Users Misuse | Breakdown | PROPEARJEFF | TAP | PLUMBING | 2025-02-12 | 36 | 2025-02-12 | 0 | 2025-02-14 | 2 | [9 empty] | Overdue
299 | APPROVAL TO PURCHASE LED LIGHTS | EBONYI, WATERWORKS, ABAKALIKI | Wear & Tear | Breakdown | SUNDAY | OTHERS | OTHERS | 2025-02-09 | 39 | 2025-02-09 | 0 |  | 39 | [9 empty] | Overdue
300 | SERVICING OF GENERATOR | PH AGGREY | Routine Servicing | Preventive | GLUFFSCO | GENERATOR | GENERATOR | 2025-02-09 | 3 | 2025-02-09 | 0 | 2025-02-11 | 2 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 1 | 2025-02-11 |  | Completed | 2025-02-12 | 0
301 | SERVICING OF ACS | BAYELSA, OPOLO | Routine Servicing | Preventive | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-05 | 43 | 2025-02-05 | 0 | 2025-02-10 | 5 | [9 empty] | Overdue
302 | SERVICING OF ICECREAM MACHINE | PH, ABA | Routine Servicing | Preventive | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-02-09 | 39 | 2025-02-09 | 0 |  | 39 | [9 empty] | Overdue
303 | NO LIGHT SOURCE AT THE UNDER BAR CHILLER | AKWA IBOM, ORON RD | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2025-02-09 | 39 | 2025-02-09 | 0 | 2025-02-10 | 1 | [9 empty] | Overdue
304 | PFI IKOT EKPENE, UYO | AKWA IBOM, IKOT EKPENE RD | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-01-21 | 58 | 2025-01-21 | 0 | 2025-01-21 | 0 | 2025-01-21 | 2025-01-21 | 0 | 2025-01-21 | 1 | 2025-01-22 | 57 |  |  | Overdue
305 | COLD ROOM NOT ATTAINING TEMPERATURE | ENUGU, CHIME AVENUE | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-10 | 0 | [9 empty] | Overdue
306 | COLD ROOM NOT ATTAINING TEMPERATURE | AKWA IBOM, NWANIBA | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2025-02-09 | 39 | 2025-02-10 | 1 |  | 38 | [9 empty] | Overdue
307 | FADED PYLON LIGHT WITH RUSTED PYLON POLE. | PH, ABA | Wear & Tear | Breakdown | ACORN | OTHERS | OTHERS | 2025-01-17 | 62 | 2025-01-17 | 0 |  | 62 | [9 empty] | Overdue
308 | Lobby Ac's /Dry Store Ac's/ Office Ac not working | DELTA, EFFURUN | Wear & Tear | Breakdown | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-28 | 13 | 2025-01-28 | 0 | 2025-02-10 | 13 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 |  | Completed | 2025-02-10 | 1
309 | REQUEST FOR SERVICING OF ACTIVATED FILTERS (SAND FILTER AND ACTIVATED CARBON) - CR NSUKKA | ENUGU, NSUKKA | Wear & Tear | Breakdown | PRO-EQUIPTECH | WATER TREATMENT PLANT BLD | BUILDING | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-12 | 2 | [9 empty] | Overdue
310 | REQUEST FOR ICE CREAM MACHINE COVER | PH, ONNE RD, GRA | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-11 | 1 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 37 |  |  | Overdue
311 | GENERATOR BREAKDOWN | PH, GRA BIRABI | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-02-10 | 1 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 |  | Completed | 2025-02-11 | 1
312 | CABINET NOT WORKING | EBONYI, WATERWORKS, ABAKALIKI | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
313 | GENERATOR SERVICING | ANAMBRA, ZIK AVENUE, AWKA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-02-10 | 1 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 |  | Completed | 2025-02-11 | 1
314 | MAINTENANCE ISSUES | BAYELSA, YENAGOA | Wear & Tear | Breakdown | GLUFFSCO | OTHERS | OTHERS | 2025-02-10 | 38 | 2025-02-10 | 0 |  | 38 | [9 empty] | Overdue
315 | OKIGWE DAMAGED DRAINAGE SLABS | IMO, OKIGWE | Wear & Tear | Breakdown | DT CONSULT | OTHERS | OTHERS | 2024-12-08 | 102 | 2024-12-08 | 0 |  | 102 | [9 empty] | Overdue
316 | COLD ROOM NOT ATTAINING TEMPERATURE (CR LIMCA RD) | ANAMBRA, LIMCA RD, ONITSHA | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2025-01-29 | 50 | 2025-01-29 | 0 |  | 50 | [9 empty] | Overdue
317 | PAINTING OF INTERIOR AND EXTERIOR ---CR CHIME AVENUE | ENUGU, CHIME AVENUE | Wear & Tear | Breakdown | JOWNY | OTHERS | OTHERS | 2024-12-18 | 92 | 2024-12-21 | 3 | 2024-12-21 | 0 | [9 empty] | Overdue
318 | LOBBY AC DUE FOR SERVICING | AKWA IBOM, ABAK RD | Wear & Tear | Breakdown | MOFFEN | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-10 | 38 | 2025-02-11 | 1 |  | 37 | [9 empty] | Overdue
319 | BROKEN WASH HAND SINK STAND | EDO, UGBOWO, BENIN | Wear & Tear | Breakdown | FRANK | KITCHEN WASH HAND SINK | PLUMBING | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 |  | Completed | 2025-02-11 | 1
320 | FAULTY BOH UNDERBAR | IMO, IKENEGBU, OWERRI | Wear & Tear | Breakdown | BCE | UPRIGHT UNDERBAR MACHINE | HVAC | 2025-02-11 | 37 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 36 |  |  | Overdue
321 | FAULTY COLD ROOM DOOR LOCK | BAYELSA, OPOLO | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2025-02-11 | 37 | 2025-02-11 | 0 |  | 37 | [9 empty] | Overdue
322 | GENERATOR SERVICING | BAYELSA, YENAGOA | Routine Servicing | Preventive | PAGISEL | GENERATOR | GENERATOR | 2025-02-10 | 38 | 2025-02-11 | 1 |  | 37 | [9 empty] | Overdue
323 | OKIGWE DAMAGED DRAINAGE SLABS | IMO, OKIGWE | Wear & Tear | Breakdown | DT CONSUILT | OTHERS | OTHERS | 2024-12-08 | 102 | 2024-12-08 | 0 |  | 102 | [9 empty] | Overdue
324 | LOBBY AC DUE FOR SERVICING | AKWA IBOM, ABAK RD | Routine Servicing | Preventive | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-10 | 38 | 2025-02-11 | 1 | 2025-02-11 | 0 | [9 empty] | Overdue
325 | FAULTY FREEZER ROOM. | ABIA, FACTORY RD, ABA | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2025-01-28 | 51 | 2025-01-28 | 0 | 2025-01-29 | 1 | 2025-01-29 | 2025-01-29 | 0 | 2025-01-29 | 0 | 2025-01-29 | 50 |  |  | Overdue
326 | REQUEST FOR NEW CABBAGE SHREDDER- CR LIMCA RD ONITSHA | ANAMBRA, LIMCA RD, ONITSHA | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 37 |  |  | Overdue
327 | FREEZER ROOM NOT ATTAINING TEMPERATURE | ABIA, AZIKIWE RD, UMUAHIA | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2025-02-11 | 1 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 |  | Completed | 2025-02-12 | 1
328 | FAULTY GENERATOR BATTERY - CR NWANIBA | AKWA IBOM, NWANIBA | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-11 | 2 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-12 | 1 | 2025-02-13 | 0 | 2025-02-13 |  | Completed | 2025-02-13 | 1
329 | GENERATOR BREAK DOWN | PH, UST | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-11 |  | Completed | 2025-02-11 | 1
330 | COLD AND FREEZER ROOM NOT ATTAINING TEMPERATURE - CR NSUKKA | ENUGU, NSUKKA | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2025-02-11 | 37 | 2025-02-11 | 0 | 2025-02-12 | 1 | [9 empty] | Overdue
331 | BLOCKED GREASE TRAPS AND MANHOLES | AKWA IBOM, AKA RD | Others | Breakdown | UCH | OTHERS | OTHERS | 2025-02-11 | 37 | 2025-02-12 | 1 |  | 36 | [9 empty] | Overdue
332 | GENERATOR SERVICING-CR OKIGWE | IMO, OKIGWE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-02-11 | 37 | 2025-02-12 | 1 | 2025-02-12 | 0 | [9 empty] | Overdue
333 | PFI FOR CHICKEN REPUBLIC IWOFE PH | PH, IWOFE | Wear & Tear | Breakdown | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-02-12 | 36 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 36 |  |  | Overdue
334 | LEAKING AERATION TANK | IMO, WETHERAL RD, OWERRI | Wear & Tear | Breakdown | PRO-EQUIP | AERATION TANK | WTP | 2025-01-06 | 73 | 2025-01-06 | 0 | 2025-01-09 | 3 | [9 empty] | Overdue
335 | GEN TRIPPING OFF | EBONYI, AFIKPO, ABAKALIKI | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 |  | Completed | 2025-02-12 | 1
336 | FAULTY GASKET FOR FOUR HEAD PRESSURE FRYER | PH, ONNE RD, GRA | Wear & Tear | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-12 | 36 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 36 |  |  |  |  | Overdue
337 | CABINET NOT WORKING | EBONYI, WATERWORKS, ABAKALIKI | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-11 | 37 | 2025-02-12 | 1 | 2025-02-12 | 0 | [9 empty] | Overdue
338 | UNDER BAR UPRIGHT CHILLER NOT ATTAINING TEMPERATURE | AKWA IBOM, NWANIBA | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2025-02-09 | 39 | 2025-02-12 | 3 | 2025-02-12 | 0 | [9 empty] | Overdue
339 | BOH AIR VENT NOT COMING ON- AFIKPO | EBONYI, AFIKPO, ABAKALIKI | Wear & Tear | Breakdown | UCH | OTHERS | OTHERS | 2025-02-12 | 36 | 2025-02-12 | 0 |  | 36 | [9 empty] | Overdue
340 | SERVICING OF THE A.C'S - AWKA ROAD | Awak | Wear & Tear | Breakdown | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2025-01-27 | 52 | 2025-01-28 | 1 |  | 51 | [9 empty] | Overdue
341 | HIGH GAS COMSUMPTION-WEAK/OLD CONNECTION | BAYELSA, YENAGOA | Wear & Tear | Breakdown | PRO-EQUITECH | GAS CYLINDER | GAS | 2025-02-12 | 36 | 2025-02-12 | 0 |  | 36 | [9 empty] | Overdue
342 | REPLACEMENT OF INSECUTOR | BAYELSA, OPOLO | Wear & Tear | Breakdown | GLUFFSCO | OTHERS | OTHERS | 2025-01-29 | 50 | 2025-02-03 | 5 | 2025-02-12 | 9 | 2025-02-14 |  | 34 | [6 empty] | Overdue
343 | REMINDER OF MAINTENANCE ISSUES/ PURCHASE OF INSECUTOR | BAYELSA, YENAGOA | Wear & Tear | Breakdown | GLUFFSCO | OTHERS | OTHERS | 2025-01-16 | 63 | 2025-02-10 | 25 | 2025-02-12 | 2 | [9 empty] | Overdue
344 | OFFICE AC DRIPPING WATER | PH, ONNE RD, GRA | Wear & Tear | Breakdown | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-02 | 46 | 2025-02-02 | 0 |  | 46 | [9 empty] | Overdue
345 | Cold room and freezer room not attaining temperature | EBONYI, WATERWORKS, ABAKALIKI | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2025-01-18 | 26 | 2025-01-19 | 1 | 2025-02-04 | 16 | 2025-02-05 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 8 | 2025-02-13 |  | Completed | 2025-02-13 | 1
346 | CR ABA-OWERRI ROAD COLDROOM GAS LEAKAGE | ABIA, ABA-OWERRI RD | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2025-02-13 | 35 | 2025-02-13 | 0 |  | 35 | [9 empty] | Overdue
347 | FREEZER ROOM NOT ATTAINING TEMPERATURE | PH AGGREY | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2025-02-13 | 35 | 2025-02-13 | 0 |  | 35 | [9 empty] | Overdue
348 | PEELED WALL IN DRY STORE | ABIA, ABA-OWERRI RD | Wear & Tear | Breakdown | FULL TRUN | WALL | BUILDING | 2025-02-12 | 36 | 2025-02-12 | 0 |  | 36 | [9 empty] | Overdue
349 | FAULTY HAND DRYER | ABIA, AZIKIWE RD, UMUAHIA | Wear & Tear | Breakdown | LEO | HAND DRYER LOBBY | ELECTRICAL | 2025-02-13 | 35 | 2025-02-13 | 0 |  | 35 | [9 empty] | Overdue
350 | CRACKED DRY STORE WALLS | ABIA, OGBOR HILLS | Wear & Tear | Breakdown | LEO | WALL | BUILDING | 2025-02-13 | 35 | 2025-02-13 | 0 |  | 35 | [9 empty] | Overdue
351 | OVERCONSUMPTION OF DIESEL BY GENERATOR - CR NSUKKA | ENUGU, NSUKKA | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-14 | 34 | 2025-02-14 | 0 | 2025-02-14 | 0 | [9 empty] | Overdue
352 | SUPPLY OF ELECTRICAL MATERIAL | BAYELSA, YENAGOA | Wear & Tear | Breakdown | GLUFFSCO | OTHERS | OTHERS | 2025-02-10 | 4 | 2025-02-10 | 0 | 2025-02-12 | 2 | 2025-02-12 | 2025-02-13 | 1 | 2025-02-13 | 0 | 2025-02-13 | 1 | 2025-02-14 |  | Completed | 2025-02-14 | 1
353 | CHIPS MACHINE-CHIME AVENUE | ENUGU, CHIME AVENUE | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-13 | 35 | 2025-02-14 | 1 | 2025-02-14 | 0 | [9 empty] | Overdue
354 | SIX HEAD MACHINE NOT COMING UP | DELTA, EFFURUN | Wear & Tear | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-14 | 34 | 2025-02-14 | 0 | 2025-02-14 | 0 | [9 empty] | Overdue
355 | REPLACEMENT OF BOH OF HOUSE CEILING/CASHIER'S COUNTER - AWKA ROAD | ANAMBRA, AWKA RD, ONITSHA | Wear & Tear | Breakdown | JOWNY | CEILING BOARD | BUILDING | 2025-01-16 | 63 | 2025-02-01 | 16 |  | 47 | [9 empty] | Overdue
356 | GENERATOR LEAKING WATER | ABIA, ABA-OWERRI RD | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-13 | 1 | 2025-02-14 | 1 | 2025-02-14 | 0 | 2025-02-14 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 |  | Completed | 2025-02-14 | 1
357 | ASSETS NEEDED IN THE STORE - CR AWKA ROAD, ONITSHA | ANAMBRA, AWKA RD, ONITSHA | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2025-01-28 | 51 | 2025-02-13 | 16 |  | 35 | [9 empty] | Overdue
358 | FAULTY AIR VENTS | ABIA, AZIKIWE RD, UMUAHIA | Wear & Tear | Breakdown | leo | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2025-02-13 | 35 | 2025-02-14 | 1 |  | 34 | [9 empty] | Overdue
359 | FREEZER ROOM AND COLD ROOM NOT ATTENDING TEMPERATURE | PH, ONNE RD, GRA | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2025-02-13 | 1 | 2025-02-14 | 1 | 2025-02-14 | 0 | 2025-02-14 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 |  | Completed | 2025-02-14 | 1
360 | CHIPS MACHINE | ENUGU, CHIME AVENUE | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-13 | 35 | 2025-02-14 | 1 |  | 34 | [9 empty] | Overdue
361 | REQUEST PRESSURE FRYER CRUMB COLLECTOR GASKET | CALABAR, NDIDEM | Wear & Tear | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-14 | 34 | 2025-02-14 | 0 |  | 34 | [9 empty] | Overdue
362 | GENERATOR BREAK DOWN | PH, GRA BIRABI | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 |  | Completed | 2025-02-14 | 1
363 | DISPLAY CABINET NOT ATTENDING TEMPERATURE | ABIA, ADAZI RD | Wear & Tear | Breakdown | LEO | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-13 | 1 | 2025-02-14 | 1 | 2025-02-14 | 0 | 2025-02-14 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 |  | Completed | 2025-02-14 | 1
364 | LOBBY AC NOT WORKING PROPERLY | PH, RUKPOKWU | Wear & Tear | Breakdown | ECS | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-13 | 1 | 2025-02-13 | 0 | 2025-02-14 | 1 | 2025-02-14 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 |  | Completed | 2025-02-14 | 1
365 | FEEZER ROOM NOT ATTAINING TEMPERTURE | PH, ABA | Wear & Tear | Breakdown | MOFEEN | FREEZER ROOM | HVAC | 2025-02-13 | 35 | 2025-02-14 | 1 |  | 34 | [9 empty] | Overdue
366 | FAULTY BOH CHILLER | PH, RUKPOKWU | Wear & Tear | Breakdown | MOFEEN | NBC CHILLER | HVAC | 2025-02-13 | 35 | 2025-02-13 | 0 |  | 35 | [9 empty] | Overdue
367 | DISPLAY CABINET NOT HEATING UP | ANAMBRA, AWKA RD, ONITSHA | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-14 | 34 | 2025-02-14 | 0 |  | 34 | [9 empty] | Overdue
368 | FAULTY SHREDDED MACHINE | ABIA, ADAZI RD | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2025-02-14 | 34 | 2025-02-14 | 0 |  | 34 | [9 empty] | Overdue
369 | FAULTY AIR-CONDITIONER | IMO, OKIGWE | Wear & Tear | Breakdown | MOFEEN | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-15 | 33 | 2025-02-15 | 0 |  | 33 | [9 empty] | Overdue
370 | COLDROOM AND FREEZER ROOM NOT ATTAINING TEMPERATURE | PH, ONNE RD, GRA | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 | 0 | 2025-02-14 |  | Completed | 2025-02-14 | 1
371 | FAULTY SHREDDED MACHINE | ABIA, ADAZI RD | Wear & Tear | Breakdown | LEO | OTHERS | OTHERS | 2025-02-15 | 33 | 2025-02-15 | 0 |  | 33 | [9 empty] | Overdue
372 | REPLACEMENT OF BOH OF HOUSE CEILING/CASHIER'S COUNTER - AWKA ROAD | ANAMBRA, AWKA RD, ONITSHA | Others | Breakdown | JOWNY | CASHIER COUNTER | BUILDING | 2025-01-26 | 53 | 2025-01-26 | 0 |  | 53 | [9 empty] | Overdue
373 | GENERATOR LEAKING WATER | PH, ABA | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-14 | 34 | 2025-02-15 | 1 |  | 33 | [9 empty] | Overdue
374 | FAULTY COLD ROOM SELF LOCK KNOB | DELTA, OKPE RD | Wear & Tear | Breakdown | MOFEEN | COLD ROOM UNIT | HVAC | 2025-02-14 | 34 | 2025-02-15 | 1 |  | 33 | [9 empty] | Overdue
375 | SPOILT BOH CHILLER DOOR | IMO, IKENEGBU, OWERRI | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2025-02-15 | 33 | 2025-02-15 | 0 |  | 33 | [9 empty] | Overdue
376 | Re: FAULTY HAND WASH TAP | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | PROPEAR | TAP | PLUMBING | 2025-02-12 | 8 | 2025-02-12 | 0 | 2025-02-18 | 6 | 2025-02-20 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 |  | Completed | 2025-02-20 | 1
377 | EQUIPMENT STATUS REPORT | PPU Ilupeju | Wear & Tear | Breakdown | MACADAMS | HAND DRYER LOBBY | ELECTRICAL | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | 2025-02-05 |  | 43 | [6 empty] | Overdue
378 | ICE CREAM MACHINE SERVICING | OYO, OWODE | Routine Servicing | Preventive | JUST FOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
379 | FAULTY DOSING PUMP | IBADAN, AKOBO | Wear & Tear | Breakdown | PRO-EQUIPTECH | DOSING PUMP | WTP | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-05 |  | Completed | 2025-02-05 | 1
380 | FAULTY LIGHT BULB AND LOW CABINET TEMPERATURE | IBADAN, CHALLENGE | Wear & Tear | Breakdown | KITCH TECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
381 | REQUEST FOR LID GASKET | OYO, OWODE | Wear & Tear | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2025-02-05 | 43 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-06 |  | 42 | [6 empty] | Overdue
382 | FAULTY AC - CUSTOMER RESTROOM AND DRY STORE | OGUN, OKE-ILEWO | Wear & Tear | Breakdown | TONA OGUNS | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 |  | Completed | 2025-02-06 | 1
383 | Lobby Ac's /Dry Store Ac's/ Office Ac not working | DELTA, EFFURUN | Routine Servicing | Preventive | MOFFEEN | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 |  | Completed | 2025-02-06 | 1
384 | BROKEN TILES IN THE STORE | EDO, UGBOWO, BENIN | Wear & Tear | Breakdown | DT CONSULT | OTHERS | OTHERS | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 |  | Completed | 2025-02-06 | 1
385 | DOCUMENT WITH ISSUES | LAG, EJIGBO | Wear & Tear | Breakdown | ILUPEJU
386 | EXCESS FURNITURE AND BAD CHAIRS AT OMOLE ANNEX LAGOS; AND 1 RIM OF LETTER HEADED PAPERS | LAG, OMOLE | Wear & Tear | Breakdown | OMOLE | CUSTOMER CHAIR | FURNITURE | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 |  | Completed | 2025-02-06 | 1
387 | COLD ROOM NOT ATTAINING TEMPERATURE | IBADAN, VENTURA MALL | Routine Servicing | Preventive | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 | 0 | 2025-02-06 |  | Completed | 2025-02-06 | 1
388 | COLD ROOM NOT ATTAINING TEMPERATURE | OYO, OGBOMOSHO | Routine Servicing | Preventive | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 0 |  |  |  | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 |  | Completed | 2025-02-07 | 1
389 | : INVERTER NOT WORKING | OGUN, OKE-ILEWO | Routine Servicing | Preventive | NISTECH | INVERTER SYSTEM | INVERTER | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-05 |  | 43 | 2025-02-05 | 43 |  |  | 2025-02-07 |  | Completed | 2025-02-07 | 1
390 | SERVICING OF GENERATOR | ILORIN, ASA DAM | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 | 0 | 2025-02-07 |  | 41 | 2025-02-07 | 41 |  |  | 2025-02-07 |  | Completed | 2025-02-07 | 1
391 | NEED FOR CHANGING COLROOM CURTAIN AND LOCK. | ILORIN, MM WAY | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-02-08 | 0 | 2025-02-08 | 0 |  | 40 | 2025-02-08 | 2025-02-08 | 0 | 2025-02-08 | 0 | 2025-02-08 | 0 | 2025-02-08 | 343753 | Completed | 2025-02-08 | 1
392 | INVERTER NOT WORKING | OGUN, OKE-ILEWO | Routine Servicing | Preventive | NISTECH | INVERTER SYSTEM | INVERTER | 2025-02-08 | 0 | 2025-02-08 | 0 |  | 40 | 2025-02-08 | 2025-02-08 | 0 | 2025-02-08 | 0 | 2025-02-08 | 0 | 2025-02-08 |  | Completed | 2025-02-08 | 1
393 | STRUCTURAL DEFECT/BROKEN CAR PARK | IBADAN, AKOBO | Wear & Tear | Breakdown | REVELATION E. | OTHERS | OTHERS | 2025-02-08 | 1 | 2025-02-08 | 0 |  | 40 | 2025-02-08 | 2025-02-08 | 0 | 2025-02-08 | 0 | 2025-02-08 | 1 | 2025-02-09 |  | Completed | 2025-02-09 | 1
394 | EQUIPMENT STATUS REPORT | PPU Ilupeju | Wear & Tear | Breakdown | MACADAMS | OTHERS | OTHERS | 2025-02-09 | 39 | 2025-02-09 | 0 | 2025-02-09 | 0 | 2025-02-09 | 2025-02-09 | 0 | 2025-02-09 | 0 | 2025-02-09 | 39 |  |  | Overdue
395 | Lobby Ac's /Dry Store Ac's/ Office Ac not working | DELTA, EFFURUN | Routine Servicing | Preventive | MOFFEEN | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2025-02-09 | 0 | 2025-02-09 | 0 | 2025-02-09 | 0 | 2025-02-09 | 2025-02-09 | 0 | 2025-02-09 | 0 | 2025-02-09 | 0 | 2025-02-09 |  | Completed | 2025-02-09 | 1
396 | FREZZER ROOM NOT ATTANNING TEMPERATURE | OSUN, AYETORO | Routine Servicing | Preventive | TONA OGUNS | FREEZER ROOM | HVAC | 2025-02-09 | 0 | 2025-02-09 | 0 | 2025-02-09 | 0 | 2025-02-09 | 2025-02-09 | 0 | 2025-02-09 | 0 | 2025-02-09 | 0 | 2025-02-09 | 152475 | Completed | 2025-02-09 | 1
397 | LOBBY AC NOT WORKUNG EFFECTIVELY | LAG, ETERNA LEKKI | Routine Servicing | Preventive | TONA OGUNS | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 |  | Completed | 2025-02-10 | 1
398 | BACK FLOW FROM BIO-DIGESTER | OGUN, OKE-ILEWO | Wear & Tear | Breakdown | ENGINEERING CHRIS | OTHERS | OTHERS | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 38 |  |  |  |  | Overdue
399 | GENERATOR DUE FOR SERVICING | OSUN, AYETORO | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 |  | Completed | 2025-02-10 | 1
400 | GENERATOR SERVICING - CR OJOO | IBADAN, OJOO | Routine Servicing | Preventive | WAREHOUSE | GENERATOR | GENERATOR | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 252625 | Completed | 2025-02-10 | 1
401 | VEGETABLES SHREDDING MACHINE NOT WORKING | OSUN, GBONGAN | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 38 | 2025-02-10 |  | Overdue
402 | FREEZER AND COLD ROOM NOT ATTAINING TEMPERATURE | OGUN, FATGBEMS IBB WAY | Routine Servicing | Preventive | TONA OGUNS | FREEZER ROOM | HVAC | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 |  | 38 | [6 empty] | Overdue
403 | FAULTY EXTRACTOR FAN | ILORIN, GRA | Wear & Tear | Breakdown | SEASONED BENDAN | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 38 |  |  | Overdue
404 | FAULTY LIGHT BULB AND LOW CABINET TEMPERATURE | IBADAN, CHALLENGE | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-10 | 38 |  | 38 | [11 empty] | Overdue
405 | DIRTY WATER AT OMOLE OFFICE | LAG, OMOLE | Routine Servicing | Preventive | KITCHTECH | WATER TREATMENT PLANT BLD | BUILDING | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 38 |  |  | Overdue
406 | SEWAGE EVACUATION. | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-02-16 | 0 | 2025-02-16 | 0 | 2025-02-16 | 0 | 2025-02-16 | 2025-02-16 | 0 | 2025-02-16 | 0 | 2025-02-16 | 0 | 2025-02-16 |  | Completed | 2025-02-16 | 1
407 | FAULTY CUSTOMER TOILET DOOR | LAG, MAGODO | Users Misuse | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-02-16 | 32 | 2025-02-16 | 0 |  | 32 | [9 empty] | Overdue
408 | Repainting of chipped edges of cashier counter | LAG, OSOLOWAY | Wear & Tear | Breakdown | GENEROUS | CASHIER COUNTER | BUILDING | 2025-02-14 | 34 | 2025-02-16 | 2 | 2025-02-16 | 0 | [9 empty] | Overdue
409 | WATER IS NOT COMING INTO THE STORE | LAG, JOEL OGUNNAIKE | Others | Breakdown | PROPEAR | OTHERS | OTHERS | 2025-02-16 | 0 | 2025-02-16 | 0 | 2025-02-16 | 0 | 2025-02-16 | 2025-02-16 | 0 | 2025-02-16 | 0 | 2025-02-16 | 0 | 2025-02-16 |  | Completed | 2025-02-16 | 1
410 | FAULTY FOUR HEAD MACHINE | LAG, AWOLOWO | Routine Servicing | Preventive | ISMAIL | OTHERS | OTHERS | 2025-02-14 | 3 | 2025-02-14 | 0 | 2025-02-17 | 3 | 2025-02-17 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 |  | Completed | 2025-02-17 | 1
411 | WATER DROPLETS ON CEILING IN ILUPEJU LABORATORY | LAG, ILUPEJU | Wear & Tear | Breakdown | MATOLAD | ROOF | BUILDING | 2025-02-13 | 35 | 2025-02-13 | 0 |  | 35 | [9 empty] | Overdue
412 | HAND WAS SINK NOT WORKING | LAG, FREEDOMWAY | Users Misuse | Breakdown | JOEL | LOBBY WASH HAND BASIN | PLUMBING | 2025-02-17 | 31 | 2025-02-17 | 0 |  | 31 | [9 empty] | Overdue
413 | LOW POWER SUPPLY |  | Electrical Surge | Breakdown | FRIDAY | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-02-10 | 38 | 2025-02-12 | 2 | 2025-02-15 | 3 | [9 empty] | Overdue
414 | FUALTY DISPLAY CABINET | IMO, IKENEGBU, OWERRI | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-17 | 31 | 2025-02-17 | 0 | 2025-02-17 | 0 | [9 empty] | Overdue
415 | Leackge over air tank | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | PROPEARJEFF | OVERHEAD WATER TANK | WTP | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
416 | FAULTY EXTRACTOR AT BOH | LAG, BADORE | Wear & Tear | Breakdown | VIRGIN STEEL | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2025-02-11 | 37 | 2025-02-11 | 0 | 2025-02-11 | 0 | 2025-02-13 | 2025-02-19 | 6 | 2025-02-19 | 1 | 2025-02-20 | 28 | 2025-03-03 |  | Overdue
417 | EVACUATION OF PUBLIC DRAINAGE IN CR IPAJA/ AYOBO | LAG, IPAJA RD | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2025-02-16 | 32 | 2025-02-16 | 0 | 2025-02-17 | 1 | 2025-02-17 | 2025-02-21 | 4 | 2025-02-22 | 26 |  |  |  | 400000 | Overdue
418 | INVERTER NOT WORKING | KANO, AIRPORT RD | Wear & Tear | Breakdown | BELLOSON | INVERTER SYSTEM | INVERTER | 2025-02-08 | 40 | 2025-02-17 | 9 |  | 31 | [9 empty] | Overdue
419 | FAULTY ICE CREAM MACHINE | LAG, IPAJA RD | Wear & Tear | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-02-13 | 35 | 2025-02-13 | 0 |  | 35 | [9 empty] | Overdue
420 | REPAIRING OF THE CAR PARK FLOOR INTERLOCK | LAG, IPAJA RD | Wear & Tear | Breakdown | PENTACOSTAL | OTHERS | OTHERS | 2025-02-16 | 32 | 2025-02-17 | 1 |  | 31 | [9 empty] | Overdue
421 | BLINKING INSECT KILLER TUBES. | LAG, AGUNGI | Wear & Tear | Breakdown | ADEREMI KAZEEM | INSECT KILLER BOH | ELECTRICAL | 2025-02-17 | 31 | 2025-02-17 | 0 |  | 31 | [9 empty] | Overdue
422 | FAULTY CUSTOMER RESTROOM | LAG, MARINA | Wear & Tear | Breakdown | FOLLTEC | 5HP STANDING AC UNIT 3 | HVAC | 2025-02-17 | 31 | 2025-02-17 | 0 |  | 31 | [9 empty] | Overdue
423 | FAULTY CABINET LAMP HOLDER | LAG, IKEJA MALL | Wear & Tear | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-12 | 7 | 2025-02-12 | 0 | 2025-02-13 | 1 | [7 empty] | 2025-02-19 |  | Completed | 2025-02-19 | 1
424 | GENERATOR DUE FOR SERVICING | LAG, ABULE EGBA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-02-17 | 31 | 2025-02-17 | 0 |  | 31 | [9 empty] | Overdue
425 | GENERATOR DUE FOR SERVICING | LAG, IKORODU | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-02-14 | 34 | 2025-02-14 | 0 |  | 34 | [9 empty] | Overdue
426 | REQUEST FOR CABINET BULB | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 102125 | Completed | 2025-02-12 | 1
427 | FAULTY CABINET BULB HOLDER. | LAG, LEKKI PHASE 1 | Wear & Tear |  | KITCHTECH | DISPLAY CABINET |  | 2025-02-06 | 6 | 2025-02-06 | 0 | 2025-02-12 | 6 | 2025-02-12 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-02-12 | 35475 | Completed | 2025-02-12 | 1
428 | FAULTY TUBOR CHARGER. |  | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-02-12 | 36 | 2025-02-12 | 0 | 2025-02-12 | 0 | [9 empty] | Overdue
429 | FAULTY WATER PUMPING MACHINE | KADUNA, AHMADU DELLO WAY | Wear & Tear | Breakdown | OLANIYI OJO | DOSING PUMP | WTP | 2025-02-17 | 31 | 2025-02-17 | 0 |  | 31 | [9 empty] | Overdue
430 | CABINET NOT ATTENDING TEMPREATURE | LAG, ONIRU | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-17 | 31 | 2025-02-17 | 0 |  | 31 | [9 empty] | Overdue
431 | Blocked freezer and cold room drainage | LAG, VGC | Wear & Tear | Breakdown | JOEL | COLD ROOM UNIT | HVAC | 2025-02-17 | 31 | 2025-02-17 | 0 |  | 31 | [9 empty] | Overdue
432 | FAULTY LOBBY INSECTROCUTOR | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | ISMAIL | INSECT KILLER LOBBY 1 | ELECTRICAL | 2025-02-17 | 31 | 2025-02-17 | 0 |  | 31 | [9 empty] | Overdue
433 | CABINET BULBS NOT WORKING PX BADORE. | LAG, BADORE | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-17 | 31 | 2025-02-17 | 0 |  | 31 | [9 empty] | Overdue
434 | SLANT PYLON | LAG, IKORODU | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-02-17 | 31 | 2025-02-17 | 0 | 2025-02-17 | 0 | [9 empty] | Overdue
435 | FAULTY WATER PUMPING MACHINE | KADUNA, AHMADU DELLO WAY | Others | Breakdown | OLANIYI | SUBMERSIBLE PUMP | WTP | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 |  | Completed | 2025-02-17 | 1
436 | PX BADORE FAULT SOCKETS | LAG, BADORE | Electrical Surge | Breakdown | JOEL | OTHERS | OTHERS | 2025-02-12 | 3 | 2025-02-12 | 0 | 2025-02-15 | 3 | 2025-02-15 | 2025-02-15 | 0 | 2025-02-15 | 0 | 2025-02-15 | 0 | 2025-02-15 |  | Completed | 2025-02-15 | 1
437 | Wobbling Table | OGUN, HEYDEN IBAFO | Wear & Tear | Breakdown | MATOLAD | CUSTOMER TABLE | FURNITURE | 2025-02-13 | 35 | 2025-02-13 | 0 | 2025-02-15 | 2 | [9 empty] | Overdue
438 | FAULTY ROLLER SHUTTER | LAG, AWOLOWO | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-02-11 | 37 | 2025-02-12 | 1 | 2025-02-12 | 0 | 2025-02-12 |  | 36 | [6 empty] | Overdue
439 | LEAKING GAS | LAG, BADORE | Wear & Tear | Breakdown | JOEL | GAS HOSE & SUNDRIES | GAS | 2025-02-16 | #VALUE! | 2025-02-16 | 0 | 2025-02-17 | 1 | 2025-02-17 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | #VALUE! | 2025-02-17 |  | Completed | 17/0202025 | 0
440 | TOILET SINK LEAKING | LAG, TEJUOSHO | Users Misuse | Breakdown | OLUWATOSIN | TOILET WASH HAND BASIN | PLUMBING | 2025-02-10 | 7 | 2025-02-10 | 0 | 2025-02-17 | 7 | 2025-02-17 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 | 0 | 2025-02-17 |  | Completed | 2025-02-17 | 1
441 | FALLING WOODEN STRUCTURE | LAG, AJAH | Wear & Tear | Breakdown | ADEBOLA | OTHERS | OTHERS | 2025-02-12 | 36 | 2025-02-12 | 0 | 2025-02-17 | 5 | 2025-03-08 | 2025-03-10 | 2 | 2025-03-10 | 10 |  |  |  |  | Overdue
442 | HAND WASH DISPENSER NOT WORKING | LAG, IKEJA MALL | Users Misuse | Breakdown | PROPEAR | OTHERS | OTHERS | 2025-02-12 | 36 | 2025-02-12 | 0 | 2025-02-12 | 0 | [9 empty] | Overdue
443 | EVACUATION OF SEPTIC TANK | LAG, MAGODO | Others | Breakdown | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 | 0 |  | 337560 | Completed | 2025-02-13 | 0
444 | BAD CABINET STAND AND CABINET LIGHT OUT | LAG, FREEDOMWAY | Others | Breakdown | FULL TURN | OTHERS | OTHERS | 2025-02-17 | 31 | 2025-02-17 | 0 | 2025-02-18 | 1 | 2025-02-18 | 2025-02-18 | 0 | [6 empty] | Overdue
445 | ISSUES SIGHTED DURING OSC | LAG, OMOLE | Others | Breakdown | PROPEARJEFF | OTHERS | OTHERS | 2025-02-19 | 1 | 2025-02-19 | 0 | 2025-02-20 | 1 | 2025-02-20 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 |  | Completed | 2025-02-20 | 1
446 | STIFF ENTRANCE DOOR | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | TAIDAV | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-02-18 | 7 | 2025-02-18 | 0 | 2025-02-25 | 7 | 2025-02-25 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 |  | Completed | 2025-02-25 | 1
447 | CHIPPED WALL TILES EDGES IN BOH | LAG, OGUNLANA DRIVE | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-02-13 | 35 | 2025-02-13 | 0 |  | 35 | [9 empty] | Overdue
448 | Poor lighting in the store | KANO, KATSINA RD | Wear & Tear | Breakdown | THOMPSON | 18W ROUND LIGHT FITTING | ELECTRICAL | 2025-02-20 | 28 | 2025-02-20 | 0 |  | 28 | [9 empty] | Overdue
449 | HIGH CONSUMPTION OF DIESEL | LAG, OMOLE | Corrective Action | Corrective | MIDTECH | GENERATOR | GENERATOR | 2025-02-17 | 31 | 2025-02-18 | 1 | 2025-02-18 | 0 | [9 empty] | Overdue
450 | RUSTY CEILING IN THE COLD ROOM AND FREEZER ROOM | LAG, OGUNLANA DRIVE | Wear & Tear | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2025-02-20 | 28 | 2025-02-20 | 0 | 2025-02-21 | 1 | 2025-03-03 | 2025-03-18 | 15 | [5 empty] | 350000 | Overdue
451 | saggy water treatment roof | LAG, ILUPEJU | Wear & Tear | Breakdown | MATOLAD | ROOF | BUILDING | 2025-02-20 | 28 | 2025-02-20 | 0 |  | 28 | [9 empty] | Overdue
452 | DIESEL MAIN TANK LEAKING AND WASHING | LAG, TEJUOSHO | Others | Breakdown | DAMI FOTE | GENERATOR | GENERATOR | 2025-02-20 | 28 | 2025-02-20 | 0 |  | 28 | [9 empty] | Overdue
453 | HOT WATER NOT ATTAINING TEMPERATURE | LAG, ILUPEJU | Wear & Tear | Breakdown | ADEREMI WAHAB | WATER HEATER | PLUMBING | 2025-02-20 | 28 | 2025-02-20 | 0 |  | 28 | [9 empty] | Overdue
454 | NEPA TEAM VISITED TODAY 20TH 2025 | LAG, AJAH | Wear & Tear | Breakdown |  | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-02-20 | 28 | 2025-02-20 | 0 |  | 28 | [9 empty] | Overdue
455 | RUSTY TAP AND LEAKING PIPE | LAG, OGUNLANA DRIVE | Wear & Tear | Breakdown | TOSIN | TAP | PLUMBING | 2025-02-20 | 5 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-25 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 |  | Completed | 2025-02-25 | 1
456 | FAULTY 6 HEAD FILTRATION MACHINE | LAG, MOBIL OGBA | Wear & Tear | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2025-02-20 | 28 | 2025-02-20 | 0 | 2025-02-21 | 1 | 2025-02-21 | 2025-02-21 | 0 | 2025-02-21 | 27 |  |  |  | 199950 | Overdue
457 | DAILY EQUIPMENT STATUS | PPU Ajah | Others | Breakdown | PRO-EQUIP | TAP | PLUMBING | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-13 | 3 | 2025-02-13 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 | 35 | 2025-02-15 |  | Overdue
458 | DAILY EQUIPMENT STATUS | PPU Ajah | Wear & Tear | Breakdown | BCE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-13 | 3 | 2025-02-13 |  | 35 | [6 empty] | Overdue
459 | Damaged Cumings Generator Wire | SOKOTO, BANK RD | Electrical Surge | Breakdown | MOSES | GENERATOR | GENERATOR | 2025-02-20 | 28 | 2025-02-21 | 1 |  | 27 | [9 empty] | Overdue
460 | LEAKAGE FROM ONE OF THE PUMPING MACHINES | LAG, TEJUOSHO | Wear & Tear | Breakdown | PRO-EQUIP | SUBMERSIBLE PUMP | WTP | 2025-02-16 | 32 | 2025-02-16 | 0 |  | 32 | [9 empty] | Overdue
461 | REQUEST FOR DROP LIGHT, HAND DRYER AND BULBS | LAG, FREEDOMWAY | Wear & Tear | Breakdown | ISMAIL | DROPPING LIGHT | ELECTRICAL | 2025-02-20 | 28 | 2025-02-20 | 0 |  | 28 | [9 empty] | Overdue
462 | FAULTY WARMER | LAG, IKEJA MALL | Wear & Tear | Breakdown | TAIDAV | UPRIGHT WARMER MACHINE | HVAC | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 |  | Completed | 2025-02-20 | 1
463 | FAULTY WARMER | LAG, FREEDOMWAY | Wear & Tear | Breakdown | ISMAIL | UPRIGHT WARMER MACHINE | HVAC | 2025-02-19 | 1 | 2025-02-19 | 0 | 2025-02-20 | 1 | 2025-02-20 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 |  | Completed | 2025-02-20 | 1
464 | BURNT SOCKET | ABUJA, KARU | Electrical Surge | Breakdown | ANDREW | OTHERS | OTHERS | 2025-02-19 | 2 | 2025-02-20 | 1 | 2025-02-21 | 1 | 2025-02-21 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 |  | Completed | 2025-02-21 | 1
465 | FAULTY CHEST FREEZER | ABUJA, KARU | Wear & Tear | Breakdown | DANTEM | CHEST FREEZER | HVAC | 2025-02-19 | 29 | 2025-02-21 | 2 |  | 27 | [9 empty] | Overdue
466 | Installation of 4 Hornet vent | ABUJA, KARU | Others | Breakdown | ANDREW | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2025-02-20 | 28 | 2025-02-21 | 1 |  | 27 | [9 empty] | Overdue
467 | OVER FILLED SEPTIC TANK | ABUJA, DUTSE ALHAJI | Others | Breakdown | JPILLAR | SEPTIC TANK | EVACUATION | 2025-02-19 | 29 | 2025-02-20 | 1 |  | 28 | [9 empty] | Overdue
468 | POWER SURGE | ABUJA, KARU | Electrical Surge | Breakdown | ANDREW | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-02-20 | 1 | 2025-02-21 | 1 | 2025-02-21 | 0 | 2025-02-21 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 |  | Completed | 2025-02-21 | 1
469 | FAULTY OVEN | PPU Ilupeju | Electrical Surge | Breakdown | SAEED | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-02-21 | 27 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 27 | 2025-02-24 |  | Overdue
470 | STATUS UPDATE: NAFDAC GHP INSPECTION AT CR IDI-IROKO | LAG, IDI-IROKO RD | Wear & Tear | Breakdown | MATOLAD | ROOF | BUILDING | 2025-02-20 | 28 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 | 28 | 2025-02-22 |  | Overdue
471 | FAULTY INVERTER | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | DALEMATRIX | INVERTER SYSTEM | INVERTER | 2025-02-19 | 29 | 2025-02-19 | 0 | 2025-02-20 | 1 | [9 empty] | Overdue
472 | BAD EXTRATOR BLEND | LAG, FESTAC | Wear & Tear | Breakdown | ABBEY | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2025-02-18 | 30 | 2025-02-18 | 0 | 2025-02-19 | 1 | 2025-02-19 | 2025-02-21 | 2 | 2025-02-21 | 6 | 2025-02-27 | 21 |  | 905000 | Overdue
473 | PEST CONTROL-ROACHES AND RODENTS IN THE STORE | LAG, MARINA | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-02-21 | 7 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 7 | 2025-02-28 | 170000 | Completed | 2025-02-28 | 1
474 | OPEN BODY OF KIOSK - EXTERIOR IMAGE CONCERN (REMINDER) | LAG, OBA AKRAN | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-02-21 | 27 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 2025-02-21 | 0 | 2025-02-21 | 27 |  |  |  |  | Overdue
475 | GENERATOR DUE FOR SERVICE | LAG, FESTAC | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-02-21 | 27 | 2025-02-21 | 0 |  | 27 | [9 empty] | Overdue
476 | REPLACEMENT OF BROKEN TILES | PPU Ilupeju | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-02-19 | 29 | 2025-02-19 | 0 | 2025-02-19 | 0 | 2025-02-19 | 2025-02-21 | 2 | [6 empty] | Overdue
477 | FAULTY COLD ROOM | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-02-05 | 43 | 2025-02-05 | 0 |  | 43 | [9 empty] | Overdue
478 | NO WATER IN THE STORE | LAG, AGUNGI | Electrical Surge | Breakdown | JOEL | TAP | PLUMBING | 2025-02-21 | 27 | 2025-02-21 | 0 |  | 27 | [9 empty] | Overdue
479 | BURNT WARMER SOCKET | LAG, AGUNGI | Wear & Tear | Breakdown | ADEREMI KAZEEM | UPRIGHT WARMER MACHINE | HVAC | 2025-02-21 | 27 | 2025-02-21 | 0 |  | 27 | [9 empty] | Overdue
480 | FAULTY RESTROOM AND DRY STORE AC | LAG, MARINA | Wear & Tear | Breakdown | TAYO | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-21 | 27 | 2025-02-21 | 0 |  | 27 | [9 empty] | Overdue
481 | RUSTY CEILING IN THE COLD ROOM AND FREEZER ROOM | LAG, OGUNLANA DRIVE | Wear & Tear | Breakdown | WESTERN DESIGN | PAINTING | BUILDING | 2025-02-20 | 28 | 2025-02-20 | 0 | 2025-02-21 | 1 | [9 empty] | Overdue
482 | REQUEST FOR PYLON WASHING. | LAG, IDIMU | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-02-11 | 37 | 2025-02-13 | 2 | 2025-02-13 | 0 | 2025-02-13 | 2025-02-21 | 8 | [6 empty] | Overdue
483 | Re: Poor Ambience: Faulty AC (36856) | BENUE, OLD OTUKPO | Routine Servicing | Preventive |  | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-24 | 2 | 2025-02-24 | 0 | 2025-02-26 | 2 | 2025-02-26 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 |  | Completed | 2025-02-26 | 1
484 | GAS LEAKAGE IN THE STORE | LAG, DOMINO E-CENTRE | Corrective Action | Corrective | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-02-26 | 22 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 | 2025-02-28 | 2 | 2025-02-28 | 20 |  |  |  | 250000 | Overdue
485 | NO LIGHT CURRENTLY IN THE STORE DUE TO BURNT INVERTER AND BYPASS CHANGE OVER | LAG, OSOLOWAY | Electrical Surge | Breakdown | KOLA | OTHERS | OTHERS | 2025-02-28 | 20 | 2025-02-28 | 0 |  | 20 | [9 empty] | Overdue
486 | CHNAGING ROOM LIGHT | LAG, NNPC ALAPERE | Electrical Surge | Breakdown | KOLA | OTHERS | OTHERS | 2025-02-26 | 22 | 2025-02-26 | 0 | 2025-02-26 | 0 | [9 empty] | Overdue
487 | COLD ROOM EVAPORATOR | LAG, JIBOWU | Routine Servicing | Preventive | DYNAMITE | COLD ROOM UNIT | HVAC | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-10 | 7 | 2025-02-10 | 18 | 2025-02-28 | 20 |  | 1150000 | Overdue
488 | FAULTY CHIPS FRYER MACHINE | LAG, AJAH | Wear & Tear | Breakdown | JOEL | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 |  | Completed | 2025-02-27 | 1
489 | INACCURATE METER READING |  | Corrective Action | Corrective | BOYEHTECH | OTHERS | OTHERS | 2025-02-17 | 31 | 2025-02-18 | 1 | 2025-02-18 | 0 | 2025-02-24 | 2025-02-28 | 4 | 2025-02-28 | 20 |  |  |  | 1250000 | Overdue
490 | Broken pipes in cold and freezer room leading to ice formation on floor | LAG, OSOLOWAY | Wear & Tear | Breakdown | OLUWATOSIN | OTHERS | OTHERS | 2025-02-05 | 5 | 2025-02-06 | 1 | 2025-02-06 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 38 |  |  | 2025-02-10 |  | Completed | 2025-02-10 | 1
491 | REQUEST FOR DROP LIGHT, HAND DRYER AND BULBS | LAG, FREEDOMWAY | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-02-20 | 28 | 2025-02-20 | 0 | 2025-02-28 | 8 | [9 empty] | Overdue
492 | AC SERVICING | ABUJA, KARU | Routine Servicing | Preventive | DANTEM | OTHERS | OTHERS | 2025-02-26 | 3 | 2025-02-27 | 1 | 2025-02-27 | 0 | 2025-03-01 | 2025-03-01 | 0 | 2025-03-01 | 0 | 2025-03-01 | 0 | 2025-03-01 | 48375 | Completed | 2025-03-01 | 1
493 | AC SERVICING | LAG, MMA2 | Routine Servicing | Preventive | ADEGBENRO | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-13 | 35 | 2025-02-13 | 0 |  | 35 | [9 empty] | Overdue
494 | FAULTY PUSH BUTTON AND CRACKED FLOOR | LAG, GBAGADA | Wear & Tear | Breakdown | THIO | OTHERS | OTHERS | 2025-02-11 | 37 | 2025-02-11 | 0 | 2025-02-11 | 0 | [9 empty] | Overdue
495 | REPAINTING OF CASHIER COUNTER | LAG, GBAGADA | Wear & Tear | Breakdown | MATOLAD | CASHIER COUNTER | BUILDING | 2025-02-27 | 21 | 2025-03-01 | 2 | 2025-03-01 | 0 | [9 empty] | Overdue
496 | FAULTY COLDROOM FAN | LAG, ONIRU | Wear & Tear | Breakdown | TONAOGUNS | COLD ROOM UNIT | HVAC | 2025-02-19 | 3 | 2025-02-19 | 0 | 2025-02-19 | 0 | 2025-02-22 | 2025-02-22 | 0 |  |  |  |  | 2025-02-22 | 126500 | Completed | 2025-02-22 | 1
497 | OPEBI EXTRACTOR NOT WORKING | LAG, OPEBI | Wear & Tear | Breakdown | FRIDAY | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2025-02-26 | 22 | 2025-02-27 | 1 | 2025-03-01 | 2 | 2025-03-03 | 2025-03-03 | 0 | 2025-03-03 | 0 | 2025-03-03 | 17 |  | 315000 | Overdue
498 | OFFICE AC NON FUNCTIONAL | LAG, ENTOURAGE MALL | Routine Servicing | Preventive | TONAOGUNS | 5HP STANDING AC UNIT 3 | HVAC | 2025-02-17 | 17 | 2025-02-17 | 0 | 2025-03-01 | 12 | [7 empty] | 2025-03-06 |  | Completed | 2025-03-06 | 1
499 | REPOSITIONING OF AC | LAG, ETERNA LEKKI | Corrective Action | Corrective | TONAOGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-28 | 20 | 2025-02-28 | 0 | 2025-03-01 | 1 | [9 empty] | Overdue
500 | Magodo Hcw5 pack control table attachment | LAG, MAGODO | Others | Breakdown | LAMBTECH | OTHERS | OTHERS | 2025-02-26 | 22 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 | 2025-02-28 | 2 | 2025-02-28 | 0 | 2025-02-28 | 20 |  |  | Overdue
501 | BOH OF EXTRACTOR NOT WORKING PROPERLY | LAG, MARINA | Wear & Tear | Breakdown | SEASON BENDAN | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2025-02-21 | 27 | 2025-02-21 | 0 |  | 27 | [9 empty] | Overdue
502 | FALLING CEILLING AND WATER HEATER | LAG, OBA AKRAN | Wear & Tear | Breakdown | MATOLAD | CEILING BOARD | BUILDING | 2025-02-24 | 24 | 2025-02-24 | 0 |  | 24 | [9 empty] | Overdue
503 | ISSUE WITH THE GENERATOR SET BROUGHT TO CR MOBIL OGBA | LAG, MOBIL OGBA | Wear & Tear | Breakdown | DELIGHTSOME | GENERATOR | GENERATOR | 2025-02-28 | 20 | 2025-02-28 | 0 |  | 20 | [9 empty] | Overdue
504 | FAULTY EXTRACTOR | LAG, GBAGADA | Wear & Tear | Breakdown | ABBEY | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2025-02-14 | 34 | 2025-02-14 | 0 | 2025-02-17 | 3 | 2025-02-17 | 2025-02-17 | 0 | 2025-02-17 | 8 | 2025-02-25 | 23 |  | 215000 | Overdue
505 | FAULTY UNDER BAR FRIDGE FOR BACK OF HOUSE | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | G.B BOYEJO | NBC CHILLER | HVAC | 2025-02-22 | 26 | 2025-02-22 | 0 |  | 26 | [9 empty] | Overdue
506 | SEWAGE EVACUATION. | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 | 0 | 2025-02-20 |  | Completed | 2025-02-20 | 1
507 | SEWAGE EVACUATION. | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 |  | Completed | 2025-02-25 | 1
508 | SEWAGE EVACUATION | LAG, OKE-AFA | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2025-02-21 | 1 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 1 | 2025-02-22 |  | Completed | 2025-02-22 | 1
509 | SEWAGE EVACUATION | LAG, FREEDOMWAY | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-02-27 | 1 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 1 | 2025-02-28 |  | Completed | 2025-02-28 | 1
510 | EXPOSED NAKED WIRE IN THE STORE | LAG, FESTAC | Wear & Tear | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-02-25 | 2 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 2 | 2025-02-27 |  | Completed | 2025-02-27 | 1
511 | BURNT LAMP HOLDERS AND DEAD BULBS | LAG, MMA2 | Wear & Tear | Breakdown | TIMILEHIN | 18W ROUND LIGHT FITTING | ELECTRICAL | 2025-02-23 | 4 | 2025-02-23 | 0 | 2025-02-26 | 3 | 2025-02-26 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 | 1 | 2025-02-27 |  | Completed | 2025-02-27 | 1
512 | LOBBY ACS NOT WORKING | LAG, MARINA | Wear & Tear | Breakdown | FOLLTEC | 5HP STANDING AC UNIT 2 | HVAC | 2025-02-28 | 20 | 2025-02-28 | 0 | 2025-02-28 | 0 | [9 empty] | Overdue
513 | REQUEST FOR A NEW INVERTER | KADUNA, AHMADU DELLO WAY | Others | Breakdown | OLANIYI | INVERTER SYSTEM | INVERTER | 2025-02-27 | 6 | 2025-02-27 | 0 | 2025-03-05 | 6 | 2025-03-05 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 |  | Completed | 2025-03-05 | 1
514 | DISPLAY CABINET NOT ATTAINING TEMPERATURE | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-24 | 3 | 2025-02-24 | 0 | 2025-02-27 | 3 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 |  | Completed | 2025-02-27 | 1
515 | GAS LEAKAGE AND BURNER SERVICING | LAG, EKORO | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-02-22 | 26 | 2025-02-22 | 0 | 2025-02-22 | 0 | 2025-02-22 | 2025-02-22 | 0 | 2025-02-22 | 1 | 2025-02-23 | 25 | 2025-02-25 | 85250 | Overdue
516 | GAS LEAKAGE AND BURNER SERVICING | LAG, EKORO | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-02-25 | 23 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 2025-02-27 | 2 | 2025-02-27 | 1 | 2025-02-28 | 20 |  | 95000 | Overdue
517 | MACHINE NOT ATTAININIG TEMPERATURE | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 |  | 21 | [9 empty] | Overdue
518 | Servicing of gas burners and replacement of worn out hoses | LAG, OSOLOWAY | Routine Servicing | Preventive | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-02-28 | 20 | 2025-02-28 | 0 | 2025-02-28 | 0 | 2025-02-28 | 2025-02-28 | 0 | 2025-02-28 | 0 | 2025-02-28 | 20 | 2025-03-03 |  | Overdue
519 | HIGH BURNER FOR CR STORES ( CARRIBEAN RICE) | LAG, OKE-AFA | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 21 |  | 54000 | Overdue
520 | HIGH BURNER FOR CR STORES ( CARRIBEAN RICE) | LAG, IRE-AKARI | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 21 |  | 54000 | Overdue
521 | HIGH BURNER FOR CR STORES ( CARRIBEAN RICE) | LAG, FESTAC | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 21 |  | 54000 | Overdue
522 | HIGH BURNER FOR CR STORES ( CARRIBEAN RICE) | LAG, OSOLOWAY | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 21 |  | 54000 | Overdue
523 | HIGH BURNER FOR CR STORES ( CARRIBEAN RICE) | LAG, FREEDOMWAY | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 21 |  | 54000 | Overdue
524 | HIGH BURNER FOR CR STORES ( CARRIBEAN RICE) | LAG, AJAH | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 21 |  | 54000 | Overdue
525 | HIGH BURNER FOR CR STORES ( CARRIBEAN RICE) | LAG, SKYMALL | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 21 |  | 54000 | Overdue
526 | HIGH BURNER FOR CR STORES ( CARRIBEAN RICE) | LAG, VGC | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 21 |  | 54000 | Overdue
527 | HIGH BURNER FOR CR STORES ( CARRIBEAN RICE) | LAG, BADORE | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 21 |  | 54000 | Overdue
528 | HIGH BURNER FOR CR STORES ( CARRIBEAN RICE) | LAG, AGUNGI | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 21 |  | 54000 | Overdue
529 | HIGH BURNER FOR CR STORES ( CARRIBEAN RICE) | LAG, TOTAL LEKKI | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 21 |  | 54000 | Overdue
530 | HIGH BURNER FOR CR STORES ( CARRIBEAN RICE) | LAG, ETERNA LEKKI | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 21 |  | 54000 | Overdue
531 | HIGH BURNER FOR CR STORES ( CARRIBEAN RICE) | LAG, MARINA | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 21 |  | 54000 | Overdue
532 | HIGH BURNER FOR CR STORES ( CARRIBEAN RICE) | LAG, AWOLOWO 2 | Others | Breakdown | BERRADE | COOKING BURNER | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 21 |  | 54000 | Overdue
533 | FAULTY BOH UPRIGHT CHILLER | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2025-02-27 | 21 | 2025-02-27 | 0 |  | 21 | [9 empty] | Overdue
534 | ISSUES SIGHTED DURING OSC | LAG, TEJUOSHO | Wear & Tear | Breakdown | ACORN | OTHERS | OTHERS | 2025-02-27 | 21 | 2025-02-27 | 0 |  | 21 | [9 empty] | Overdue
535 | ISSUES SIGHTED DURING OSC | LAG, DOMINO E-CENTRE | Others | Breakdown | ARIZMANYA | OTHERS | OTHERS | 2025-02-27 | 21 | 2025-02-27 | 0 |  | 21 | [9 empty] | Overdue
536 | ISSUES SIGHTED DURING OSC | LAG, DOMINO E-CENTRE | Others | Breakdown | ARIZMANYA | OTHERS | OTHERS | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-03-27 | 28 | [9 empty] | Overdue
537 | ISSUES SIGHTED DURING OSC | LAG, DOMINO E-CENTRE | Others | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-02-27 | 21 | 2025-02-27 | 0 |  | 21 | [9 empty] | Overdue
538 | ISSUES SIGHTED DURING OSC | LAG, DOMINO E-CENTRE | Others | Breakdown | MATOLAD | CUSTOMER TABLE | FURNITURE | 2025-02-27 | 21 | 2025-02-27 | 0 |  | 21 | [9 empty] | Overdue
539 | FAULTY HAND DRYER IN CUSTOMER REST ROOM | BENUE, OLD OTUKPO | Others | Breakdown |  | HAND DRYER TOILET | ELECTRICAL | 2025-02-27 | 21 | 2025-02-27 | 0 |  | 21 | [9 empty] | Overdue
540 | FREEZER ROOM NOT WORKING | LAG, IKEJA MALL | Routine Servicing | Preventive | TONAOGUN | FREEZER ROOM | HVAC | 2025-02-26 | 1 | 2025-02-26 | 0 | 2025-02-27 | 1 | [7 empty] | 2025-02-27 |  | Completed | 2025-02-27 | 1
541 | GENERATOR SERVICING. | ABUJA, MPAPE | Routine Servicing | Preventive | CONCIRCLE | GENERATOR | GENERATOR | 2025-02-28 | 6 | 2025-02-28 | 0 | 2025-03-01 | 1 | 2025-03-06 | 2025-03-06 | 0 | 2025-03-06 | 0 | 2025-03-06 | 0 | 2025-03-06 |  | Completed | 2025-03-06 | 1
542 | ENGINE OIL REQUEST | LAG, OGUNLANA DRIVE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-02-22 | 26 | 2025-02-22 | 0 | 2025-02-22 | 0 | [9 empty] | Overdue
543 | BROKEN WC FOR MALE CHANGING ROOM | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | PROEQUIP | OTHERS | OTHERS | 2025-02-25 | 23 | 2025-02-25 | 0 |  | 23 | [9 empty] | Overdue
544 | FAULTY BULB | LAG, AJOSE ADEOGUN | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-02-23 | 4 | 2025-02-23 | 0 | 2025-02-27 | 4 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 |  | Completed | 2025-02-27 | 1
545 | FAULTY B.O.H SOCKETS. | LAG, LEKKI PHASE 1 | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-02-26 | 22 | 2025-02-26 | 0 | 2025-02-27 | 1 | [9 empty] | Overdue
546 | KITCHEN UNDER BAR-CHILLER DRIPPING OUT WATER | LAG, TOTAL LEKKI | Corrective Action | Corrective | BCE | NBC CHILLER | HVAC | 2025-02-24 | 24 | 2025-02-24 | 0 | 2025-02-27 | 3 | [9 empty] | Overdue
547 | SERVICING OF ACs & LEAKAGE | KADUNA, AHMADU DELLO WAY | Routine Servicing | Preventive | DANTEM | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-22 | 26 | 2025-02-22 | 0 |  | 26 | [9 empty] | Overdue
548 | Dutse: OVER FILLED SEPTIC TANK (Urgent attention ( |  | Corrective Action | Corrective | JPILLAR | SEPTIC TANK | EVACUATION | 2025-02-19 | 7 | 2025-02-19 | 0 | 2025-02-26 | 7 | 2025-02-26 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 |  | Completed | 2025-02-26 | 1
549 | FAULTY KETTLE |  | Wear & Tear | Breakdown | MOSES | OTHERS | OTHERS | 2025-02-26 | 1 | 2025-02-26 | 0 | 2025-02-27 | 1 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 |  | Completed | 2025-02-27 | 1
550 | SERVICING OF ACs & LEAKAGE | PPU Kaduna | Routine Servicing | Preventive | NGUTANNI | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-22 | 26 | 2025-02-22 | 0 | 2025-02-25 | 3 | [9 empty] | Overdue
551 | BLOCK SEWAGE CHAMBER. | LAG, ALIMOSHO | Corrective Action | Corrective | PENTECOSTAL | SEPTIC TANK | EVACUATION | 2025-02-26 | 22 | 2025-02-26 | 0 | 2025-02-27 | 1 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 21 |  |  |  | 83025 | Overdue
552 | FAT TRAP BASKET WITHOUT HANDLE | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | ZEBRA | GREASE TRAP | GREASE_TRAP | 2025-02-24 | 24 | 2025-02-24 | 0 | 2025-02-27 | 3 | [9 empty] | Overdue
553 | LEAKING PIPE | LAG, BADORE | Wear & Tear | Breakdown | JOEL | OTHERS | OTHERS | 2025-02-25 | 2 | 2025-02-25 | 0 | 2025-02-27 | 2 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 |  | Completed | 2025-02-27 | 1
554 | LEAKING PIPE FROM MALE REST ROOM | LAG, IKOTUN | Wear & Tear | Breakdown | OLUWATOSIN | OTHERS | OTHERS | 2025-02-17 | 1 | 2025-02-17 | 0 | 2025-02-18 | 1 | 2025-02-18 | 2025-02-18 | 0 | 2025-02-18 | 0 | 2025-02-18 | 0 | 2025-02-18 |  | Completed | 2025-02-18 | 1
555 | FEMALE NOT FLUSHING | LAG, BADORE | Wear & Tear | Breakdown | JOEL | OTHERS | OTHERS | 2025-02-25 | 2 | 2025-02-25 | 0 | 2025-02-27 | 2 | 2025-02-27 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 | 0 | 2025-02-27 |  | Completed | 2025-02-27 | 1
556 | FAULTY RATIONAL MACHINE | LAG, ILUPEJU | Routine Servicing | Preventive | BERRADE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2025-02-24 | 24 | 2025-02-24 | 0 | 2025-02-26 | 2 | 2025-02-26 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 | 22 | 2025-02-26 | 340000 | Overdue
557 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, LEKKI PHASE 1 | Routine Servicing | Preventive | TONAOGUNS | COLD ROOM UNIT | HVAC | 2025-02-23 | 25 | 2025-02-23 | 0 | 2025-02-23 | 0 | 2025-02-24 |  | 24 | [6 empty] | Overdue
558 | LEAKAGE IN BOTH FEMALE AND MALE CUSTOMER'S RESTROOM | LAG, MARINA | Corrective Action | Corrective | JOEL | OTHERS | OTHERS | 2025-02-22 | 2 | 2025-02-22 | 0 | 2025-02-24 | 2 | 2025-02-24 | 2025-02-24 | 0 | 2025-02-24 | 0 | 2025-02-24 | 0 | 2025-02-24 |  | Completed | 2025-02-24 | 1
559 | FAULTY DRAINAGE PUMP | LAG, AWOLOWO 2 | Corrective Action | Corrective | JOEL | OTHERS | OTHERS | 2025-02-25 | 1 | 2025-02-25 | 0 | 2025-02-26 | 1 | 2025-02-26 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 |  | Completed | 2025-02-26 | 1
560 | FAULTY SEWAGE PUMP | LAG, AWOLOWO | Corrective Action | Corrective | JOEL | OTHERS | OTHERS | 2025-02-22 | 4 | 2025-02-23 | 1 | 2025-02-26 | 3 | 2025-02-26 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 |  | Completed | 2025-02-26 | 1
561 | FAULTY INSECTICUTOR | LAG, IDIMU | Electrical Surge | Breakdown | FRIDAY | INSECT KILLER BOH | ELECTRICAL | 2025-02-24 | 2 | 2025-02-24 | 0 | 2025-02-24 | 0 | 2025-02-26 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 |  | Completed | 2025-02-26 | 1
562 | REQUEST FOR INSECTICUTOR FITTINGS | LAG, IDIMU | Wear & Tear | Breakdown | FRIDAY | OTHERS | OTHERS | 2025-02-24 | 2 | 2025-02-24 | 0 | 2025-02-24 | 0 | 2025-02-26 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 |  | Completed | 2025-02-26 | 1
563 | BROKEN DOWN CABINT GLASS | LAG, FESTAC | Wear & Tear | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-25 | 1 | 2025-02-25 | 0 | 2025-02-26 | 1 | 2025-02-26 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 | 0 | 2025-02-26 |  | Completed | 2025-02-26 | 1
564 | FAULTY GENERATOR - FAN BELTS REPLACED ON YOUR 200KVA AT CR-AGUNGI, AGUNGI-AJAH ROAD, LEKKI-EPE EXPRESS WAY, LAGOS. | LAG, AGUNGI | Others | Breakdown | KB | GENERATOR | GENERATOR | 2025-02-22 | 26 | 2025-02-22 | 0 | 2025-02-24 | 2 | 2025-02-25 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 23 |  | 290250 | Overdue
565 | FAULTY GENERATOR - FAN BELTS REPLACED ON YOUR 200KVA AT CR-AGUNGI, AGUNGI-AJAH ROAD, LEKKI-EPE EXPRESS WAY, LAGOS. | LAG, AGUNGI | Corrective Action | Corrective | KB | GENERATOR | GENERATOR | 2025-02-22 | 26 | 2025-02-22 | 0 | 2025-02-24 | 2 | 2025-02-24 | 2025-02-24 | 0 | 2025-02-24 | 0 | 2025-02-24 | 24 |  | 258000 | Overdue
566 | LEAKAGE UNDER FRYER AND COOK SINK | LAG, FESTAC | Wear & Tear | Breakdown | OLUWATOSIN | OTHERS | OTHERS | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 |  | Completed | 2025-02-25 | 1
567 | COOK AND FRYER TAP WATER NOT ATTAINING TEMPERATURE | LAG, ETERNA LEKKI | Corrective Action | Corrective | JOEL | OTHERS | OTHERS | 2025-02-22 | 3 | 2025-02-22 | 0 | 2025-02-25 | 3 | 2025-02-25 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 |  | Completed | 2025-02-25 | 1
568 | FAULTY CONNECTING PIPE IN FEMALE CUSTOMER REST ROOM | LAG, AGUNGI | Corrective Action | Corrective | JOEL | OTHERS | OTHERS | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 |  | Completed | 2025-02-25 | 1
569 | Faulty Back of House Tap | OGUN, HEYDEN IBAFO | Corrective Action | Corrective | MOSES | TAP | PLUMBING | 2025-02-04 | 21 | 2025-02-04 | 0 | 2025-02-25 | 21 | 2025-02-25 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 |  | Completed | 2025-02-25 | 1
570 | FOH AND BOH BLACKOUT | LAG, AWOLOWO | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 |  | Completed | 2025-02-25 | 1
571 | CR ONIRU MAINTAINANCE ISSUE | LAG, ONIRU | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-02-03 | 45 | 2025-02-03 | 0 | 2025-02-11 | 8 | [9 empty] | Overdue
572 | CR ONIRU MAINTAINANCE ISSUE | LAG, ONIRU | Wear & Tear | Breakdown | PROEQUIP | AERATION TANK | WTP | 2025-02-13 | 35 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 | 2025-02-25 | 12 | 2025-02-25 | 23 |  |  |  |  | Overdue
573 | FAULTY ROTISSERIE MACHINE | LAG, AGUNGI | Wear & Tear | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2025-02-16 | 32 | 2025-02-16 | 0 | 2025-02-20 | 4 | 2025-02-20 | 2025-02-20 | 0 | 2025-02-20 | 5 | 2025-02-25 | 23 | 2025-02-25 | 406350 | Overdue
574 | PX OGUDU MAINTENANCE. | LAG, OGUDU | Wear & Tear | Breakdown | KITCHTEC | OTHERS | OTHERS | 2025-02-11 | 14 | 2025-02-11 | 0 | 2025-02-25 | 14 | 2025-02-25 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 |  | Completed | 2025-02-25 | 1
575 | MINOR MAINTENANCE | LAG, MOBIL OGBA | Others | Breakdown | MOSES | OTHERS | OTHERS | 2025-02-24 | 1 | 2025-02-24 | 0 | 2025-02-25 | 1 |  | 2025-02-25 | 45713 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 |  | Completed | 2025-02-25 | 1
576 | FAULTU INSECT KILLER(EXPOSED WIRE,OPEN SOCKETS) | LAG, AJOSE ADEOGUN | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-02-24 | 1 | 2025-02-24 | 0 | 2025-02-25 | 1 |  | 2025-02-25 | 45713 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 |  | Completed | 2025-02-25 | 1
577 | FAULTY SOCKET FOR DRYSTORE A/C | LAG, AJOSE ADEOGUN | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-02-23 | 2 | 2025-02-23 | 0 | 2025-02-25 | 2 |  | 2025-02-25 | 45713 | 2025-02-25 | 0 | 2025-02-25 | 0 | 2025-02-25 |  | Completed | 2025-02-25 | 1
578 | FAULTY WC HANDLE | LAG, ILUPEJU | Wear & Tear | Breakdown | PROPEAR | OTHERS | OTHERS | 2025-02-21 | 9 | 2025-02-21 | 0 | 2025-03-02 | 9 | 2025-03-02 | 2025-03-02 | 0 | 2025-03-02 | 0 | 2025-03-02 | 0 | 2025-03-02 |  | Completed | 2025-03-02 | 1
579 | BAD CEILING SHEETS | LAG, IKEJA MALL | Wear & Tear | Breakdown | MATOLAD | CEILING BOARD | BUILDING | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-22 | 12 | 2025-02-24 | 2025-02-24 | 0 | 2025-02-24 | 1 | 2025-02-25 | 23 |  | 145000 | Overdue
580 | FAULTY CABINET BULB AND CABINET CALIBRATOR | LAG, ONIRU | Electrical Surge | Breakdown | KITCHTEC | OTHERS | OTHERS | 2025-02-04 | 14 | 2025-02-04 | 0 | 2025-02-18 | 14 | 2025-02-18 | 2025-02-18 | 0 | 2025-02-18 | 0 | 2025-02-18 | 0 | 2025-02-18 |  | Completed | 2025-02-18 | 1
581 | INEFFECTIVE GREASE TREAP | LAG, ONIRU | Corrective Action | Corrective | ZEBRA | GREASE TRAP | GREASE_TRAP | 2025-02-18 | 30 | 2025-02-18 | 0 | 2025-02-24 | 6 | 2025-03-07 | 2025-03-14 | 7 | 2025-03-14 | 1 | 2025-03-15 | 5 |  | 330000 | Overdue
582 | freezer room not attaining temperature | KANO, KATSINA RD | Routine Servicing | Preventive | AKINTOLA | FREEZER ROOM | HVAC | 2025-02-22 | 1 | 2025-02-22 | 0 | 2025-02-23 | 1 | 2025-02-23 | 2025-02-23 | 0 | 2025-02-23 | 0 | 2025-02-23 | 0 | 2025-02-23 |  | Completed | 2025-02-23 | 1
583 | CUSTOMER MALE RESTROOM NOT FLUSHING/MALE URINAL | LAG, AWOLOWO | Corrective Action | Corrective | JOEL | OTHERS | OTHERS | 2025-02-24 | 0 | 2025-02-24 | 0 | 2025-02-24 | 0 | 2025-02-24 | 2025-02-24 | 0 | 2025-02-24 | 0 | 2025-02-24 | 0 | 2025-02-24 |  | Completed | 2025-02-24 | 1
584 | WC IN STAFF AREA WITH DETACHED COVER | LAG, AWOLOWO | Corrective Action | Corrective | JOEL | OTHERS | OTHERS | 2025-02-19 | 5 | 2025-02-19 | 0 | 2025-02-24 | 5 | 2025-02-24 | 2025-02-24 | 0 | 2025-02-24 | 0 | 2025-02-24 | 0 | 2025-02-24 |  | Completed | 2025-02-24 | 1
585 | TORN WARMER AND FLAME GRILLED MACHINE GASKETS | LAG, MAGODO | Corrective Action | Corrective | BCE | OTHERS | OTHERS | 2025-02-18 | 30 | 2025-02-18 | 0 | 2025-02-20 | 2 | 2025-02-20 | 2025-02-20 | 0 | 2025-02-20 | 4 | 2025-02-24 | 24 |  |  | Overdue
586 | FAULTY AIR COONDITION IN THE DRY STORE | KADUNA, AHMADU DELLO WAY | Wear & Tear | Breakdown | NGUTAN | 5HP STANDING AC UNIT 1 | HVAC | 2025-02-25 | 23 | 2025-02-25 | 0 |  | 23 | [9 empty] | Overdue
587 | REPLACEMENT OF PHCN METER | LAG, AJAH | Wear & Tear | Breakdown | BONDGATE | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-02-12 | 36 | 2025-02-12 | 0 | 2025-02-18 | 6 | 2025-02-19 | 2025-02-19 | 0 | 2025-02-19 | 0 | 2025-02-19 | 29 |  |  | Overdue
588 | NOTICE OF TEMPORARY STORE CLOSURE-CR KACHIA RAOD | KADUNA, KACHIA RD | Wear & Tear | Breakdown | CONCIRCLE | GENERATOR | GENERATOR | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-03-05 | 6 | 2025-03-06 | 2025-03-11 | 5 | 2025-03-11 | 9 |  |  |  |  | Overdue
589 | TEMPORAL STORE CLOSURE- CR KEFFI | NASSARAWA, KEFFI | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-02-23 | 13 | 2025-02-23 | 0 | 2025-02-24 | 1 | 2025-03-08 | 2025-03-08 | 0 | 2025-03-08 | 0 | 2025-03-08 | 0 | 2025-03-08 | 5972500 | Completed | 2025-03-08 | 1
590 | REQUEST FOR REPAINTING OF CK's SPICE MIXER | LAG, ILUPEJU | Wear & Tear | Breakdown | GENEROUS | PAINTING | BUILDING | 2025-02-25 | 23 | 2025-02-25 | 0 | 2025-03-05 | 8 | 2025-03-05 |  | 15 | [6 empty] | Overdue
591 | FAULTY FAN | LAG, FESTAC | Electrical Surge | Breakdown | TIMILEHIN | WALL FAN | HVAC | 2025-02-28 | 13 | 2025-02-28 | 0 | 2025-03-03 | 3 | 2025-03-13 |  | 7 | 2025-03-13 | 0 | 2025-03-13 | 0 | 2025-03-13 |  | Completed | 2025-03-13 | 1
592 | LOBBY TELEVISION NOT SHOWING | LAG, IDI-IROKO RD | Corrective Action | Corrective | ACORN | TELEVISION | AUDIOVISUAL | 2025-02-22 | 26 | 2025-02-22 | 0 | 2025-02-24 | 2 | 2025-02-26 | 2025-02-27 | 1 | 2025-02-28 | 7 | 2025-03-07 | 13 |  | 500000 | Overdue
593 | ROLLER SHUTTER NOT ROLLING UP |  | Corrective Action | Corrective | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-02-27 | 6 | 2025-02-27 | 0 | 2025-03-05 | 6 | 2025-03-05 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 |  | Completed | 2025-03-05 | 1
594 | COLDROOM EVAPORARING FAN RUSTING |  | Routine Servicing | Preventive | ECS | COLD ROOM UNIT | HVAC | 2025-02-27 | 21 | 2025-02-27 | 0 | 2025-03-07 | 8 | [9 empty] | Overdue
595 | CRITICAL FOOD SAFETY; FAULLTY BURGER FRIDGE. | KADUNA, AHMADU DELLO WAY | Routine Servicing | Preventive | OLANIYI | OTHERS | OTHERS | 2025-02-25 | 8 | 2025-02-28 | 3 | 2025-03-05 | 5 | 2025-03-05 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 |  | Completed | 2025-03-05 | 1
596 | ROLLER SHUTTER NOT WORKING | LAG, ALIMOSHO | Corrective Action | Corrective | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-02-05 | 13 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-02-10 | 2025-02-10 | 0 | 2025-02-10 | 0 | 2025-02-10 | 8 | 2025-02-18 | 94375.48 | Completed | 2025-02-18 | 1
597 | UNDERBAR CHILLER NOT ATTAINING TEMPERATURE | ABUJA, AMINU KANO | Wear & Tear | Breakdown | DANTEM | NBC CHILLER | HVAC | 2025-03-13 | 7 | 2025-03-19 | 6 |  | 1 | [9 empty] | Overdue
598 | FAULTY WARMER HANDLE | LAG, OMOLE | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-02-07 | 38 | 2025-02-08 | 1 | 2025-02-13 | 5 | 2025-02-13 | 2025-02-13 | 0 | 2025-02-13 | 0 | 2025-02-13 | 32 | 2025-02-23 |  | Completed | 2025-03-17 | 0
599 | FAULTY DRY STORE DOOR,CUSTOMER RESTROOM DOOR,STAFF EATING ROOM DOOR AND OFFICE DOOR. | LAG, AJAH | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-02-23 | 25 | 2025-02-23 | 0 | 2025-03-11 | 16 | 2025-03-13 | 2025-03-14 | 1 | 2025-03-14 | 0 | 2025-03-14 | 6 |  | 450000 | Overdue
600 | FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, BADORE | Routine Servicing | Preventive | TONAOGUNS | FREEZER ROOM | HVAC | 2025-02-16 | 32 | 2025-02-16 | 0 | 2025-03-07 | 19 | 2025-03-07 | 2025-03-07 | 0 | 2025-03-07 | 4 | 2025-03-11 | 9 |  | 165125 | Overdue
601 | NO WATER IN THE STORE | LAG, AGUNGI | Electrical Surge | Breakdown | JOEL | WATER TREATMENT PLANT BLD | BUILDING | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 |  | Completed | 2025-02-21 | 1
602 | FAULTY HAND DRYER | LAG, IKORODU | Wear & Tear | Breakdown | PROPEAR | HAND DRYER LOBBY | ELECTRICAL | 2025-02-10 | 38 | 2025-02-10 | 0 | 2025-02-10 | 0 | [9 empty] | Overdue
603 | FAULTY FREEZER ROOM | KADUNA, KACHIA RD | Routine Servicing | Preventive | OLANIYI | FREEZER ROOM | HVAC | 2025-02-28 | 0 | 2025-02-28 | 0 | 2025-02-28 | 0 | 2025-02-28 | 2025-02-28 | 0 | 2025-02-28 | 0 | 2025-02-28 | 0 | 2025-02-28 |  | Completed | 2025-02-28 | 1
604 | FILLED SEPTIC TANK | LAG, IDI-IROKO RD | Corrective Action | Corrective | MOONLIGHT | SEPTIC TANK | EVACUATION | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 | 0 | 2025-02-03 |  | Completed | 2025-02-03 | 1
605 | REQUEST FOR INSECUTOR BULBS | SOKOTO, BANK RD | Electrical Surge | Breakdown | MOSES | INSECT KILLER BOH | ELECTRICAL | 2025-02-09 | 39 | 2025-02-09 | 0 | 2025-03-15 | 34 | [9 empty] | Overdue
606 | Re: LOBBY TV NOT DISPLAYING | LAG, TEJUOSHO | Electrical Surge | Breakdown | ACORN | TELEVISION | AUDIOVISUAL | 2025-02-21 | 27 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-03-15 |  | 5 | [6 empty] | Overdue
607 | DAMAGED WOODEN FRAME FOR WALLPAPER | LAG, EKORO | Wear & Tear | Breakdown | ADEBOLA | OTHERS | OTHERS | 2025-02-25 | 23 | 2025-03-07 | 10 | 2025-03-14 | 7 | 2025-03-14 | 2025-03-14 | 0 | 2025-03-14 | 6 |  |  |  | 355000 | Overdue
608 | BROKEN CABINET GLASS |  | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-02-20 | 22 | 2025-02-20 | 0 | 2025-02-28 | 8 | 2025-03-14 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 |  | Completed | 2025-03-14 | 1
609 | BROKEN PARKING LOT FLOOR | LAG, IKORODU | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-02-11 | 37 | 2025-02-11 | 0 | 2025-03-10 | 27 | 2025-03-10 |  | 10 | [6 empty] | Overdue
610 | REQUEST FOR CABINET BULB | LAG, AWOLOWO 2 | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-02-04 | 37 | 2025-02-05 | 1 | 2025-02-13 | 8 | 2025-02-13 | 2025-02-13 | 0 | 2025-03-13 | 0 | 2025-03-13 | 0 | 2025-03-13 |  | Completed | 2025-03-13 | 1
611 | Remodeling of Freedom way Car Park | LAG, FREEDOMWAY | Others | Breakdown | ACORN | OTHERS | OTHERS | 2025-02-05 | 43 | 2025-02-05 | 0 | 2025-02-05 | 0 | 2025-03-09 | 2025-03-10 | 1 | 2025-03-10 | 9 | 2025-03-19 | 1 |  |  | Overdue
612 | COLD ROOM AND FREEZER ROOM NOT FUNCTIONING | LAG, ONIRU | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-02-12 | 36 | 2025-02-12 | 0 | 2025-02-12 | 0 | 2025-03-11 | 2025-03-14 | 3 | 2025-03-14 | 5 | 2025-03-19 | 1 |  | 890000 | Overdue
613 | FAULTY GENERATOR | LAG, ISAWO-IKORODU | Wear & Tear | Breakdown | DELIGHTSOME | GENERATOR | GENERATOR | 2025-02-02 | 46 | 2025-02-02 | 0 | 2025-02-10 | 8 | [9 empty] | Overdue
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
Formulas:
Days Since Request = IF([Request Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Request Date],TODAY()-[Request Date]))
Days Delayed by Helpdesk = IF([Date Shared by Helpdesk]<>"",[Date Shared by Helpdesk]-[Request Date],IF([Request Date]="","",TODAY()-[Request Date]))
Days Delayed by Vendor/Technician = IF(M6<>"",M6-[Date Shared by Helpdesk],IF([Date Shared by Helpdesk]="","",TODAY()-[Date Shared by Helpdesk]))
Days Since Negotiation Request = TODAY() - [Date Negotiated]
Days Since Negotiation Request = IF([Date Negotiated]<>"",[Date Negotiated]-[Date Sent for Negotiation],IF([Date Sent for Negotiation]="","",TODAY()-[Date Sent for Negotiation]))
Days Since Approval Request = IF([Approved Date]<>"",[Approved Date]-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval Request = IF(#REF!<>"",#REF!-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval = IF([Approved Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Approved Date],TODAY()-[Approved Date]))
Days Since Approval = IF(#REF!="","",IF([Actual delivery date]<>"",[Actual delivery date]-#REF!,TODAY()-#REF!))
Status = IF([Request Date]="","",IF([Actual delivery date]<>"","Completed",IF(TODAY()<[Expected Delivery Date],"Planned",IF(TODAY()=[Expected Delivery Date],"Due","Overdue"))))
Note on AA6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vendor gave feedback thaat part is not available on 18 of Jan
Note on C50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PIE EXPRESS ADEOLA ODEKU
Note on C56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SANGOTEDO
Note on C69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: px ebute metta
Note on C179: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: adeola odeku
Note on C192: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PIE EXPRESS FAGBA
Note on C200: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PI EXPRESSIGANDO
Note on C260: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR SANGOTEDO
Note on C270: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX BARIGA
Note on C416: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX IGANDO
Note on C492: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PPU RHAMART
Note on C551: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PPU Dutse Alhaji
Note on C552: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pie Express Agidingbi
Note on C596: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR IYANA IYESI
Note on C597: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR IYANA IYESI
Note on C611: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pie Express Fagba

## MARCH
Legend
Completed on time
Completed late
S/N | ACTION/TASK | Store | Reason for Breakdown | Maintenance Category | Responsible | Specific Equipment | Category | Request Date | Days Since Request | Date Shared by Helpdesk | Days Delayed by Helpdesk | Date Attended/Checked by Vendor/Technician | Days Delayed by Vendor/Technician | Date Sent for Negotiation | Date Negotiated | Days Since Negotiation Request | Date Approval Requested | Days Since Approval Request | Approved Date | Days Since Approval | Expected Delivery Date | Cost | Status | Actual delivery date | Compliance check | Insert Comment
1 | Routine service of Acs. | KADUNA, AHMADU DELLO WAY | Wear & Tear | Breakdown | NGUTAN | 5HP STANDING AC UNIT 1 | HVAC | 2025-03-04 | 16 | 2025-03-04 | 0 |  | 16 |  |  | 45736 | [6 empty] | Overdue
2 | LEAKING TOILET | ABUJA, KARU | Users Misuse | Breakdown | JPILLAR | OTHERS | OTHERS | 2025-03-02 | 3 | 2025-03-04 | 2 | 2025-03-05 | 1 | 2025-03-05 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 |  | Completed | 2025-03-05 | 1
3 | PRESSURE FRYER TEMPERATURE DROP | KADUNA, ZARIA | Wear & Tear | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-03-03 | 17 | 2025-03-03 | 0 | 2025-03-04 | 1 | 2025-03-04 |  | 16 | [6 empty] | Overdue
4 | Septic Tank Evacuation and excavation | LAG, OSOLOWAY | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-03-03 | 17 | 2025-03-03 | 0 | 2025-03-04 | 1 | 2025-03-04 |  | 16 | [6 empty] | Overdue
5 | FAULTY ICE CREAM MACHINE | LAG, ONIRU | Wear & Tear | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-03-04 | 16 | 2025-03-04 | 0 |  | 16 | [9 empty] | Overdue
6 | FAULTY INSECTICUTOR BULBS | KADUNA, CONSTITUTION RD | Wear & Tear | Breakdown | OLANIYI | INSECT KILLER BOH | ELECTRICAL | 2025-03-04 | 16 | 2025-03-04 | 0 |  | 16 | [9 empty] | Overdue
7 | BURNT INSECT OCUTOR BULBS | OGUN, HEYDEN IBAFO | Wear & Tear | Breakdown | MOSES | INSECT KILLER BOH | ELECTRICAL | 2025-03-04 | 0 | 2025-03-04 | 0 | 2025-03-04 | 0 | 2025-03-04 | 2025-03-04 | 0 | 2025-03-04 | 0 | 2025-03-04 | 0 | 2025-03-04 |  | Completed | 2025-03-04 | 1
8 | CABINET NOT ATTAINING TEMPERATTURE | LAG, AKOWONJO | Wear & Tear | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-05 | 15 | 2025-03-05 | 0 |  | 15 | [9 empty] | Overdue
9 | FAULTY SWING DOOR | ABUJA, KARU | Wear & Tear | Breakdown |  | OTHERS | OTHERS | 2025-03-02 | 18 | 2025-03-06 | 4 |  | 14 | [9 empty] | Overdue
10 | FORCE FLOW FROM GAS CONTROL | OGUN, HEYDEN IBAFO | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-03-06 | 8 | 2025-03-06 | 0 | 2025-03-06 | 0 | 2025-03-06 | 2025-03-06 | 0 | 2025-03-06 | 2 | 2025-03-08 | 6 | 2025-03-14 | 223250 | Completed | 2025-03-14 | 1
12 | PX JIBOWU BROKEN CABINET GLASS | LAG, JIBOWU | Wear & Tear | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-06 | 8 | 2025-03-06 | 0 | 2025-03-14 | 8 | 2025-03-14 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 |  | Completed | 2025-03-14 | 1
13 | FAULTY CABINET | AKWA IBOM, IKOT EKPENE RD | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-05 | 15 | 2025-03-05 | 0 | 2025-03-06 | 1 | [9 empty] | Overdue
14 | FAULTY CABINET | KADUNA, CONSTITUTION RD | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-06 | 14 | 2025-03-06 | 0 |  | 14 | [9 empty] | Overdue
15 | FAULTY CABINET BULB HOLDER. | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-04 | 16 | 2025-03-05 | 1 |  | 15 | [9 empty] | Overdue
16 | FAULTY CABINET | LAG, OPEBI | Wear & Tear | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-03 | 17 | 2025-03-03 | 0 | 2025-03-04 | 1 | [9 empty] | Overdue
17 | PAINT OF LOBBY CHAIR AND TABLES. | LAG, MARINA | Wear & Tear | Breakdown | MATOLAD | CUSTOMER TABLE | FURNITURE | 2025-03-03 | 17 | 2025-03-03 | 0 | 2025-03-05 | 2 | 2025-03-05 | 2025-03-05 | 0 | 2025-03-05 | 1 | 2025-03-06 | 14 |  |  | Overdue
18 | FOOD CABINET NOT ATTAINING TEMPERATURE | LAG, DIYA STREET | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-06 | 14 | 2025-03-06 | 0 |  | 14 | [9 empty] | Overdue
19 | LOBBY ENTANCE DOOR HANDLE | LAG, IKORODU | Users Misuse | Breakdown | TAIDAV | OTHERS | OTHERS | 2025-03-05 | 4 | 2025-03-05 | 0 | 2025-03-06 | 1 | 2025-03-09 | 2025-03-09 | 0 | 2025-03-09 | 0 | 2025-03-09 | 0 | 2025-03-09 |  | Completed | 2025-03-09 | 1
20 | DETACHED SIGNAGE BOARD | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-03-05 | 9 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 | 2025-03-06 | 1 | 2025-03-06 | 3 | 2025-03-09 | 5 | 2025-03-14 | 79875 | Completed | 2025-03-14 | 1
21 | GENERATOR DUE FOR SERVICING | LAG, AJAH | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-03-06 | 14 | 2025-03-06 | 0 | 2025-03-06 | 0 | [9 empty] | Overdue
22 | DIRTY WATER COMING OUT IN THE STORE | LAG, MOBIL OGBA | Corrective Action | Corrective | PROEQUIP | AERATION TANK | WTP | 2025-03-02 | 18 | 2025-03-02 | 0 | 2025-03-06 | 4 | 2025-03-06 | 2025-03-14 | 8 | 2025-03-14 | 1 | 2025-03-15 | 5 |  | 600000 | Overdue
23 | DAMAGE TAP IN FRYER SINK | LAG, FREEDOMWAY | Wear & Tear | Breakdown | JOEL | TAP | PLUMBING | 2025-03-05 | 1 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-06 | 2025-03-06 | 0 | 2025-03-06 | 0 | 2025-03-06 | 0 | 2025-03-06 |  | Completed | 2025-03-06 | 1
24 | Repair of generator at aguda store |  | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-03-07 | 13 | 2025-03-07 | 0 | 2025-03-07 | 0 | [9 empty] | Overdue
25 | Faulty Change over | LAG, ILUPEJU | Electrical Surge | Breakdown | GBATMO | CHANGE OVER | ELECTRICAL | 2025-03-01 | 9 | 2025-03-01 | 0 | 2025-03-01 | 0 | 2025-03-01 | 2025-03-02 | 1 | 2025-03-02 | 1 | 2025-03-03 | 7 | 2025-03-10 | 250000 | Completed | 2025-03-10 | 1
26 | FAULTY SUBMERSIBLE MACHINE | LAG, TEJUOSHO | Wear & Tear | Breakdown | Proequip | SUBMERSIBLE PUMP | WTP | 2025-03-07 | 3 | 2025-03-07 | 0 | 2025-03-07 | 0 | 2025-03-10 | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-10 |  | Completed | 2025-03-10 | 1
28 | Septic Tank Evacuation and excavation | LAG, OSOLOWAY | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-03-03 | 17 | 2025-03-03 | 0 | 2025-03-04 | 1 | 2025-03-04 | 2025-03-07 | 3 | 2025-03-07 | 0 | 2025-03-07 | 13 |  | 475000 | Overdue
29 | FAULTY ROLLER SHUTTERS | LAG, IDIMU | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-03-04 | 10 | 2025-03-04 | 0 | 2025-03-04 | 0 | 2025-03-04 | 2025-03-05 | 1 | 2025-03-05 | 0 | 2025-03-05 | 9 | 2025-03-14 | 70735 | Completed | 2025-03-14 | 1
30 | BAD TOILET FLUSHER | LAG, OBA AKRAN | Users Misuse | Breakdown | ADEREMI | OTHERS | OTHERS | 2025-03-07 | 13 | 2025-03-07 | 0 | 2025-03-07 | 0 | [9 empty] | Overdue
31 | Issues that needs to be resolved at aguda store |  | Others | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-03-07 | 13 | 2025-03-07 | 0 | 2025-03-07 | 0 | [9 empty] | Overdue
32 | REQUEST FOR EXTRA GAS LINE EXTENSION. | LAG, MARINA | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-03-07 | 13 | 2025-03-07 | 0 | 2025-03-07 | 0 | 2025-03-07 | 2025-03-07 | 0 | 2025-03-07 | 0 | 2025-03-07 | 13 |  | 90750 | Overdue
33 | ROLLER SHUTTER at EBUTE-METTA |  | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-03-05 | 15 | 2025-03-05 | 0 | 2025-03-07 | 2 |  | 2025-03-07 | 45723 | 2025-03-07 | 0 | 2025-03-07 | 13 |  | 150000 | Overdue
34 | FIRE OUTBREAK IN STORE WATER TREATMENT | NASSARAWA, LAFIA | Electrical Surge | Breakdown | JPILLAR | WATER TREATMENT PLANT BLD | BUILDING | 2025-03-08 | 12 | 2025-03-08 | 0 |  | 12 | [9 empty] | Overdue
35 | FAULTY 6 HEAD MACHINE | LAG, IKOTUN | Wear & Tear | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-03-05 | 15 | 2025-03-05 | 0 | 2025-03-06 | 1 | 2025-03-06 | 2025-03-06 | 0 | 2025-03-06 | 7 | 2025-03-13 | 7 |  | 227900 | Overdue
36 | FAULTY SOUND SYSTEM | LAG, ALIMOSHO | Wear & Tear | Breakdown | ACORN | OTHERS | OTHERS | 2025-03-04 | 16 | 2025-03-04 | 0 | 2025-03-04 | 0 | [9 empty] | Overdue
37 | Faulty insecutor bulb | LAG, IRE-AKARI | Electrical Surge | Breakdown | FRIDAY | INSECT KILLER BOH | ELECTRICAL | 2025-03-06 | 2 | 2025-03-06 | 0 | 2025-03-08 | 2 | 2025-03-08 |  | 12 |  |  |  |  | 2025-03-08 |  | Completed | 2025-03-08 | 1
38 | GENERATOR SERVICING | IBADAN, BODIJA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-03-03 | 1 | 2025-03-03 | 0 | 2025-03-04 | 1 | 2025-03-04 | 2025-03-04 | 0 | 2025-03-04 | 0 | 2025-03-04 | 0 | 2025-03-04 |  | Completed | 2025-03-04 | 1
39 | FAULTY FREEZER ROOM INTERNAL FAN | SOKOTO, BANK RD | Routine Servicing | Preventive | DANTEM | FREEZER ROOM | HVAC | 2025-03-04 | 7 | 2025-03-04 | 0 | 2025-03-08 | 4 | 2025-03-11 | 2025-03-11 | 0 | 2025-03-11 | 0 | 2025-03-11 | 0 | 2025-03-11 | 366125 | Completed | 2025-03-11 | 1
40 | MINOR REPAIRS IN STORE | LAG, GBAGADA | Others | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-03-08 | 2 | 2025-03-08 | 0 | 2025-03-08 | 0 | 2025-03-10 | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-10 |  | Completed | 2025-03-10 | 1
41 | MAINTENANCE ISSUE | LAG, OMOLE | Others | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-03-06 | 1 | 2025-03-06 | 0 | 2025-03-07 | 1 | 2025-03-07 | 2025-03-07 | 0 | 2025-03-07 | 0 | 2025-03-07 | 0 | 2025-03-07 |  | Completed | 2025-03-07 | 1
42 | MAINTENANCE ISSUE | LAG, OMOLE | Others | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-03-06 | 7 | 2025-03-06 | 0 | 2025-03-08 | 2 | 2025-03-08 | 2025-03-11 | 3 | 2025-03-11 | 0 | 2025-03-11 | 2 | 2025-03-13 |  | Completed | 2025-03-13 | 1
43 | SEEWAGE EVACUATION | LAG, AGUNGI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-03-08 | 12 | 2025-03-08 | 0 | 2025-03-08 | 0 | [9 empty] | Overdue
44 | FAULTY FREEZER ROOM ELECTRIC BOARD | ABUJA, KARU | Electrical Surge | Breakdown | DANTEM | FREEZER ROOM | HVAC | 2025-03-07 | 10 | 2025-03-07 | 0 | 2025-03-08 | 1 | 2025-03-17 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 |  | Completed | 2025-03-17 | 1
45 | GENERATOR UNABLE TO TURN ON | LAG, LEKKI PHASE 1 | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-03-08 | 0 | 2025-03-08 | 0 | 2025-03-08 | 0 |  |  | #REF! |  |  |  |  | 2025-03-08 |  | Completed | 2025-03-08 | 1
46 | RUSTED POP CEILING RAIL IN THE DRY STORE | LAG, JIBOWU | Wear & Tear | Breakdown | ARIZMAYAN | CEILING BOARD | BUILDING | 2025-03-07 | 13 | 2025-03-07 | 0 | 2025-03-08 | 1 | 2025-03-11 | 2025-03-11 | 0 | 2025-03-12 | 0 | 2025-03-12 |  |  |  | Overdue
47 | FREEZER ROOM NOT ATTAINING TEMPERATURE(FOOD SAFETY CRITICAL) | KADUNA, CONSTITUTION RD | Corrective Action | Corrective | OLANIYI | FREEZER ROOM | HVAC | 2025-03-05 | 2 | 2025-03-05 | 0 | 2025-03-07 | 2 | 2025-03-07 | 2025-03-07 | 0 | 2025-03-07 | 0 | 2025-03-07 |  | 2025-03-07 |  | Completed | 2025-03-07 | 1
48 | CRITICAL FOOD SAFETY; FREEZER ROOM NOT ATTAINING TEMPERATURE. | KADUNA, AHMADU DELLO WAY | Routine Servicing | Preventive | OLANIYI | FREEZER ROOM | HVAC | 2025-03-04 | 1 | 2025-03-04 | 0 | 2025-03-05 | 1 | 2025-03-05 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 |  | Completed | 2025-03-05 | 1
49 | LEAKAGE IN BOTH FEMALE AND MALE CUSTOMER'S RESTROOM | LAG, MARINA | Corrective Action | Corrective | BERRADE | OTHERS | OTHERS | 2025-03-05 | 15 | 2025-03-05 | 0 | 2025-03-07 | 2 | 2025-03-07 | 2025-03-07 | 0 | [5 empty] | 410250 | Overdue
50 | EXTRACTOR NOT WORKING | KADUNA, CONSTITUTION RD | Others | Breakdown | OLANIYI | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2025-03-06 | 1 | 2025-03-06 | 0 | 2025-03-07 | 1 | 2025-03-07 | 2025-03-07 | 0 | 2025-03-07 | 0 | 2025-03-07 | 0 | 2025-03-07 |  | Completed | 2025-03-07 | 1
51 | FAULTY MALE WATER CLOSET | LAG, AJOSE ADEOGUN | Corrective Action | Corrective | JOEL | OTHERS | OTHERS | 2025-03-05 | 2 | 2025-03-05 | 0 | 2025-03-07 | 2 | 2025-03-07 | 2025-03-07 | 0 | 2025-03-07 | 0 | 2025-03-07 | 0 | 2025-03-07 |  | Completed | 2025-03-07 | 1
52 | FOOD CABINET NOT ATTAINING TEMPERATURE | LAG, DIYA STREET | Wear & Tear | Breakdown | BCE | OTHERS | OTHERS | 2025-03-06 | 14 | 2025-03-06 | 0 | 2025-03-07 | 1 | 2025-03-07 | 2025-03-07 | 0 | 2025-03-07 | 4 | 2025-03-11 | 9 |  | 536425 | Overdue
53 | CEILING FAIL |  | Wear & Tear | Breakdown | PENTECOSTAL | CEILING BOARD | BUILDING | 2025-03-05 | 15 | 2025-03-05 | 0 | 2025-03-05 | 0 | [9 empty] | Overdue
54 | INVERTER NOT BACKING UP | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | DALEMATRIX | INVERTER DB | ELECTRICAL | 2025-03-05 | 15 | 2025-03-06 | 1 | 2025-03-06 | 0 | [9 empty] | Overdue
55 | PRESSURE FRYER TEMPERATURE DROP | KADUNA, ZARIA | Corrective Action | Corrective | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-03-03 | 17 | 2025-03-03 | 0 | 2025-03-03 | 0 | 2025-03-06 | 2025-03-06 | 0 | 2025-03-06 | 0 | 2025-03-06 | 14 |  | 565450 | Overdue
56 | PRESSURE FRYER SAYING HIGH LIMIT | LAG, TEJUOSHO | Routine Servicing | Preventive | HEFHEM | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-03-04 | 2 | 2025-03-04 | 0 | 2025-03-04 | 0 | 2025-03-06 | 2025-03-06 | 0 | 2025-03-06 | 0 | 2025-03-06 | 0 | 2025-03-06 |  | Completed | 2025-03-06 | 1
57 | TWO DEAD CORRIDOR BULBS | LAG, BODE THOMAS | Electrical Surge | Breakdown | TImilehin | OTHERS | OTHERS | 2025-03-02 | 7 | 2025-03-02 | 0 | 2025-03-09 | 7 | 2025-03-09 | 2025-03-09 | 0 | 2025-03-09 | 0 | 2025-03-09 | 0 | 2025-03-09 |  | Completed | 2025-03-09 | 1
58 | TOASTING MACHINE FAULTY FROM CURRENT SURGE | LAG, BODE THOMAS | Electrical Surge | Breakdown | TImilehin | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2025-03-03 | 6 | 2025-03-03 | 0 | 2025-03-09 | 6 | 2025-03-09 | 2025-03-09 | 0 | 2025-03-09 | 0 | 2025-03-09 | 0 | 2025-03-09 |  | Completed | 2025-03-09 | 1
59 | GENERATOR DUE FOR SERVICING | LAG, OGUNLANA DRIVE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-03-09 | 11 | 2025-03-09 | 0 | 2025-03-09 | 0 | [9 empty] | Overdue
60 | FAULTY SOUND SYSTEM | LAG, ALIMOSHO | Others | Breakdown | ACORN | OTHERS | OTHERS | 2025-03-03 | 17 | 2025-03-04 | 1 | 2025-03-05 | 1 | [9 empty] | Overdue
61 | Septic Tank Evacuation and excavation | LAG, OSOLOWAY | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-03-03 | 17 | 2025-03-03 | 0 | 2025-03-04 | 1 | 2025-03-04 | 2025-03-07 | 3 | 2025-03-07 | 0 | 2025-03-07 | 13 |  | 470000 | Overdue
62 | SEPTIC TANK EVACUATION | LAG, ETERNA LEKKI | Others | Breakdown | BERRADE | SEPTIC TANK | EVACUATION | 2025-03-09 | 11 | 2025-03-09 | 0 | 2025-03-09 | 0 | [9 empty] | Overdue
63 | FAULTY ROLLE R SHORTER | LAG, AKOWONJO | Corrective Action | Corrective | PENTECOSTAL | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-03-03 | 17 | 2025-03-03 | 0 | 2025-03-03 | 0 | 2025-03-04 | 2025-03-04 | 0 | 2025-03-04 | 1 | 2025-03-05 | 15 |  | 100000 | Overdue
64 | BAD TAPE AT BOH | LAG, OBA AKRAN | Wear & Tear | Breakdown | ADEREMI | INSECT KILLER BOH | ELECTRICAL | 2025-03-03 | 17 | 2025-03-03 | 0 | 2025-03-03 | 0 | [9 empty] | Overdue
65 | FAULTY INSECTICUTOR BULBS | KADUNA, CONSTITUTION RD | Electrical Surge | Breakdown | OLANIYI | INSECT KILLER BOH | ELECTRICAL | 2025-03-04 | 1 | 2025-03-04 | 0 | 2025-03-05 | 1 | 2025-03-05 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 |  | Completed | 2025-03-05 | 1
66 | GENERATOR DUE FOR SEVICE | LAG, AKOWONJO | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-03-05 | 15 | 2025-03-05 | 0 | 2025-03-05 | 0 | [9 empty] | Overdue
67 | GAS LEAKAGE IN THE KITCHEN | LAG, IKORODU | Corrective Action | Corrective | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-03-05 | 15 | 2025-03-05 | 0 | 2025-03-05 | 0 | [9 empty] | Overdue
68 | CEILING FALL AT EBUTEMETTA |  | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-03-05 | 15 | 2025-03-05 | 0 | 2025-03-06 | 1 | 2025-03-09 | 2025-03-11 | 2 | 2025-03-11 | 6 | 2025-03-17 | 3 |  | 400000 | Overdue
69 | STORE'S INVERTER TRIPS OFF WHEN THERES POWER OUTAGE. | KADUNA, AHMADU DELLO WAY | Electrical Surge | Breakdown | OLANIYI | INVERTER DB | ELECTRICAL | 2025-03-09 | 11 | 2025-03-09 | 0 | 2025-03-09 | 0 | [9 empty] | Overdue
70 | FAULTY OFFICE AC | LAG, GBAGADA | Routine Servicing | Preventive | THIO | 5HP STANDING AC UNIT 3 | HVAC | 2025-03-09 | 11 | 2025-03-09 | 0 | 2025-03-09 | 0 | [9 empty] | Overdue
71 | FAULTY WARMER GASKET | PH, RUMUOLA | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-03-05 | 15 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 | 15 |  | 120400 | Overdue
72 | LEAKING SINKS (FRYER AND COOK) |  | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2025-03-03 | 2 | 2025-03-03 | 0 | 2025-03-05 | 2 | 2025-03-05 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 |  | Completed | 2025-03-05 | 1
73 | Faulty Change over | LAG, ILUPEJU | Electrical Surge | Breakdown | GBATMO | CHANGE OVER | ELECTRICAL | 2025-03-01 | 7 | 2025-03-01 | 0 | 2025-03-01 | 0 | 2025-03-01 | 2025-03-02 | 1 | 2025-03-02 | 1 | 2025-03-03 | 5 | 2025-03-08 | 250000 | Completed | 2025-03-08 | 1
74 | FAULTY ENTRANCE DOOR | LAG, ILUPEJU | Wear & Tear | Breakdown | TAIDAV | OTHERS | OTHERS | 2025-03-05 | 4 | 2025-03-05 | 0 | 2025-03-09 | 4 | 2025-03-09 | 2025-03-09 | 0 | 2025-03-09 | 0 | 2025-03-09 | 0 | 2025-03-09 |  | Completed | 2025-03-09 | 1
75 | FAULTY LOBBY DOOR HANDLE | LAG, OKOTA | Wear & Tear | Breakdown | TAIDAV | OTHERS | OTHERS | 2025-03-06 | 3 | 2025-03-07 | 1 | 2025-03-09 | 2 | 2025-03-09 | 2025-03-09 | 0 | 2025-03-09 | 0 | 2025-03-09 | 0 | 2025-03-09 |  | Completed | 2025-03-09 | 1
76 | CEILING FAIL |  | Wear & Tear | Breakdown | BCE | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2025-03-05 | 15 | 2025-03-05 | 0 | 2025-03-05 | 0 | [9 empty] | Overdue
77 | MAINTAINANCE ISSUES AT PPU HOTORO. | KANO, HOTORO | Others | Breakdown | THOMPSON | OTHERS | OTHERS | 2025-03-10 | 10 | 2025-03-10 | 0 | 2025-03-11 | 1 | [9 empty] | Overdue
78 | LEAKING SINK | LAG, BADORE | Wear & Tear | Breakdown | JOEL | KITCHEN WASH HAND SINK | PLUMBING | 2025-03-10 | 1 | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-10 | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-10 | 1 | 2025-03-11 |  | Completed | 2025-03-11 | 1
79 | REPAINTING OF CASHIER COUNTER | LAG, GBAGADA | Wear & Tear | Breakdown | ADEBOLA | PAINTING | BUILDING | 2025-03-01 | 19 | 2025-03-01 | 0 | 2025-03-05 | 4 | 2025-03-09 | 2025-03-14 | 5 | 2025-03-14 | 6 |  |  |  | 300000 | Overdue
80 | MAINTENANCE ISSUEs In CR OMOLE | LAG, OMOLE | Wear & Tear | Breakdown | TIMILEHIN | CHANGE OVER | ELECTRICAL | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-10 | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-10 |  | Completed | 2025-03-10 | 1
81 | Issues that needs to be resolved | LAG, DIYA STREET | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-03-11 | 9 | 2025-03-11 | 0 |  | 9 | [9 empty] | Overdue
82 | Contaminated Diesel at CR Festac | LAG, FESTAC | Others | Breakdown | MIDTECH | GENERATOR | GENERATOR | 2025-03-11 | 9 | 2025-03-11 | 0 | 2025-03-12 | 1 | [9 empty] | Overdue
83 | CK FLOODED FRONT OF HOUSE | LAG, ILUPEJU | Corrective Action | Corrective | PRO-EQUIP | DOSING PUMP | WTP | 2025-03-11 | 9 | 2025-03-11 | 0 |  | 9 | [9 empty] | Overdue
84 | Re: REQUEST FOR PURCHASE OF CARD READER FOR PREPAID METER |  | Corrective Action | Corrective | TIMILEHIN | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-03-12 | 8 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 | 2025-03-13 | 1 | 2025-03-13 | 2 | 2025-03-15 | 5 |  | 27950 | Overdue
85 | REPAIR OF IRON BAR TO RESTRICT CAR | LAG, LATEEF JAKANDE | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-03-12 | 8 | 2025-03-12 | 0 | 2025-03-12 | 0 | [9 empty] | Overdue
86 | PX VGC DOOR HANDLE AND CHIPPED WOODEN EDGES | LAG, VGC | Wear & Tear | Breakdown |  | OTHERS | OTHERS | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
87 | CABINET BULB | LAG, OBA AKRAN | Wear & Tear | Breakdown | TIMILEHIN | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-12 | 8 | 2025-03-12 | 0 | 2025-03-12 | 0 | [9 empty] | Overdue
88 | COLD ROOM AND FREEZER ROOM NOT WORKING | LAG, AKOWONJO | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-03-07 | 13 | 2025-03-07 | 0 | 2025-03-11 | 4 | 2025-03-11 |  | 9 | [6 empty] | Overdue
89 | COLLECTRAMATIC NOT ATTAINING TEMPERATURE | LAG, ABULE EGBA | Wear & Tear | Breakdown | BCE | COLLECTRAMATIC OIL PUMP MACHINE | KITCHEN_EQUIPMENT | 2025-03-11 | 1 | 2025-03-11 | 0 | 2025-03-12 | 1 | 2025-03-12 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 |  | Completed | 2025-03-12 | 1
90 | RATIONAL TRIPPING OFF AND ON | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | BCE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2025-03-11 | 9 | 2025-03-11 | 0 | 2025-03-12 | 1 | [9 empty] | Overdue
91 | FAULTY UNDERBAR SOCKET AND TOASTING MACHINE SOCKET. | LAG, IDI-IROKO RD | Wear & Tear | Breakdown | TAYO | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 |  | Completed | 2025-03-12 | 1
92 | FAULTY FREEZER ROOM IN THE STORE | LAG, IPAJA RD | Wear & Tear | Breakdown | DYNAMITE | FREEZER ROOM | HVAC | 2025-03-12 | 8 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-13 |  | 7 | [6 empty] | Overdue
93 | BURNT INSECTOCUTOR AT THE BOH | LAG, IDI-IROKO RD | Wear & Tear | Breakdown | TAYO | INSECT KILLER BOH | ELECTRICAL | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 |  | Completed | 2025-03-12 | 1
94 | FAULTY GENERATOR PPU ONIRU | PPU Oniru | Wear & Tear | Breakdown | DELIGHTSOME | GENERATOR | GENERATOR | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
95 | FLICKERING LIGHT BULB | LAG, ILUPEJU | Wear & Tear | Breakdown | KOLA | DROPPING LIGHT | ELECTRICAL | 2025-03-12 | 8 | 2025-03-12 | 0 | 2025-03-17 | 5 | [9 empty] | Overdue
96 | FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, OMOLE | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2025-03-11 | 9 | 2025-03-12 | 1 |  | 8 | [9 empty] | Overdue
97 | REPLACEMENT CABINET GLASS BROKEN (PX DIYA) | LAG, DIYA STREET | Users Misuse | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-08 | 5 | 2025-03-08 | 0 | 2025-03-12 | 4 | 2025-03-12 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 | 1 | 2025-03-13 |  | Completed | 2025-03-13 | 1
98 | BURNT ALMOND CABLE | LAG, AJOSE ADEOGUN | Electrical Surge | Breakdown | ISMAIL | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-03-12 | 8 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 | 2025-03-12 | 0 | 2025-03-12 | 1 | 2025-03-13 | 7 |  |  | Overdue
99 | REPLACEMENT DAMAGED LOBBY WALL PAPER | LAG, BODE THOMAS | Wear & Tear | Breakdown | D ONTOP | WALL | BUILDING | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
100 | INVERVER NOT CHARGING UP |  | Wear & Tear | Breakdown | CURRENTDATA | INVERTER SYSTEM | INVERTER | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
101 | POWER OUTAGE AT JIBOWU - FAULTY GENERATOR | LAG, JIBOWU | Wear & Tear | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-03-10 | 10 | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-11 | 2025-03-11 | 0 | 2025-03-12 | 8 |  |  |  |  | Overdue
102 | CABINET GLASS FRAME REMOVED | LAG, AJAH | Users Misuse | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-10 | 10 | 2025-03-10 | 0 | 2025-03-13 | 3 |  |  |  |  | #REF! |  | #REF! |  |  | Overdue
103 | FAULTY SHREDDING MACHINE | LAG, JIBOWU | Wear & Tear | Breakdown | BCE | SHREDDER | KITCHEN_EQUIPMENT | 2025-03-03 | 17 | 2025-03-03 | 0 |  | 17 | [9 empty] | Overdue
104 | WELDING WORKS IN THE STORE | LAG, VGC | Wear & Tear | Breakdown | MODEL | OTHERS | OTHERS | 2025-03-05 | 15 | 2025-03-05 | 0 | 2025-03-12 | 7 | 2025-03-12 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 | 8 |  |  | Overdue
105 | FAULTY EXTERNAL FREEZER ROOM | SOKOTO, BANK RD | Wear & Tear | Breakdown | DANTEM | FREEZER ROOM | HVAC | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
106 | EQUIPMENT STATUS REPORT | PPU Ilupeju | Wear & Tear | Breakdown | BCE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
107 | ROLLER SHUTTER NOT WORKING | LAG, OPEBI | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-03-09 | 11 | 2025-03-09 | 0 | 2025-03-11 | 2 | 2025-03-11 | 2025-03-11 | 0 | 2025-03-12 | 0 | 2025-03-12 | 8 |  |  | Overdue
108 | FAULTY PRESSURE FRYER | SOKOTO, BANK RD | Wear & Tear | Breakdown | BCE | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
109 | REQUEST FOR BLENDER | LAG, IPAJA RD | Others | Breakdown | TAYO | OTHERS | OTHERS | 2025-03-07 | 5 | 2025-03-07 | 0 | 2025-03-07 | 0 | 2025-03-07 | 2025-03-07 | 0 | 2025-03-07 | 0 | 2025-03-07 | 5 | 2025-03-12 |  | Completed | 2025-03-12 | 1
110 | BLOCKED FEMALE CHANGING ROOM BATHROOM | LAG, AKOWONJO | Users Misuse | Breakdown | ADEREMI WAHAB | OTHERS | OTHERS | 2025-03-11 | 1 | 2025-03-11 | 0 | 2025-03-12 | 1 | 2025-03-12 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 |  | Completed | 2025-03-12 | 1
111 | FREEZER ROOM AND COLD ROOM NOT ATTAINING TEMPERATURE | LAG, FREEDOMWAY | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2025-03-12 | 8 | 2025-03-12 | 0 | 2025-03-17 | 5 | [9 empty] | Overdue
112 | EXPOSED BREAKER | LAG, BODE THOMAS | Wear & Tear | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-03-08 | 4 | 2025-03-09 | 1 | 2025-03-12 | 3 | 2025-03-12 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-12 |  | Completed | 2025-03-12 | 1
113 | HIGH DIESEL CONSUMPTION | LAG, AGUNGI | Corrective Action | Corrective | KB | GENERATOR | GENERATOR | 2025-03-12 | 6 | 2025-03-12 | 0 | 2025-03-18 | 6 | 2025-03-18 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 |  | Completed | 2025-03-18 | 1
114 | Issues that needs to be resolved at aguda store (Suspended ceiling n Plumbing) |  | Others | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-03-07 | 13 | 2025-03-07 | 0 | 2025-03-07 | 0 | 2025-03-12 | 2025-03-18 | 6 | [5 empty] | 300000 | Overdue
115 | POLARITY ISSUE IN THE STORE | LAG, OGUNLANA DRIVE | Electrical Surge | Breakdown | TIMILEHIN | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-03-11 | 1 | 2025-03-11 | 0 | 2025-03-11 | 0 | 2025-03-11 | 2025-03-11 | 0 | 2025-03-11 | 0 | 2025-03-11 | 1 | 2025-03-12 |  | Completed | 2025-03-12 | 1
116 | FAULTY CABINET LAMPHOLDER | LAG, AKOWONJO | Wear & Tear | Breakdown | FRIDAY | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
117 | FAULTY FOH SOCKET | LAG, MAGODO | Wear & Tear | Breakdown | KOLA | OTHERS | OTHERS | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
118 | BAD CUSTOMER RESTROOM DOOR AND LOBBY SWING DOOR | LAG, OKOTA | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
119 | Issues that needs to be resolved at aguda store |  | Others | Breakdown | MATOLAD | CUSTOMER TABLE | FURNITURE | 2025-03-12 | 8 | 2025-03-12 | 0 | 2025-03-13 | 1 | 2025-03-13 | 2025-03-14 | 1 | 2025-03-14 | 0 | 2025-03-14 | 6 |  | 1550000 | Overdue
120 | Display cabinet lamp holders faulty |  | Wear & Tear | Breakdown | KITCHTECH | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
121 | POLARITY ISSUE | LAG, AWOLOWO | Electrical Surge | Breakdown | ISMAIL | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
122 | BOH CHILLER NOT WORKING | LAG, SKYMALL | Wear & Tear | Breakdown | BCE | NBC CHILLER | HVAC | 2025-03-12 | 8 | 2025-03-12 | 0 | 2025-03-12 | 0 | [9 empty] | Overdue
123 | STORE LIGHT ISSUES WITH THE FILLING STATION |  | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-03-07 | 13 | 2025-03-12 | 5 | 2025-03-12 | 0 | 2025-03-17 | 2025-03-17 | 0 | 2025-03-17 | 1 | 2025-03-18 | 2 |  |  | Overdue
124 | BREAKING DOWN OF GENERATOR | LAG, FESTAC | Wear & Tear | Breakdown | MIDTECH | GENERATOR | GENERATOR | 2025-03-11 | 9 | 2025-03-11 | 0 | 2025-03-12 | 1 | 2025-03-12 | 2025-03-12 | 0 | 2025-03-12 | 1 | 2025-03-13 | 7 |  | 56000 | Overdue
125 | FAULTY FOH SOCKET | LAG, MAGODO | Wear & Tear | Breakdown | KOLA | OTHERS | OTHERS | 2025-03-12 | 8 | 2025-03-12 | 0 | 2025-03-13 | 1 | [9 empty] | Overdue
126 | Air conditioning units due for service | LAG, ILUPEJU | Wear & Tear | Breakdown | TRIPPLE O | 5HP STANDING AC UNIT 2 | HVAC | 2025-03-13 | 7 |  | 7 | [11 empty] | Overdue
127 | REPORT OF DAILY HYGIENE WALKTHROUGH AND CLOSURE ACTION PLAN FOR OPEN OPPORTUNITIES FROM PPU ONIRU | PPU Oniru | Others | Breakdown | ADEREMI KAZEEM | OTHERS | OTHERS | 2025-03-11 | 9 | 2025-03-12 | 1 |  | 8 | [9 empty] | Overdue
128 | WOMBLING TABLE | LAG, AKOWONJO | Wear & Tear | Breakdown | MATOLAD | CUSTOMER TABLE | FURNITURE | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
129 | FAULTY COLDROOM AND FREEZER DOOR | LAG, IKORODU | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
130 | BAD SWING DOOR | LAG, OGUDU | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
131 | WOBBLING FRONT OF HOUSE ENTRANCE DOOR | LAG, BODE THOMAS | Wear & Tear | Breakdown | TAIDAV | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-03-12 | 6 | 2025-03-12 | 0 | 2025-03-18 | 6 | 2025-03-18 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 |  | Completed | 2025-03-18 | 1
132 | STORE WIRE DISCONNECTED AND CUT OFF |  | Others | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-03-11 | 9 | 2025-03-11 | 0 | 2025-03-12 | 1 | [9 empty] | Overdue
133 | DEAD BULBS IN FREEZER ROOM AND BOH | LAG, SKYMALL | Wear & Tear | Breakdown | ADEREMI KAZEEM | 18W ROUND LIGHT FITTING | ELECTRICAL | 2025-03-08 | 12 | 2025-03-08 | 0 |  | 12 | [9 empty] | Overdue
134 | FAULTY ROLLER SHUTTERS | LAG, IDIMU | Wear & Tear | Breakdown | BASSCOMM | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-03-04 | 10 | 2025-03-04 | 0 | 2025-03-05 | 1 | 2025-03-05 | 2025-03-05 | 0 | 2025-03-06 | 1 | 2025-03-07 | 7 | 2025-03-14 | 253915 | Completed | 2025-03-14 | 1
135 | FAULTY COLDROOM BULB LAMPHOLDER | LAG, MARINA | Wear & Tear | Breakdown | ISMAIL | 18W ROUND LIGHT FITTING | ELECTRICAL | 2025-03-11 | 9 | 2025-03-11 | 0 |  | 9 | [9 empty] | Overdue
136 | FAULTY ROLLER SHUTTER |  | Wear & Tear | Breakdown | PENTECOSTAL | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-03-13 | 7 | 2025-03-13 | 0 |  | 7 | [9 empty] | Overdue
137 | FAULTY SOCKETS | LAG, AJAH | Wear & Tear | Breakdown | ADEREMI KAZEEM | OTHERS | OTHERS | 2025-03-05 | 1 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 | 2025-03-05 | 0 | 2025-03-05 | 0 | 2025-03-05 | 1 | 2025-03-06 |  | Completed | 2025-03-06 | 1
138 | FAULTY SOCKETS | LAG, AJAH | Wear & Tear | Breakdown | ADEREMI KAZEEM | OTHERS | OTHERS | 2025-03-13 | 7 | 2025-03-13 | 0 |  | 7 | [9 empty] | Overdue
139 | GENERATOR SERVICING | PPU Ajah | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-03-10 | 10 | 2025-03-10 | 0 | 2025-03-13 | 3 | [9 empty] | Overdue
140 | BROKEN HAND SANITIZER DISPENSER | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | JOEL | OTHERS | OTHERS | 2025-03-13 | 4 | 2025-03-13 | 0 | 2025-03-17 | 4 | 2025-03-17 |  | 3 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 |  | Completed | 2025-03-17 | 1
141 | CR FREEDOM WAY COLD ROOM DOOR PUSHER NOT WORKING | LAG, FREEDOMWAY | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-03-13 | 7 | 2025-03-13 | 0 |  | 7 | [9 empty] | Overdue
142 | FAULTY RATIONALE MACHINE | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | BCE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2025-03-13 | 7 | 2025-03-13 | 0 | 2025-03-13 | 0 | [9 empty] | Overdue
143 | BAD DOOR AT WASTE BIN AREA AND WATER TREATMENT AREA | LAG, BADORE | Wear & Tear | Breakdown | MODEL | WASTE BIN HOUSE | BUILDING | 2025-03-10 | 10 | 2025-03-10 | 0 | 2025-03-13 | 3 | 2025-03-13 | 2025-03-13 | 0 | 2025-03-13 | 7 |  |  |  | 320000 | Overdue
144 | FAULTY AC IN THE STORE | LAG, FESTAC | Wear & Tear | Breakdown | THIO | 5HP STANDING AC UNIT 2 | HVAC | 2025-03-02 | 18 | 2025-03-07 | 5 | 2025-03-10 | 3 | [9 empty] | Overdue
145 | CARBINET BULB HOLDER FAULTY | LAG, IKEJA MALL | Wear & Tear | Breakdown | HEFHEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-13 | 7 | 2025-03-13 | 0 | 2025-03-17 | 4 | [9 empty] | Overdue
146 | AC NOT COOLING | KADUNA, BARNAWA | Wear & Tear | Breakdown | DANTEM | 5HP STANDING AC UNIT 2 | HVAC | 2025-03-13 | 7 | 2025-03-13 | 0 |  | 7 | [9 empty] | Overdue
147 | IPAJA AYOBO GENERATOR SUPPLYING LOW VOLTAGE | LAG, IPAJA RD | Wear & Tear | Breakdown | MIDTECH | GENERATOR | GENERATOR | 2025-03-13 | 7 | 2025-03-13 | 0 | 2025-03-13 | 0 | 2025-03-14 | 2025-03-14 | 0 | 2025-03-14 | 1 | 2025-03-15 | 5 |  | 418375 | Overdue
148 | FAULTY DRY STORE DOOR,CUSTOMER RESTROOM DOOR,STAFF EATING ROOM DOOR AND OFFICE DOOR. | LAG, AJAH | Wear & Tear | Breakdown
149 | STORE WIRE DISCONNECTED AND CUT OFF |  | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-03-04 | 16 | 2025-03-04 | 0 | 2025-03-05 | 1 | [9 empty] | Overdue
150 | FAULTY AC | LAG, ILUPEJU | Routine Servicing | Preventive | TONAOGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2025-03-11 | 9 | 2025-03-11 | 0 | 2025-03-11 | 0 | [9 empty] | Overdue
151 | LOBBY AIR CONDITIONER NOT WORKING | LAG, AJAH | Wear & Tear | Breakdown | TONA OGUNS | 5HP STANDING AC UNIT 2 | HVAC | 2025-03-07 | 13 | 2025-03-07 | 0 | 2025-03-13 | 6 | 2025-03-13 | 2025-03-13 | 0 | 2025-03-13 | 0 | 2025-03-13 | 7 |  | 329380 | Overdue
152 | OPEBI STORE AC NOT EFFECTIVE ( VERY CRITICAL) | LAG, OPEBI | Routine Servicing | Preventive | TONAOGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2025-03-07 | 13 | 2025-03-07 | 0 | 2025-03-10 | 3 | 2025-03-11 |  | 9 | [5 empty] | 944000 | Overdue
153 | UNUSED PIPES AT CK AIDING PEST INGRESS | LAG, ILUPEJU | Corrective Action | Corrective | ACORN | WALL | BUILDING | 2025-03-13 | 7 | 2025-03-13 | 0 |  | 7 | [9 empty] | Overdue
154 | SERVICING OF GREASE TRAP | LAG, IKOTUN | Routine Servicing | Preventive | PENTECOSTAL | GREASE TRAP | GREASE_TRAP | 2025-03-13 | 7 | 2025-03-13 | 0 |  | 7 | [9 empty] | Overdue
155 | FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, BADORE | Routine Servicing | Preventive | TONAOGUNS | FREEZER ROOM | HVAC
156 | CR OGUDU NON-CONFORMITIES ACTION PLAN | LAG, OGUDU | Wear & Tear | Breakdown | KOLA | OTHERS | OTHERS | 2025-03-13 | 7 | 2025-03-13 | 0 | 2025-03-13 | 0 | [9 empty] | Overdue
157 | BROKEN TILES IN THE STORE | LAG, OPEBI | Wear & Tear | Breakdown |  | OTHERS | OTHERS | 2025-03-13 | 7 | 2025-03-13 | 0 |  | 7 | [9 empty] | Overdue
158 | COLDROOM AND FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, IKORODU | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2025-03-11 | 9 | 2025-03-11 | 0 |  | 9 | [9 empty] | Overdue
159 | FAULTY WARMER GASKET | LAG, OPEBI | Wear & Tear | Breakdown | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-03-13 | 7 | 2025-03-13 | 0 | 2025-03-13 | 0 | 2025-03-13 | 2025-03-13 | 0 | 2025-03-13 | 7 |  |  |  |  | Overdue
160 | FAULTY CUSTOMERS RESTROOM A.C | LAG, GBAGADA | Routine Servicing | Preventive | THIO | 5HP STANDING AC UNIT 4 | HVAC | 2025-03-11 | 9 | 2025-03-11 | 0 | 2025-03-11 | 0 | [9 empty] | Overdue
161 | FAULTY EXTRACTOR BULB | LAG, CONOIL IKEJA | Wear & Tear | Breakdown | TIMILEHIN | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2025-03-07 | 1 | 2025-03-08 | 1 | 2025-03-08 | 0 | 2025-03-08 | 2025-03-08 | 0 | 2025-03-08 | 0 | 2025-03-08 | 0 | 2025-03-08 |  | Completed | 2025-03-08 | 1
162 | FAULTY FREEZEROOM LIGHT | LAG, CONOIL IKEJA | Electrical Surge | Breakdown | TIMILEHIN | FREEZER ROOM | HVAC | 2025-03-11 | 0 | 2025-03-11 | 0 | 2025-03-11 | 0 | 2025-03-11 | 2025-03-11 | 0 | 2025-03-11 | 0 | 2025-03-11 | 0 | 2025-03-11 |  | Completed | 2025-03-11 | 1
163 | RE: COLDROOM AND FREEZER ROOM NOT ATTAINING TEMPERATURE | LAG, IKORODU | Routine Servicing | Preventive | TONAOGUNS | OTHERS | OTHERS | 2025-03-11 | 9 | 2025-03-11 | 0 | 2025-03-11 | 0 | [9 empty] | Overdue
164 | GENERATOR DUE FOR SERVICE | LAG, DIYA STREET | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-03-11 | 9 | 2025-03-11 | 0 | 2025-03-11 | 0 | [9 empty] | Overdue
165 | GENERATOR DUE FOR SERVICE | LAG, ONIRU | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-03-11 | 9 | 2025-03-11 | 0 |  | 9 | [9 empty] | Overdue
166 | FAULTY PART OF CHIPS FRYER | LAG, OGUDU | Wear & Tear | Breakdown | BCE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT | 2025-03-08 | 12 | 2025-03-08 | 0 | 2025-03-11 | 3 | 2025-03-11 | 2025-03-11 | 0 | 2025-03-11 | 9 |  |  |  | 701975 | Overdue
167 | COLLAPSED CEILING IN DRY STORE | LAG, VGC | Wear & Tear | Breakdown | MATOLAD | CEILING BOARD | BUILDING | 2025-03-11 | 9 | 2025-03-11 | 0 | 2025-03-11 | 0 | [9 empty] | Overdue
168 | FAULTY FEMALE AND MALE CUSTOMER REST-ROOM TOILET HANGER | LAG, OPEBI | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-03-11 | 9 | 2025-03-11 | 0 | 2025-03-11 | 0 | [9 empty] | Overdue
169 | GENERATOR DUE FOR SERVICE | LAG, FREEDOMWAY | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-03-13 | 7 | 2025-03-13 | 0 | 2025-03-13 | 0 | [9 empty] | Overdue
170 | FAULTY ELECTRICITY ALARM SENSOR | LAG, IKOTUN | Electrical Surge | Breakdown | EMMANUEL | FIRE ALARM PANEL | FIRE | 2025-03-13 | 7 | 2025-03-13 | 0 | 2025-03-13 | 0 | [9 empty] | Overdue
171 | BURNT WATER TREATMENT PUMPING MACHINE | LAG, FREEDOMWAY | Electrical Surge | Breakdown | PROPEAR | WATER TREATMENT PLANT BLD | BUILDING | 2025-03-10 | 10 | 2025-03-10 | 0 | 2025-03-10 | 0 | [9 empty] | Overdue
172 | FULTY FREEZER ROOM | LAG, IDIMU | Routine Servicing | Preventive | DYNAMITE | FREEZER ROOM | HVAC | 2025-03-10 | 10 | 2025-03-10 | 0 | 2025-03-11 | 1 | [9 empty] | Overdue
173 | FAULTY FREEZER ROOM | LAG, JIBOWU | Routine Servicing | Preventive | DYNAMITE | FREEZER ROOM | HVAC | 2025-03-14 | 6 | 2025-03-14 | 0 | 2025-03-14 | 0 | [9 empty] | Overdue
174 | Electrical Equipments not Powering ON - Food Safety Concern | LAG, OMOLE | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 677250 | Completed | 2025-03-14 | 1
175 | Loose grease trap baskets | LAG, OSOLOWAY | Wear & Tear | Breakdown | PENTICCOSTAL | GREASE TRAP | GREASE_TRAP | 2025-03-14 | 6 | 2025-03-14 | 0 | 2025-03-14 | 0 | [9 empty] | Overdue
176 | BAD DOOR AT WASTE BIN AREA AND WATER TREATMENT AREA | LAG, BADORE | Wear & Tear | Breakdown | MODEL | OTHERS | OTHERS | 2025-03-10 | 10 | 2025-03-10 | 0 | 2025-03-12 | 2 | 2025-03-13 | 2025-03-13 | 0 | 2025-03-13 | 1 | 2025-03-14 | 6 |  | 320000 | Overdue
177 | FAULTY GAS BURNER CONTROL AND SERVICING. | LAG, ABULE EGBA | Wear & Tear | Breakdown | BERRADE | GAS HOSE & SUNDRIES | GAS | 2025-03-15 | 5 | 2025-03-15 | 0 | 2025-03-15 | 0 | 2025-03-17 | 2025-03-17 | 0 | 2025-03-17 | 3 |  |  |  | 52125 | Overdue
178 | RE: RATIOANAL MAKING UNUSUAL SOUND. | LAG, IKEJA MALL | Routine Servicing | Preventive | BCE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2025-03-15 | 5 | 2025-03-15 | 0 | 2025-03-15 | 0 | [9 empty] | Overdue
179 | RE: FAULTY FREEZER ROOM | ABUJA, KARU | Routine Servicing | Preventive | DANTEM | FREEZER ROOM | HVAC | 2025-03-13 | 7 | 2025-03-13 | 0 | 2025-03-15 | 2 | [9 empty] | Overdue
180 | Re: DAILY EQUIPMENT STATUS | PPU Ajah | Others | Breakdown | JOEL | OTHERS | OTHERS | 2025-03-14 | 1 | 2025-03-14 | 0 | 2025-03-15 | 1 | 2025-03-15 | 2025-03-15 | 0 | 2025-03-15 | 0 | 2025-03-15 | 0 | 2025-03-15 |  | Completed | 2025-03-15 | 1
181 | FAULTY CABINET BULB AND DOOR LOCK. | LAG, OGUDU | Others | Breakdown | FULL TURN | OTHERS | OTHERS | 2025-03-13 | 4 | 2025-03-13 | 0 | 2025-03-14 | 1 | 2025-03-14 | 2025-03-14 | 0 | 2025-03-15 | 0 | 2025-03-15 | 2 | 2025-03-17 | 39825.75 | Completed | 2025-03-17 | 1
182 | Re: LEAKING DIESEL | LAG, OMOLE | Wear & Tear | Breakdown | MID TECH | GENERATOR | GENERATOR | 2025-03-15 | 5 | 2025-03-15 | 0 | 2025-03-15 | 0 | 2025-03-15 | 2025-03-15 | 0 | 2025-03-15 | 5 |  |  |  | 80000 | Overdue
183 | Re: REQUEST ENGINE OIL | LAG, OGUNLANA DRIVE | Others | Breakdown | GAMMA | GENERATOR | GENERATOR | 2025-03-15 | 5 | 2025-03-15 | 0 | 2025-03-15 | 0 | [9 empty] | Overdue
184 | Store painting needed |  | Wear & Tear | Breakdown | GENEROUS | PAINTING | BUILDING | 2025-03-11 | 9 | 2025-03-11 | 0 | 2025-03-11 | 0 | 2025-03-15 | 2025-03-18 | 3 | 2025-03-18 | 2 |  |  |  | 510000 | Overdue
185 | Re: Issues that needs to be resolved |  | Routine Servicing | Preventive | PENTECOSTAL | OTHERS | OTHERS | 2025-03-11 | 9 | 2025-03-11 | 0 | 2025-03-11 | 0 | 2025-03-17 |  | 3 | [6 empty] | Overdue
186 | Re: Issues that needs to be resolved |  | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-03-11 | 9 | 2025-03-11 | 0 | 2025-03-13 | 2 | 2025-03-13 | 2025-03-14 | 1 | 2025-03-14 | 1 | 2025-03-15 | 5 |  | 1550000 | Overdue
187 | Re: FAULTY HAND | LAG, IKEJA MALL | Others | Breakdown | ACORN | OTHERS | OTHERS | 2025-03-15 | 5 | 2025-03-15 | 0 | 2025-03-16 | 1 | 2025-03-19 | 2025-03-19 | 0 | 2025-03-19 | 0 | 2025-03-19 | 1 |  |  | Overdue
188 | Re: BURSTED PIPE IN THE WATER TREATMENT PL | LAG, OMOLE | Wear & Tear | Breakdown | PROPEAR | WATER TREATMENT PLANT BLD | BUILDING | 2025-03-15 | 5 | 2025-03-15 | 0 | 2025-03-15 | 0 | [9 empty] | Overdue
189 | SERVICING OF GREASE TRAP | LAG, IKOTUN | Routine Servicing | Preventive | PENTECOSTAL | GREASE TRAP | GREASE_TRAP | 2025-03-14 | 6 | 2025-03-14 | 0 | 2025-03-15 | 1 | 2025-03-15 |  | 5 | [6 empty] | Overdue
190 | FAULTY WARMER | LAG, AGUNGI | Routine Servicing | Preventive | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-03-14 | 1 | 2025-03-14 | 0 | 2025-03-15 | 1 | 2025-03-15 | 2025-03-15 | 0 | 2025-03-15 | 0 | 2025-03-15 | 0 | 2025-03-15 |  | Completed | 2025-03-15 | 1
191 | FAULTY WARMER | KADUNA, CONSTITUTION RD | Routine Servicing | Preventive | BCE | UPRIGHT WARMER MACHINE | HVAC | 2025-03-10 | 10 | 2025-03-10 | 0 | 2025-03-10 | 0 | [9 empty] | Overdue
192 | Re: FAULTY PRESSURE FRYER MACHINE | LAG, OKE-AFA | Wear & Tear | Breakdown | HEFHEM | PRESURE FRYER 1 | KITCHEN_EQUIPMENT | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 |  | Completed | 2025-03-14 | 1
193 | FAULTY ROTESERRIE MACHINE (NNPC ALAPERE) | LAG, NNPC ALAPERE | Routine Servicing | Preventive | HEFHEM | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT | 2025-03-14 | 3 | 2025-03-14 | 0 | 2025-03-15 | 1 | 2025-03-15 | 2025-03-15 | 0 | 2025-03-15 | 0 | 2025-03-15 | 2 | 2025-03-17 |  | Completed | 2025-03-17 | 1
194 | Re: GREASE TRAP NOT FLOWING | LAG, BADORE | Routine Servicing | Preventive | JOEL | GREASE TRAP | GREASE_TRAP | 2025-03-13 | 1 | 2025-03-13 | 0 | 2025-03-14 | 1 | 2025-03-14 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 |  | Completed | 2025-03-14 | 1
195 | BAD INVERTER | LAG, OBA AKRAN | Electrical Surge | Breakdown | DALEMATRIX | INVERTER DB | ELECTRICAL | 2025-03-14 | 6 | 2025-03-14 | 0 | 2025-03-14 | 0 | [9 empty] | Overdue
196 | BACK OF HOUSE FLOORING | LAG, JIBOWU | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-03-12 | 8 | 2025-03-12 | 0 | 2025-03-14 | 2 | 2025-03-14 | 2025-03-18 | 4 | [5 empty] | 165000 | Overdue
197 | : Re: INVERVER NOT CHARGING UP |  | Electrical Surge | Breakdown | CURRENTDATA | INVERTER BATTERIES | INVERTER | 2025-03-12 | 8 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-14 | 2025-03-14 | 0 | 2025-03-14 | 6 |  |  |  |  | Overdue
198 | Re: WATER NOT RUNNING IN THE STORE | LAG, VGC | Routine Servicing | Preventive | JOEL | OTHERS | OTHERS | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 |  | Completed | 2025-03-14 | 1
199 | Air conditioning units due for service | LAG, ILUPEJU | Routine Servicing | Preventive | ODERINDE | 5HP STANDING AC UNIT 1 | HVAC | 2025-03-13 | 7 | 2025-03-14 | 1 | 2025-03-14 | 0 | [9 empty] | Overdue
200 | Re: NEPA POWER SUPPLY ISSUE | LAG, OMOLE | Electrical Surge | Breakdown | TIMILEHIN | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-03-14 | 6 | 2025-03-14 | 0 | 2025-03-14 | 0 | [9 empty] | Overdue
201 | REQUEST FOR BLENDER | LAG, EKORO | Users Misuse | Breakdown | TAYO | OTHERS | OTHERS | 2025-03-13 | 1 | 2025-03-13 | 0 | 2025-03-14 | 1 | 2025-03-14 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 |  | Completed | 2025-03-14 | 1
202 | FAULTY COLD ROOM | LAG, LEKKI PHASE 1 | Routine Servicing | Preventive | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-03-16 | 4 | 2025-03-16 | 0 | 2025-03-16 | 0 | [9 empty] | Overdue
203 | ALL THE STORE LOBBY LIGHT AND CASH POINT NOT WORKING | LAG, LEKKI PHASE 1 | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-03-09 | 1 | 2025-03-09 | 0 | 2025-03-10 | 1 | 2025-03-10 | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-10 |  | Completed | 2025-03-10 | 1
204 | FAULTY CHEST FREEZER | Central Kitchen | Routine Servicing | Preventive | BB | CHEST FREEZER | HVAC | 2025-03-15 | 5 | 2025-03-15 | 0 | 2025-03-16 | 1 | [9 empty] | Overdue
205 | NO WATER IN THE STORE | ABUJA, KARU | Others | Breakdown | JPILLAR | WATER TREATMENT PLANT BLD | BUILDING | 2025-03-10 | 4 | 2025-03-10 | 0 | 2025-03-14 | 4 | 2025-03-14 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 | 0 | 2025-03-14 |  | Completed | 2025-03-14 | 1
206 | NO RUNNING WATER IN THE STORE | LAG, AWOLOWO | Others | Breakdown | JOEL | OTHERS | OTHERS | 2025-03-09 | 1 | 2025-03-09 | 0 | 2025-03-10 | 1 | 2025-03-10 | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-10 | 0 | 2025-03-10 |  | Completed | 2025-03-10 | 1
207 | LEAKING WATER TREATMENT PLANT SURFACE PUMP | LAG, AKOWONJO | Wear & Tear | Breakdown | PROPEARJEFF | WATER TREATMENT PLANT BLD | BUILDING | 2025-03-04 | 0 | 2025-03-04 | 0 | 2025-03-04 | 0 | 2025-03-04 | 2025-03-04 | 0 | 2025-03-04 | 0 | 2025-03-04 | 0 | 2025-03-04 |  | Completed | 2025-03-04 | 1
208 | REPALCEMENT OF FEMALE CLOAK ROOM DOOR | LAG, OGUNLANA DRIVE | Wear & Tear | Breakdown | MATOLAD | OTHERS | OTHERS | 2025-03-09 | 11 | 2025-03-09 | 0 | 2025-03-10 | 1 | 2025-03-17 | 2025-03-18 | 1 | 2025-03-18 | 0 | 2025-03-18 | 2 | 2025-03-19 | 300000 | Overdue
209 | BROKEN CABINET GLASS | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-10 | 10 | 2025-03-11 | 1 | 2025-03-17 | 6 | [9 empty] | Overdue
210 | POWER OUTAGE | PPU Ajah | Electrical Surge | Breakdown | EEDC | MAIN ELECTRICAL PANEL | ELECTRICAL | 2025-03-17 | 3 |  | 3 | [11 empty] | Overdue
211 | LEAKING COLD ROOM PIPE/LEAKING COLD ROOM PIPE INSIDE THE CEILING | LAG, SKYMALL | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-03-03 | 17 | 2025-03-03 | 0 | 2025-03-17 | 14 | [9 empty] | Overdue
212 | GENERATOR DUE FOR SERVICE | LAG, OKOTA | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-03-17 | 3 | 2025-03-17 | 0 |  | 3 | [9 empty] | Overdue
213 | SEPTIC TANK EVACUATION | LAG, IKORODU | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2025-03-17 | 3 | 2025-03-17 | 0 |  | 3 | [9 empty] | Overdue
214 | CR FREEDOM WAY COLD ROOM DOOR PUSHER NOT WORKING | LAG, FREEDOMWAY | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-03-13 | 7 | 2025-03-13 | 0 | 2025-03-17 | 4 | [9 empty] | Overdue
215 | FIXING OF BATEERY ALTERNATOR |  | Wear & Tear | Breakdown | MIDTECH | GENERATOR | GENERATOR | 2025-03-16 | 4 | 2025-03-16 | 0 |  | 4 | [9 empty] | Overdue
216 | LOBBY/A/C NOT WORKING | LAG, OKOTA | Wear & Tear | Breakdown | G.B BOYEJO | 5HP STANDING AC UNIT 1 | HVAC | 2025-03-17 | 3 | 2025-03-17 | 0 |  | 3 | [9 empty] | Overdue
217 | FREEZER ROOM BREAKDOWN (NOT ATTAINING TEMPERATURE) | LAG, OGUDU | Wear & Tear | Breakdown | TONA OGUNS | FREEZER ROOM | HVAC | 2025-03-17 | 3 | 2025-03-17 | 0 |  | 3 | [9 empty] | Overdue
218 | FLICKERING LIGHT BULB | LAG, ILUPEJU | Wear & Tear | Breakdown | ADEWALE | OTHERS | OTHERS | 2025-03-12 | 6 | 2025-03-12 | 0 | 2025-03-12 | 0 | 2025-03-18 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 |  | Completed | 2025-03-18 | 1
219 | OPEBI STORE WEAK STRUCTURE | LAG, OPEBI | Wear & Tear | Breakdown | VENYS | OTHERS | OTHERS | 2025-03-13 | 4 | 2025-03-13 | 0 | 2025-03-17 | 4 | 2025-03-17 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 | 136983.72 | Completed | 2025-03-17 | 1
220 | CABINET BULB |  | Electrical Surge | Breakdown | KITCHTEC | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-17 | 3 | 2025-03-17 | 0 |  | 3 | [9 empty] | Overdue
221 | WATER LEAKAGE FROM RATIONALE MACHINE INSTALLATION AREA | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | PROEQUIP | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2025-03-17 | 3 | 2025-03-17 | 0 |  | 3 | [9 empty] | Overdue
222 | BAD 2 LOBBY AC AND 1 OFFICE AC | LAG, MOBIL OGBA | Routine Servicing | Preventive | TRIPPLEO | OTHERS | OTHERS | 2025-03-17 | 3 | 2025-03-17 | 0 | 2025-03-17 | 0 | [9 empty] | Overdue
223 | HIGH DIESEL CONSUMPTION (LTR PER HOUR) | LAG, IDI-IROKO RD | Routine Servicing | Preventive | MIDTECH | OTHERS | OTHERS | 2025-03-10 | 10 | 2025-03-10 | 0 | 2025-03-10 | 0 | [9 empty] | Overdue
224 | GENERATOR SERVICE. | KADUNA, AHMADU DELLO WAY | Routine Servicing | Preventive | CONCIRCLE | GENERATOR | GENERATOR | 2025-03-17 | 3 | 2025-03-17 | 0 | 2025-03-17 | 0 | [9 empty] | Overdue
225 | FREEZER NOT WORKING | LAG, IKEJA MALL | Routine Servicing | Preventive | TONA OGUNS | FREEZER ROOM | HVAC | 2025-03-17 | 3 | 2025-03-17 | 0 |  | 3 | [9 empty] | Overdue
226 | BAD ENTRANCE DOOR HANDLE | LAG, MOBIL OGBA | Wear & Tear | Breakdown | TAIDAV | OTHERS | OTHERS | 2025-03-17 | 3 | 2025-03-17 | 0 |  | 3 | [9 empty] | Overdue
227 | PULLING HINGES | LAG, OMOLE | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-03-15 | 2 | 2025-03-17 | 2 | 2025-03-17 | 0 | 2025-03-17 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 |  | Completed | 2025-03-17 | 1
228 | REPLACEMENT DAMAGED LOBBY WALL PAPER | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | ADEBOLA4ONAS | OTHERS | OTHERS | 2025-03-12 | 8 | 2025-03-12 | 0 | 2025-03-17 | 5 | [9 empty] | Overdue
229 | REPLACEMENT DAMAGED LOBBY WALL PAPER | LAG, BODE THOMAS | Wear & Tear | Breakdown |  | OTHERS | OTHERS | 2025-03-12 | 8 | 2025-03-12 | 0 |  | 8 | [9 empty] | Overdue
230 | AIR VENTS REQUEST | LAG, VGC | Others | Breakdown | ABBEY | OTHERS | OTHERS | 2025-03-05 | 15 | 2025-03-05 | 0 | 2025-03-17 | 12 | 2025-03-17 | 2025-03-17 | 0 | 2025-03-17 | 1 | 2025-03-18 | 2 |  | 195000 | Overdue
231 | FAULTY COOK TAP | LAG, TOTAL LEKKI | Wear & Tear | Breakdown | JOEL | TAP | PLUMBING | 2025-03-17 | 3 | 2025-03-17 | 0 |  | 3 | [9 empty] | Overdue
232 | GENERATOR DUE FOR SERVICE | LAG, ETERNA LEKKI | Routine Servicing | Preventive | MIDTECH | GENERATOR | GENERATOR | 2025-03-17 | 3 | 2025-03-17 | 0 |  | 3 | [9 empty] | Overdue
233 | GENERATOR DUE FOR SERVICE + RADIATOR LEAKAGE - CR-TEJUOSHO, YABA, LAGOS | LAG, TEJUOSHO | Routine Servicing | Preventive | KB | GENERATOR | GENERATOR | 2025-03-15 | 5 | 2025-03-15 | 0 | 2025-03-17 | 2 | 2025-03-17 | 2025-03-17 | 0 | 2025-03-17 | 3 |  |  |  | 333250 | Overdue
234 | SOAP AND SANITIZER DISPENSER | PPU Oniru | Others | Breakdown | PRO-EQUIPTECH | OTHERS | OTHERS | 2025-03-17 | 3 | 2025-03-17 | 0 |  | 3 | [9 empty] | Overdue
235 | LOBBY AC NOT ATTAINING TEMPRETURE |  | Routine Servicing | Preventive | TONA OGUNS | 5HP STANDING AC UNIT 1 | HVAC | 2025-03-17 | 3 | 2025-03-17 | 0 | 2025-03-17 | 0 | [9 empty] | Overdue
236 | LEAKAGE UNDER FRYER AND COOK SINK | LAG, FESTAC | Wear & Tear | Breakdown | OLUWATOSIN | OTHERS | OTHERS | 2025-03-17 | 1 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-18 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 |  | Completed | 2025-03-18 | 1
237 | Request for Repair of Male changing room Door | LAG, BADORE | Wear & Tear | Breakdown | FULL TURN | OTHERS | OTHERS | 2025-03-16 | 4 | 2025-03-17 | 1 | 2025-03-17 | 0 | 2025-03-17 | 2025-03-17 | 0 | 2025-03-17 | 1 | 2025-03-18 | 2 |  | 34400 | Overdue
238 | WALL FAN AT THE BOH | LAG, FESTAC | Others | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-03-17 | 3 | 2025-03-17 | 0 |  | 3 | [9 empty] | Overdue
239 | BLINKING LED BULBS/ DEAD LOBBY BULB IN THE STORE | LAG, AKOWONJO | Electrical Surge | Breakdown | FRIDAY | OTHERS | OTHERS | 2025-03-17 | 3 | 2025-03-17 | 0 |  | 3 | [9 empty] | Overdue
240 | POWER SURGE IN STORE( BAD EXTRACTOR LIGHTS BULBS) | LAG, IDI-IROKO RD | Electrical Surge | Breakdown | TAYO | EXTRACTION SYSTEM (FRESH AIR) | HVAC | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 |  | Completed | 2025-03-17 | 1
241 | FAULTY DRYSTORE AIR CONDITIONER | LAG, AKOWONJO | Routine Servicing | Preventive | ADEGBENRO | SPLIT UNIT DRY STORE | HVAC | 2025-03-17 | 3 | 2025-03-17 | 0 |  | 3 | [9 empty] | Overdue
242 | FAULTY HENNY PENNY ,MACHINE | LAG, AWOLOWO | Corrective Action | Corrective | ISMAIL | OTHERS | OTHERS | 2025-03-15 | 2 | 2025-03-15 | 0 | 2025-03-17 | 2 | 2025-03-17 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 |  | Completed | 2025-03-17 | 1
243 | DE-WEEDING OF TRANSFORMER HOUSE | LAG, OSOLOWAY | Others | Breakdown | GBATMO | TRANSFORMER | ELECTRICAL | 2025-03-14 | 6 | 2025-03-14 | 0 | 2025-03-17 | 3 | [9 empty] | Overdue
244 | POLARITY ISSUE A | LAG, AWOLOWO | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-03-16 | 1 | 2025-03-16 | 0 | 2025-03-17 | 1 | 2025-03-17 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 | 0 | 2025-03-17 |  | Completed | 2025-03-17 | 1
245 | LEAKAGE HOT WATER SOURCE AT FRYER SECTION. | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | ADEREMI WAHAB | WATER HEATER | PLUMBING | 2025-03-18 | 1 | 2025-03-18 | 0 | 2025-03-19 | 1 | 2025-03-19 | 2025-03-19 | 0 | 2025-03-19 | 0 | 2025-03-19 | 0 | 2025-03-19 |  | Completed | 2025-03-19 | 1
246 | NO RUNNING WATER IN THE STORE | LAG, ETERNA LEKKI | Wear & Tear | Breakdown | JOEL | TAP | PLUMBING | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 |  | Completed | 2025-03-18 | 1
247 | FAULTY ICE CREAM MACHINE | LAG, AWOLOWO | Wear & Tear | Breakdown | JUSTFOOD | ICE CREAM MACHINE | KITCHEN_EQUIPMENT | 2025-03-16 | 4 | 2025-03-16 | 0 |  | 4 | [9 empty] | Overdue
248 | FAULTY WALL SOCKETS | LAG, IKOTUN | Wear & Tear | Breakdown | EMMANUEL | OTHERS | OTHERS | 2025-03-05 | 15 | 2025-03-05 | 0 | 2025-03-06 | 1 | [9 empty] | Overdue
249 | FAULTY CHEST FREEZER | LAG, DOMINO E-CENTRE | Wear & Tear | Breakdown | BB COMMERCIAL | CHEST FREEZER | HVAC | 2025-03-15 | 5 | 2025-03-15 | 0 | 2025-03-17 | 2 | [9 empty] | Overdue
250 | FAULTY TISSUE HANGER IN THE CUSTOMER RESTROOM | LAG, OPEBI | Users Misuse | Breakdown | PROPARJEFF | OTHERS | OTHERS | 2025-03-15 | 5 | 2025-03-15 | 0 |  | 5 | [9 empty] | Overdue
251 | TOASTER NOT ATTAINING TEMPERATURE | LAG, TEJUOSHO | Wear & Tear | Breakdown | TIMILEHIN | TOASTER MACHINE | KITCHEN_EQUIPMENT | 2025-03-18 | 2 | 2025-03-18 | 0 |  | 2 | [9 empty] | Overdue
252 | REQUEST FOR INSECTOCUTOR BULBS AND CEILING LIGHTS | LAG, IDI-IROKO RD | Wear & Tear | Breakdown | TAYO | OTHERS | OTHERS | 2025-03-18 | 2 | 2025-03-18 | 0 |  | 2 | [9 empty] | Overdue
253 | LOBBY/ DRY STORE AC NOT ATTAINNING TEMPERATURE | LAG, TEJUOSHO | Wear & Tear | Breakdown | G.B BOYEJO | 5HP STANDING AC UNIT 1 | HVAC | 2025-03-17 | 3 | 2025-03-18 | 1 |  | 2 | [9 empty] | Overdue
254 | COLD ROOM NOT ATTAINING TEMPERATURE | LAG, JOEL OGUNNAIKE | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-03-18 | 2 | 2025-03-18 | 0 | 2025-03-19 | 1 | [9 empty] | Overdue
255 | FAULTY AC IN DRY STORE AND DOWN STAIRS LOBBY | LAG, BADORE | Wear & Tear | Breakdown
256 | STORE LIGHT ISSUES WITH THE FILLING STATION |  | Electrical Surge | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-03-07 | 11 | 2025-03-12 | 5 | 2025-03-12 | 0 | 2025-03-17 | 2025-03-17 | 0 | 2025-03-17 | 1 | 2025-03-18 | 0 | 2025-03-18 | 31830 | Completed | 2025-03-18 | 1
257 | GENERATOR DUE FOR SERVICING | LAG, MARINA | Routine Servicing | Preventive | MID TECH | GENERATOR | GENERATOR | 2025-03-18 | 2 | 2025-03-18 | 0 | 2025-03-18 | 0 | [9 empty] | Overdue
258 | GENERATOR DUE FOR SERVICING | LAG, GBAGADA | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-03-18 | 2 | 2025-03-18 | 0 | 2025-03-18 | 0 | [9 empty] | Overdue
259 | GENERATOR DUE FOR SERVICING | LAG, NNPC ALAPERE | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-03-18 | 2 | 2025-03-18 | 0 | 2025-03-18 | 0 | [9 empty] | Overdue
260 | PX EKORO ROLLER SHUTTER IS STEVEE AND HANDING TO ROLL UP | LAG, EKORO | Wear & Tear | Breakdown | PENTECOSTAL | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-03-18 | 2 | 2025-03-18 | 0 | 2025-03-19 | 1 | 2025-03-19 |  | 1 | [6 empty] | Overdue
261 | MATERIALS INSTALLATION |  | Others | Breakdown | TIMILEHIN | OTHERS | OTHERS | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 |  | Completed | 2025-03-18 | 1
262 | BROKEN HANDWASH BASIN STAND | LAG, MARINA | Wear & Tear | Breakdown | PROPEAR | LOBBY WASH HAND BASIN | PLUMBING | 2025-03-18 | 2 | 2025-03-18 | 0 |  | 2 | [9 empty] | Overdue
263 | COLLAPSED OFFICE TABLE | LAG, VGC | Wear & Tear | Breakdown | ADEBOLA4ONAS | OFFICE DESK | FURNITURE | 2025-03-18 | 2 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 | 2025-03-18 | 0 | 2025-03-18 | 0 | 2025-03-18 | 2 |  | 500000 | Overdue
264 | Issues that needs to be resolved at aguda store (Tiles and civil works) |  | Wear & Tear | Breakdown | ARIZMAYAN | OTHERS | OTHERS | 2025-03-07 | 13 | 2025-03-07 | 0 | 2025-03-12 | 5 | 2025-03-12 | 2025-03-18 | 6 | 2025-03-18 | 0 | 2025-03-18 | 2 |  | 395000 | Overdue
265 | FAULTY EXTRACTOR BULB | LAG, IKOTUN | Electrical Surge | Breakdown | EMMANUEL | EXTRACTION SYSTEM (EXTRACTOR) | HVAC | 2025-03-18 | 2 | 2025-03-18 | 0 | 2025-03-18 | 0 | [9 empty] | Overdue
266 | LOBBY TV NOT WORKING | LAG, MARINA | Wear & Tear | Breakdown | ACORN | TELEVISION | AUDIOVISUAL | 2025-03-18 | 2 | 2025-03-18 | 0 | 2025-03-19 | 1 | 2025-03-19 | 2025-03-19 | 0 | 2025-03-19 | 1 |  |  |  |  | Overdue
267 | BAD WATER TREATMENT NET | LAG, AJOSE ADEOGUN | Wear & Tear | Breakdown | TAIDAV | WATER TREATMENT PLANT BLD | BUILDING | 2025-03-19 | 1 | 2025-03-19 | 0 |  | 1 | [9 empty] | Overdue
268 | COLDROOM NOT ATTAINING TEMPERATURE | LAG, OPEBI | Wear & Tear | Breakdown | TONA OGUNS | COLD ROOM UNIT | HVAC | 2025-03-19 | 1 | 2025-03-19 | 0 |  | 1 | [9 empty] | Overdue
269 | FAULTY GENERATOR ONIRU PPU | PPU Oniru | Wear & Tear | Breakdown | DELIGHTSOME | GENERATOR | GENERATOR | 2025-03-19 | 1 | 2025-03-19 | 0 |  | 1 | [9 empty] | Overdue
270 | MISSING GRILL ON AC OUTDOOR UNIT | LAG, OSOLOWAY | Wear & Tear | Breakdown | MODEL | 5HP STANDING AC UNIT 1 | HVAC | 2025-03-14 | 6 | 2025-03-14 | 0 | 2025-03-19 | 5 | 2025-03-19 |  | 1 | [6 empty] | Overdue
271 | ALL THE STORE LOBBY LIGHT AND CASH POINT NOT WORKING | LAG, LEKKI PHASE 1 | Electrical Surge | Breakdown | ISMAIL | OTHERS | OTHERS | 2025-03-19 | 1 | 2025-03-19 | 0 |  | 1 | [9 empty] | Overdue
272 | Faulty Rationale Oven | PPU Ilupeju | Wear & Tear | Breakdown | BCE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2025-03-19 | 1 | 2025-03-19 | 0 |  | 1 | [9 empty] | Overdue
273 | BLOWN BULB AT THE BOH | LAG, ENTOURAGE MALL | Wear & Tear | Breakdown | ISMAIL | 18W ROUND LIGHT FITTING | ELECTRICAL | 2025-03-19 | 0 | 2025-03-19 | 0 | 2025-03-19 | 0 | 2025-03-19 | 2025-03-19 | 0 | 2025-03-19 | 0 | 2025-03-19 | 0 | 2025-03-19 |  | Completed | 2025-03-19 | 1
274 | FAULTY UV LIGHT | LAG, EKORO | Wear & Tear | Breakdown | PROPEARJEFF | UV LIGHT | WTP | 2025-03-19 | 1 | 2025-03-19 | 0 |  | 1 | [9 empty] | Overdue
275 | BROKEN CABINET GLASS |  | Users Misuse | Breakdown | TAIDAV | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-18 | 2 | 2025-03-18 | 0 | 2025-03-19 | 1 | [9 empty] | Overdue
276 | REPLACEMENT OF ENTRANCE DOOR GASKET | LAG, GBAGADA | Wear & Tear | Breakdown | TAIDAV | ENTRANCE ROLLER SHUTTER | SECURITY | 2025-03-18 | 1 | 2025-03-18 | 0 | 2025-03-19 | 1 | 2025-03-19 | 2025-03-19 | 0 | 2025-03-19 | 0 | 2025-03-19 | 0 | 2025-03-19 |  | Completed | 2025-03-19 | 1
277 | REQUEST FOR GENERATOR SERVICING | LAG, AJOSE ADEOGUN | Routine Servicing | Preventive | GAMMA | GENERATOR | GENERATOR | 2025-03-19 | 1 | 2025-03-19 | 0 |  | 1 | [9 empty] | Overdue
278 | EVACUATION OF SEWAGE AT THE HEAD OFFICE | LAG, ILUPEJU | Others | Breakdown | MOONLIGHT | SEPTIC TANK | EVACUATION | 2025-03-18 | 2 | 2025-03-18 | 0 | 2025-03-19 | 1 | [9 empty] | Overdue
279 | A/C NOT WORKING | KADUNA, YAKUBU GOWON | Wear & Tear | Breakdown | OLANIYI | 5HP STANDING AC UNIT 1 | HVAC | 2025-03-18 | 1 | 2025-03-18 | 0 | 2025-03-19 | 1 | 2025-03-19 | 2025-03-19 | 0 | 2025-03-19 | 0 | 2025-03-19 | 0 | 2025-03-19 |  | Completed | 2025-03-19 | 1
280 | DIESEL TANK CALIBRATION | LAG, AGUNGI | Wear & Tear | Breakdown | DAMI FOTE | GENERATOR | GENERATOR | 2025-03-18 | 2 | 2025-03-19 | 1 |  | 1 | [9 empty] | Overdue
281 | EVACUATION OF SOAK AWAY | BENUE, OLD OTUKPO | Others | Breakdown | TEKNEKA | SEPTIC TANK | EVACUATION | 2025-03-17 | 3 | 2025-03-19 | 2 |  | 1 | [9 empty] | Overdue
282 | REQUEST FOR CABINET BULBS | LAG, VGC | Wear & Tear | Breakdown | ADEREMI KAZEEM | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-19 | 1 | 2025-03-19 | 0 |  | 1 | [9 empty] | Overdue
283 | OFFICE AC STOPPED WORKING | LAG, AWOLOWO 2 | Wear & Tear | Breakdown | G.B BOYEJO | 5HP STANDING AC UNIT 1 | HVAC | 2025-03-19 | 1 | 2025-03-19 | 0 |  | 1 | [9 empty] | Overdue
284 | LOBBY'S AC NAKED WIRES AND DRY STORE AC | LAG, MARINA | Wear & Tear | Breakdown | G.B BOYEJO | 5HP STANDING AC UNIT 1 | HVAC | 2025-03-19 | 1 | 2025-03-19 | 0 |  | 1 | [9 empty] | Overdue
285 | FAULTY DICING MACHINE | PPU Oniru | Wear & Tear | Breakdown | BCE | DICING MACHINE | KITCHEN_EQUIPMENT | 2025-03-19 | 1 | 2025-03-19 | 0 |  | 1 | [9 empty] | Overdue
286 | FAULTY GENERATOR ONIRU PPU | LAG, ONIRU | Wear & Tear | Breakdown | DELIGHSOME | GENERATOR | GENERATOR | 2025-03-19 | 1 | 2025-03-19 | 0 | 2025-03-20 | 1 | [9 empty] | Overdue
287 | TORN WATER TREATMENT NET | LAG, LEKKI PHASE 1 | Wear & Tear | Breakdown | TAIDAV | WATER TREATMENT PLANT BLD | BUILDING | 2025-03-11 | 9 | 2025-03-11 | 0 |  | 9 | [9 empty] | Overdue
288 | CABINET NOT WORKING | NASSARAWA, KEFFI | Wear & Tear | Breakdown | BCE | DISPLAY CABINET | KITCHEN_EQUIPMENT | 2025-03-18 | 2 | 2025-03-20 | 2 |  | 0 | [9 empty] | Overdue
289 | FAULTY HAND RAIL HOLDER | ABUJA, KARU | Wear & Tear | Breakdown | ANDREW | OTHERS | OTHERS | 2025-03-20 | 0 | 2025-03-20 | 0 |  | 0 | [9 empty] | Overdue
290 | RATIOANAL MAKING UNUSUAL SOUND. | LAG, IKEJA MALL | Corrective Action | Corrective | BCE | RATIONAL MACHINE | KITCHEN_EQUIPMENT | 2025-03-15 | 5 | 2025-03-15 | 0 | 2025-03-20 | 5 | [9 empty] | Overdue
291 | MAINTENANCE OPPORTUNITIES | LAG, DIYA STREET | Wear & Tear | Breakdown | PENTECOSTAL | OTHERS | OTHERS | 2025-03-18 | 2 | 2025-03-18 | 0 | 2025-03-20 | 2 | 2025-03-20 |  | 0 | [6 empty] | Overdue
292 | MAINTENANCE OPPORTUNITIES | LAG, DIYA STREET | Wear & Tear | Breakdown | WESTERN DESIGGN | PAINTING | BUILDING | 2025-03-18 | 2 | 2025-03-18 | 0 | 2025-03-20 | 2 | 2025-03-20 |  | 0 | [6 empty] | Overdue
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
Formulas:
Days Since Request = IF([Request Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Request Date],TODAY()-[Request Date]))
Days Delayed by Helpdesk = IF([Date Shared by Helpdesk]<>"",[Date Shared by Helpdesk]-[Request Date],IF([Request Date]="","",TODAY()-[Request Date]))
Days Delayed by Vendor/Technician = IF(M6<>"",M6-[Date Shared by Helpdesk],IF([Date Shared by Helpdesk]="","",TODAY()-[Date Shared by Helpdesk]))
Days Since Negotiation Request = TODAY() - [Date Negotiated]
Days Since Negotiation Request = IF([Date Negotiated]<>"",[Date Negotiated]-[Date Sent for Negotiation],IF([Date Sent for Negotiation]="","",TODAY()-[Date Sent for Negotiation]))
Days Since Approval Request = IF([Approved Date]<>"",[Approved Date]-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval Request = IF(#REF!<>"",#REF!-[Date Approval Requested],IF([Date Approval Requested]="","",TODAY()-[Date Approval Requested]))
Days Since Approval = IF([Approved Date]="","",IF([Actual delivery date]<>"",[Actual delivery date]-[Approved Date],TODAY()-[Approved Date]))
Days Since Approval = IF(#REF!="","",IF([Actual delivery date]<>"",[Actual delivery date]-#REF!,TODAY()-#REF!))
Status = IF([Request Date]="","",IF([Actual delivery date]<>"","Completed",IF(TODAY()<[Expected Delivery Date],"Planned",IF(TODAY()=[Expected Delivery Date],"Due","Overdue"))))
Note on AA6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vendor gave feedback thaat part is not available on 18 of Jan
Note on C28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR AGUDA
Note on C34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR AGUDA
Note on C36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR EBUTE-METTA
Note on C56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR HEYDEN EBUTE-METTA
Note on C71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR EBUTE METTA
Note on C75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR SANGOTEDO
Note on C79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX EBUTE META
Note on C87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: px bariga
Note on C103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ADEOLA ODEKU
Note on C117: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: cr aguda
Note on C122: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR AGUDA
Note on C123: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR AGUDA
Note on C126: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX EBUTE META
Note on C135: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX ADEOLA ODEKU
Note on C139: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: px heyden vgc
Note on C152: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PIE EXPRESS ADEOLA ODEKU
Note on C179: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: adeola odeku
Note on C187: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR AGUDA
Note on C188: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR AGUDA
Note on C189: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR AGUDA
Note on C192: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PIE EXPRESS FAGBA
Note on C200: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR ADEOLA ODEKU
Note on C218: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR Aguda
Note on C223: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR AGUDA
Note on C238: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR SANGOTEDO
Note on C259: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR HEYDEN EBUTE-METTA
Note on C264: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR AGUDA
Note on C267: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR AGUDA
Note on C278: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AGUDA
Note on C416: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PX IGANDO
Note on C492: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PPU RHAMART
Note on C551: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PPU Dutse Alhaji
Note on C552: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pie Express Agidingbi

## Sheet1
| FREEZER ROOMS | AND COLD ROOMS
| RATIONALE INSTALLATION - PROGRESS REPORT |  | - AJOSE
| PX FESTAC COUNTER ;> WAS ITDONE BY MATOLAD OR ANOTHER CONTRACTPR. READ MAIL TRAIL TO CONFIRM |  |  | M
NOISY AIR CURTAIN > CR MARINA SHOULD BE RENOGOTIATED AS IT KEEPS GETING FUMBLED
OCTOBER ...... | FAULTY INVERTER - OJOO IBADAN NEEDS CAREFUL EXAMINATION
TREAT CABINET BULBS
treat LEAKING AERATION TANK, SAND AND CARBON MEDIA - CR IKOT EKPENE - SINCE AUGUUST TO NOVEMBER
| EVACUATION OF SEPTIC TANK IN CR MAGODO 200&220, SEARCH,FILL UP AND CLEAR ONE |  |  |  | 50000
| FAULTY ROLLER SHUTTER SINCE SEPTEMBER; VERY CMPLICATED |  |  |  | 10000
| Re: Repainting of Okigwe ppu internal and exterior area and re-tiling of production area wall and floor. . SINCE SEPTEMBER |  |  |  | 10000
| FREEZER ROOM NOT ATTAINING TEMPERATURE . "CR Siluko Benin SINCE SEPT |  |  |  | 10000
| FAULTY SIGNAGE AND PYLON LIGHT - CR NWANIBA SINCE SEPTEMBER TODECEMBER, TRETATMAIL TRAIL AS URGENT. |  |  |  | 12000
| : OPEN CEILING AROUND THE EXTRACTOR AREA SINCE JULY 26 |  |  |  | 10000
FAULTY HENNY PENNY FORE HEAD MACHINE - OCTOBER DELETE ONE

## Sheet4
Find below mail trail from PPU Okigwe
Kindly assist with servicing their generator,
Please treat as urgent.
Regards,
Inioluwa.
FAULTY ENTRANCE GLASS pending sincE NOVEMBER

## Sheet2 (hidden)
BUILDING | ELECTRICAL | EVACUATION | FIRE | FURNITURE | GAS | GENERATOR | GREASE_TRAP | HVAC | INVERTER | KITCHEN_EQUIPMENT | OTHERS | PLUMBING | SECURITY | AUDIOVISUAL | WTP
CASHIER COUNTER | 18W ROUND LIGHT FITTING | SEPTIC TANK | FIRE ALARM PANEL | CHEMICAL CUPBOARD | GAS CYLINDER | 135KVA GENERATOR | GREASE TRAP | 5HP STANDING AC UNIT 1 | BATTERY RACK | CHIPS DUMP | BALOON STAND | KITCHEN WASH HAND SINK | ENTRANCE ROLLER SHUTTER |  | AERATION TANK
CEILING BOARD | CHANGE OVER |  | FIRE EXTINGUISHER | CHICKEN DUMP TROLLEY | GAS HOSE & SUNDRIES |  |  | 5HP STANDING AC UNIT 2 | INVERTER BATTERIES | CHIPS FRYER 1 | LOBBY WALL MIRROR | LOBBY WASH HAND BASIN | WINDOW ROLLER SHUTTER | TELEVISION | DOSING PUMP
CHAMBER | DIRECT POWER DB |  | SMOKE DETECTOR | CHICKEN TROLLEY |  |  |  | 5HP STANDING AC UNIT 3 | INVERTER SYSTEM | CHIPS FRYER 2 | OTHERS | TAP |  | GOTV DECODER | DOSING TANK
CULVERT | DROPPING LIGHT |  |  | CUSTOMER CHAIR |  |  |  | 5HP STANDING AC UNIT 4 |  | COLLECTRAMATIC OIL PUMP MACHINE | TOILET WALL MIRROR | TOILET WASH HAND BASIN |  | DSTV DECODER | FILTRATION PUMP 1
DRAIN COVER | FLOODLIGHT |  |  | CUSTOMER TABLE |  |  |  | CHEST FREEZER |  | COOKING BURNER |  | WATER HEATER |  | AMPLIFIER | FILTRATION PUMP 2
P.O.P | GEAR SWITCH |  |  | FLOOR CUPBOARD |  |  |  | COLD ROOM UNIT |  | DICING MACHINE |  |  |  |  | FILTRATION TANK
PAINTING | HAND DRYER LOBBY |  |  | OFFICE DESK |  |  |  | DEEP FREEZER |  | DISPLAY CABINET |  |  |  |  | FILTRATION VESSEL 1
PAVEMENT | HAND DRYER TOILET |  |  | PRODUCTION TABLE |  |  |  | EXTRACTION SYSTEM (EXTRACTOR) |  | GRINDING MACHINE |  |  |  |  | FILTRATION VESSEL 2
ROOF | INSECT KILLER BOH |  |  | WALL MOUNTED CLOSED CUPBOARD |  |  |  | EXTRACTION SYSTEM (FRESH AIR) |  | ICE CREAM MACHINE |  |  |  |  | GROUND WATER TANK
SLAB | INSECT KILLER LOBBY 1 |  |  | WALL MOUNTED SHELVE |  |  |  | FREEZER ROOM |  | OPEN FRYER MACHINE 1 |  |  |  |  | OVERHEAD WATER TANK
WALL | INSECT KILLER LOBBY 2 | [6 empty] | NBC CHILLER |  | OPEN FRYER MACHINE 2 |  |  |  |  | SUBMERSIBLE PUMP
WASTE BIN HOUSE | INVERTER DB | [6 empty] | SPLIT UNIT DRY STORE |  | PRESURE FRYER 1 |  |  |  |  | TRANSFER PUMP 1
WATER TREATMENT PLANT BLD | MAIN ELECTRICAL PANEL | [6 empty] | SPLIT UNIT MANAGER'S OFFICE |  | PRESURE FRYER 2 |  |  |  |  | TRANSFER PUMP 2
WINDOW | TRANSFORMER | [6 empty] | SPLIT UNIT TOILET |  | RATIONAL MACHINE |  |  |  |  | UV LIGHT
[8 empty] | UPRIGHT UNDERBAR MACHINE |  | ROTISSIERI MACHINE
[8 empty] | UPRIGHT WARMER MACHINE |  | SHREDDER
[8 empty] | WALL FAN |  | TOASTER MACHINE
Reason for Breakdwon
Routine Servicing
Wear & Tear
Electrical Surge
Corrective Action
Users Misuse
Others

## Sheet3 (hidden)
Reason for Breakdwon | Maintenance Breakdown | STORE | SPECIFIC EQUIPMENT | CATEGORY
Routine Servicing | Preventive | LAG, AJAH | CASHIER COUNTER | BUILDING
Wear & Tear | Breakdown | LAG, AJOSE ADEOGUN | CEILING BOARD | BUILDING
Electrical Surge | Breakdown | LAG, AKOWONJO | CHAMBER | BUILDING
Corrective Action | Corrective | LAG, BODE THOMAS | CULVERT | BUILDING
Users Misuse | Breakdown | LAG, DOMINO E-CENTRE | DRAIN COVER | BUILDING
Others | Breakdown | LAG, FESTAC | P.O.P | BUILDING
|  | LAG, AWOLOWO | PAINTING | BUILDING
|  | LAG, ILUPEJU | PAVEMENT | BUILDING
|  | LAG, IRE-AKARI | ROOF | BUILDING
|  | LAG, JIBOWU | SLAB | BUILDING
|  | LAG, ETERNA LEKKI | WALL | BUILDING
|  | LAG, IKEJA MALL | WASTE BIN HOUSE | BUILDING
|  | LAG, MARINA | WATER TREATMENT PLANT BLD | BUILDING
|  | LAG, OGUDU | WINDOW | BUILDING
|  | LAG, OKE-AFA | 18W ROUND LIGHT FITTING | ELECTRICAL
|  | LAG, OKOTA | CHANGE OVER | ELECTRICAL
|  | LAG, OMOLE | DIRECT POWER DB | ELECTRICAL
|  | LAG, OPEBI | DROPPING LIGHT | ELECTRICAL
|  | LAG, ENTOURAGE MALL | FLOODLIGHT | ELECTRICAL
|  | LAG, LEKKI PHASE 1 | GEAR SWITCH | ELECTRICAL
|  | ABUJA, AMINU KANO | HAND DRYER LOBBY | ELECTRICAL
|  | ABUJA, ADETOKUNBO ADEMOLA | HAND DRYER TOILET | ELECTRICAL
|  | ABUJA, AREA 8 | INSECT KILLER BOH | ELECTRICAL
|  | ABUJA, KUBWA | INSECT KILLER LOBBY 1 | ELECTRICAL
|  | ABUJA, GWARIMPA | INSECT KILLER LOBBY 2 | ELECTRICAL
|  | KADUNA, YAKUBU GOWON | INVERTER DB | ELECTRICAL
|  | NASSARAWA, NYANYA | MAIN ELECTRICAL PANEL | ELECTRICAL
|  | ABUJA, OANDO ZONE 6 | TRANSFORMER | ELECTRICAL
|  | KADUNA, ZARIA | SEPTIC TANK | EVACUATION
|  | KADUNA, BARNAWA | FIRE ALARM PANEL | FIRE
|  | EDO, AIRPORT RD, BENIN | FIRE EXTINGUISHER | FIRE
|  | EDO, UGBOWO, BENIN | SMOKE DETECTOR | FIRE
|  | PH, TRANS AMADI | CHEMICAL CUPBOARD | FURNITURE
|  | PH, RUMUBIAKANI | CHICKEN DUMP TROLLEY | FURNITURE
|  | PH, ABACHA RD | CHICKEN TROLLEY | FURNITURE
|  | IBADAN, RING-ROAD | CUSTOMER CHAIR | FURNITURE
|  | IBADAN, CHALLENGE | CUSTOMER TABLE | FURNITURE
|  | LAG, TOTAL ONIGBAGBO | FLOOR CUPBOARD | FURNITURE
|  | ABUJA, AMINU KANO DT | OFFICE DESK | FURNITURE
|  | ILORIN, GRA | PRODUCTION TABLE | FURNITURE
|  | LAG, MMA2 | WALL MOUNTED CLOSED CUPBOARD | FURNITURE
|  | PH, ABA | WALL MOUNTED SHELVE | FURNITURE
|  | LAG, VGC | GAS CYLINDER | GAS
|  | LAG, TEJUOSHO | GAS HOSE & SUNDRIES | GAS
|  | LAG, ONIRU | GENERATOR | GENERATOR
|  | LAG, ABULE EGBA | GREASE TRAP | GREASE_TRAP
|  | PH, GRA BIRABI | 5HP STANDING AC UNIT 1 | HVAC
|  | ILORIN, TAIWO RD | 5HP STANDING AC UNIT 2 | HVAC
|  | PH, DOX RD | 5HP STANDING AC UNIT 3 | HVAC
|  | ABUJA, GARKI | 5HP STANDING AC UNIT 4 | HVAC
|  | NIGER, SULEJA | CHEST FREEZER | HVAC
|  | LAG, GBAGADA | COLD ROOM UNIT | HVAC
|  | LAG, MAGODO | DEEP FREEZER | HVAC
|  | KANO, MM WAY | EXTRACTION SYSTEM (EXTRACTOR) | HVAC
|  | LAG, SKYMALL | EXTRACTION SYSTEM (FRESH AIR) | HVAC
|  | LAG, AWOLOWO 2 | FREEZER ROOM | HVAC
|  | KADUNA, CONSTITUTION RD | NBC CHILLER | HVAC
|  | LAG, IDIMU | SPLIT UNIT DRY STORE | HVAC
|  | IBADAN, BODIJA | SPLIT UNIT MANAGER'S OFFICE | HVAC
|  | PH AGGREY | SPLIT UNIT TOILET | HVAC
|  | LAG, OSOLOWAY | UPRIGHT UNDERBAR MACHINE | HVAC
|  | KANO, AIRPORT RD | UPRIGHT WARMER MACHINE | HVAC
|  | LAG, WAREHOUSE RD, APAPA | WALL FAN | HVAC
|  | IBADAN, IDI-APE (IWO RD) | BATTERY RACK | INVERTER
|  | LAG, FREEDOMWAY | INVERTER BATTERIES | INVERTER
|  | IBADAN, MOKOLA | INVERTER SYSTEM | INVERTER
|  | LAG, IKORODU | CHIPS DUMP | KITCHEN_EQUIPMENT
|  | ABUJA, LUGBE | CHIPS FRYER 1 | KITCHEN_EQUIPMENT
|  | LAG, NNPC ALAPERE | CHIPS FRYER 2 | KITCHEN_EQUIPMENT
|  | LAG AHMADU BELLO WAY | COLLECTRAMATIC OIL PUMP MACHINE | KITCHEN_EQUIPMENT
|  | NIGER, BOSSO-MINNA | COOKING BURNER | KITCHEN_EQUIPMENT
|  | LAG, LATEEF JAKANDE | DICING MACHINE | KITCHEN_EQUIPMENT
|  | KANO, AKTH | DISPLAY CABINET | KITCHEN_EQUIPMENT
|  | KADUNA, KACHIA RD | GRINDING MACHINE | KITCHEN_EQUIPMENT
|  | ABUJA, GADO NASKO, KUBWA 2 | ICE CREAM MACHINE | KITCHEN_EQUIPMENT
|  | SOKOTO, BANK RD | OPEN FRYER MACHINE 1 | KITCHEN_EQUIPMENT
|  | PH NTA ROAD | OPEN FRYER MACHINE 2 | KITCHEN_EQUIPMENT
|  | PH, WOJI | PRESURE FRYER 1 | KITCHEN_EQUIPMENT
|  | ILORIN, MM WAY | PRESURE FRYER 2 | KITCHEN_EQUIPMENT
|  | NASSARAWA, LAFIA | RATIONAL MACHINE | KITCHEN_EQUIPMENT
|  | AKWA IBOM, ORON RD | ROTISSIERI MACHINE | KITCHEN_EQUIPMENT
|  | BAYELSA, YENAGOA | SHREDDER | KITCHEN_EQUIPMENT
|  | OSUN, GBONGAN | TOASTER MACHINE | KITCHEN_EQUIPMENT
|  | AKWA IBOM, IKOT EKPENE RD | BALOON STAND | OTHERS
|  | LAG, OGUNLANA DRIVE | LOBBY WALL MIRROR | OTHERS
|  | ABIA, FACTORY RD, ABA | OTHERS | OTHERS
|  | LAG, OBA AKRAN | TOILET WALL MIRROR | OTHERS
|  | LAG, HEYDEN ALAPERE | KITCHEN WASH HAND SINK | PLUMBING
|  | LAG, MOBIL OGBA | LOBBY WASH HAND BASIN | PLUMBING
|  | KADUNA, AHMADU DELLO WAY | TAP | PLUMBING
|  | LAG, JOEL OGUNNAIKE | TOILET WASH HAND BASIN | PLUMBING
|  | PH, RUKPOKWU | WATER HEATER | PLUMBING
|  | LAG, AGUNGI | ENTRANCE ROLLER SHUTTER | SECURITY
|  | AKWA IBOM, ABAK RD | WINDOW ROLLER SHUTTER | SECURITY
|  | PH, RUMUOLA | TELEVISION | AUDIOVISUAL
|  | PH, ONNE | GOTV DECODER | AUDIOVISUAL
|  | LAG, IDI-IROKO RD | DSTV DECODER | AUDIOVISUAL
|  | PH ABULOMA | AMPLIFIER | AUDIOVISUAL
|  | LAG, DIYA STREET | AERATION TANK | WTP
|  | ILORIN, OFFA GARAGE | DOSING PUMP | WTP
|  | ABUJA, MPAPE | DOSING TANK | WTP
|  | KANO, KATSINA RD | FILTRATION PUMP 1 | WTP
|  | ABUJA, DEI-DEI | FILTRATION PUMP 2 | WTP
|  | IMO, IKENEGBU, OWERRI | FILTRATION TANK | WTP
|  | IMO, WETHERAL RD, OWERRI | FILTRATION VESSEL 1 | WTP
|  | PH, IWOFE | FILTRATION VESSEL 2 | WTP
|  | OSUN, AYETORO | GROUND WATER TANK | WTP
|  | EBONYI, AFIKPO, ABAKALIKI | OVERHEAD WATER TANK | WTP
|  | OGUN, OKE-ILEWO | SUBMERSIBLE PUMP | WTP
|  | PH, OYIGBO | TRANSFER PUMP 1 | WTP
|  | EBONYI, WATERWORKS, ABAKALIKI | TRANSFER PUMP 2 | WTP
|  | LAG, IKOTUN | UV LIGHT | WTP
LAG, IPAJA RD
ABUJA, APO RESETTLEMENT
ILORIN, OLOFAWAY
LAG, EJIGBO
ABIA, AZIKIWE RD, UMUAHIA
DELTA, SAPELE-WARRI RD
ENUGU, CHIME AVENUE
PH, ONNE RD, GRA
ABIA, ABA-OWERRI RD
ANAMBRA, AWKA RD, ONITSHA
DELTA, EFFURUN
LAG, HEYDEN IPAJA
ABIA, ADAZI RD
LAG, BADORE
LAG, ALIMOSHO
ABUJA, DUTSE ALHAJI
DELTA, ISOKO RD
ABUJA, KARU
ABUJA, GWAGWALADA
EDO, SAPELE RD, BENIN
LAG, FATGBEMS
OGUN, FATGBEMS IBB WAY
IBADAN, VENTURA MALL
IBADAN, AKOBO
ILORIN, ASA DAM
ANAMBRA, ZIK AVENUE, AWKA
AKWA IBOM, AKA RD
IMO, OKIGWE
ABUJA, LIFE-CAMP
LAG, SALOLO
OGUN, HEYDEN IBAFO
ENUGU, POLO MALL
EDO, RAHMAT PARK, BENIN
ABUJA, DAWAKI
LAG, CONOIL IKEJA
BENUE, OLD OTUKPO
ABUJA, IDU
LAG, ISAWO-IKORODU
KANO, HOTORO
LAG, TOTAL LEKKI
BAYELSA, TOMBIA
NASSARAWA, KEFFI
BAYELSA, OPOLO
KANO, IBRAHIM TAIWO
EDO, SAKPOMBA
PH, UST
ENUGU, NSUKKA
EDO, SILUKO
PH, D-LINE
PH, OMOKU
ENUGU, ABAKPA
LAG, EKORO
ANAMBRA, LIMCA RD, ONITSHA
ABIA, OGBOR HILLS
AKWA IBOM, NWANIBA
IBADAN, OJOO
OGUN, SOKENU
ABUJA, GWARIMPA 2
CALABAR, NDIDEM
OYO, OGBOMOSHO
AKWA IBOM, EKET-ORON RD
DELTA, OKPE RD
ABUJA, UTAKO
OYO, OWODE
Head Office
Central Kitchen
PPU Ilupeju
PPU Opebi
PPU Ajah
PPU Oniru
PPU Kaduna
PPU Tombia
PPU PH